## Project
Selector | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Index | Parent Feature | Key | Task Name | Issue Type | Status | ART | Resource Names | Task Type | Source | Σ Total SP | Σ Done SP | Focus Duration | Low-Risk Duration | Remaining SP | % Complete | Σ Realistic Estimate | Σ Worst Case Estimate | RefinementLevel
| 1 |  |  | 01.00.00.00.00.00.00.00 | [9 empty] | 505.5 | 0 | 1 hr | 1 hr | 505.5 | 0 | 650 | 962
| 2 |  |  | 01.01.00.00.00.00.00.00 | [9 empty] | 73 | 0 | 1 hr | 1 hr | 73 | 0 | 46 | 58
TAP-94739 | 3 | TAP-97668, TAP-111760 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 40 | 50 | Story Points
TAP-96814_HAPPYJAWS | 4 |  |  | 01.01.01.01.00.00.00.00 | TAP-94739 | TAP-96814 | [TAP-96814_HAPPY JAWS] ¦ [Architecture] Document Software Concept Architecture for IRR | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 40 | 50
TAP-97584_HAPPY JAWS | 5 |  |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-97584_HAPPY JAWS] ¦ [IRR][Arch] Describe wristed controller system functional architecture | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 5 | 17 | 1 hr | 1 hr | -12 | 100%
TAP-99738_HAPPY JAWS | 6 |  |  | 01.01.01.03.00.00.00.00 | TAP-94739 | TAP-99738 | [TAP-99738_HAPPY JAWS] ¦ [IRR][SW] Prepare for Planning Discussion on IDU Actuator Plug-and-Play Architecture | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 2 | 19 | 1 hr | 1 hr | -17 | 100%
TAP-97602_SIRIUS | 7 |  |  | 01.01.01.04.00.00.00.00 | TAP-94739 | TAP-97602 | [TAP-97602_SIRIUS] ¦ [IRR][Arch] Analyze requirement impact | User Story | Done | Core Instruments - Sirius |  |  |  | 3 | 22 | 1 hr | 1 hr | -19 | 100%
TAP-106673_SIRIUS | 8 |  |  | 01.01.01.05.00.00.00.00 | TAP-94739 | TAP-106673 | [TAP-106673_SIRIUS] ¦ [IRR][Arch] Analyze WS5 prototype functions and architecture | User Story | Done | Core Instruments - Sirius |  |  |  | 2 | 24 | 1 hr | 1 hr | -22 | 100%
| 9 |  |  | 01.01.01.06.00.00.00.00 | TAP-94739 | TAP-111973 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 24 | 1 hr | 1 hr | -24 | 100% | 40 | 50
TAP-97668 | 10 | TAP-120097 | TAP-94739 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | In progress |  |  |  |  | 32.5 | 24 | 1 hr | 1 hr | 8.5 | 0% | 6 | 8 | Story Points
| 11 |  |  | 01.01.02.01.00.00.00.00 | TAP-97668 | TAP-111972 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 24 | 1 hr | 1 hr | -24 | 100% | 6 | 8
TAP-97600_HAPPY JAWS | 12 |  |  | 01.01.02.02.00.00.00.00 | TAP-97668 | TAP-97600 | [TAP-97600_HAPPY JAWS] ¦ [IRR][Arch] Identify impacts and opportunities on testing strategy | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 3.5 | 27.5 | 1 hr | 1 hr | -24 | 100%
TAP-97595_HAPPY JAWS | 13 |  |  | 01.01.02.03.00.00.00.00 | TAP-97668 | TAP-97595 | [TAP-97595_HAPPY JAWS] ¦ [IRR][Arch] Review and refine state logic and state machines | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 3 | 30.5 | 1 hr | 1 hr | -27.5 | 100%
TAP-97586_SIRIUS | 14 |  |  | 01.01.02.04.00.00.00.00 | TAP-97668 | TAP-97586 | [TAP-97586_SIRIUS] ¦ [IRR][Arch] Migration and branch sync considerations | User Story | Done | Core Instruments - Sirius |  |  |  | 2 | 32.5 | 1 hr | 1 hr | -30.5 | 100%
TAP-97581_HAPPY JAWS | 15 |  |  | 01.01.02.05.00.00.00.00 | TAP-97668 | TAP-97581 | [TAP-97581_HAPPY JAWS] ¦ [IRR][Arch] Define internal structure and interfaces for wristed instrument controller | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 5 | 37.5 | 1 hr | 1 hr | -32.5 | 100%
TAP-97568_HAPPY JAWS | 16 |  |  | 01.01.02.06.00.00.00.00 | TAP-97668 | TAP-97568 | [TAP-97568_HAPPY JAWS] ¦ [IRR][Arch] Select architecture concept for wristed controller family | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 7 | 44.5 | 1 hr | 1 hr | -37.5 | 100%
TAP-114763_HAPPY JAWS | 17 |  |  | 01.01.02.07.00.00.00.00 | TAP-97668 | TAP-114763 | [TAP-114763_HAPPY JAWS] ¦ [IRR][Arch] Refine design inputs to wristed instrument architecture | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 7 | 44.5 | 1 hr | 1 hr | -37.5 | 0%
TAP-114765_HAPPY JAWS | 18 |  |  | 01.01.02.08.00.00.00.00 | TAP-97668 | TAP-114765 | [TAP-114765_HAPPY JAWS] ¦ [IRR][Arch] Update functional decomposition documents | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 2 | 46.5 | 1 hr | 1 hr | -44.5 | 100% | 0 | 0
TAP-114792_HAPPY JAWS | 19 |  |  | 01.01.02.09.00.00.00.00 | TAP-97668 | TAP-114792 | [TAP-114792_HAPPY JAWS] ¦ [IRR][Arch] Decide on controller design with impact on software architecture | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 2 | 48.5 | 1 hr | 1 hr | -46.5 | 100% | 0 | 0
TAP-114794_SIRIUS | 20 |  |  | 01.01.02.10.00.00.00.00 | TAP-97668 | TAP-114794 | [TAP-114794_SIRIUS] ¦ [IRR][Arch] Requirements workshop | User Story | Done | Core Instruments - Sirius |  |  |  | 5 | 53.5 | 1 hr | 1 hr | -48.5 | 100% | 0 | 0
TAP-123215_HAPPY JAWS | 21 |  |  | 01.01.02.11.00.00.00.00 | TAP-97668 | TAP-123215 | [TAP-123215_HAPPY JAWS] ¦ [IRR][Arch] Create consolidated wristed architecture prototype (Part 1) | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 3 | 56.5 | 1 hr | 1 hr | -53.5 | 100%
TAP-120097 | 22 | TAP-111760 | TAP-97668 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture in SW | Feature | PROPOSED |  |  |  |  | 28.5 | 56.5 | 1 hr | 1 hr | -28 | 0% | 0 | 0 | Story Points
TAP-97689_HAPPY JAWS | 23 |  |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-97689 | [TAP-97689_HAPPY JAWS] ¦ [IRR][Arch] Update instrument data model for wristed instruments | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 1 | 56.5 | 1 hr | 1 hr | -55.5 | 0%
TAP-106674_HAPPY JAWS | 24 |  |  | 01.01.03.02.00.00.00.00 | TAP-120097 | TAP-106674 | [TAP-106674_HAPPY JAWS] ¦ [IRR][Arch] Validate consolidated wristed architecture prototype | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 4 | 56.5 | 1 hr | 1 hr | -52.5 | 0%
TAP-97598_HAPPY JAWS | 25 |  |  | 01.01.03.03.00.00.00.00 | TAP-120097 | TAP-97598 | [TAP-97598_HAPPY JAWS] ¦ [IRR][Arch] Finalize external interfaces of wristed controller SWI | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 2 | 56.5 | 1 hr | 1 hr | -54.5 | 0%
TAP-114803_HAPPY JAWS | 26 |  |  | 01.01.03.04.00.00.00.00 | TAP-120097 | TAP-114803 | [TAP-114803_HAPPY JAWS] ¦ [IRR][Arch] Migrate IRR branch to new arch and validate | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 2 | 56.5 | 1 hr | 1 hr | -54.5 | 28.25 | 0 | 0
TAP-115970_HAPPY JAWS | 27 |  |  | 01.01.03.05.00.00.00.00 | TAP-120097 | TAP-115970 | [TAP-115970_HAPPY JAWS] ¦ [IRR][Arch] Complete V&V Impact Analysis and Initial V&V Strategy | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3.5 | 56.5 | 1 hr | 1 hr | -53 | 0%
TAP-117147_HAPPY JAWS | 28 |  |  | 01.01.03.06.00.00.00.00 | TAP-120097 | TAP-117147 | [TAP-117147_HAPPY JAWS] ¦ [IRR][Arch] Simulink design guidelines and patterns within IRR controller | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 2 | 56.5 | 1 hr | 1 hr | -54.5 | 28.25 | 0 | 0
TAP-116501_HAPPY JAWS | 29 |  |  | 01.01.03.07.00.00.00.00 | TAP-120097 | TAP-116501 | [TAP-116501_HAPPY JAWS] ¦ [IRR][Arch] Reserve time for requirement updates | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 10 | 56.5 | 1 hr | 1 hr | -46.5 | 5.65 | 0 | 0
TAP-105494_HAPPY JAWS | 30 |  |  | 01.01.03.08.00.00.00.00 | TAP-120097 | TAP-105494 | [TAP-105494_HAPPY JAWS] ¦ [IRR][Arch] Create consolidated wristed architecture prototype (Part 2) | User Story | In progress | Core Instruments - Happy Jaws |  |  |  | 4 | 56.5 | 1 hr | 1 hr | -52.5 | 0%
| 31 |  |  | 01.02.00.00.00.00.00.00 | [9 empty] | 27 | 56.5 | 1 hr | 1 hr | -29.5 | 2.0926 | 80 | 90
TAP-111730 | 32 | TAP-111760, TAP-124062 | TAP-106315 | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 27 | 56.5 | 1 hr | 1 hr | -29.5 | 0% | 30 | 40 | Story Points
| 33 |  |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 56.5 | 1 hr | 1 hr | -56.5 | 100% | 30 | 40
TAP-116458_HAPPY JAWS | 34 |  |  | 01.02.01.02.00.00.00.00 | TAP-111730 | TAP-116458 | [TAP-116458_HAPPY JAWS] ¦ [IRR][Clamping] Update switching logic in jaw torque estimator | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 6 | 62.5 | 1 hr | 1 hr | -56.5 | 100% | 0 | 0
TAP-116459_HAPPY JAWS | 35 |  |  | 01.02.01.03.00.00.00.00 | TAP-111730 | TAP-116459 | [TAP-116459_HAPPY JAWS] ¦ [IRR][Clamping] Continue Investigating Improvements to force estimator | User Story | In progress | Core Instruments - Happy Jaws |  |  |  | 8 | 62.5 | 1 hr | 1 hr | -54.5 | 7.8125 | 0 | 0
TAP-116460_HAPPY JAWS | 36 |  |  | 01.02.01.04.00.00.00.00 | TAP-111730 | TAP-116460 | [TAP-116460_HAPPY JAWS] ¦ [IRR][Clamping] Investigate jaw torque buildup issue | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 8 | 62.5 | 1 hr | 1 hr | -54.5 | 7.8125 | 0 | 0
TAP-116461_HAPPY JAWS | 37 |  |  | 01.02.01.05.00.00.00.00 | TAP-111730 | TAP-116461 | [TAP-116461_HAPPY JAWS] ¦ [IRR][Clamping] Technical design review | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 8 | 62.5 | 1 hr | 1 hr | -54.5 | 7.8125 | 0 | 0
TAP-116462_SIRIUS | 38 |  |  | 01.02.01.06.00.00.00.00 | TAP-111730 | TAP-116462 | [TAP-116462_SIRIUS] ¦ [IRR][Clamping] Adjust clamping parameters post June RUFS | User Story | Cancelled | Core Instruments - Sirius |  |  |  | 8 | 62.5 | 1 hr | 1 hr | -54.5 | 7.8125 | 0 | 0
TAP-116463_HAPPY JAWS | 39 |  |  | 01.02.01.07.00.00.00.00 | TAP-111730 | TAP-116463 | [TAP-116463_HAPPY JAWS] ¦ [IRR][Clamping] Collect clamp data on previously identified low clamp force instrument | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 2 | 64.5 | 1 hr | 1 hr | -62.5 | 100% | 0 | 0
TAP-121692_HAPPY JAWS | 40 |  |  | 01.02.01.08.00.00.00.00 | TAP-111730 | TAP-121692 | [TAP-121692_HAPPY JAWS] ¦ [IRR][Clamping] Investigate effect of updated pulley radius | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 5 | 69.5 | 1 hr | 1 hr | -64.5 | 100% | 0 | 0
TAP-122144_HAPPY JAWS | 41 |  |  | 01.02.01.09.00.00.00.00 | TAP-111730 | TAP-122144 | [TAP-122144_HAPPY JAWS] ¦ [IRR][Clamping] Improvements to force estimator | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 6 | 75.5 | 1 hr | 1 hr | -69.5 | 100% | 0 | 0
TAP-111731 | 42 | TAP-111760 |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 0% | 50 | 50 | Feature Estimation
| 43 |  |  | 01.02.02.01.00.00.00.00 | TAP-111731 | TAP-111906 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 100% | 50 | 50
TAP-112037_ANIMATORS | 44 |  |  | 01.02.02.02.00.00.00.00 | TAP-111731 | TAP-112037 | [TAP-112037_ANIMATORS] ¦ [Animators] Reduce Force Variation when articulating during clamp | Feature Estimation | Open | Shared Services - Animators |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 100% | 0 | 0
TAP-124062 | 45 |  | TAP-111730 | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 0% | 0 | 0 | Feature Estimation
| 46 |  |  | 01.03.00.00.00.00.00.00 | [9 empty] | 42 | 75.5 | 1 hr | 1 hr | -33.5 | 1.7976 | 136 | 234
TAP-112076 | 47 | TAP-111760 |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 0% | 10 | 10 | Feature Estimation
| 48 |  |  | 01.03.01.01.00.00.00.00 | TAP-112076 | TAP-112078 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 100% | 10 | 10
TAP-94966 | 49 | TAP-111556, TAP-111760 | TAP-111562 | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | Accepted |  |  |  |  | 35 | 75.5 | 1 hr | 1 hr | -40.5 | 0% | 45 | 78 | Story Points
| 50 |  |  | 01.03.02.01.00.00.00.00 | TAP-94966 | TAP-111781 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 100% | 20 | 33
| 51 |  |  | 01.03.02.02.00.00.00.00 | TAP-94966 | TAP-111786 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 100% | 25 | 45
TAP-116502_HAPPY JAWS | 52 |  |  | 01.03.02.03.00.00.00.00 | TAP-94966 | TAP-116502 | [TAP-116502_HAPPY JAWS] ¦ [IRR][Cutting] Reproduce position estimation failures & Investigate | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 4 | 79.5 | 1 hr | 1 hr | -75.5 | 100% | 0 | 0
TAP-116503_HAPPY JAWS | 53 |  |  | 01.03.02.04.00.00.00.00 | TAP-94966 | TAP-116503 | [TAP-116503_HAPPY JAWS] ¦ [IRR][Cutting] Develop hard-stop detection for robust closing | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 5 | 84.5 | 1 hr | 1 hr | -79.5 | 100% | 0 | 0
TAP-116504_HAPPY JAWS | 54 |  |  | 01.03.02.05.00.00.00.00 | TAP-94966 | TAP-116504 | [TAP-116504_HAPPY JAWS] ¦ [IRR][Cutting] Develop calibration for robust position estimation | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 1 | 85.5 | 1 hr | 1 hr | -84.5 | 100% | 0 | 0
TAP-116505_HAPPY JAWS | 55 |  |  | 01.03.02.06.00.00.00.00 | TAP-94966 | TAP-116505 | [TAP-116505_HAPPY JAWS] ¦ [IRR][Cutting] Update cutting KPIs for capturing reliable performance / HW variation | User Story | In progress | Core Instruments - Happy Jaws |  |  |  | 5 | 85.5 | 1 hr | 1 hr | -80.5 | 17.1 | 0 | 0
TAP-116508_HAPPY JAWS | 56 |  |  | 01.03.02.07.00.00.00.00 | TAP-94966 | TAP-116508 | [TAP-116508_HAPPY JAWS] ¦ [IRR][Use-life] Document use-life model | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 2 | 87.5 | 1 hr | 1 hr | -85.5 | 100% | 0 | 0
TAP-116509_SIRIUS | 57 |  |  | 01.03.02.08.00.00.00.00 | TAP-94966 | TAP-116509 | [TAP-116509_SIRIUS] ¦ [IRR][Use-life] Identify dependent use-life parameters | User Story | Done | Core Instruments - Sirius |  |  |  | 8 | 95.5 | 1 hr | 1 hr | -87.5 | 100% | 0 | 0
TAP-116510_SIRIUS | 58 |  |  | 01.03.02.09.00.00.00.00 | TAP-94966 | TAP-116510 | [TAP-116510_SIRIUS] ¦ [IRR][Use-life] Investigate methods to improve use-life trade-off | User Story | Cancelled | Core Instruments - Sirius |  |  |  | 8 | 95.5 | 1 hr | 1 hr | -87.5 | 100% | 0 | 0
TAP-116511_SIRIUS | 59 |  |  | 01.03.02.10.00.00.00.00 | TAP-94966 | TAP-116511 | [TAP-116511_SIRIUS] ¦ [IRR][Use-life] Create trade-off curves 1 | User Story | In progress | Core Instruments - Sirius |  |  |  | 5 | 95.5 | 1 hr | 1 hr | -90.5 | 19.1 | 0 | 0
TAP-116512_SIRIUS | 60 |  |  | 01.03.02.11.00.00.00.00 | TAP-94966 | TAP-116512 | [TAP-116512_SIRIUS] ¦ [IRR][Use-life] Create trade-off curves 2 | User Story | In progress | Core Instruments - Sirius |  |  |  | 5 | 95.5 | 1 hr | 1 hr | -90.5 | 19.1 | 0 | 0
TAP-111554 | 61 | TAP-111760 |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 | 95.5 | 1 hr | 1 hr | -88.5 | 0% | 24 | 48 | Story Points
| 62 |  |  | 01.03.03.01.00.00.00.00 | TAP-111554 | TAP-111782 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 24 | 48
TAP-116506_HAPPY JAWS | 63 |  |  | 01.03.03.02.00.00.00.00 | TAP-111554 | TAP-116506 | [TAP-116506_HAPPY JAWS] ¦ [IRR][Cutting] Support Tissue Cutting investigation with Systems | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 5 | 95.5 | 1 hr | 1 hr | -90.5 | 19.1 | 0 | 0
TAP-116507_HAPPY JAWS | 64 |  |  | 01.03.03.03.00.00.00.00 | TAP-111554 | TAP-116507 | [TAP-116507_HAPPY JAWS] ¦ [IRR][Cutting] Get feedback from clinical team | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 2 | 95.5 | 1 hr | 1 hr | -93.5 | 47.75 | 0 | 0
TAP-111555 | 65 | TAP-111760 |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 12 | 18 | Feature Estimation
| 66 |  |  | 01.03.04.01.00.00.00.00 | TAP-111555 | TAP-111783 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 12 | 18
TAP-112012 | 67 | TAP-111760 |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 12 | 18 | Feature Estimation
| 68 |  |  | 01.03.05.01.00.00.00.00 | TAP-112012 | TAP-112015 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 12 | 18
TAP-111560 | 69 |  |  | 01.03.06.00.00.00.00.00 |  | TAP-111560 | [TAP-111560] ¦ [IRR][Feature] Enable Tuning of Use-Life to Cutting Performance Trade-offs | Feature | Cancelled |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 12 | 18
TAP-111569 | 70 | TAP-111760 |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 8 | 12 | Feature Estimation
| 71 |  |  | 01.03.07.01.00.00.00.00 | TAP-111569 | TAP-111797 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 8 | 12
TAP-111565 | 72 | TAP-111760 |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 5 | 20 | Feature Estimation
| 73 |  |  | 01.03.08.01.00.00.00.00 | TAP-111565 | TAP-111793 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 5 | 20
TAP-111794_ANIMATORS | 74 |  |  | 01.03.08.02.00.00.00.00 | TAP-111565 | TAP-111794 | [TAP-111794_ANIMATORS] ¦ [IRR][Animators] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature Estimation | Cancelled | Shared Services - Animators |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 5 | 20
TAP-111556 | 75 | TAP-111559, TAP-111760 | TAP-94966 | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 10 | 15 | Feature Estimation
| 76 |  |  | 01.03.09.01.00.00.00.00 | TAP-111556 | TAP-111784 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 10 | 15
TAP-111559 | 77 | TAP-111760 | TAP-111556 | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 10 | 15 | Feature Estimation
| 78 |  |  | 01.03.10.01.00.00.00.00 | TAP-111559 | TAP-111785 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 10 | 15
| 79 |  |  | 01.04.00.00.00.00.00.00 | [9 empty] | 60 | 95.5 | 1 hr | 1 hr | -35.5 | 1.5917 | 20 | 30
TAP-112077 | 80 | TAP-111760 | TAP-111562 | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 60 | 95.5 | 1 hr | 1 hr | -35.5 | 0% | 20 | 30 | Story Points
| 81 |  |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 100% | 20 | 30
TAP-115017_SIRIUS | 82 |  |  | 01.04.01.02.00.00.00.00 | TAP-112077 | TAP-115017 | [TAP-115017_SIRIUS] ¦ [IRR][Articulation] Finalize KPI/Simulation Script | User Story | Done | Core Instruments - Sirius |  |  |  | 7 | 102.5 | 1 hr | 1 hr | -95.5 | 100%
TAP-116519_SIRIUS | 83 |  |  | 01.04.01.03.00.00.00.00 | TAP-112077 | TAP-116519 | [TAP-116519_SIRIUS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in Boston | User Story | Done | Core Instruments - Sirius |  |  |  | 6 | 108.5 | 1 hr | 1 hr | -102.5 | 100% | 0 | 0
TAP-116520_HAPPY JAWS | 84 |  |  | 01.04.01.04.00.00.00.00 | TAP-112077 | TAP-116520 | [TAP-116520_HAPPY JAWS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in NoHa | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 36.1667 | 0 | 0
TAP-116521_HAPPY JAWS | 85 |  |  | 01.04.01.05.00.00.00.00 | TAP-112077 | TAP-116521 | [TAP-116521_HAPPY JAWS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in Wessling | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 36.1667 | 0 | 0
TAP-116522_SIRIUS | 86 |  |  | 01.04.01.06.00.00.00.00 | TAP-112077 | TAP-116522 | [TAP-116522_SIRIUS] ¦ [IRR][Articulation/Actuation] Tracking Fixture and Elmo Interface Finalization | User Story | Groomed | Core Instruments - Sirius |  |  |  | 5 | 108.5 | 1 hr | 1 hr | -103.5 | 21.7 | 0 | 0
TAP-116523_SIRIUS | 87 |  |  | 01.04.01.07.00.00.00.00 | TAP-112077 | TAP-116523 | [TAP-116523_SIRIUS] ¦ [IRR][Articulation/Actuation] Setup Engineering Test Script | User Story | Groomed | Core Instruments - Sirius |  |  |  | 5 | 108.5 | 1 hr | 1 hr | -103.5 | 21.7 | 0 | 0
TAP-116524_SIRIUS | 88 |  |  | 01.04.01.08.00.00.00.00 | TAP-112077 | TAP-116524 | [TAP-116524_SIRIUS] ¦ [IRR][Articulation/Actuation] Run Engineering Test with Tracking Fixture | User Story | Open | Core Instruments - Sirius |  |  |  | 8 | 108.5 | 1 hr | 1 hr | -100.5 | 13.5625 | 0 | 0
TAP-116525_SIRIUS | 89 |  |  | 01.04.01.09.00.00.00.00 | TAP-112077 | TAP-116525 | [TAP-116525_SIRIUS] ¦ [IRR][Articulation/Actuation] Compare Engineering Test Results with SR Tests | User Story | Open | Core Instruments - Sirius |  |  |  | 2 | 108.5 | 1 hr | 1 hr | -106.5 | 54.25 | 0 | 0
TAP-116526_HAPPY JAWS | 90 |  |  | 01.04.01.10.00.00.00.00 | TAP-112077 | TAP-116526 | [TAP-116526_HAPPY JAWS] ¦ [IRR][Articulation/Actuation] Jaw Actuation Hysteresis and Jaw Scaling Analysis Script | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 36.1667 | 0 | 0
TAP-116527_SIRIUS | 91 |  |  | 01.04.01.11.00.00.00.00 | TAP-112077 | TAP-116527 | [TAP-116527_SIRIUS] ¦ [IRR][Articulation/Actuation] Investigate Jaw Actuation Issues with Engineering Test | User Story | Open | Core Instruments - Sirius |  |  |  | 4 | 108.5 | 1 hr | 1 hr | -104.5 | 27.125 | 0 | 0
TAP-116528_SIRIUS | 92 |  |  | 01.04.01.12.00.00.00.00 | TAP-112077 | TAP-116528 | [TAP-116528_SIRIUS] ¦ [IRR][Articulation/Actuation] Articulation Under Load in Simulation | User Story | Open | Core Instruments - Sirius |  |  |  | 5 | 108.5 | 1 hr | 1 hr | -103.5 | 21.7 | 0 | 0
TAP-116529_HAPPY JAWS | 93 |  |  | 01.04.01.13.00.00.00.00 | TAP-112077 | TAP-116529 | [TAP-116529_HAPPY JAWS] ¦ [IRR][Articulation/Actuation] Investigate Instrument Shaking when J6 Moving | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 1 | 108.5 | 1 hr | 1 hr | -107.5 | 108.5 | 0 | 0
TAP-116530_SIRIUS | 94 |  |  | 01.04.01.14.00.00.00.00 | TAP-112077 | TAP-116530 | [TAP-116530_SIRIUS] ¦ [IRR][Articulation/Actuation] Get Clinical Feedback | User Story | Open | Core Instruments - Sirius |  |  |  | 1 | 108.5 | 1 hr | 1 hr | -107.5 | 108.5 | 0 | 0
TAP-116586_SIRIUS | 95 |  |  | 01.04.01.15.00.00.00.00 | TAP-112077 | TAP-116586 | [TAP-116586_SIRIUS] ¦ [IRR][Articulation/Actuation] Evaluate/Implement Other KPIs given Engineering Test Results | User Story | Open | Core Instruments - Sirius |  |  |  | 4 | 108.5 | 1 hr | 1 hr | -104.5 | 27.125 | 0 | 0
TAP-118635_SIRIUS | 96 |  |  | 01.04.01.16.00.00.00.00 | TAP-112077 | TAP-118635 | [TAP-118635_SIRIUS] ¦ [IRR][Articulation] Investigate delay-compensation tracking error KPI | User Story | In progress | Core Instruments - Sirius |  |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 0%
TAP-122341_SIRIUS | 97 |  |  | 01.04.01.17.00.00.00.00 | TAP-112077 | TAP-122341 | [TAP-122341_SIRIUS] ¦ [IRR] Update HW Inventory in Boston | User Story | Open | Core Instruments - Sirius |  |  |  | 0 | 108.5 | 1 hr | 1 hr | -108.5 | 0% | 0 | 0
TAP-120096 | 98 | TAP-111760 |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 | 108.5 | 1 hr | 1 hr | -108.5 | 0% | 0 | 0 | Feature Estimation
| 99 |  |  | 01.05.00.00.00.00.00.00 | [9 empty] | 169.5 | 108.5 | 1 hr | 1 hr | 61 | 0.64012 | 174 | 235
TAP-103448 | 100 | TAP-111760 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 | 108.5 | 1 hr | 1 hr | -94.5 | 0% | 0 | 0 | Story Points
TAP-99022_I2E | 101 |  |  | 01.05.01.01.00.00.00.00 | TAP-103448 | TAP-99022 | [TAP-99022_I2E] ¦ [v3.1][IRR][IDU CMD][I2E] Add Shears functionality to M-IRR's tool within Discrete Control Command | User Story | Done | Advanced Instruments - I2E |  |  |  | 5 | 113.5 | 1 hr | 1 hr | -108.5 | 100%
TAP-114885_I2E | 102 |  |  | 01.05.01.02.00.00.00.00 | TAP-103448 | TAP-114885 | [TAP-114885_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port LED Capability to IDU CMD / Common | User Story | Open | Advanced Instruments - I2E |  |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.8333 | 0 | 0
TAP-114886_I2E | 103 |  |  | 01.05.01.03.00.00.00.00 | TAP-103448 | TAP-114886 | [TAP-114886_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port Automatic Data Recorder Triggering on Errors | User Story | Open | Advanced Instruments - I2E |  |  |  | 2 | 113.5 | 1 hr | 1 hr | -111.5 | 56.75 | 0 | 0
TAP-114887_I2E | 104 |  |  | 01.05.01.04.00.00.00.00 | TAP-103448 | TAP-114887 | [TAP-114887_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port automatically running IDU CMD on 2X fixtures | User Story | Open | Advanced Instruments - I2E |  |  |  | 1 | 113.5 | 1 hr | 1 hr | -112.5 | 113.5 | 0 | 0
TAP-114892_I2E | 105 |  |  | 01.05.01.05.00.00.00.00 | TAP-103448 | TAP-114892 | [TAP-114892_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port tmp file logging when parsing/running trajectory files to IDU CMD | User Story | Open | Advanced Instruments - I2E |  |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.8333 | 0 | 0
TAP-111562 | 106 | TAP-94966, TAP-112077 | TAP-111719 | 01.05.02.00.00.00.00.00 |  | TAP-111562 | [TAP-111562] ¦ [IRR][Enabler] Set up fixtures and processing scripts for IRR HW Testing | Feature | Cancelled |  |  |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 0% | 0 | 0
TAP-116286 | 107 | TAP-111760 |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 | 113.5 | 1 hr | 1 hr | -95.5 | 0% | 0 | 0 | Story Points
TAP-116513_HAPPY JAWS | 108 |  |  | 01.05.03.01.00.00.00.00 | TAP-116286 | TAP-116513 | [TAP-116513_HAPPY JAWS] ¦ [IRR][Analysis] Collect clamp data on previously identified low clamp force instrument | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 18 | 113.5 | 1 hr | 1 hr | -95.5 | 0% | 0 | 0
TAP-116514_SIRIUS | 109 |  |  | 01.05.03.02.00.00.00.00 | TAP-116286 | TAP-116514 | [TAP-116514_SIRIUS] ¦ [IRR][Analysis] Obtain brand new needle drivers | User Story | Open | Core Instruments - Sirius |  |  |  | 2 | 113.5 | 1 hr | 1 hr | -111.5 | 56.75 | 0 | 0
TAP-116515_HAPPY JAWS | 110 |  |  | 01.05.03.03.00.00.00.00 | TAP-116286 | TAP-116515 | [TAP-116515_HAPPY JAWS] ¦ [IRR][Analysis] Collect KPI data on a set of brand new instruments | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.8333 | 0 | 0
TAP-116516_HAPPY JAWS | 111 |  |  | 01.05.03.04.00.00.00.00 | TAP-116286 | TAP-116516 | [TAP-116516_HAPPY JAWS] ¦ [IRR][Analysis] Reprocess instruments | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 2 | 113.5 | 1 hr | 1 hr | -111.5 | 56.75 | 0 | 0
TAP-116517_HAPPY JAWS | 112 |  |  | 01.05.03.05.00.00.00.00 | TAP-116286 | TAP-116517 | [TAP-116517_HAPPY JAWS] ¦ [IRR][Analysis] Collect KPI data on a set of reprocessed instruments | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.8333 | 0 | 0
TAP-116518_SIRIUS | 113 |  |  | 01.05.03.06.00.00.00.00 | TAP-116286 | TAP-116518 | [TAP-116518_SIRIUS] ¦ [IRR][Analysis] Investigate instrument aging effects on KPIs | User Story | Open | Core Instruments - Sirius |  |  |  | 8 | 113.5 | 1 hr | 1 hr | -105.5 | 14.1875 | 0 | 0
TAP-95983 | 114 | TAP-111760 |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 108 | 113.5 | 1 hr | 1 hr | -5.5 | 0% | 41 | 73 | Story Points
TAP-88491_HAPPY JAWS | 115 |  |  | 01.05.04.01.00.00.00.00 | TAP-95983 | TAP-88491 | [TAP-88491_HAPPY JAWS] ¦ [IRR][PlantSim][Happy Jaws] Introduce IDU Standalones to Modeling Team | User Story | Done | Core Instruments - Happy Jaws |  |  |  | 1 | 114.5 | 1 hr | 1 hr | -113.5 | 100%
TAP-87610_SIRIUS | 116 |  |  | 01.05.04.02.00.00.00.00 | TAP-95983 | TAP-87610 | [TAP-87610_SIRIUS] ¦ [IRR][PlantSim][Sirius] Setup VM with Docker and git on Server in Mounds View | User Story | In progress | Core Instruments - Sirius |  |  |  | 4 | 114.5 | 1 hr | 1 hr | -110.5 | 0%
| 117 |  |  | 01.05.04.03.00.00.00.00 | TAP-95983 | TAP-111914 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 114.5 | 1 hr | 1 hr | -114.5 | 100% | 10 | 20
TAP-112038_ANIMATORS | 118 |  |  | 01.05.04.04.00.00.00.00 | TAP-95983 | TAP-112038 | [TAP-112038_ANIMATORS] ¦ [Animators] Reduce Force Variation when articulating during clamp | Feature Estimation | Cancelled | Shared Services - Animators |  |  |  | 0 | 114.5 | 1 hr | 1 hr | -114.5 | 100% | 10 | 20
| 119 |  |  | 01.05.04.05.00.00.00.00 | TAP-95983 | TAP-111921 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 114.5 | 1 hr | 1 hr | -114.5 | 100% | 3 | 5
TAP-111725_SIRIUS | 120 |  |  | 01.05.04.06.00.00.00.00 | TAP-95983 | TAP-111725 | [TAP-111725_SIRIUS] ¦ [IRR][Enabler][Playback] Implement SW or tool updates to enable playback simulation | User Story | Done | Core Instruments - Sirius |  |  |  | 15 | 129.5 | 1 hr | 1 hr | -114.5 | 100% | 0 | 0
TAP-115103_ANIMATORS | 121 |  |  | 01.05.04.07.00.00.00.00 | TAP-95983 | TAP-115103 | [TAP-115103_ANIMATORS] ¦ [IRR][PlantModels] Wristed Instrument Model Credibility and Risk Assessment (Validation) | User Story | Open | Shared Services - Animators |  |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 0 | 0
TAP-115108_ANIMATORS | 122 |  |  | 01.05.04.08.00.00.00.00 | TAP-95983 | TAP-115108 | [TAP-115108_ANIMATORS] ¦ [IRR][PlantModels] Document model stability and variability over the supported parameter space | User Story | Open | Shared Services - Animators |  |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 0 | 0
| 123 |  |  | 01.05.04.09.00.00.00.00 | TAP-95983 | TAP-111915 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 3 | 8
| 124 |  |  | 01.05.04.10.00.00.00.00 | TAP-95983 | TAP-111790 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 5 | 10
| 125 |  |  | 01.05.04.11.00.00.00.00 | TAP-95983 | TAP-111788 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 20 | 30
TAP-111789_FRED | 126 |  |  | 01.05.04.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-111789_FRED] ¦ [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | Feature Estimation | Open | Foundation - Fred |  |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 0 | 0
TAP-114540_SIRIUS | 127 |  |  | 01.05.04.13.00.00.00.00 | TAP-95983 | TAP-114540 | [TAP-114540_SIRIUS] ¦ [IRR][Sirius] Update Reliability Logging for Failure Detection Log Collection | User Story | Open | Core Instruments - Sirius |  |  |  | 2 | 129.5 | 1 hr | 1 hr | -127.5 | 64.75 | 0 | 0
TAP-116408_PUPPETEERS | 128 |  |  | 01.05.04.14.00.00.00.00 | TAP-95983 | TAP-116408 | [TAP-116408_PUPPETEERS] ¦ [IRR][Puppeteers] Support for framework for wristed testing | User Story | Open | Core Instruments - Puppeteers |  |  |  | 13 | 129.5 | 1 hr | 1 hr | -116.5 | 9.9615 | 0 | 0
TAP-116440_ANIMATORS | 129 |  |  | 01.05.04.15.00.00.00.00 | TAP-95983 | TAP-116440 | [TAP-116440_ANIMATORS] ¦ [IRR][PlantModels] Provide an interface for external loads on the instrument | User Story | Done | Shared Services - Animators |  |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 100% | 0 | 0
TAP-116441_ANIMATORS | 130 |  |  | 01.05.04.16.00.00.00.00 | TAP-95983 | TAP-116441 | [TAP-116441_ANIMATORS] ¦ [IRR][PlantModels] Provide a mask summarizing the plant model parameters | User Story | Open | Shared Services - Animators |  |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 26.9 | 0 | 0
TAP-116442_ANIMATORS | 131 |  |  | 01.05.04.17.00.00.00.00 | TAP-95983 | TAP-116442 | [TAP-116442_ANIMATORS] ¦ [IRR][PlantModels] Request/Coordinate support for the ein_ng build process on the HPC cluster | User Story | In progress | Shared Services - Animators |  |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 26.9 | 0 | 0
TAP-116456_ANIMATORS | 132 |  |  | 01.05.04.18.00.00.00.00 | TAP-95983 | TAP-116456 | [TAP-116456_ANIMATORS] ¦ [IRR][PlantModels] Setup an evaluation framework for parameter scan simulations | User Story | Open | Shared Services - Animators |  |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 26.9 | 0 | 0
TAP-116457_ANIMATORS | 133 |  |  | 01.05.04.19.00.00.00.00 | TAP-95983 | TAP-116457 | [TAP-116457_ANIMATORS] ¦ [IRR][PlantModels] Familiarize with the IDU standalone tester | User Story | Done | Shared Services - Animators |  |  |  | 10 | 144.5 | 1 hr | 1 hr | -134.5 | 100% | 0 | 0
TAP-116491_HAPPY JAWS | 134 |  |  | 01.05.04.20.00.00.00.00 | TAP-95983 | TAP-116491 | [TAP-116491_HAPPY JAWS] ¦ [IRR][Playback][Happy Jaws] Evaluate Playback tools and Use Cases | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 2 | 144.5 | 1 hr | 1 hr | -142.5 | 72.25 | 0 | 0
TAP-116492_HAPPY JAWS | 135 |  |  | 01.05.04.21.00.00.00.00 | TAP-95983 | TAP-116492 | [TAP-116492_HAPPY JAWS] ¦ [IRR][HW Testing][Happy Jaws] Investigate Engineering Test Infrastructure Improvements | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 4 | 144.5 | 1 hr | 1 hr | -140.5 | 36.125 | 0 | 0
TAP-116493_HAPPY JAWS | 136 |  |  | 01.05.04.22.00.00.00.00 | TAP-95983 | TAP-116493 | [TAP-116493_HAPPY JAWS] ¦ [IRR][HW Testing][Happy Jaws] Implement Standardized Engineering Test Scripts | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 7 | 144.5 | 1 hr | 1 hr | -137.5 | 20.6429 | 0 | 0
TAP-116494_SIRIUS | 137 |  |  | 01.05.04.23.00.00.00.00 | TAP-95983 | TAP-116494 | [TAP-116494_SIRIUS] ¦ [IRR][Playback][Sirius] Create script for running playback simulation | User Story | Open | Core Instruments - Sirius |  |  |  | 6 | 144.5 | 1 hr | 1 hr | -138.5 | 24.0833 | 0 | 0
TAP-116495_SIRIUS | 138 |  |  | 01.05.04.24.00.00.00.00 | TAP-95983 | TAP-116495 | [TAP-116495_SIRIUS] ¦ [IRR][Spike][Equivalency][Sirius] Develop Equivalency Test for IRR Controller | User Story | Open | Core Instruments - Sirius |  |  |  | 5 | 144.5 | 1 hr | 1 hr | -139.5 | 28.9 | 0 | 0
TAP-116496_SIRIUS | 139 |  |  | 01.05.04.25.00.00.00.00 | TAP-95983 | TAP-116496 | [TAP-116496_SIRIUS] ¦ [IRR][HW Testing][Sirius] Documentation of HW Test Fixturing and Setup | User Story | Open | Core Instruments - Sirius |  |  |  | 7 | 144.5 | 1 hr | 1 hr | -137.5 | 20.6429 | 0 | 0
TAP-116497_SIRIUS | 140 |  |  | 01.05.04.26.00.00.00.00 | TAP-95983 | TAP-116497 | [TAP-116497_SIRIUS] ¦ [IRR][HW Testing][Sirius] Implement Standardized Engineering Test Reports | User Story | Open | Core Instruments - Sirius |  |  |  | 5 | 144.5 | 1 hr | 1 hr | -139.5 | 28.9 | 0 | 0
TAP-116498_SIRIUS | 141 |  |  | 01.05.04.27.00.00.00.00 | TAP-95983 | TAP-116498 | [TAP-116498_SIRIUS] ¦ [IRR][Sirius] Derating Tool Documentation | User Story | Done | Core Instruments - Sirius |  |  |  | 1 | 145.5 | 1 hr | 1 hr | -144.5 | 100% | 0 | 0
TAP-116499_SIRIUS | 142 |  |  | 01.05.04.28.00.00.00.00 | TAP-95983 | TAP-116499 | [TAP-116499_SIRIUS] ¦ [IRR][Sirius] Continuous Shmio Logging Documentation | User Story | Done | Core Instruments - Sirius |  |  |  | 1 | 146.5 | 1 hr | 1 hr | -145.5 | 100% | 0 | 0
TAP-116500_SIRIUS | 143 |  |  | 01.05.04.29.00.00.00.00 | TAP-95983 | TAP-116500 | [TAP-116500_SIRIUS] ¦ [IRR][Sirius] Single signal logging Documentation | User Story | Open | Core Instruments - Sirius |  |  |  | 1 | 146.5 | 1 hr | 1 hr | -145.5 | 146.5 | 0 | 0
TAP-118633_SIRIUS | 144 |  |  | 01.05.04.30.00.00.00.00 | TAP-95983 | TAP-118633 | [TAP-118633_SIRIUS] ¦ [IRR][Enabler][Tools] Replace calibration_override to replace with state machine variant subsystem | User Story | Done | Core Instruments - Sirius |  |  |  | 2 | 148.5 | 1 hr | 1 hr | -146.5 | 100% | 0 | 0
TAP-121182_SIRIUS | 145 |  |  | 01.05.04.31.00.00.00.00 | TAP-95983 | TAP-121182 | [TAP-121182_SIRIUS] ¦ [IRR][Enabler] Tools to analyze motor position controller | User Story | Open | Core Instruments - Sirius |  |  |  | 2 | 148.5 | 1 hr | 1 hr | -146.5 | 74.25 | 0 | 0
TAP-111719 | 146 | TAP-111562, TAP-111760 | TAP-124116 | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 | 148.5 | 1 hr | 1 hr | -143.5 | 0% | 15 | 22 | Story Points
| 147 |  |  | 01.05.05.01.00.00.00.00 | TAP-111719 | TAP-111916 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 148.5 | 1 hr | 1 hr | -148.5 | 0% | 0 | 0
TAP-112039_FRED | 148 |  |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112039 | [TAP-112039_FRED] ¦ [IRR][Fred] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Foundation - Fred |  |  |  | 0 | 148.5 | 1 hr | 1 hr | -148.5 | 0% | 1 | 2
TAP-112040_I2E | 149 |  |  | 01.05.05.03.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-112040_I2E] ¦ [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E |  |  |  | 0 | 148.5 | 1 hr | 1 hr | -148.5 | 100% | 14 | 20
TAP-114445_I2E | 150 |  |  | 01.05.05.04.00.00.00.00 | TAP-111719 | TAP-114445 | [TAP-114445_I2E] ¦ [MIRR][I2E][Spike] Support Sebastian in testing/configuring Galil | User Story | In progress | Advanced Instruments - I2E |  |  |  | 2 | 148.5 | 1 hr | 1 hr | -146.5 | 74.25 | 0 | 0
TAP-114446_I2E | 151 |  |  | 01.05.05.05.00.00.00.00 | TAP-111719 | TAP-114446 | [TAP-114446_I2E] ¦ [MIRR][I2E] Add Ethercat Master/shmios to Diagnostic Folder and rc.startup | User Story | Open | Advanced Instruments - I2E |  |  |  | 3 | 148.5 | 1 hr | 1 hr | -145.5 | 49.5 | 0 | 0
TAP-111721 | 152 | TAP-111760 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 | 148.5 | 1 hr | 1 hr | -124 | 0% | 27 | 30 | Story Points
| 153 |  |  | 01.05.06.01.00.00.00.00 | TAP-111721 | TAP-111917 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 148.5 | 1 hr | 1 hr | -148.5 | 100% | 27 | 30
TAP-115880_SIRIUS | 154 |  |  | 01.05.06.02.00.00.00.00 | TAP-111721 | TAP-115880 | [TAP-115880_SIRIUS] ¦ [IRR][ORSI] Update Lab SW for Hard Stop recovery | User Story | Open | Core Instruments - Sirius |  |  |  | 3 | 148.5 | 1 hr | 1 hr | -145.5 | 49.5 | 0 | 0
TAP-116068_SIRIUS | 155 |  |  | 01.05.06.03.00.00.00.00 | TAP-111721 | TAP-116068 | [TAP-116068_SIRIUS] ¦ [IRR] Generate Controller Prototype for "tipped pulley" HW Design | User Story | Cancelled | Core Instruments - Sirius |  |  |  | 3 | 148.5 | 1 hr | 1 hr | -145.5 | 49.5 | 0 | 0
TAP-116464_SIRIUS | 156 |  |  | 01.05.06.04.00.00.00.00 | TAP-111721 | TAP-116464 | [TAP-116464_SIRIUS] ¦ [IRR][ORSI] Decide on parameters to derate with clinical | User Story | Done | Core Instruments - Sirius |  |  |  | 0.5 | 149 | 1 hr | 1 hr | -148.5 | 100% | 0 | 0
TAP-116465_SIRIUS | 157 |  |  | 01.05.06.05.00.00.00.00 | TAP-111721 | TAP-116465 | [TAP-116465_SIRIUS] ¦ [IRR][RUFS] Attend RUFS | User Story | Done | Core Instruments - Sirius |  |  |  | 5 | 154 | 1 hr | 1 hr | -149 | 100% | 0 | 0
TAP-116466_SIRIUS | 158 |  |  | 01.05.06.06.00.00.00.00 | TAP-111721 | TAP-116466 | [TAP-116466_SIRIUS] ¦ [IRR][ORSI] Reserve time for protocol development and ORSI related controller development | User Story | Cancelled | Core Instruments - Sirius |  |  |  | 5 | 154 | 1 hr | 1 hr | -149 | 100% | 0 | 0
TAP-116467_SIRIUS | 159 |  |  | 01.05.06.07.00.00.00.00 | TAP-111721 | TAP-116467 | [TAP-116467_SIRIUS] ¦ [IRR][RUFS] Prepare lab branch | User Story | Done | Core Instruments - Sirius |  |  |  | 4 | 158 | 1 hr | 1 hr | -154 | 100% | 0 | 0
TAP-121702_SIRIUS | 160 |  |  | 01.05.06.08.00.00.00.00 | TAP-111721 | TAP-121702 | [TAP-121702_SIRIUS] ¦ [IRR] Update IRR SW With Detachment Detection | User Story | In progress | Core Instruments - Sirius |  |  |  | 5 | 158 | 1 hr | 1 hr | -153 | 31.6 | 0 | 0
TAP-122340_HAPPY JAWS | 161 |  |  | 01.05.06.09.00.00.00.00 | TAP-111721 | TAP-122340 | [TAP-122340_HAPPY JAWS] ¦ [IRR] Update Lab SW with Protection Against Slow Close | User Story | In progress | Core Instruments - Happy Jaws |  |  |  | 1 | 158 | 1 hr | 1 hr | -157 | 158 | 0 | 0
TAP-122855_SIRIUS | 162 |  |  | 01.05.06.10.00.00.00.00 | TAP-111721 | TAP-122855 | [TAP-122855_SIRIUS] ¦ [IRR][RUFS] Lab support | User Story | Done | Core Instruments - Sirius |  |  |  | 2 | 160 | 1 hr | 1 hr | -158 | 100% | 0 | 0
TAP-122954_SIRIUS | 163 |  |  | 01.05.06.11.00.00.00.00 | TAP-111721 | TAP-122954 | [TAP-122954_SIRIUS] ¦ [IRR] Prepare lab branch for IRR Summer NoHa Lab | User Story | Open | Core Instruments - Sirius |  |  |  | 2 | 160 | 1 hr | 1 hr | -158 | 80 | 0 | 0
TAP-123066_PUPPETEERS | 164 |  |  | 01.05.06.12.00.00.00.00 | TAP-111721 | TAP-123066 | [TAP-123066_PUPPETEERS] ¦ [IRR][Puppeteers] Merge latest JBO updates to IRR staging branch for ORSI lab | User Story | In progress | Core Instruments - Puppeteers |  |  |  | 2 | 160 | 1 hr | 1 hr | -158 | 80 | 0 | 0
TAP-111722 | 165 | TAP-111760 |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 27 | 30 | Feature Estimation
| 166 |  |  | 01.05.07.01.00.00.00.00 | TAP-111722 | TAP-111918 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 100% | 27 | 30
TAP-111723 | 167 | TAP-111760 |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 27 | 30 | Feature Estimation
| 168 |  |  | 01.05.08.01.00.00.00.00 | TAP-111723 | TAP-111919 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 100% | 27 | 30
TAP-111724 | 169 | TAP-111760 |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 27 | 30 | Feature Estimation
| 170 |  |  | 01.05.09.01.00.00.00.00 | TAP-111724 | TAP-111920 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 100% | 27 | 30
TAP-112119 | 171 | TAP-111760 |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 10 | 20 | Feature Estimation
| 172 |  |  | 01.05.10.01.00.00.00.00 | TAP-112119 | TAP-112120 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 100% | 10 | 20
| 173 |  |  | 01.06.00.00.00.00.00.00 | [9 empty] | 134 | 160 | 1 hr | 1 hr | -26 | 1.194 | 184 | 295
TAP-94125 | 174 | TAP-111753, TAP-111760 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Instrument Homing Compatible with WS5 Structure | Feature | Accepted |  |  |  |  | 77 | 160 | 1 hr | 1 hr | -83 | 0% | 50 | 70 | Story Points
TAP-97747_SIRIUS | 175 |  |  | 01.06.01.01.00.00.00.00 | TAP-94125 | TAP-97747 | [TAP-97747_SIRIUS] ¦ [WS5][Homing][Sirius] Evaluate Homing Controller Architecture and Identify Improvements | User Story | Open | Core Instruments - Sirius |  |  |  | 5 | 160 | 1 hr | 1 hr | -155 | 0%
TAP-97748_SIRIUS | 176 |  |  | 01.06.01.02.00.00.00.00 | TAP-94125 | TAP-97748 | [TAP-97748_SIRIUS] ¦ [WS5][Homing][Sirius] Update DD for Homing Controller | User Story | Open | Core Instruments - Sirius |  |  |  | 4 | 160 | 1 hr | 1 hr | -156 | 0%
TAP-97749_SIRIUS | 177 |  |  | 01.06.01.03.00.00.00.00 | TAP-94125 | TAP-97749 | [TAP-97749_SIRIUS] ¦ [WS5][Homing][Sirius] Run and fix Static Analysis on Homing Controller | User Story | Open | Core Instruments - Sirius |  |  |  | 5 | 160 | 1 hr | 1 hr | -155 | 0%
TAP-97750_SIRIUS | 178 |  |  | 01.06.01.04.00.00.00.00 | TAP-94125 | TAP-97750 | [TAP-97750_SIRIUS] ¦ [WS5][Homing][Sirius] Create/Update Unit tests for Homing Controller | User Story | Open | Core Instruments - Sirius |  |  |  | 6 | 160 | 1 hr | 1 hr | -154 | 0%
TAP-97751_SIRIUS | 179 |  |  | 01.06.01.05.00.00.00.00 | TAP-94125 | TAP-97751 | [TAP-97751_SIRIUS] ¦ [WS5][Homing][Sirius] cFMEA Risk analysis for Homing Controller | User Story | Open | Core Instruments - Sirius |  |  |  | 5 | 160 | 1 hr | 1 hr | -155 | 0%
TAP-97752_SIRIUS | 180 |  |  | 01.06.01.06.00.00.00.00 | TAP-94125 | TAP-97752 | [TAP-97752_SIRIUS] ¦ [WS5][Homing][Sirius] Reserve for RCM creation | User Story | Open | Core Instruments - Sirius |  |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 0%
TAP-97753_SIRIUS | 181 |  |  | 01.06.01.07.00.00.00.00 | TAP-94125 | TAP-97753 | [TAP-97753_SIRIUS] ¦ [WS5][Homing][Sirius] Develop requirements for homing controller (Part 1) | User Story | Open | Core Instruments - Sirius |  |  |  | 6 | 160 | 1 hr | 1 hr | -154 | 0%
TAP-97754_SIRIUS | 182 |  |  | 01.06.01.08.00.00.00.00 | TAP-94125 | TAP-97754 | [TAP-97754_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: ENGAGE_COUPLERS | User Story | Open | Core Instruments - Sirius |  |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97755_SIRIUS | 183 |  |  | 01.06.01.09.00.00.00.00 | TAP-94125 | TAP-97755 | [TAP-97755_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_JAW | User Story | Open | Core Instruments - Sirius |  |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97756_SIRIUS | 184 |  |  | 01.06.01.10.00.00.00.00 | TAP-94125 | TAP-97756 | [TAP-97756_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_TENSION | User Story | Open | Core Instruments - Sirius |  |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97757_SIRIUS | 185 |  |  | 01.06.01.11.00.00.00.00 | TAP-94125 | TAP-97757 | [TAP-97757_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_YAW/HOME_PITCH | User Story | Open | Core Instruments - Sirius |  |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97758_SIRIUS | 186 |  |  | 01.06.01.12.00.00.00.00 | TAP-94125 | TAP-97758 | [TAP-97758_SIRIUS] ¦ [WS5][Homing][Sirius] Develop requirements for homing controller (Part 2) | User Story | Open | Core Instruments - Sirius |  |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 0%
TAP-97910_SIRIUS | 187 |  |  | 01.06.01.13.00.00.00.00 | TAP-94125 | TAP-97910 | [TAP-97910_SIRIUS] ¦ [WS5][Homing][Sirius] Homing Controller Implementation Sync | User Story | Cancelled | Core Instruments - Sirius |  |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 0%
| 188 |  |  | 01.06.01.14.00.00.00.00 | TAP-94125 | TAP-111778 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 100% | 50 | 70
TAP-95800 | 189 | TAP-111754, TAP-111760 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development Motor Controller Compatible with WS5 Structure | Feature | Accepted |  |  |  |  | 29 | 160 | 1 hr | 1 hr | -131 | 0% | 15 | 35 | Story Points
TAP-91185_SIRIUS | 190 |  |  | 01.06.02.01.00.00.00.00 | TAP-95800 | TAP-91185 | [TAP-91185_SIRIUS] ¦ [IRG][SW][WS5] Investigate alternative IDU motor position control approaches | User Story | Open | Core Instruments - Sirius |  |  |  | 4 | 160 | 1 hr | 1 hr | -156 | 0%
| 191 |  |  | 01.06.02.02.00.00.00.00 | TAP-95800 | TAP-111779 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 100% | 15 | 35
TAP-116475_SIRIUS | 192 |  |  | 01.06.02.03.00.00.00.00 | TAP-95800 | TAP-116475 | [TAP-116475_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Informal design review | User Story | Open | Core Instruments - Sirius |  |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 53.3333 | 0 | 0
TAP-116476_SIRIUS | 193 |  |  | 01.06.02.04.00.00.00.00 | TAP-95800 | TAP-116476 | [TAP-116476_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Decide on testing strategy | User Story | Open | Core Instruments - Sirius |  |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 53.3333 | 0 | 0
TAP-116477_SIRIUS | 194 |  |  | 01.06.02.05.00.00.00.00 | TAP-95800 | TAP-116477 | [TAP-116477_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Create MIL/Unit tests for motor controller | User Story | Open | Core Instruments - Sirius |  |  |  | 9 | 160 | 1 hr | 1 hr | -151 | 17.7778 | 0 | 0
TAP-116478_SIRIUS | 195 |  |  | 01.06.02.06.00.00.00.00 | TAP-95800 | TAP-116478 | [TAP-116478_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Update and fix Static Analysis issues | User Story | Done | Core Instruments - Sirius |  |  |  | 2 | 162 | 1 hr | 1 hr | -160 | 100% | 0 | 0
TAP-116479_SIRIUS | 196 |  |  | 01.06.02.07.00.00.00.00 | TAP-95800 | TAP-116479 | [TAP-116479_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Develop requirements | User Story | Open | Core Instruments - Sirius |  |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54 | 0 | 0
TAP-116480_SIRIUS | 197 |  |  | 01.06.02.08.00.00.00.00 | TAP-95800 | TAP-116480 | [TAP-116480_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Perform cFMEA | User Story | Open | Core Instruments - Sirius |  |  |  | 4 | 162 | 1 hr | 1 hr | -158 | 40.5 | 0 | 0
TAP-116482_SIRIUS | 198 |  |  | 01.06.02.09.00.00.00.00 | TAP-95800 | TAP-116482 | [TAP-116482_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Draft design documents | User Story | Open | Core Instruments - Sirius |  |  |  | 1 | 162 | 1 hr | 1 hr | -161 | 162 | 0 | 0
TAP-111740 | 199 | TAP-111756, TAP-111760 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 28 | 162 | 1 hr | 1 hr | -134 | 0% | 60 | 80 | Story Points
| 200 |  |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 60 | 80
TAP-115106_HAPPY JAWS | 201 |  |  | 01.06.03.02.00.00.00.00 | TAP-111740 | TAP-115106 | [TAP-115106_HAPPY JAWS] ¦ [IRR][Phase 1b][Happy Jaws] Refactor teleoperation SWI to consolidate IK and improve architecture | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54 | 0 | 0
TAP-116483_HAPPY JAWS | 202 |  |  | 01.06.03.03.00.00.00.00 | TAP-111740 | TAP-116483 | [TAP-116483_HAPPY JAWS] ¦ [IRR][Phase 1b][Teleoperation] Informal design review | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54 | 0 | 0
TAP-116484_HAPPY JAWS | 203 |  |  | 01.06.03.04.00.00.00.00 | TAP-111740 | TAP-116484 | [TAP-116484_HAPPY JAWS] ¦ [IRR][Phase 1b][Teleoperation] Decide on testing strategy | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54 | 0 | 0
TAP-116485_HAPPY JAWS | 204 |  |  | 01.06.03.05.00.00.00.00 | TAP-111740 | TAP-116485 | [TAP-116485_HAPPY JAWS] ¦ [IRR][Phase 1b][Teleoperation] Create MIL/Unit tests for teleop SWI | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 9 | 162 | 1 hr | 1 hr | -153 | 18 | 0 | 0
TAP-116486_SIRIUS | 205 |  |  | 01.06.03.06.00.00.00.00 | TAP-111740 | TAP-116486 | [TAP-116486_SIRIUS] ¦ [IRR][Phase 1b][Teleoperation] Update and fix Static Analysis issues | User Story | Open | Core Instruments - Sirius |  |  |  | 2 | 162 | 1 hr | 1 hr | -160 | 81 | 0 | 0
TAP-116487_HAPPY JAWS | 206 |  |  | 01.06.03.07.00.00.00.00 | TAP-111740 | TAP-116487 | [TAP-116487_HAPPY JAWS] ¦ [IRR][Phase 1b][Teleoperation] Develop requirements | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54 | 0 | 0
TAP-116488_HAPPY JAWS | 207 |  |  | 01.06.03.08.00.00.00.00 | TAP-111740 | TAP-116488 | [TAP-116488_HAPPY JAWS] ¦ [IRR][Phase 1b][Teleoperation] Perform cFMEA | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 4 | 162 | 1 hr | 1 hr | -158 | 40.5 | 0 | 0
TAP-116490_HAPPY JAWS | 208 |  |  | 01.06.03.09.00.00.00.00 | TAP-111740 | TAP-116490 | [TAP-116490_HAPPY JAWS] ¦ [IRR][Phase 1b][Teleoperation] Draft design documents | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 1 | 162 | 1 hr | 1 hr | -161 | 162 | 0 | 0
TAP-111749 | 209 | TAP-111757, TAP-111760 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 16 | 30 | Feature Estimation
| 210 |  |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 16 | 30
TAP-112328_SIRIUS | 211 |  |  | 01.06.04.02.00.00.00.00 | TAP-111749 | TAP-112328 | [TAP-112328_SIRIUS] ¦ [IRR] Evaluate risk rank of alternate instrument hardware failure modes | User Story | Open | Core Instruments - Sirius |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 0 | 0
TAP-111750 | 212 | TAP-111758, TAP-111760 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Procedure Manager SWI for IRR | Feature | Accepted |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 15 | 35 | Feature Estimation
| 213 |  |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 15 | 35
TAP-111751 | 214 | TAP-111759, TAP-111760 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 28 | 45 | Feature Estimation
| 215 |  |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 28 | 45
TAP-117678 | 216 | TAP-111760 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 0 | 0 | Feature Estimation
| 217 |  |  | 01.07.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 10 | 20
TAP-111834 | 218 | TAP-111760 | TAP-113995 | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 10 | 20 | Feature Estimation
TAP-112842_JACOBIANS | 219 |  |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-112842_JACOBIANS] ¦ Support Kinematic Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 10 | 20
| 220 |  |  | 02.00.00.00.00.00.00.00 | [9 empty] | 76 | 162 | 1 hr | 1 hr | -86 | 2.1316 | 716 | 1266
| 221 |  |  | 02.01.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 2.1316 | 50 | 100
TAP-111747 | 222 | TAP-113104 |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 50 | 100 | Feature Estimation
| 223 |  |  | 02.01.01.01.00.00.00.00 | TAP-111747 | TAP-111913 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 50 | 100
| 224 |  |  | 02.02.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 65 | 85
TAP-111772 | 225 | TAP-113104 |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 15 | 20 | Feature Estimation
| 226 |  |  | 02.02.01.01.00.00.00.00 | TAP-111772 | TAP-111965 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 15 | 20
TAP-111773 | 227 | TAP-113104 |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 50 | 65 | Feature Estimation
| 228 |  |  | 02.02.02.01.00.00.00.00 | TAP-111773 | TAP-111966 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 50 | 65
| 229 |  |  | 02.03.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 45 | 90
TAP-111838 | 230 | TAP-111842, TAP-113104 |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 10 | 15 | Feature Estimation
| 231 |  |  | 02.03.01.01.00.00.00.00 | TAP-111838 | TAP-111967 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 10 | 15
TAP-104213 | 232 | TAP-111842, TAP-113104 |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 15 | 45 | Feature Estimation
| 233 |  |  | 02.03.02.01.00.00.00.00 | TAP-104213 | TAP-111968 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 15 | 45
TAP-111842 | 234 | TAP-113104 | TAP-104213, TAP-111838 | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 20 | 30 | Feature Estimation
| 235 |  |  | 02.03.03.01.00.00.00.00 | TAP-111842 | TAP-111969 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 20 | 30
| 236 |  |  | 02.04.00.00.00.00.00.00 | [9 empty] | 25 | 162 | 1 hr | 1 hr | -137 | 6.48 | 102 | 172
TAP-111774 | 237 | TAP-111775, TAP-112080, TAP-113104 |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 10 | 162 | 1 hr | 1 hr | -152 | 0% | 20 | 34 | Story Points
| 238 |  |  | 02.04.01.01.00.00.00.00 | TAP-111774 | TAP-111970 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 8 | 13
TAP-112183_JACOBIANS | 239 |  |  | 02.04.01.02.00.00.00.00 | TAP-111774 | TAP-112183 | [TAP-112183_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 5 | 8
TAP-112184_CASTLE BLACK | 240 |  |  | 02.04.01.03.00.00.00.00 | TAP-111774 | TAP-112184 | [TAP-112184_CASTLE BLACK] ¦ [IRR][Castle Black] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 100% | 7 | 13
TAP-116177_CASTLE BLACK | 241 |  |  | 02.04.01.04.00.00.00.00 | TAP-111774 | TAP-116177 | [TAP-116177_CASTLE BLACK] ¦ [Spike] Investigate Instrument Observer Mitigations | User Story | Open | Shared Services - Castle Black |  |  |  | 1 | 162 | 1 hr | 1 hr | -161 | 162 | 0 | 0
TAP-116194_PUPPETEERS | 242 |  |  | 02.04.01.05.00.00.00.00 | TAP-111774 | TAP-116194 | [TAP-116194_PUPPETEERS] ¦ [IRR][Puppeteers]cFMEA - Investigate risk analysis for MSO Joint Tracking Check- initial | User Story | Done | Core Instruments - Puppeteers |  |  |  | 5 | 167 | 1 hr | 1 hr | -162 | 100% | 0 | 0
TAP-116202_PUPPETEERS | 243 |  |  | 02.04.01.06.00.00.00.00 | TAP-111774 | TAP-116202 | [TAP-116202_PUPPETEERS] ¦ [IRR][Puppeteers] Create cFMEA draft in Excel Sheet for MSO Joint Tracking Check | User Story | Done | Core Instruments - Puppeteers |  |  |  | 3 | 170 | 1 hr | 1 hr | -167 | 100% | 0 | 0
TAP-116207_PUPPETEERS | 244 |  |  | 02.04.01.07.00.00.00.00 | TAP-111774 | TAP-116207 | [TAP-116207_PUPPETEERS] ¦ [IRR][Puppeteers] Review all MSO Joint Tracking check FMs | User Story | Cancelled | Core Instruments - Puppeteers |  |  |  | 3 | 170 | 1 hr | 1 hr | -167 | 100% | 0 | 0
TAP-116407_PUPPETEERS | 245 |  |  | 02.04.01.08.00.00.00.00 | TAP-111774 | TAP-116407 | [TAP-116407_PUPPETEERS] ¦ [IRR][Puppeteers]cFMEA - Investigate risk analysis for MSO Joint Tracking Check- postReview | User Story | Cancelled | Core Instruments - Puppeteers |  |  |  | 3 | 170 | 1 hr | 1 hr | -167 | 100% | 0 | 0
TAP-116645_PUPPETEERS | 246 |  |  | 02.04.01.09.00.00.00.00 | TAP-111774 | TAP-116645 | [TAP-116645_PUPPETEERS] ¦ [Puppeteers] cFMEA and Polarian Training | User Story | Done | Core Instruments - Puppeteers |  |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 100% | 0 | 0
TAP-112080 | 247 | TAP-111775, TAP-113104 | TAP-111774 | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 14 | 171 | 1 hr | 1 hr | -157 | 0% | 37 | 63 | Story Points
| 248 |  |  | 02.04.02.01.00.00.00.00 | TAP-112080 | TAP-112081 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 13 | 22
TAP-112185_JACOBIANS | 249 |  |  | 02.04.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112185_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 10 | 15
TAP-112186_ORGANELLES | 250 |  |  | 02.04.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112186_ORGANELLES] ¦ [IRR][Organelles] UFSW - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 4 | 6
TAP-112187_INBETWEENERS | 251 |  |  | 02.04.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112187_INBETWEENERS] ¦ [IRR][Inbetweeners] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 10 | 20
TAP-116414_PUPPETEERS | 252 |  |  | 02.04.02.05.00.00.00.00 | TAP-112080 | TAP-116414 | [TAP-116414_PUPPETEERS] ¦ [IRR][Puppeteers] Kinematics prototype for MSO joint check replacement | User Story | Open | Core Instruments - Puppeteers |  |  |  | 13 | 171 | 1 hr | 1 hr | -158 | 13.1538 | 0 | 0
TAP-116211_PUPPETEERS | 253 |  |  | 02.04.02.06.00.00.00.00 | TAP-112080 | TAP-116211 | [TAP-116211_PUPPETEERS] ¦ [IRR][Puppeteers] Review, Approve and Release cFMEA in Polarian | User Story | Groomed | Core Instruments - Puppeteers |  |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 171 | 0 | 0
TAP-111775 | 254 | TAP-113104 | TAP-111774, TAP-112080 | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 0% | 45 | 75 | Feature Estimation
| 255 |  |  | 02.04.03.01.00.00.00.00 | TAP-111775 | TAP-111971 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 16 | 24
TAP-112188_JACOBIANS | 256 |  |  | 02.04.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-112188_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 15 | 25
TAP-112189_ORGANELLES | 257 |  |  | 02.04.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-112189_ORGANELLES] ¦ [IRR][Organelles] UFSW - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 4 | 6
TAP-112190_INBETWEENERS | 258 |  |  | 02.04.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-112190_INBETWEENERS] ¦ [IRR][Inbetweeners] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 10 | 20
TAP-121472_PUPPETEERS | 259 |  |  | 02.04.03.05.00.00.00.00 | TAP-111775 | TAP-121472 | [TAP-121472_PUPPETEERS] ¦ [IRR][Puppeteers] Update Polarion | User Story | Open | Core Instruments - Puppeteers |  |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 171 | 0 | 0
| 260 |  |  | 02.05.00.00.00.00.00.00 | [9 empty] | 0 | 171 | 1 hr | 1 hr | -171 | 171 | 321 | 603
TAP-123862 | 261 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 262 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR][MaybePnP] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 263 | TAP-113104 |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 170 | 325 | Feature Estimation
| 264 |  |  | 02.05.03.01.00.00.00.00 | TAP-111642 | TAP-111941 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 150 | 300
TAP-111942_I2E | 265 |  |  | 02.05.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111942_I2E] ¦ [IRR][I2E] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - I2E |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 17 | 20
TAP-111943_ORGANELLES | 266 |  |  | 02.05.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111943_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 3 | 5
TAP-111944_CASTLE BLACK | 267 |  |  | 02.05.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111944_CASTLE BLACK] ¦ [IRR][Castle Black] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | Shared Services - Castle Black |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 0 | 0
TAP-111656 | 268 | TAP-113104 |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 151 | 278 | Feature Estimation
TAP-111933_CLASSY 2 | 269 |  |  | 02.05.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111933_CLASSY 2] ¦ [IRR][CLASSY 2] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 10 | 15
TAP-111935_BOOSTERS | 270 |  |  | 02.05.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111935_BOOSTERS] ¦ [IRR][Boosters] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 10 | 15
TAP-111936_INBETWEENERS | 271 |  |  | 02.05.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111936_INBETWEENERS] ¦ [IRR][Inbetweeners] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 20 | 30
TAP-111937_CASTLE BLACK | 272 |  |  | 02.05.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111937_CASTLE BLACK] ¦ [IRR][Castle Black] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 0 | 0
TAP-111938_ORGANELLES | 273 |  |  | 02.05.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111938_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 3 | 5
TAP-111939_I2E | 274 |  |  | 02.05.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111939_I2E] ¦ [IRR][I2E] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 8 | 13
| 275 |  |  | 02.05.04.07.00.00.00.00 | TAP-111656 | TAP-111940 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 100 | 200
| 276 |  |  | 02.06.00.00.00.00.00.00 | [9 empty] | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 15 | 30
TAP-111925 | 277 | TAP-113104 |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 15 | 30 | Feature Estimation
| 278 |  |  | 02.06.01.01.00.00.00.00 | TAP-111925 | TAP-111945 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 100% | 15 | 30
TAP-112113 | 279 | TAP-113104 |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
| 280 |  |  | 02.06.02.01.00.00.00.00 | TAP-112113 | TAP-112123 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0
| 281 |  |  | 02.07.00.00.00.00.00.00 | [9 empty] | 51 | 171 | 1 hr | 1 hr | -120 | 3.3529 | 118 | 186
TAP-111865 | 282 | TAP-113104 |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
| 283 |  |  | 02.07.02.00.00.00.00.00 | [9 empty] | 39 | 171 | 1 hr | 1 hr | -132 | 4.3846 | 0 | 0
TAP-113111 | 284 | TAP-111689, TAP-111695 |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 285 | TAP-111687, TAP-111689, TAP-111695 |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 286 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 | 171 | 1 hr | 1 hr | -147 | 0% | 0 | 0 | Story Points
TAP-116170_CASTLE BLACK | 287 |  |  | 02.07.02.03.01.00.00.00 | TAP-114692 | TAP-116170 | [TAP-116170_CASTLE BLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | In progress | Shared Services - Castle Black |  |  |  | 2 | 171 | 1 hr | 1 hr | -169 | 85.5 | 0 | 0
TAP-116199_PUPPETEERS | 288 |  |  | 02.07.02.03.02.00.00.00 | TAP-114692 | TAP-116199 | [TAP-116199_PUPPETEERS] ¦ [IRR][Puppeteers] Sree session | User Story | Done | Core Instruments - Puppeteers |  |  |  | 1 | 172 | 1 hr | 1 hr | -171 | 100% | 0 | 0
TAP-116198_PUPPETEERS | 289 |  |  | 02.07.02.03.03.00.00.00 | TAP-114692 | TAP-116198 | [TAP-116198_PUPPETEERS] ¦ [IRR][Puppeteers] testing protoype changes | User Story | Open | Core Instruments - Puppeteers |  |  |  | 3 | 172 | 1 hr | 1 hr | -169 | 57.3333 | 0 | 0
TAP-116195_PUPPETEERS | 290 |  |  | 02.07.02.03.04.00.00.00 | TAP-114692 | TAP-116195 | [TAP-116195_PUPPETEERS] ¦ [IRR][Puppeteers] Architectual changes for use life calculations | User Story | Done | Core Instruments - Puppeteers |  |  |  | 5 | 177 | 1 hr | 1 hr | -172 | 100% | 0 | 0
TAP-116193_PUPPETEERS | 291 |  |  | 02.07.02.03.05.00.00.00 | TAP-114692 | TAP-116193 | [TAP-116193_PUPPETEERS] ¦ [IRR][Puppeteers] interface changes for use life | User Story | Done | Core Instruments - Puppeteers |  |  |  | 8 | 185 | 1 hr | 1 hr | -177 | 100% | 0 | 0
TAP-123411_PUPPETEERS | 292 |  |  | 02.07.02.03.06.00.00.00 | TAP-114692 | TAP-123411 | [TAP-123411_PUPPETEERS] ¦ [IRR][Puppeteers] Add notcode triggers to sra | User Story | In progress | Core Instruments - Puppeteers |  |  |  | 3 | 185 | 1 hr | 1 hr | -182 | 61.6667 | 0 | 0
TAP-123143_SIRIUS | 293 |  |  | 02.07.02.03.07.00.00.00 | TAP-114692 | TAP-123143 | [TAP-123143_SIRIUS] ¦ [IRR][Sirius] Manually update use life notcodes for staging/IRR-v3-control-development | User Story | Done | Core Instruments - Sirius |  |  |  | 2 | 187 | 1 hr | 1 hr | -185 | 100% | 0 | 0 | Feature Estimation
TAP-114689 | 294 | TAP-111687 |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Accepted |  |  |  |  | 15 | 187 | 1 hr | 1 hr | -172 | 0% | 0 | 0 | Story Points
TAP-115102_PIXEL POETS | 295 |  |  | 02.07.02.04.01.00.00.00 | TAP-114689 | TAP-115102 | [TAP-115102_PIXEL POETS] ¦ [MIRR][Pixel Poets] Finalize Design for Use Life Indicator | User Story | Done | Advanced Instruments - Pixel Poets |  |  |  | 1 | 188 | 1 hr | 1 hr | -187 | 100% | 0 | 0
TAP-115105_PIXEL POETS | 296 |  |  | 02.07.02.04.02.00.00.00 | TAP-114689 | TAP-115105 | [TAP-115105_PIXEL POETS] ¦ [MIRR][Pixel Poets] Define DDS Interface Definitions | User Story | Done | Advanced Instruments - Pixel Poets |  |  |  | 2 | 190 | 1 hr | 1 hr | -188 | 100% | 0 | 0
TAP-116036_PIXEL POETS | 297 |  |  | 02.07.02.04.03.00.00.00 | TAP-114689 | TAP-116036 | [TAP-116036_PIXEL POETS] ¦ [4.1][MIRR][Pixel Poets] MVP for Use Life Countdown Timer | User Story | Done | Advanced Instruments - Pixel Poets |  |  |  | 10 | 200 | 1 hr | 1 hr | -190 | 100% | 0 | 0
TAP-116170_CASTLE BLACK | 298 |  |  | 02.07.02.04.04.00.00.00 | TAP-114689 | TAP-116170 | [TAP-116170_CASTLE BLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | In progress | Shared Services - Castle Black |  |  |  | 2 | 200 | 1 hr | 1 hr | -198 | 100 | 0 | 0
TAP-122695_PIXEL POETS | 299 |  |  | 02.07.02.04.05.00.00.00 | TAP-114689 | TAP-122695 | [TAP-122695_PIXEL POETS] ¦ [4.1][MIRR][Pixel Poets] update MIRR notcodes and strings | User Story | Cancelled | Advanced Instruments - Pixel Poets |  |  |  | 2 | 200 | 1 hr | 1 hr | -198 | 100 | 0 | 0
| 300 |  |  | 02.07.03.00.00.00.00.00 | [9 empty] | 12 | 200 | 1 hr | 1 hr | -188 | 16.6667 | 118 | 186
TAP-90375 | 301 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 | 200 | 1 hr | 1 hr | -191 | 0% |  |  | Story Points
TAP-96606_STELLARS | 302 |  |  | 02.07.03.01.01.00.00.00 | TAP-90375 | TAP-96606 | [TAP-96606_STELLARS] ¦ [Stellars] [TAP-90375] [Enabler] Identify Jama linking to be updated | User Story | Open | Released Product Engineering - Stellars |  |  |  | 1 | 200 | 1 hr | 1 hr | -199 | 0%
TAP-97206_STELLARS | 303 |  |  | 02.07.03.01.02.00.00.00 | TAP-90375 | TAP-97206 | [TAP-97206_STELLARS] ¦ [Stellars] [TAP-90375] [Enabler] Identify User Indication Requirements to Test | User Story | Cancelled | Released Product Engineering - Stellars |  |  |  | 1 | 200 | 1 hr | 1 hr | -199 | 0%
TAP-97207_STELLARS | 304 |  |  | 02.07.03.01.03.00.00.00 | TAP-90375 | TAP-97207 | [TAP-97207_STELLARS] ¦ [Stellars] [TAP-90375] [Enabler] Draft TS and Perform Dry runs | User Story | Cancelled | Released Product Engineering - Stellars |  |  |  | 1 | 200 | 1 hr | 1 hr | -199 | 0%
TAP-97208_STELLARS | 305 |  |  | 02.07.03.01.04.00.00.00 | TAP-90375 | TAP-97208 | [TAP-97208_STELLARS] ¦ [Stellars] [TAP-90375] [enabler]Jama Pull and merge | User Story | Open | Released Product Engineering - Stellars |  |  |  | 5 | 200 | 1 hr | 1 hr | -195 | 0%
TAP-97213_STELLARS | 306 |  |  | 02.07.03.01.05.00.00.00 | TAP-90375 | TAP-97213 | [TAP-97213_STELLARS] ¦ [Stellars] [TAP-90375] Implement, Test and Review UII updates | User Story | Open | Released Product Engineering - Stellars |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0%
TAP-111861 | 307 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0% | 34 | 46 | Story Points
TAP-112869_I2E | 308 |  |  | 02.07.03.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-112869_I2E] ¦ [IRR][I2E] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 12 | 18
TAP-112870_ORGANELLES | 309 |  |  | 02.07.03.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-112870_ORGANELLES] ¦ [IRR][Organelles] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 15 | 20
TAP-112871_DRUSHTI | 310 |  |  | 02.07.03.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-112871_DRUSHTI] ¦ [IRR][Drushti] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 7 | 8
TAP-115871_PUPPETEERS | 311 |  |  | 02.07.03.02.04.00.00.00 | TAP-111861 | TAP-115871 | [TAP-115871_PUPPETEERS] ¦ [IRR] Increment Use count when instrument is expired | User Story | Groomed | Core Instruments - Puppeteers |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 66.6667 | 0 | 0
TAP-111687 | 312 |  | TAP-113123, TAP-114689 | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 28 | 46 | Feature Estimation
TAP-111903_PIXEL POETS | 313 |  |  | 02.07.03.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111903_PIXEL POETS] ¦ [IRR] [Pixel Poets] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 20 | 34
TAP-112872_ORGANELLES | 314 |  |  | 02.07.03.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-112872_ORGANELLES] ¦ [IRR] [Organelles] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 8 | 12
TAP-112873_FRED | 315 |  |  | 02.07.03.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-112873_FRED] ¦ [IRR] [Fred] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 0 | 0
TAP-111689 | 316 |  | TAP-113111, TAP-113123 | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 32 | 48 | Feature Estimation
TAP-111904_PIXEL POETS | 317 |  |  | 02.07.03.04.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111904_PIXEL POETS] ¦ [IRR] [Pixel Poets] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 17 | 28
TAP-112874_ORGANELLES | 318 |  |  | 02.07.03.04.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-112874_ORGANELLES] ¦ [IRR] [Organelles] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 8 | 12
TAP-112875_DRUSHTI | 319 |  |  | 02.07.03.04.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-112875_DRUSHTI] ¦ [IRR] [Drushti] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 7 | 8
TAP-111695 | 320 |  | TAP-113111, TAP-113123 | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 24 | 46 | Feature Estimation
TAP-111905_PIXEL POETS | 321 |  |  | 02.07.03.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111905_PIXEL POETS] ¦ [IRR][Pixel Poets] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 11 | 26
TAP-112876_ORGANELLES | 322 |  |  | 02.07.03.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-112876_ORGANELLES] ¦ [IRR][Organelles] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 6 | 12
TAP-112877_DRUSHTI | 323 |  |  | 02.07.03.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-112877_DRUSHTI] ¦ [IRR][Drushti] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 7 | 8
| 324 |  |  | 03.00.00.00.00.00.00.00 | [9 empty] | 6 | 200 | 1 hr | 1 hr | -194 | 33.3333 | 396 | 678
| 325 |  |  | 03.01.00.00.00.00.00.00 | [9 empty] | 6 | 200 | 1 hr | 1 hr | -194 | 33.3333 | 126 | 200
TAP-111753 | 326 | TAP-111761, TAP-111765 | TAP-94125 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 30 | 50 | Feature Estimation
| 327 |  |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 30 | 50
TAP-111754 | 328 | TAP-110382, TAP-111765 | TAP-95800 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0% | 10 | 15 | Feature Estimation
| 329 |  |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 15
TAP-116481_SIRIUS | 330 |  |  | 03.01.02.02.00.00.00.00 | TAP-111754 | TAP-116481 | [TAP-116481_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Sirius |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 66.6667 | 0 | 0
TAP-111756 | 331 | TAP-111762, TAP-111765 | TAP-111740 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0% | 35 | 45 | Feature Estimation
| 332 |  |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 35 | 45
TAP-116489_HAPPY JAWS | 333 |  |  | 03.01.03.02.00.00.00.00 | TAP-111756 | TAP-116489 | [TAP-116489_HAPPY JAWS] ¦ [IRR][Phase 1b][Teleoperation] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Happy Jaws |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 66.6667 | 0 | 0
TAP-111757 | 334 | TAP-111748, TAP-111765 | TAP-111749 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 16 | 30 | Feature Estimation
| 335 |  |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 16 | 30
TAP-111758 | 336 | TAP-111764, TAP-111765 | TAP-111750 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 15 | 30 | Feature Estimation
| 337 |  |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 15 | 30
TAP-111759 | 338 | TAP-111766, TAP-111765 | TAP-111751 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 20 | 30 | Feature Estimation
| 339 |  |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 20 | 30
| 340 |  |  | 03.02.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 78 | 113
TAP-111761 | 341 | TAP-111765 | TAP-111753 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 25 | 30 | Feature Estimation
| 342 |  |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 25 | 30
TAP-110382 | 343 | TAP-111765 | TAP-111754 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 5 | 8 | Feature Estimation
| 344 |  |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 5 | 8
TAP-111762 | 345 | TAP-111765 | TAP-111756 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 15 | 25 | Feature Estimation
| 346 |  |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 15 | 25
TAP-111748 | 347 | TAP-111765 | TAP-111757 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 8 | 15 | Feature Estimation
| 348 |  |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 8 | 15
TAP-111764 | 349 | TAP-111765 | TAP-111758 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 10 | 15 | Feature Estimation
| 350 |  |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 15
TAP-111766 | 351 | TAP-111765 | TAP-111759 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 15 | 20 | Feature Estimation
| 352 |  |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 15 | 20
| 353 |  |  | 03.03.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 192 | 365
TAP-112082 | 354 | TAP-111765 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 50 | 125 | Feature Estimation
| 355 |  |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 15 | 60
TAP-113209_I2E | 356 |  |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-113209_I2E] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 15
TAP-113210_ORGANELLES | 357 |  |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-113210_ORGANELLES] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 20
TAP-113211_PIXEL POETS | 358 |  |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-113211_PIXEL POETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 8 | 15
TAP-113212_JACOBIANS | 359 |  |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-113212_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 7 | 15
TAP-112093 | 360 | TAP-111765 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 55 | 70 | Feature Estimation
| 361 |  |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 55 | 70
TAP-112094 | 362 | TAP-111765 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 87 | 170 | Feature Estimation
| 363 |  |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 87 | 170
| 364 |  |  | 04.00.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 200 | 400
TAP-113100 | 365 | TAP-113101 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 200 | 400 | Feature Estimation
| 366 |  |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 200 | 400
| 367 |  |  | 05.00.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 301 | 487
TAP-111900 | 368 | TAP-121104 | TAP-111767 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 79 | 152 | Feature Estimation
| 369 |  |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 30 | 60
TAP-112678_BUG HUNTERS | 370 |  |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-112678_BUG HUNTERS] ¦ [M-IRR][Bug Hunters] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Bug Hunters |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 0 | 1
TAP-112679_I2E | 371 |  |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-112679_I2E] ¦ [M-IRR][I2E] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - I2E |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 15
TAP-112680_JACOBIANS | 372 |  |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-112680_JACOBIANS] ¦ [M-IRR][Jacobians] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Jacobians |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 13 | 20
TAP-112681_ORGANELLES | 373 |  |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-112681_ORGANELLES] ¦ [M-IRR][Organelles] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Organelles |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 30
TAP-112682_PIXEL POETS | 374 |  |  | 05.01.06.00.00.00.00.00 | TAP-111900 | TAP-112682 | [TAP-112682_PIXEL POETS] ¦ [M-IRR][Pixel Poets] Formal Software Verification activities | Feature Estimation | Cancelled | Advanced Instruments - Pixel Poets |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 30
TAP-112683_SCRUMBLEDORES | 375 |  |  | 05.01.07.00.00.00.00.00 | TAP-111900 | TAP-112683 | [TAP-112683_SCRUMBLEDORES] ¦ [M-IRR][Scrumbledores] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Scrumbledores |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 9 | 12
TAP-112684_SUNRISERS | 376 |  |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-112684_SUNRISERS] ¦ [M-IRR][Sunrisers] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 3 | 6
TAP-112685_TEAMBD | 377 |  |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-112685_TEAMBD] ¦ [M-IRR][TeamBD] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 3 | 5
TAP-112686_CASTLE BLACK | 378 |  |  | 05.01.10.00.00.00.00.00 | TAP-111900 | TAP-112686 | [TAP-112686_CASTLE BLACK] ¦ [M-IRR][Castle Black] Formal Software Verification activities | Feature Estimation | Cancelled | Shared Services - Castle Black |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 3 | 5
TAP-112688_COSSACKS | 379 |  |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-112688_COSSACKS] ¦ [M-IRR][Cossacks] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 1 | 3
TAP-112689_ICONICS | 380 |  |  | 05.01.12.00.00.00.00.00 | TAP-111900 | TAP-112689 | [TAP-112689_ICONICS] ¦ [M-IRR][Iconics] Formal Software Verification activities | Feature Estimation | Cancelled | Released Product Engineering - Iconics |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 1 | 3
TAP-112042 | 381 | TAP-121104 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 22 | 30 | Feature Estimation
TAP-112222_BUILDERS | 382 |  |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112222_BUILDERS] ¦ [V3.1][IRR][Builders] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 22 | 30
TAP-111692 | 383 | TAP-121104 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 130 | 195 | Feature Estimation
TAP-112223_ASTRA NPS DEVELOPERS | 384 |  |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-112223_ASTRA NPS DEVELOPERS] ¦ [IRR][Astra NPS Developers] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 20 | 25
TAP-112224_TOOLS RULES | 385 |  |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-112224_TOOLS RULES] ¦ [IRR][Tools Rules] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 20 | 25
TAP-112226_INBETWEENERS | 386 |  |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-112226_INBETWEENERS] ¦ [IRR][Inbetweeners] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 50 | 65
TAP-112227_TRIPLE TEA | 387 |  |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-112227_TRIPLE TEA] ¦ [IRR][Triple Tea] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 40 | 80
TAP-112231 | 388 | TAP-121104 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 40 | 50 | Feature Estimation
TAP-112236_ASTRA NPS VALIDATORS | 389 |  |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112236_ASTRA NPS VALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 40 | 50
TAP-112233 | 390 | TAP-121104 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 10 | 20 | Feature Estimation
TAP-112237_ASTRA NPS VALIDATORS | 391 |  |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112237_ASTRA NPS VALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 10 | 20
TAP-112234 | 392 | TAP-121104 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 20 | 40 | Feature Estimation
TAP-112240_TOOLS RULES | 393 |  |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112240_TOOLS RULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 100% | 20 | 40
TAP-113127 | 394 | TAP-121104 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 0 | 0 | Feature Estimation
| 395 |  |  | 06.00.00.00.00.00.00.00 | [9 empty] | 241.25 | 200 | 1 hr | 1 hr | 41.25 | 0.82902 | 0 | 0
| 396 |  |  | 06.01.00.00.00.00.00.00 | [9 empty] | 225.25 | 200 | 1 hr | 1 hr | 25.25 | 0.8879 | 0 | 0
| 397 |  |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 |  | Defect | Investigation |  |  |  |  | 30 | 200 | 1 hr | 1 hr | -170 | 6.6667 | 0 | 0
TAP-115187 | 398 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 | 229 | 1 hr | 1 hr | -200 | 100% | 0 | 0
TAP-115835_STELLARS | 399 |  |  | 06.01.01.01.01.00.00.00 | TAP-115187 | TAP-115835 | [TAP-115835_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 1 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 5 | 234 | 1 hr | 1 hr | -229 | 100%
TAP-115839_STELLARS | 400 |  |  | 06.01.01.01.02.00.00.00 | TAP-115187 | TAP-115839 | [TAP-115839_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Draft Implementation changes - Part2 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 2 | 236 | 1 hr | 1 hr | -234 | 100% | 0 | 0
TAP-115837_STELLARS | 401 |  |  | 06.01.01.01.03.00.00.00 | TAP-115187 | TAP-115837 | [TAP-115837_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify FM/FMEA updates - Part 1 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 1 | 237 | 1 hr | 1 hr | -236 | 100%
TAP-115838_STELLARS | 402 |  |  | 06.01.01.01.04.00.00.00 | TAP-115187 | TAP-115838 | [TAP-115838_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Update CCB fields and Review - part 1 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 3 | 240 | 1 hr | 1 hr | -237 | 100%
TAP-115840_STELLARS | 403 |  |  | 06.01.01.01.05.00.00.00 | TAP-115187 | TAP-115840 | [TAP-115840_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Finalise and review Requirement Changes | User Story | Done | Released Product Engineering - Stellars |  |  |  | 2 | 242 | 1 hr | 1 hr | -240 | 100%
TAP-116265_STELLARS | 404 |  |  | 06.01.01.01.06.00.00.00 | TAP-115187 | TAP-116265 | [TAP-116265_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 2 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 2 | 244 | 1 hr | 1 hr | -242 | 100%
TAP-116278_SUNRISERS | 405 |  |  | 06.01.01.01.07.00.00.00 | TAP-115187 | TAP-116278 | [TAP-116278_SUNRISERS] ¦ [Sunrisers] [RAS-7203] [Enabler] Implementation changes review - SP2 | User Story | Done | Released Product Engineering - Sunrisers |  |  |  | 1 | 245 | 1 hr | 1 hr | -244 | 100% | 0 | 0
TAP-116308_STELLARS | 406 |  |  | 06.01.01.01.08.00.00.00 | TAP-115187 | TAP-116308 | [TAP-116308_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 3 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 2 | 247 | 1 hr | 1 hr | -245 | 100%
TAP-116316_STELLARS | 407 |  |  | 06.01.01.01.09.00.00.00 | TAP-115187 | TAP-116316 | [TAP-116316_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Draft and Review FM/FMEA updates | User Story | Done | Released Product Engineering - Stellars |  |  |  | 2 | 249 | 1 hr | 1 hr | -247 | 100%
TAP-116323_STELLARS | 408 |  |  | 06.01.01.01.10.00.00.00 | TAP-115187 | TAP-116323 | [TAP-116323_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify FM/FMEA updates - Part 2 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 3 | 252 | 1 hr | 1 hr | -249 | 100%
TAP-116535_SUNRISERS | 409 |  |  | 06.01.01.01.11.00.00.00 | TAP-115187 | TAP-116535 | [TAP-116535_SUNRISERS] ¦ [Sunrisers] [RAS-7203] [Enabler] Implementation changes review - SP3 | User Story | Done | Released Product Engineering - Sunrisers |  |  |  | 3 | 255 | 1 hr | 1 hr | -252 | 100% | 0 | 0
TAP-117437_STELLARS | 410 |  |  | 06.01.01.01.12.00.00.00 | TAP-115187 | TAP-117437 | [TAP-117437_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 3 | User Story | Cancelled | Released Product Engineering - Stellars |  |  |  | 3 | 255 | 1 hr | 1 hr | -252 | 100% | 0 | 0
TAP-117468_STELLARS | 411 |  |  | 06.01.01.01.13.00.00.00 | TAP-115187 | TAP-117468 | [TAP-117468_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Draft Implementation changes - Part1 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 1 | 256 | 1 hr | 1 hr | -255 | 100% | 0 | 0
TAP-118097_STELLARS | 412 |  |  | 06.01.01.01.14.00.00.00 | TAP-115187 | TAP-118097 | [TAP-118097_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Update CCB fields and Review - part 2 | User Story | Done | Released Product Engineering - Stellars |  |  |  | 2 | 258 | 1 hr | 1 hr | -256 | 100%
TAP-122269 | 413 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 1 | 258 | 1 hr | 1 hr | -257 | 0% | 0 | 0 | Feature Estimation
TAP-117467_STELLARS | 414 |  |  | 06.01.01.02.01.00.00.00 | TAP-122269 | TAP-117467 | [TAP-117467_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Attend CCB Review | User Story | Open | Released Product Engineering - Stellars |  |  |  | 1 | 258 | 1 hr | 1 hr | -257 | 0%
| 415 |  |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 |  | Defect | Investigation |  |  |  |  | 108.25 | 258 | 1 hr | 1 hr | -149.75 | 0%
TAP-64314 | 416 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 | 290.25 |  | 1 hr | -258 | 100%
TAP-60617_JACOBIANS | 417 |  |  | 06.01.02.01.01.00.00.00 | TAP-64314 | TAP-60617 | [TAP-60617_JACOBIANS] ¦ [MBTI][Spike] Investigate Potential Causes of Roll Jump Discontinuity (RAS-7532) | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 6.25 | 296.5 | 1 hr | 1 hr | -290.25 | 100%
TAP-64835_JACOBIANS | 418 |  |  | 06.01.02.01.02.00.00.00 | TAP-64314 | TAP-64835 | [TAP-64835_JACOBIANS] ¦ [MBTI][Spike] (RAS-7532) Simulate Potential fixes for Roll Jump Discontinuity | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 6.25 | 296.5 | 1 hr | 1 hr | -290.25 | 0%
TAP-64849_JACOBIANS | 419 |  |  | 06.01.02.01.03.00.00.00 | TAP-64314 | TAP-64849 | [TAP-64849_JACOBIANS] ¦ [MBTI][Spike] (RAS-7532) Provide Documentation for Issue If Needed for Potential CAPA of Roll Defect Issue | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 6.25 | 296.5 | 1 hr | 1 hr | -290.25 | 0%
TAP-67852_JACOBIANS | 420 |  |  | 06.01.02.01.04.00.00.00 | TAP-64314 | TAP-67852 | [TAP-67852_JACOBIANS] ¦ [CAPA][Jacobians] Technical Root Cause Analysis for CAPA | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 8 | 304.5 | 1 hr | 1 hr | -296.5 | 100%
TAP-67859_JACOBIANS | 421 |  |  | 06.01.02.01.05.00.00.00 | TAP-64314 | TAP-67859 | [TAP-67859_JACOBIANS] ¦ [CAPA][Jacobians] Process Root Cause Analysis for CAPA | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 8 | 312.5 | 1 hr | 1 hr | -304.5 | 100%
TAP-67866_JACOBIANS | 422 |  |  | 06.01.02.01.06.00.00.00 | TAP-64314 | TAP-67866 | [TAP-67866_JACOBIANS] ¦ [CAPA][Jacobians] Investigation Meetings, Discussions, and Cause Mapping (1 of 2) | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 3 | 315.5 | 1 hr | 1 hr | -312.5 | 100%
TAP-67873_JACOBIANS | 423 |  |  | 06.01.02.01.07.00.00.00 | TAP-64314 | TAP-67873 | [TAP-67873_JACOBIANS] ¦ [CAPA][Jacobians] Investigation Meetings, Discussions, and Cause Mapping (2 of 2) | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 3 | 318.5 | 1 hr | 1 hr | -315.5 | 100%
TAP-67880_JACOBIANS | 424 |  |  | 06.01.02.01.08.00.00.00 | TAP-64314 | TAP-67880 | [TAP-67880_JACOBIANS] ¦ [CAPA][Jacobians] Clearly Document Root Cause Analysis | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 319.5 | 1 hr | 1 hr | -318.5 | 100%
TAP-67881_JACOBIANS | 425 |  |  | 06.01.02.01.09.00.00.00 | TAP-64314 | TAP-67881 | [TAP-67881_JACOBIANS] ¦ [CAPA][Jacobians] Write Action Plan | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1.5 | 321 | 1 hr | 1 hr | -319.5 | 100%
TAP-67882_JACOBIANS | 426 |  |  | 06.01.02.01.10.00.00.00 | TAP-64314 | TAP-67882 | [TAP-67882_JACOBIANS] ¦ [CAPA][Jacobians] Write Effectiveness Plan | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1.5 | 322.5 | 1 hr | 1 hr | -321 | 100%
TAP-64315 | 427 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 347.5 |  | 1 hr | -322.5 | 100%
TAP-72807_JACOBIANS | 428 |  |  | 06.01.02.02.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-72807_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 8 | 355.5 | 1 hr | 1 hr | -347.5 | 100%
TAP-73681_JACOBIANS | 429 |  |  | 06.01.02.02.02.00.00.00 | TAP-64315 | TAP-73681 | [TAP-73681_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 4 | 359.5 | 1 hr | 1 hr | -355.5 | 100%
TAP-73690_JACOBIANS | 430 |  |  | 06.01.02.02.03.00.00.00 | TAP-64315 | TAP-73690 | [TAP-73690_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Document Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 2 | 361.5 | 1 hr | 1 hr | -359.5 | 100%
TAP-73728_JACOBIANS | 431 |  |  | 06.01.02.02.04.00.00.00 | TAP-64315 | TAP-73728 | [TAP-73728_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Investigation Meetings, Discussions, and Cause Mapping Kinematics Unwrapping Discontinuity | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 2 | 361.5 | 1 hr | 1 hr | -359.5 | 0%
TAP-73736_JACOBIANS | 432 |  |  | 06.01.02.02.05.00.00.00 | TAP-64315 | TAP-73736 | [TAP-73736_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Action Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 362.5 | 1 hr | 1 hr | -361.5 | 100%
TAP-73732_JACOBIANS | 433 |  |  | 06.01.02.02.06.00.00.00 | TAP-64315 | TAP-73732 | [TAP-73732_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 363.5 | 1 hr | 1 hr | -362.5 | 100%
TAP-73752_JACOBIANS | 434 |  |  | 06.01.02.02.07.00.00.00 | TAP-64315 | TAP-73752 | [TAP-73752_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 364.5 | 1 hr | 1 hr | -363.5 | 100%
TAP-76433_REFLECT | 435 |  |  | 06.01.02.02.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-76433_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect |  |  |  | 3 | 367.5 | 1 hr | 1 hr | -364.5 | 100%
TAP-76437_REFLECT | 436 |  |  | 06.01.02.02.09.00.00.00 | TAP-64315 | TAP-76437 | [TAP-76437_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Write Action and Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect |  |  |  | 2 | 369.5 | 1 hr | 1 hr | -367.5 | 100%
TAP-76441_REFLECT | 437 |  |  | 06.01.02.02.10.00.00.00 | TAP-64315 | TAP-76441 | [TAP-76441_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect |  |  |  | 2 | 371.5 | 1 hr | 1 hr | -369.5 | 100%
TAP-79223_JACOBIANS | 438 |  |  | 06.01.02.02.11.00.00.00 | TAP-64315 | TAP-79223 | [TAP-79223_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Route CAPA in Agile | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 372.5 | 1 hr | 1 hr | -371.5 | 100%
TAP-76243 | 439 |  |  | 06.01.02.03.00.00.00.00 |  | TAP-76243 | [TAP-76243] ¦ [CAPA] PI11 Kinematics SW CAPA Work: Investigation & Implementation | Feature | Cancelled |  |  |  |  | 1 | 372.5 |  | 1 hr | -371.5 | 0%
TAP-64360_JACOBIANS | 440 |  |  | 06.01.02.03.01.00.00.00 | TAP-76243 | TAP-64360 | [TAP-64360_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 10 | 372.5 | 1 hr | 1 hr | -362.5 | 0%
TAP-64119_JACOBIANS | 441 |  |  | 06.01.02.03.02.00.00.00 | TAP-76243 | TAP-64119 | [TAP-64119_JACOBIANS] ¦ [Enabler] Create Large Set of Challenging Edge Cases for Kinematic Pipeline | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 5 | 372.5 | 1 hr | 1 hr | -367.5 | 0%
TAP-74719_JACOBIANS | 442 |  |  | 06.01.02.03.03.00.00.00 | TAP-76243 | TAP-74719 | [TAP-74719_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Develop Specifications for Kinematic Pipeline Behavior At Joint Limits | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 6 | 372.5 | 1 hr | 1 hr | -366.5 | 0%
TAP-74721_JACOBIANS | 443 |  |  | 06.01.02.03.04.00.00.00 | TAP-76243 | TAP-74721 | [TAP-74721_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Design, prototype, and evaluate RCM that could have caught roll fix update | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 5 | 372.5 | 1 hr | 1 hr | -367.5 | 0%
TAP-73753_JACOBIANS | 444 |  |  | 06.01.02.03.05.00.00.00 | TAP-76243 | TAP-73753 | [TAP-73753_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 3 | 372.5 | 1 hr | 1 hr | -369.5 | 0%
TAP-83712 | 445 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 394.5 |  | 1 hr | -372.5 | 100%
TAP-86373_JACOBIANS | 446 |  |  | 06.01.02.04.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-86373_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 2 | 396.5 | 1 hr | 1 hr | -394.5 | 100%
TAP-86374_JACOBIANS | 447 |  |  | 06.01.02.04.02.00.00.00 | TAP-83712 | TAP-86374 | [TAP-86374_JACOBIANS] ¦ [CAPA][SWEEP] Fix Force Feedback issue at Static Limits | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 8 | 404.5 | 1 hr | 1 hr | -396.5 | 100%
TAP-86375_JACOBIANS | 448 |  |  | 06.01.02.04.03.00.00.00 | TAP-83712 | TAP-86375 | [TAP-86375_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Test CAPA solution | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 8 | 404.5 | 1 hr | 1 hr | -396.5 | 0%
TAP-86376_JACOBIANS | 449 |  |  | 06.01.02.04.04.00.00.00 | TAP-83712 | TAP-86376 | [TAP-86376_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Finalize Preliminary Prototypes | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 5 | 409.5 | 1 hr | 1 hr | -404.5 | 100%
TAP-89237_JACOBIANS | 450 |  |  | 06.01.02.04.05.00.00.00 | TAP-83712 | TAP-89237 | [TAP-89237_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User Studies Part 2 | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 410.5 | 1 hr | 1 hr | -409.5 | 100%
TAP-92875_JACOBIANS | 451 |  |  | 06.01.02.04.06.00.00.00 | TAP-83712 | TAP-92875 | [TAP-92875_JACOBIANS] ¦ [CAPA][SWEEP] Review MS Observer RCM | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 5 | 415.5 | 1 hr | 1 hr | -410.5 | 100%
TAP-92876_JACOBIANS | 452 |  |  | 06.01.02.04.07.00.00.00 | TAP-83712 | TAP-92876 | [TAP-92876_JACOBIANS] ¦ [CAPA][UNWRAP] Review MS Observer for UNWRAP CAPA | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 5 | 415.5 | 1 hr | 1 hr | -410.5 | 0%
TAP-93695_JACOBIANS | 453 |  |  | 06.01.02.04.08.00.00.00 | TAP-83712 | TAP-93695 | [TAP-93695_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Investigate Manual Mode Edge Case | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 416.5 | 1 hr | 1 hr | -415.5 | 100%
| 454 |  |  | 06.01.03.00.00.00.00.00 |  | RAS-9107 |  | Defect | Open |  |  |  |  | 76 | 416.5 | 1 hr | 1 hr | -340.5 | 0%
TAP-64315 | 455 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 441.5 |  | 1 hr | -416.5 | 100%
TAP-72807_JACOBIANS | 456 |  |  | 06.01.03.01.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-72807_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 8 | 449.5 | 1 hr | 1 hr | -441.5 | 100%
TAP-73681_JACOBIANS | 457 |  |  | 06.01.03.01.02.00.00.00 | TAP-64315 | TAP-73681 | [TAP-73681_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 4 | 453.5 | 1 hr | 1 hr | -449.5 | 100%
TAP-73690_JACOBIANS | 458 |  |  | 06.01.03.01.03.00.00.00 | TAP-64315 | TAP-73690 | [TAP-73690_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Document Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 2 | 455.5 | 1 hr | 1 hr | -453.5 | 100%
TAP-73728_JACOBIANS | 459 |  |  | 06.01.03.01.04.00.00.00 | TAP-64315 | TAP-73728 | [TAP-73728_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Investigation Meetings, Discussions, and Cause Mapping Kinematics Unwrapping Discontinuity | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 2 | 455.5 | 1 hr | 1 hr | -453.5 | 0%
TAP-73736_JACOBIANS | 460 |  |  | 06.01.03.01.05.00.00.00 | TAP-64315 | TAP-73736 | [TAP-73736_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Action Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 456.5 | 1 hr | 1 hr | -455.5 | 100%
TAP-73732_JACOBIANS | 461 |  |  | 06.01.03.01.06.00.00.00 | TAP-64315 | TAP-73732 | [TAP-73732_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 457.5 | 1 hr | 1 hr | -456.5 | 100%
TAP-73752_JACOBIANS | 462 |  |  | 06.01.03.01.07.00.00.00 | TAP-64315 | TAP-73752 | [TAP-73752_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 458.5 | 1 hr | 1 hr | -457.5 | 100%
TAP-76433_REFLECT | 463 |  |  | 06.01.03.01.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-76433_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect |  |  |  | 3 | 461.5 | 1 hr | 1 hr | -458.5 | 100%
TAP-76437_REFLECT | 464 |  |  | 06.01.03.01.09.00.00.00 | TAP-64315 | TAP-76437 | [TAP-76437_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Write Action and Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect |  |  |  | 2 | 463.5 | 1 hr | 1 hr | -461.5 | 100%
TAP-76441_REFLECT | 465 |  |  | 06.01.03.01.10.00.00.00 | TAP-64315 | TAP-76441 | [TAP-76441_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect |  |  |  | 2 | 465.5 | 1 hr | 1 hr | -463.5 | 100%
TAP-79223_JACOBIANS | 466 |  |  | 06.01.03.01.11.00.00.00 | TAP-64315 | TAP-79223 | [TAP-79223_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Route CAPA in Agile | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 466.5 | 1 hr | 1 hr | -465.5 | 100%
TAP-76243 | 467 |  |  | 06.01.03.02.00.00.00.00 |  | TAP-76243 | [TAP-76243] ¦ [CAPA] PI11 Kinematics SW CAPA Work: Investigation & Implementation | Feature | Cancelled |  |  |  |  | 1 | 466.5 |  | 1 hr | -465.5 | 0%
TAP-64360_JACOBIANS | 468 |  |  | 06.01.03.02.01.00.00.00 | TAP-76243 | TAP-64360 | [TAP-64360_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 10 | 466.5 | 1 hr | 1 hr | -456.5 | 0%
TAP-64119_JACOBIANS | 469 |  |  | 06.01.03.02.02.00.00.00 | TAP-76243 | TAP-64119 | [TAP-64119_JACOBIANS] ¦ [Enabler] Create Large Set of Challenging Edge Cases for Kinematic Pipeline | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 5 | 466.5 | 1 hr | 1 hr | -461.5 | 0%
TAP-74719_JACOBIANS | 470 |  |  | 06.01.03.02.03.00.00.00 | TAP-76243 | TAP-74719 | [TAP-74719_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Develop Specifications for Kinematic Pipeline Behavior At Joint Limits | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 6 | 466.5 | 1 hr | 1 hr | -460.5 | 0%
TAP-74721_JACOBIANS | 471 |  |  | 06.01.03.02.04.00.00.00 | TAP-76243 | TAP-74721 | [TAP-74721_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Design, prototype, and evaluate RCM that could have caught roll fix update | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 5 | 466.5 | 1 hr | 1 hr | -461.5 | 0%
TAP-73753_JACOBIANS | 472 |  |  | 06.01.03.02.05.00.00.00 | TAP-76243 | TAP-73753 | [TAP-73753_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians |  |  |  | 3 | 466.5 | 1 hr | 1 hr | -463.5 | 0%
TAP-83712 | 473 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 488.5 |  | 1 hr | -466.5 | 100%
TAP-86373_JACOBIANS | 474 |  |  | 06.01.03.03.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-86373_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 2 | 490.5 | 1 hr | 1 hr | -488.5 | 100%
TAP-86374_JACOBIANS | 475 |  |  | 06.01.03.03.02.00.00.00 | TAP-83712 | TAP-86374 | [TAP-86374_JACOBIANS] ¦ [CAPA][SWEEP] Fix Force Feedback issue at Static Limits | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 8 | 498.5 | 1 hr | 1 hr | -490.5 | 100%
TAP-86375_JACOBIANS | 476 |  |  | 06.01.03.03.03.00.00.00 | TAP-83712 | TAP-86375 | [TAP-86375_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Test CAPA solution | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 8 | 498.5 | 1 hr | 1 hr | -490.5 | 0%
TAP-86376_JACOBIANS | 477 |  |  | 06.01.03.03.04.00.00.00 | TAP-83712 | TAP-86376 | [TAP-86376_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Finalize Preliminary Prototypes | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 5 | 503.5 | 1 hr | 1 hr | -498.5 | 100%
TAP-89237_JACOBIANS | 478 |  |  | 06.01.03.03.05.00.00.00 | TAP-83712 | TAP-89237 | [TAP-89237_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User Studies Part 2 | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 504.5 | 1 hr | 1 hr | -503.5 | 100%
TAP-92875_JACOBIANS | 479 |  |  | 06.01.03.03.06.00.00.00 | TAP-83712 | TAP-92875 | [TAP-92875_JACOBIANS] ¦ [CAPA][SWEEP] Review MS Observer RCM | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 5 | 509.5 | 1 hr | 1 hr | -504.5 | 100%
TAP-92876_JACOBIANS | 480 |  |  | 06.01.03.03.07.00.00.00 | TAP-83712 | TAP-92876 | [TAP-92876_JACOBIANS] ¦ [CAPA][UNWRAP] Review MS Observer for UNWRAP CAPA | User Story | Cancelled | Advanced Instruments - Jacobians |  |  |  | 5 | 509.5 | 1 hr | 1 hr | -504.5 | 0%
TAP-93695_JACOBIANS | 481 |  |  | 06.01.03.03.08.00.00.00 | TAP-83712 | TAP-93695 | [TAP-93695_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Investigate Manual Mode Edge Case | User Story | Done | Advanced Instruments - Jacobians |  |  |  | 1 | 510.5 | 1 hr | 1 hr | -509.5 | 100%
| 482 |  |  | 06.01.04.00.00.00.00.00 |  | RAS-10590 |  | Defect | Confirmed |  |  |  |  | 11 | 510.5 | 1 hr | 1 hr | -499.5 | 0%
TAP-86405_VISUAL | 483 |  |  | 06.01.04.01.00.00.00.00 |  | TAP-86405 | [TAP-86405_VISUAL] ¦ [CAPA] Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual |  |  |  | 3 | 513.5 | 1 hr | 1 hr | -510.5 | 100%
TAP-89386_VISUAL | 484 |  |  | 06.01.04.02.00.00.00.00 |  | TAP-89386 | [TAP-89386_VISUAL] ¦ [CAPA] Test support - Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual |  |  |  | 1 | 514.5 | 1 hr | 1 hr | -513.5 | 100%
TAP-90083_VISUAL | 485 |  |  | 06.01.04.03.00.00.00.00 |  | TAP-90083 | [TAP-90083_VISUAL] ¦ [CAPA] Test support - Storz Controller crash on second storz power cycle with endoscope connected v3.0 | User Story | Done | Foundation - Visual |  |  |  | 1 | 515.5 | 1 hr | 1 hr | -514.5 | 100%
TAP-90540_VISUAL | 486 |  |  | 06.01.04.04.00.00.00.00 |  | TAP-90540 | [TAP-90540_VISUAL] ¦ [CAPA] Dev support - Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual |  |  |  | 2 | 517.5 | 1 hr | 1 hr | -515.5 | 100%
TAP-90683_VISUAL | 487 |  |  | 06.01.04.05.00.00.00.00 |  | TAP-90683 | [TAP-90683_VISUAL] ¦ [CAPA][Enabler] Test support - Set up Valhalla ICG tower and KS for v2.0.3/v3.0API2 testing | User Story | Done | Foundation - Visual |  |  |  | 1 | 518.5 | 1 hr | 1 hr | -517.5 | 100%
TAP-91134_VISUAL | 488 |  |  | 06.01.04.06.00.00.00.00 |  | TAP-91134 | [TAP-91134_VISUAL] ¦ [CAPA] Test support - Storz Controller crash on second storz power cycle with endoscope connected v3.0 | User Story | Done | Foundation - Visual |  |  |  | 1 | 519.5 | 1 hr | 1 hr | -518.5 | 100%
TAP-91818_VISUAL | 489 |  |  | 06.01.04.07.00.00.00.00 |  | TAP-91818 | [TAP-91818_VISUAL] ¦ [CAPA] Dev support Sprint 4 - Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual |  |  |  | 2 | 521.5 | 1 hr | 1 hr | -519.5 | 100%
| 490 |  |  | 06.02.00.00.00.00.00.00 | [10 empty] | 521.5 | 1 hr | 1 hr | -519.5 | 0%
| 491 |  |  | 06.03.00.00.00.00.00.00 | [10 empty] | 521.5 | 1 hr | 1 hr | -519.5 | 0%
| 492 |  |  | 06.04.00.00.00.00.00.00 | [9 empty] | 16 | 521.5 | 1 hr | 1 hr | -505.5 | 32.5938 | 0 | 0
| 493 |  |  | 06.04.01.00.00.00.00.00 | [9 empty] | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.5938 | 0 | 0
| 494 |  |  | 06.04.01.01.00.00.00.00 |  | RAS-13292 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.5938 | 0 | 0
TAP-120202_HAPPY JAWS | 495 |  |  | 06.04.01.01.01.00.00.00 |  | TAP-120202 | [TAP-120202_HAPPY JAWS] ¦ [v4.0] Fix unknown instrument behavior | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.5938 | 0 | 0
| 496 |  |  | 06.04.02.00.00.00.00.00 | [9 empty] | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.5938 | 0 | 0
| 497 |  |  | 06.04.02.01.00.00.00.00 |  | RAS-14234 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.5938 | 0 | 0
| 498 |  |  | 06.04.02.02.00.00.00.00 |  | RAS-14305 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.5938 | 0 | 0
| 499 |  |  | 06.04.02.03.00.00.00.00 |  | RAS-8707 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 500 |  |  | 06.04.02.04.00.00.00.00 |  | RAS-7177 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 501 |  |  | 06.04.03.00.00.00.00.00 | [9 empty] | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 502 |  |  | 06.04.03.01.00.00.00.00 |  | RAS-3230 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 503 |  |  | 06.04.03.02.00.00.00.00 |  | RAS-4262 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 504 |  |  | 06.04.04.00.00.00.00.00 | [9 empty] | 16 | 521.5 | 1 hr | 1 hr | -505.5 | 0%
| 505 |  |  | 06.04.04.01.00.00.00.00 |  | RAS-10357 |  | Defect | DEFERRED |  |  |  |  | 16 | 521.5 | 1 hr | 1 hr | -505.5 | 0%
TAP-94573 | 506 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 | 534.5 |  | 1 hr | -521.5 | 100%
TAP-96622_STELLARS | 507 |  |  | 06.04.04.01.01.01.00.00 | TAP-94573 | TAP-96622 | [TAP-96622_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Reproduce issue in SW 4.x | User Story | Done | Released Product Engineering - Stellars |  |  |  | 1 | 535.5 | 1 hr | 1 hr | -534.5 | 100%
TAP-96625_STELLARS | 508 |  |  | 06.04.04.01.01.02.00.00 | TAP-94573 | TAP-96625 | [TAP-96625_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Issue investigation through logs | User Story | Done | Released Product Engineering - Stellars |  |  |  | 5 | 540.5 | 1 hr | 1 hr | -535.5 | 100%
TAP-97845_STELLARS | 509 |  |  | 06.04.04.01.01.03.00.00 | TAP-94573 | TAP-97845 | [TAP-97845_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Undestand the current SW implementation and analyse failure | User Story | Cancelled | Released Product Engineering - Stellars |  |  |  | 5 | 540.5 | 1 hr | 1 hr | -535.5 | 0%
TAP-100121_STELLARS | 510 |  |  | 06.04.04.01.01.04.00.00 | TAP-94573 | TAP-100121 | [TAP-100121_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Reproduce issue - 2. x, 3.x Sw | User Story | Done | Released Product Engineering - Stellars |  |  |  | 2 | 542.5 | 1 hr | 1 hr | -540.5 | 100%
TAP-106195_STELLARS | 511 |  |  | 06.04.04.01.01.05.00.00 | TAP-94573 | TAP-106195 | [TAP-106195_STELLARS] ¦ {Stellars] [RAS-10357] [Spike] Identify possible solutions and impact set | User Story | Done | Released Product Engineering - Stellars |  |  |  | 4 | 546.5 | 1 hr | 1 hr | -542.5 | 100%
TAP-110875_STELLARS | 512 |  |  | 06.04.04.01.01.06.00.00 | TAP-94573 | TAP-110875 | [TAP-110875_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Complete SW impact assessment | User Story | Done | Released Product Engineering - Stellars |  |  |  | 1 | 547.5 | 1 hr | 1 hr | -546.5 | 100%
TAP-106058_I2E | 513 |  |  | 06.04.04.01.02.00.00.00 |  | TAP-106058 | [TAP-106058_I2E] ¦ [RAS-10357][I2E][Spike] Investigate erroneous instrument use count increase | User Story | Cancelled | Advanced Instruments - I2E |  |  |  | 1 | 547.5 | 1 hr | 1 hr | -546.5 | 0%
TAP-109680 | 514 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 | 547.5 | 1 hr | 1 hr | -544.5 | 0% |  |  | Feature Estimation
TAP-114754_STELLARS | 515 |  |  | 06.04.04.01.03.01.00.00 | TAP-109680 | TAP-114754 | [TAP-114754_STELLARS] ¦ [Stellars] [RAS-10357] CCB Review | User Story | Open | Released Product Engineering - Stellars |  |  |  | 3 | 547.5 | 1 hr | 1 hr | -544.5 | 0%
TAP-114755_STELLARS | 516 |  |  | 06.04.04.01.03.02.00.00 | TAP-109680 | TAP-114755 | [TAP-114755_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify Requirement Changes | User Story | Open | Released Product Engineering - Stellars |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114759_STELLARS | 517 |  |  | 06.04.04.01.03.03.00.00 | TAP-109680 | TAP-114759 | [TAP-114759_STELLARS] ¦ [Stellars] [RAS-10357] Implement, Test and Review - Incorrect Use Count update | User Story | Open | Released Product Engineering - Stellars |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114758_STELLARS | 518 |  |  | 06.04.04.01.03.04.00.00 | TAP-109680 | TAP-114758 | [TAP-114758_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify FM Updates | User Story | Open | Released Product Engineering - Stellars |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114756_STELLARS | 519 |  |  | 06.04.04.01.03.05.00.00 | TAP-109680 | TAP-114756 | [TAP-114756_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify Implementation Changes | User Story | Open | Released Product Engineering - Stellars |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114757_STELLARS | 520 |  |  | 06.04.04.01.03.06.00.00 | TAP-109680 | TAP-114757 | [TAP-114757_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify Test Changes | User Story | Open | Released Product Engineering - Stellars |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
| 521 |  |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 |  | Defect | In progress |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
| 522 |  |  | 07.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 40 | 60
TAP-111760 | 523 | TAP-111763 | TAP-94739, TAP-111559, TAP-111834, TAP-95800, TAP-120096, TAP-111719, TAP-117678, TAP-95983, TAP-111731, TAP-111555, TAP-111556, TAP-111751, TAP-111730, TAP-111554, TAP-116286, TAP-111750, TAP-111749, TAP-111724, TAP-111722, TAP-112119, TAP-111569, TAP-103448, TAP-111723, TAP-94966, TAP-112076, TAP-94125, TAP-111721, TAP-111740, TAP-111565, TAP-112012, TAP-112077, TAP-120097, TAP-123834 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 524 | TAP-113104 | TAP-111760 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 10 | 15 | Feature Estimation
TAP-111770_SEAMLESS | 525 |  |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111770_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 10 | 15
TAP-113104 | 526 | TAP-113105 | TAP-111747, TAP-111772, TAP-111838, TAP-111925, TAP-104213, TAP-111656, TAP-111865, TAP-112080, TAP-111775, TAP-111842, TAP-111773, TAP-111642, TAP-111774, TAP-112113, TAP-111763 | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 527 | TAP-111765 | TAP-113104 | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 10 | 15 | Feature Estimation
TAP-113106_SEAMLESS | 528 |  |  | 07.04.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113106_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 10 | 15
TAP-111765 | 529 | TAP-111768 | TAP-111753, TAP-111754, TAP-111756, TAP-111757, TAP-111758, TAP-111759, TAP-111761, TAP-110382, TAP-111762, TAP-111748, TAP-111764, TAP-111766, TAP-112082, TAP-112093, TAP-112094, TAP-113105 | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 530 | TAP-111769 | TAP-111765 | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 531 | TAP-111767 | TAP-111768 | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 532 | TAP-111900 | TAP-111769 | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 10 | 15 | Feature Estimation
TAP-111771_SEAMLESS | 533 |  |  | 07.08.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111771_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 10 | 15
TAP-113101 | 534 | TAP-113102 | TAP-113100 | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 535 | TAP-113103 | TAP-113101 | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 536 | TAP-121104 | TAP-113102 | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 10 | 15 | Feature Estimation
TAP-113107_SEAMLESS | 537 |  |  | 07.11.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113107_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 10 | 15
TAP-121104 | 538 |  | TAP-111900, TAP-112042, TAP-111692, TAP-112231, TAP-112233, TAP-112234, TAP-113127, TAP-113103 | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 539 |  |  | 08.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30
| 540 |  |  | 08.01.00.00.00.00.00.00 | [10 empty] | 547.5 | 1 hr | 1 hr | -547.5 | 0%
| 541 |  |  | 08.02.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30
TAP-94968 | 542 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% |  |  | Feature Estimation
TAP-86202_HAPPY JAWS | 543 |  |  | 08.02.01.01.00.00.00.00 | TAP-94968 | TAP-86202 | [TAP-86202_HAPPY JAWS] ¦ [IRG][SW][WS5] Design Validation procedure for shears use-life model | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-86203_HAPPY JAWS | 544 |  |  | 08.02.01.02.00.00.00.00 | TAP-94968 | TAP-86203 | [TAP-86203_HAPPY JAWS] ¦ [IRG][SW][WS5] Use-life model engineering report | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-111726 | 545 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30 | Feature Estimation
| 546 |  |  | 08.02.02.01.00.00.00.00 | TAP-111726 | TAP-111947 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 20 | 30
TAP-111727 | 547 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 548 |  |  | 08.02.03.01.00.00.00.00 | TAP-111727 | TAP-111948 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0
TAP-111729 | 549 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 550 |  |  | 08.02.04.01.00.00.00.00 | TAP-111729 | TAP-111949 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0
TAP-94967 | 551 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% |  |  | Feature Estimation
TAP-111733 | 552 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 553 |  |  | 08.03.01.00.00.00.00.00 | TAP-111733 | TAP-111908 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0
TAP-111734 | 554 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 555 |  |  | 08.04.01.00.00.00.00.00 | TAP-111734 | TAP-111911 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0
TAP-111735 | 556 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 557 |  |  | 08.05.01.00.00.00.00.00 | TAP-111735 | TAP-111912 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0
TAP-111570 | 558 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 559 |  |  | 08.06.01.00.00.00.00.00 | TAP-111570 | TAP-111798 |  | Feature Estimation | Open | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0
| 560 |  |  | 09.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 270 | 520
| 561 |  |  | 09.01.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 270 | 520
| 562 |  |  | 09.01.01.00.00.00.00.00 |  | MEMO:352 | [8 empty] | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-112107 | 563 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 15 | 30 | Feature Estimation
| 564 |  |  | 09.01.02.01.00.00.00.00 | TAP-112107 | TAP-112114 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 15 | 30
TAP-111934 | 565 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 566 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 10 | 10 | Feature Estimation
| 567 |  |  | 09.01.04.01.00.00.00.00 | TAP-112085 | TAP-112090 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 10 | 10
TAP-112084 | 568 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 10 | 10 | Feature Estimation
| 569 |  |  | 09.01.05.01.00.00.00.00 | TAP-112084 | TAP-112088 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 10 | 10
TAP-112101 | 570 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 160 | 320 | Feature Estimation
| 571 |  |  | 09.01.06.01.00.00.00.00 | TAP-112101 | TAP-112103 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 160 | 320
TAP-112086 | 572 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 25 | 50 | Feature Estimation
| 573 |  |  | 09.01.07.01.00.00.00.00 | TAP-112086 | TAP-112091 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 25 | 50
TAP-112087 | 574 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 50 | 100 | Feature Estimation
| 575 |  |  | 09.01.08.01.00.00.00.00 | TAP-112087 | TAP-112092 |  | Feature Estimation | Done | Core Instruments |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 50 | 100
| 576 |  |  | 09.02.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 100% | 0 | 0
TAP-112095 | 577 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 578 |  |  | 00.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-106203 | 579 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% |  |  | Feature Estimation
TAP-95980 | 580 |  |  | 00.02.00.00.00.00.00.00 |  | TAP-95980 | [TAP-95980] ¦ [IRR] Wristed Requirement Engineering for Controls | Feature | Cancelled |  |  |  |  | 0 | 547.5 |  | 1 hr | -547.5 | 0%
TAP-90081_HAPPY JAWS | 581 |  |  | 00.02.01.00.00.00.00.00 | TAP-95980 | TAP-90081 | [TAP-90081_HAPPY JAWS] ¦ [IRG][SW][WS5] Requirement strategy and framework to inform test / V&V strategy (Part I) | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-87608_HAPPY JAWS | 582 |  |  | 00.02.02.00.00.00.00.00 | TAP-95980 | TAP-87608 | [TAP-87608_HAPPY JAWS] ¦ [IRG][SW][WS5] Engineer suitable metrics to measure functional performance to satisfy system / customer requirements | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-85471_HAPPY JAWS | 583 |  |  | 00.02.03.00.00.00.00.00 | TAP-95980 | TAP-85471 | [TAP-85471_HAPPY JAWS] ¦ [IRG][SW][WS5] Link parameters to requirements for "WS5" prototype | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-91840_HAPPY JAWS | 584 |  |  | 00.02.04.00.00.00.00.00 | TAP-95980 | TAP-91840 | [TAP-91840_HAPPY JAWS] ¦ [IRG][SW][WS5] Requirement strategy and framework to inform test / V&V strategy (Part II) | User Story | Cancelled | Core Instruments - Happy Jaws |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-98620 | 585 |  |  | 00.03.00.00.00.00.00.00 |  | TAP-98620 | [TAP-98620] ¦ [IRR] Move Core Instrument Tracking Mitigation Closer to IDU Controller | Feature | Cancelled |  |  |  |  | 0 | 547.5 |  | 1 hr | -547.5 | 0%
TAP-100791 | 586 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 | 547.5 |  | 1 hr | -547.5 | 100%

## Log
DataTimeStamp | Event | Data

## Summary
Resource Names | Sum FDR