## Project
Selector | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Index | Parent Feature | Key | Task Name | Issue Type | Status | ART | Resource Names | Task Type | Source | Σ Total SP | Σ Groom SP | Σ Done SP | Focus Duration | Low-Risk Duration | Remaining SP | % Complete | Σ Realistic Estimate | Σ Worst Case Estimate | RefinementLevel
| 1 |  |  | 01.00.00.00.00.00.00.00 | [9 empty] | 505.5 | 0 | 1 hr | 1 hr | 505.5 | 0% | 650 | 962
| 2 |  |  | 01.01.00.00.00.00.00.00 | [9 empty] | 73 | 0 | 1 hr | 1 hr | 73 | 0% | 46 | 58
TAP-94739 | 3 | TAP-97668, TAP-111760 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 40 | 50 | Story Points
TAP-97584_HAPPYJAWS | 4 |  |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-97584_HAPPYJAWS] ¦ [IRR][Arch] Describe wristed controller system functional architecture | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 | 17 | 1 hr | 1 hr | -12 | 100%
TAP-99738_HAPPYJAWS | 5 |  |  | 01.01.01.03.00.00.00.00 | TAP-94739 | TAP-99738 | [TAP-99738_HAPPYJAWS] ¦ [IRR][SW] Prepare for Planning Discussion on IDU Actuator Plug-and-Play Architecture | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 19 | 1 hr | 1 hr | -17 | 100%
TAP-97602_SIRIUS | 6 |  |  | 01.01.01.04.00.00.00.00 | TAP-94739 | TAP-97602 | [TAP-97602_SIRIUS] ¦ [IRR][Arch] Analyze requirement impact | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 3 | 22 | 1 hr | 1 hr | -19 | 100%
TAP-106673_SIRIUS | 7 |  |  | 01.01.01.05.00.00.00.00 | TAP-94739 | TAP-106673 | [TAP-106673_SIRIUS] ¦ [IRR][Arch] Analyze WS5 prototype functions and architecture | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 | 24 | 1 hr | 1 hr | -22 | 100%
TAP-97668 | 8 | TAP-120097 | TAP-94739 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | In progress |  |  |  |  | 32.5 | 24 | 1 hr | 1 hr | 8.5 | 0% | 12 | 16 | Story Points
TAP-97600_HAPPYJAWS | 9 |  |  | 01.01.02.02.00.00.00.00 | TAP-97668 | TAP-97600 | [TAP-97600_HAPPYJAWS] ¦ [IRR][Arch] Identify impacts and opportunities on testing strategy | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3.5 | 27.5 | 1 hr | 1 hr | -24 | 100%
TAP-97595_HAPPYJAWS | 10 |  |  | 01.01.02.03.00.00.00.00 | TAP-97668 | TAP-97595 | [TAP-97595_HAPPYJAWS] ¦ [IRR][Arch] Review and refine state logic and state machines | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 30.5 | 1 hr | 1 hr | -27.5 | 100%
TAP-97586_SIRIUS | 11 |  |  | 01.01.02.04.00.00.00.00 | TAP-97668 | TAP-97586 | [TAP-97586_SIRIUS] ¦ [IRR][Arch] Migration and branch sync considerations | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 | 32.5 | 1 hr | 1 hr | -30.5 | 100%
TAP-97581_HAPPYJAWS | 12 |  |  | 01.01.02.05.00.00.00.00 | TAP-97668 | TAP-97581 | [TAP-97581_HAPPYJAWS] ¦ [IRR][Arch] Define internal structure and interfaces for wristed instrument controller | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 | 37.5 | 1 hr | 1 hr | -32.5 | 100%
TAP-97568_HAPPYJAWS | 13 |  |  | 01.01.02.06.00.00.00.00 | TAP-97668 | TAP-97568 | [TAP-97568_HAPPYJAWS] ¦ [IRR][Arch] Select architecture concept for wristed controller family | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 7 | 44.5 | 1 hr | 1 hr | -37.5 | 100%
TAP-114765_HAPPYJAWS | 14 |  |  | 01.01.02.08.00.00.00.00 | TAP-97668 | TAP-114765 | [TAP-114765_HAPPYJAWS] ¦ [IRR][Arch] Update functional decomposition documents | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 46.5 | 1 hr | 1 hr | -44.5 | 100% | 0 | 0
TAP-114792_HAPPYJAWS | 15 |  |  | 01.01.02.09.00.00.00.00 | TAP-97668 | TAP-114792 | [TAP-114792_HAPPYJAWS] ¦ [IRR][Arch] Decide on controller design with impact on software architecture | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 48.5 | 1 hr | 1 hr | -46.5 | 100% | 0 | 0
TAP-114794_SIRIUS | 16 |  |  | 01.01.02.10.00.00.00.00 | TAP-97668 | TAP-114794 | [TAP-114794_SIRIUS] ¦ [IRR][Arch] Requirements workshop | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 5 | 53.5 | 1 hr | 1 hr | -48.5 | 100% | 0 | 0
TAP-123215_HAPPYJAWS | 17 |  |  | 01.01.02.11.00.00.00.00 | TAP-97668 | TAP-123215 | [TAP-123215_HAPPYJAWS] ¦ [IRR][Arch] Create consolidated wristed architecture prototype (Part 1) | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 56.5 | 1 hr | 1 hr | -53.5 | 100%
TAP-120097 | 18 | TAP-111760 | TAP-97668 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture in SW | Feature | PROPOSED |  |  |  |  | 28.5 | 56.5 | 1 hr | 1 hr | -28 | 0% | 0 | 0 | Story Points
TAP-97689_HAPPYJAWS | 19 |  |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-97689 | [TAP-97689_HAPPYJAWS] ¦ [IRR][Arch] Update instrument data model for wristed instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 | 56.5 | 1 hr | 1 hr | -55.5 | 0%
TAP-106674_HAPPYJAWS | 20 |  |  | 01.01.03.02.00.00.00.00 | TAP-120097 | TAP-106674 | [TAP-106674_HAPPYJAWS] ¦ [IRR][Arch] Validate consolidated wristed architecture prototype | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 4 | 56.5 | 1 hr | 1 hr | -52.5 | 0%
TAP-97598_HAPPYJAWS | 21 |  |  | 01.01.03.03.00.00.00.00 | TAP-120097 | TAP-97598 | [TAP-97598_HAPPYJAWS] ¦ [IRR][Arch] Finalize external interfaces of wristed controller SWI | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 56.5 | 1 hr | 1 hr | -54.5 | 0%
TAP-114803_HAPPYJAWS | 22 |  |  | 01.01.03.04.00.00.00.00 | TAP-120097 | TAP-114803 | [TAP-114803_HAPPYJAWS] ¦ [IRR][Arch] Migrate IRR branch to new arch and validate | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 56.5 | 1 hr | 1 hr | -54.5 | 28.25% | 0 | 0
TAP-115970_HAPPYJAWS | 23 |  |  | 01.01.03.05.00.00.00.00 | TAP-120097 | TAP-115970 | [TAP-115970_HAPPYJAWS] ¦ [IRR][Arch] Complete V&V Impact Analysis and Initial V&V Strategy | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3.5 | 56.5 | 1 hr | 1 hr | -53 | 0%
TAP-117147_HAPPYJAWS | 24 |  |  | 01.01.03.06.00.00.00.00 | TAP-120097 | TAP-117147 | [TAP-117147_HAPPYJAWS] ¦ [IRR][Arch] Simulink design guidelines and patterns within IRR controller | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 56.5 | 1 hr | 1 hr | -54.5 | 28.25% | 0 | 0
TAP-116501_HAPPYJAWS | 25 |  |  | 01.01.03.07.00.00.00.00 | TAP-120097 | TAP-116501 | [TAP-116501_HAPPYJAWS] ¦ [IRR][Arch] Reserve time for requirement updates | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 10 | 56.5 | 1 hr | 1 hr | -46.5 | 5.65% | 0 | 0
TAP-105494_HAPPYJAWS | 26 |  |  | 01.01.03.08.00.00.00.00 | TAP-120097 | TAP-105494 | [TAP-105494_HAPPYJAWS] ¦ [IRR][Arch] Create consolidated wristed architecture prototype (Part 2) | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 4 | 56.5 | 1 hr | 1 hr | -52.5 | 0%
| 27 |  |  | 01.02.00.00.00.00.00.00 | [9 empty] | 27 | 56.5 | 1 hr | 1 hr | -29.5 | 2.093% | 80 | 90
TAP-111730 | 28 | TAP-111760, TAP-124062 | TAP-106315 | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 27 | 56.5 | 1 hr | 1 hr | -29.5 | 0% | 60 | 80 | Story Points
TAP-116458_HAPPYJAWS | 29 |  |  | 01.02.01.02.00.00.00.00 | TAP-111730 | TAP-116458 | [TAP-116458_HAPPYJAWS] ¦ [IRR][Clamping] Update switching logic in jaw torque estimator | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 6 | 62.5 | 1 hr | 1 hr | -56.5 | 100% | 0 | 0
TAP-116459_HAPPYJAWS | 30 |  |  | 01.02.01.03.00.00.00.00 | TAP-111730 | TAP-116459 | [TAP-116459_HAPPYJAWS] ¦ [IRR][Clamping] Continue Investigating Improvements to force estimator | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 8 | 62.5 | 1 hr | 1 hr | -54.5 | 7.812% | 0 | 0
TAP-116463_HAPPYJAWS | 31 |  |  | 01.02.01.07.00.00.00.00 | TAP-111730 | TAP-116463 | [TAP-116463_HAPPYJAWS] ¦ [IRR][Clamping] Collect clamp data on previously identified low clamp force instrument | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 64.5 | 1 hr | 1 hr | -62.5 | 100% | 0 | 0
TAP-121692_HAPPYJAWS | 32 |  |  | 01.02.01.08.00.00.00.00 | TAP-111730 | TAP-121692 | [TAP-121692_HAPPYJAWS] ¦ [IRR][Clamping] Investigate effect of updated pulley radius | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 | 69.5 | 1 hr | 1 hr | -64.5 | 100% | 0 | 0
TAP-122144_HAPPYJAWS | 33 |  |  | 01.02.01.09.00.00.00.00 | TAP-111730 | TAP-122144 | [TAP-122144_HAPPYJAWS] ¦ [IRR][Clamping] Improvements to force estimator | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 6 | 75.5 | 1 hr | 1 hr | -69.5 | 100% | 0 | 0
TAP-111731 | 34 | TAP-111760 |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 0% | 100 | 100 | Feature Estimation
TAP-124062 | 35 |  | TAP-111730 | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 0% | 0 | 0 | Feature Estimation
| 36 |  |  | 01.03.00.00.00.00.00.00 | [9 empty] | 42 | 75.5 | 1 hr | 1 hr | -33.5 | 1.798% | 136 | 234
TAP-112076 | 37 | TAP-111760 |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 | 75.5 | 1 hr | 1 hr | -75.5 | 0% | 20 | 20 | Feature Estimation
TAP-94966 | 38 | TAP-111556, TAP-111760 | TAP-111562 | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | Accepted |  |  |  |  | 35 | 75.5 | 1 hr | 1 hr | -40.5 | 0% | 65 | 111 | Story Points
TAP-116502_HAPPYJAWS | 39 |  |  | 01.03.02.03.00.00.00.00 | TAP-94966 | TAP-116502 | [TAP-116502_HAPPYJAWS] ¦ [IRR][Cutting] Reproduce position estimation failures & Investigate | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 4 | 79.5 | 1 hr | 1 hr | -75.5 | 100% | 0 | 0
TAP-116503_HAPPYJAWS | 40 |  |  | 01.03.02.04.00.00.00.00 | TAP-94966 | TAP-116503 | [TAP-116503_HAPPYJAWS] ¦ [IRR][Cutting] Develop hard-stop detection for robust closing | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 | 84.5 | 1 hr | 1 hr | -79.5 | 100% | 0 | 0
TAP-116504_HAPPYJAWS | 41 |  |  | 01.03.02.05.00.00.00.00 | TAP-94966 | TAP-116504 | [TAP-116504_HAPPYJAWS] ¦ [IRR][Cutting] Develop calibration for robust position estimation | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 | 85.5 | 1 hr | 1 hr | -84.5 | 100% | 0 | 0
TAP-116505_HAPPYJAWS | 42 |  |  | 01.03.02.06.00.00.00.00 | TAP-94966 | TAP-116505 | [TAP-116505_HAPPYJAWS] ¦ [IRR][Cutting] Update cutting KPIs for capturing reliable performance / HW variation | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 | 85.5 | 1 hr | 1 hr | -80.5 | 17.1% | 0 | 0
TAP-116508_HAPPYJAWS | 43 |  |  | 01.03.02.07.00.00.00.00 | TAP-94966 | TAP-116508 | [TAP-116508_HAPPYJAWS] ¦ [IRR][Use-life] Document use-life model | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 87.5 | 1 hr | 1 hr | -85.5 | 100% | 0 | 0
TAP-116509_SIRIUS | 44 |  |  | 01.03.02.08.00.00.00.00 | TAP-94966 | TAP-116509 | [TAP-116509_SIRIUS] ¦ [IRR][Use-life] Identify dependent use-life parameters | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 8 | 95.5 | 1 hr | 1 hr | -87.5 | 100% | 0 | 0
TAP-116511_SIRIUS | 45 |  |  | 01.03.02.10.00.00.00.00 | TAP-94966 | TAP-116511 | [TAP-116511_SIRIUS] ¦ [IRR][Use-life] Create trade-off curves 1 | User Story | In progress | Core Instruments - Sirius | SIRIUS |  |  | 5 | 95.5 | 1 hr | 1 hr | -90.5 | 19.1% | 0 | 0
TAP-116512_SIRIUS | 46 |  |  | 01.03.02.11.00.00.00.00 | TAP-94966 | TAP-116512 | [TAP-116512_SIRIUS] ¦ [IRR][Use-life] Create trade-off curves 2 | User Story | In progress | Core Instruments - Sirius | SIRIUS |  |  | 5 | 95.5 | 1 hr | 1 hr | -90.5 | 19.1% | 0 | 0
TAP-111554 | 47 | TAP-111760 |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 | 95.5 | 1 hr | 1 hr | -88.5 | 0% | 48 | 96 | Story Points
TAP-116506_HAPPYJAWS | 48 |  |  | 01.03.03.02.00.00.00.00 | TAP-111554 | TAP-116506 | [TAP-116506_HAPPYJAWS] ¦ [IRR][Cutting] Support Tissue Cutting investigation with Systems | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 | 95.5 | 1 hr | 1 hr | -90.5 | 19.1% | 0 | 0
TAP-116507_HAPPYJAWS | 49 |  |  | 01.03.03.03.00.00.00.00 | TAP-111554 | TAP-116507 | [TAP-116507_HAPPYJAWS] ¦ [IRR][Cutting] Get feedback from clinical team | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 95.5 | 1 hr | 1 hr | -93.5 | 47.75% | 0 | 0
TAP-111555 | 50 | TAP-111760 |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 24 | 36 | Feature Estimation
TAP-112012 | 51 | TAP-111760 |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 24 | 36 | Feature Estimation
TAP-111569 | 52 | TAP-111760 |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 16 | 24 | Feature Estimation
TAP-111565 | 53 | TAP-111760 |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 10 | 40 | Feature Estimation
TAP-111556 | 54 | TAP-111559, TAP-111760 | TAP-94966 | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 20 | 30 | Feature Estimation
TAP-111559 | 55 | TAP-111760 | TAP-111556 | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 | 95.5 | 1 hr | 1 hr | -95.5 | 0% | 20 | 30 | Feature Estimation
| 56 |  |  | 01.04.00.00.00.00.00.00 | [9 empty] | 60 | 95.5 | 1 hr | 1 hr | -35.5 | 1.592% | 20 | 30
TAP-112077 | 57 | TAP-111760 | TAP-111562 | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 60 | 95.5 | 1 hr | 1 hr | -35.5 | 0% | 40 | 60 | Story Points
TAP-115017_SIRIUS | 58 |  |  | 01.04.01.02.00.00.00.00 | TAP-112077 | TAP-115017 | [TAP-115017_SIRIUS] ¦ [IRR][Articulation] Finalize KPI/Simulation Script | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 7 | 102.5 | 1 hr | 1 hr | -95.5 | 100%
TAP-116519_SIRIUS | 59 |  |  | 01.04.01.03.00.00.00.00 | TAP-112077 | TAP-116519 | [TAP-116519_SIRIUS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in Boston | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 6 | 108.5 | 1 hr | 1 hr | -102.5 | 100% | 0 | 0
TAP-116520_HAPPYJAWS | 60 |  |  | 01.04.01.04.00.00.00.00 | TAP-112077 | TAP-116520 | [TAP-116520_HAPPYJAWS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in NoHa | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 36.17% | 0 | 0
TAP-116521_HAPPYJAWS | 61 |  |  | 01.04.01.05.00.00.00.00 | TAP-112077 | TAP-116521 | [TAP-116521_HAPPYJAWS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in Wessling | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 36.17% | 0 | 0
TAP-116522_SIRIUS | 62 |  |  | 01.04.01.06.00.00.00.00 | TAP-112077 | TAP-116522 | [TAP-116522_SIRIUS] ¦ [IRR][Articulation/Actuation] Tracking Fixture and Elmo Interface Finalization | User Story | Groomed | Core Instruments - Sirius | SIRIUS |  |  | 5 | 108.5 | 1 hr | 1 hr | -103.5 | 21.7% | 0 | 0
TAP-116523_SIRIUS | 63 |  |  | 01.04.01.07.00.00.00.00 | TAP-112077 | TAP-116523 | [TAP-116523_SIRIUS] ¦ [IRR][Articulation/Actuation] Setup Engineering Test Script | User Story | Groomed | Core Instruments - Sirius | SIRIUS |  |  | 5 | 108.5 | 1 hr | 1 hr | -103.5 | 21.7% | 0 | 0
TAP-116524_SIRIUS | 64 |  |  | 01.04.01.08.00.00.00.00 | TAP-112077 | TAP-116524 | [TAP-116524_SIRIUS] ¦ [IRR][Articulation/Actuation] Run Engineering Test with Tracking Fixture | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 8 | 108.5 | 1 hr | 1 hr | -100.5 | 13.56% | 0 | 0
TAP-116525_SIRIUS | 65 |  |  | 01.04.01.09.00.00.00.00 | TAP-112077 | TAP-116525 | [TAP-116525_SIRIUS] ¦ [IRR][Articulation/Actuation] Compare Engineering Test Results with SR Tests | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 | 108.5 | 1 hr | 1 hr | -106.5 | 54.25% | 0 | 0
TAP-116526_HAPPYJAWS | 66 |  |  | 01.04.01.10.00.00.00.00 | TAP-112077 | TAP-116526 | [TAP-116526_HAPPYJAWS] ¦ [IRR][Articulation/Actuation] Jaw Actuation Hysteresis and Jaw Scaling Analysis Script | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 36.17% | 0 | 0
TAP-116527_SIRIUS | 67 |  |  | 01.04.01.11.00.00.00.00 | TAP-112077 | TAP-116527 | [TAP-116527_SIRIUS] ¦ [IRR][Articulation/Actuation] Investigate Jaw Actuation Issues with Engineering Test | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 4 | 108.5 | 1 hr | 1 hr | -104.5 | 27.12% | 0 | 0
TAP-116528_SIRIUS | 68 |  |  | 01.04.01.12.00.00.00.00 | TAP-112077 | TAP-116528 | [TAP-116528_SIRIUS] ¦ [IRR][Articulation/Actuation] Articulation Under Load in Simulation | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 5 | 108.5 | 1 hr | 1 hr | -103.5 | 21.7% | 0 | 0
TAP-116529_HAPPYJAWS | 69 |  |  | 01.04.01.13.00.00.00.00 | TAP-112077 | TAP-116529 | [TAP-116529_HAPPYJAWS] ¦ [IRR][Articulation/Actuation] Investigate Instrument Shaking when J6 Moving | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 | 108.5 | 1 hr | 1 hr | -107.5 | 108.5% | 0 | 0
TAP-116530_SIRIUS | 70 |  |  | 01.04.01.14.00.00.00.00 | TAP-112077 | TAP-116530 | [TAP-116530_SIRIUS] ¦ [IRR][Articulation/Actuation] Get Clinical Feedback | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 1 | 108.5 | 1 hr | 1 hr | -107.5 | 108.5% | 0 | 0
TAP-116586_SIRIUS | 71 |  |  | 01.04.01.15.00.00.00.00 | TAP-112077 | TAP-116586 | [TAP-116586_SIRIUS] ¦ [IRR][Articulation/Actuation] Evaluate/Implement Other KPIs given Engineering Test Results | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 4 | 108.5 | 1 hr | 1 hr | -104.5 | 27.12% | 0 | 0
TAP-118635_SIRIUS | 72 |  |  | 01.04.01.16.00.00.00.00 | TAP-112077 | TAP-118635 | [TAP-118635_SIRIUS] ¦ [IRR][Articulation] Investigate delay-compensation tracking error KPI | User Story | In progress | Core Instruments - Sirius | SIRIUS |  |  | 3 | 108.5 | 1 hr | 1 hr | -105.5 | 0%
TAP-122341_SIRIUS | 73 |  |  | 01.04.01.17.00.00.00.00 | TAP-112077 | TAP-122341 | [TAP-122341_SIRIUS] ¦ [IRR] Update HW Inventory in Boston | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 0 | 108.5 | 1 hr | 1 hr | -108.5 | 0% | 0 | 0
TAP-120096 | 74 | TAP-111760 |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 | 108.5 | 1 hr | 1 hr | -108.5 | 0% | 0 | 0 | Feature Estimation
| 75 |  |  | 01.05.00.00.00.00.00.00 | [9 empty] | 169.5 | 108.5 | 1 hr | 1 hr | 61 | 0.6401% | 174 | 235
TAP-103448 | 76 | TAP-111760 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 | 108.5 | 1 hr | 1 hr | -94.5 | 0% | 0 | 0 | Story Points
TAP-99022_I2E | 77 |  |  | 01.05.01.01.00.00.00.00 | TAP-103448 | TAP-99022 | [TAP-99022_I2E] ¦ [v3.1][IRR][IDU CMD][I2E] Add Shears functionality to M-IRR's tool within Discrete Control Command | User Story | Done | Advanced Instruments - I2E | I2E |  |  | 5 | 113.5 | 1 hr | 1 hr | -108.5 | 100%
TAP-114885_I2E | 78 |  |  | 01.05.01.02.00.00.00.00 | TAP-103448 | TAP-114885 | [TAP-114885_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port LED Capability to IDU CMD / Common | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.83% | 0 | 0
TAP-114886_I2E | 79 |  |  | 01.05.01.03.00.00.00.00 | TAP-103448 | TAP-114886 | [TAP-114886_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port Automatic Data Recorder Triggering on Errors | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 2 | 113.5 | 1 hr | 1 hr | -111.5 | 56.75% | 0 | 0
TAP-114887_I2E | 80 |  |  | 01.05.01.04.00.00.00.00 | TAP-103448 | TAP-114887 | [TAP-114887_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port automatically running IDU CMD on 2X fixtures | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 1 | 113.5 | 1 hr | 1 hr | -112.5 | 113.5% | 0 | 0
TAP-114892_I2E | 81 |  |  | 01.05.01.05.00.00.00.00 | TAP-103448 | TAP-114892 | [TAP-114892_I2E] ¦ [Newton][I2E][IDU CMD][IDU Fix Ctl] Port tmp file logging when parsing/running trajectory files to IDU CMD | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.83% | 0 | 0
TAP-116286 | 82 | TAP-111760 |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 | 113.5 | 1 hr | 1 hr | -95.5 | 0% | 0 | 0 | Story Points
TAP-116514_SIRIUS | 83 |  |  | 01.05.03.02.00.00.00.00 | TAP-116286 | TAP-116514 | [TAP-116514_SIRIUS] ¦ [IRR][Analysis] Obtain brand new needle drivers | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 | 113.5 | 1 hr | 1 hr | -111.5 | 56.75% | 0 | 0
TAP-116515_HAPPYJAWS | 84 |  |  | 01.05.03.03.00.00.00.00 | TAP-116286 | TAP-116515 | [TAP-116515_HAPPYJAWS] ¦ [IRR][Analysis] Collect KPI data on a set of brand new instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.83% | 0 | 0
TAP-116516_HAPPYJAWS | 85 |  |  | 01.05.03.04.00.00.00.00 | TAP-116286 | TAP-116516 | [TAP-116516_HAPPYJAWS] ¦ [IRR][Analysis] Reprocess instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 113.5 | 1 hr | 1 hr | -111.5 | 56.75% | 0 | 0
TAP-116517_HAPPYJAWS | 86 |  |  | 01.05.03.05.00.00.00.00 | TAP-116286 | TAP-116517 | [TAP-116517_HAPPYJAWS] ¦ [IRR][Analysis] Collect KPI data on a set of reprocessed instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 113.5 | 1 hr | 1 hr | -110.5 | 37.83% | 0 | 0
TAP-116518_SIRIUS | 87 |  |  | 01.05.03.06.00.00.00.00 | TAP-116286 | TAP-116518 | [TAP-116518_SIRIUS] ¦ [IRR][Analysis] Investigate instrument aging effects on KPIs | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 8 | 113.5 | 1 hr | 1 hr | -105.5 | 14.19% | 0 | 0
TAP-95983 | 88 | TAP-111760 |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 108 | 113.5 | 1 hr | 1 hr | -5.5 | 0% | 41 | 73 | Story Points
TAP-88491_HAPPYJAWS | 89 |  |  | 01.05.04.01.00.00.00.00 | TAP-95983 | TAP-88491 | [TAP-88491_HAPPYJAWS] ¦ [IRR][PlantSim][Happy Jaws] Introduce IDU Standalones to Modeling Team | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 | 114.5 | 1 hr | 1 hr | -113.5 | 100%
TAP-87610_SIRIUS | 90 |  |  | 01.05.04.02.00.00.00.00 | TAP-95983 | TAP-87610 | [TAP-87610_SIRIUS] ¦ [IRR][PlantSim][Sirius] Setup VM with Docker and git on Server in Mounds View | User Story | In progress | Core Instruments - Sirius | SIRIUS |  |  | 4 | 114.5 | 1 hr | 1 hr | -110.5 | 0%
TAP-111725_SIRIUS | 91 |  |  | 01.05.04.06.00.00.00.00 | TAP-95983 | TAP-111725 | [TAP-111725_SIRIUS] ¦ [IRR][Enabler][Playback] Implement SW or tool updates to enable playback simulation | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 15 | 129.5 | 1 hr | 1 hr | -114.5 | 100% | 0 | 0
TAP-115103_ANIMATORS | 92 |  |  | 01.05.04.07.00.00.00.00 | TAP-95983 | TAP-115103 | [TAP-115103_ANIMATORS] ¦ [IRR][PlantModels] Wristed Instrument Model Credibility and Risk Assessment (Validation) | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 0 | 0
TAP-115108_ANIMATORS | 93 |  |  | 01.05.04.08.00.00.00.00 | TAP-95983 | TAP-115108 | [TAP-115108_ANIMATORS] ¦ [IRR][PlantModels] Document model stability and variability over the supported parameter space | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 0 | 129.5 | 1 hr | 1 hr | -129.5 | 100% | 0 | 0
TAP-114540_SIRIUS | 94 |  |  | 01.05.04.13.00.00.00.00 | TAP-95983 | TAP-114540 | [TAP-114540_SIRIUS] ¦ [IRR][Sirius] Update Reliability Logging for Failure Detection Log Collection | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 | 129.5 | 1 hr | 1 hr | -127.5 | 64.75% | 0 | 0
TAP-116408_PUPPETEERS | 95 |  |  | 01.05.04.14.00.00.00.00 | TAP-95983 | TAP-116408 | [TAP-116408_PUPPETEERS] ¦ [IRR][Puppeteers] Support for framework for wristed testing | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 13 | 129.5 | 1 hr | 1 hr | -116.5 | 9.962% | 0 | 0
TAP-116440_ANIMATORS | 96 |  |  | 01.05.04.15.00.00.00.00 | TAP-95983 | TAP-116440 | [TAP-116440_ANIMATORS] ¦ [IRR][PlantModels] Provide an interface for external loads on the instrument | User Story | Done | Shared Services - Animators | ANIMATORS |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 100% | 0 | 0
TAP-116441_ANIMATORS | 97 |  |  | 01.05.04.16.00.00.00.00 | TAP-95983 | TAP-116441 | [TAP-116441_ANIMATORS] ¦ [IRR][PlantModels] Provide a mask summarizing the plant model parameters | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 26.9% | 0 | 0
TAP-116442_ANIMATORS | 98 |  |  | 01.05.04.17.00.00.00.00 | TAP-95983 | TAP-116442 | [TAP-116442_ANIMATORS] ¦ [IRR][PlantModels] Request/Coordinate support for the ein_ng build process on the HPC cluster | User Story | In progress | Shared Services - Animators | ANIMATORS |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 26.9% | 0 | 0
TAP-116456_ANIMATORS | 99 |  |  | 01.05.04.18.00.00.00.00 | TAP-95983 | TAP-116456 | [TAP-116456_ANIMATORS] ¦ [IRR][PlantModels] Setup an evaluation framework for parameter scan simulations | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 5 | 134.5 | 1 hr | 1 hr | -129.5 | 26.9% | 0 | 0
TAP-116457_ANIMATORS | 100 |  |  | 01.05.04.19.00.00.00.00 | TAP-95983 | TAP-116457 | [TAP-116457_ANIMATORS] ¦ [IRR][PlantModels] Familiarize with the IDU standalone tester | User Story | Done | Shared Services - Animators | ANIMATORS |  |  | 10 | 144.5 | 1 hr | 1 hr | -134.5 | 100% | 0 | 0
TAP-116491_HAPPYJAWS | 101 |  |  | 01.05.04.20.00.00.00.00 | TAP-95983 | TAP-116491 | [TAP-116491_HAPPYJAWS] ¦ [IRR][Playback][Happy Jaws] Evaluate Playback tools and Use Cases | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 2 | 144.5 | 1 hr | 1 hr | -142.5 | 72.25% | 0 | 0
TAP-116492_HAPPYJAWS | 102 |  |  | 01.05.04.21.00.00.00.00 | TAP-95983 | TAP-116492 | [TAP-116492_HAPPYJAWS] ¦ [IRR][HW Testing][Happy Jaws] Investigate Engineering Test Infrastructure Improvements | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 4 | 144.5 | 1 hr | 1 hr | -140.5 | 36.12% | 0 | 0
TAP-116493_HAPPYJAWS | 103 |  |  | 01.05.04.22.00.00.00.00 | TAP-95983 | TAP-116493 | [TAP-116493_HAPPYJAWS] ¦ [IRR][HW Testing][Happy Jaws] Implement Standardized Engineering Test Scripts | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 7 | 144.5 | 1 hr | 1 hr | -137.5 | 20.64% | 0 | 0
TAP-116494_SIRIUS | 104 |  |  | 01.05.04.23.00.00.00.00 | TAP-95983 | TAP-116494 | [TAP-116494_SIRIUS] ¦ [IRR][Playback][Sirius] Create script for running playback simulation | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 6 | 144.5 | 1 hr | 1 hr | -138.5 | 24.08% | 0 | 0
TAP-116495_SIRIUS | 105 |  |  | 01.05.04.24.00.00.00.00 | TAP-95983 | TAP-116495 | [TAP-116495_SIRIUS] ¦ [IRR][Spike][Equivalency][Sirius] Develop Equivalency Test for IRR Controller | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 5 | 144.5 | 1 hr | 1 hr | -139.5 | 28.9% | 0 | 0
TAP-116496_SIRIUS | 106 |  |  | 01.05.04.25.00.00.00.00 | TAP-95983 | TAP-116496 | [TAP-116496_SIRIUS] ¦ [IRR][HW Testing][Sirius] Documentation of HW Test Fixturing and Setup | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 7 | 144.5 | 1 hr | 1 hr | -137.5 | 20.64% | 0 | 0
TAP-116497_SIRIUS | 107 |  |  | 01.05.04.26.00.00.00.00 | TAP-95983 | TAP-116497 | [TAP-116497_SIRIUS] ¦ [IRR][HW Testing][Sirius] Implement Standardized Engineering Test Reports | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 5 | 144.5 | 1 hr | 1 hr | -139.5 | 28.9% | 0 | 0
TAP-116498_SIRIUS | 108 |  |  | 01.05.04.27.00.00.00.00 | TAP-95983 | TAP-116498 | [TAP-116498_SIRIUS] ¦ [IRR][Sirius] Derating Tool Documentation | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 1 | 145.5 | 1 hr | 1 hr | -144.5 | 100% | 0 | 0
TAP-116499_SIRIUS | 109 |  |  | 01.05.04.28.00.00.00.00 | TAP-95983 | TAP-116499 | [TAP-116499_SIRIUS] ¦ [IRR][Sirius] Continuous Shmio Logging Documentation | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 1 | 146.5 | 1 hr | 1 hr | -145.5 | 100% | 0 | 0
TAP-116500_SIRIUS | 110 |  |  | 01.05.04.29.00.00.00.00 | TAP-95983 | TAP-116500 | [TAP-116500_SIRIUS] ¦ [IRR][Sirius] Single signal logging Documentation | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 1 | 146.5 | 1 hr | 1 hr | -145.5 | 146.5% | 0 | 0
TAP-118633_SIRIUS | 111 |  |  | 01.05.04.30.00.00.00.00 | TAP-95983 | TAP-118633 | [TAP-118633_SIRIUS] ¦ [IRR][Enabler][Tools] Replace calibration_override to replace with state machine variant subsystem | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 | 148.5 | 1 hr | 1 hr | -146.5 | 100% | 0 | 0
TAP-121182_SIRIUS | 112 |  |  | 01.05.04.31.00.00.00.00 | TAP-95983 | TAP-121182 | [TAP-121182_SIRIUS] ¦ [IRR][Enabler] Tools to analyze motor position controller | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 | 148.5 | 1 hr | 1 hr | -146.5 | 74.25% | 0 | 0
TAP-111719 | 113 | TAP-111562, TAP-111760 | TAP-124116 | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 | 148.5 | 1 hr | 1 hr | -143.5 | 0% | 15 | 22 | Story Points
TAP-114445_I2E | 114 |  |  | 01.05.05.04.00.00.00.00 | TAP-111719 | TAP-114445 | [TAP-114445_I2E] ¦ [MIRR][I2E][Spike] Support Sebastian in testing/configuring Galil | User Story | In progress | Advanced Instruments - I2E | I2E |  |  | 2 | 148.5 | 1 hr | 1 hr | -146.5 | 74.25% | 0 | 0
TAP-114446_I2E | 115 |  |  | 01.05.05.05.00.00.00.00 | TAP-111719 | TAP-114446 | [TAP-114446_I2E] ¦ [MIRR][I2E] Add Ethercat Master/shmios to Diagnostic Folder and rc.startup | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 3 | 148.5 | 1 hr | 1 hr | -145.5 | 49.5% | 0 | 0
TAP-111721 | 116 | TAP-111760 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 | 148.5 | 1 hr | 1 hr | -124 | 0% | 54 | 60 | Story Points
TAP-115880_SIRIUS | 117 |  |  | 01.05.06.02.00.00.00.00 | TAP-111721 | TAP-115880 | [TAP-115880_SIRIUS] ¦ [IRR][ORSI] Update Lab SW for Hard Stop recovery | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 | 148.5 | 1 hr | 1 hr | -145.5 | 49.5% | 0 | 0
TAP-116464_SIRIUS | 118 |  |  | 01.05.06.04.00.00.00.00 | TAP-111721 | TAP-116464 | [TAP-116464_SIRIUS] ¦ [IRR][ORSI] Decide on parameters to derate with clinical | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 0.5 | 149 | 1 hr | 1 hr | -148.5 | 100% | 0 | 0
TAP-116465_SIRIUS | 119 |  |  | 01.05.06.05.00.00.00.00 | TAP-111721 | TAP-116465 | [TAP-116465_SIRIUS] ¦ [IRR][RUFS] Attend RUFS | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 5 | 154 | 1 hr | 1 hr | -149 | 100% | 0 | 0
TAP-116467_SIRIUS | 120 |  |  | 01.05.06.07.00.00.00.00 | TAP-111721 | TAP-116467 | [TAP-116467_SIRIUS] ¦ [IRR][RUFS] Prepare lab branch | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 4 | 158 | 1 hr | 1 hr | -154 | 100% | 0 | 0
TAP-121702_SIRIUS | 121 |  |  | 01.05.06.08.00.00.00.00 | TAP-111721 | TAP-121702 | [TAP-121702_SIRIUS] ¦ [IRR] Update IRR SW With Detachment Detection | User Story | In progress | Core Instruments - Sirius | SIRIUS |  |  | 5 | 158 | 1 hr | 1 hr | -153 | 31.6% | 0 | 0
TAP-122340_HAPPYJAWS | 122 |  |  | 01.05.06.09.00.00.00.00 | TAP-111721 | TAP-122340 | [TAP-122340_HAPPYJAWS] ¦ [IRR] Update Lab SW with Protection Against Slow Close | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 | 158 | 1 hr | 1 hr | -157 | 158% | 0 | 0
TAP-122855_SIRIUS | 123 |  |  | 01.05.06.10.00.00.00.00 | TAP-111721 | TAP-122855 | [TAP-122855_SIRIUS] ¦ [IRR][RUFS] Lab support | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 | 160 | 1 hr | 1 hr | -158 | 100% | 0 | 0
TAP-122954_SIRIUS | 124 |  |  | 01.05.06.11.00.00.00.00 | TAP-111721 | TAP-122954 | [TAP-122954_SIRIUS] ¦ [IRR] Prepare lab branch for IRR Summer NoHa Lab | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 | 160 | 1 hr | 1 hr | -158 | 80% | 0 | 0
TAP-123066_PUPPETEERS | 125 |  |  | 01.05.06.12.00.00.00.00 | TAP-111721 | TAP-123066 | [TAP-123066_PUPPETEERS] ¦ [IRR][Puppeteers] Merge latest JBO updates to IRR staging branch for ORSI lab | User Story | In progress | Core Instruments - Puppeteers | PUPPETEERS |  |  | 2 | 160 | 1 hr | 1 hr | -158 | 80% | 0 | 0
TAP-111722 | 126 | TAP-111760 |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 54 | 60 | Feature Estimation
TAP-111723 | 127 | TAP-111760 |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 54 | 60 | Feature Estimation
TAP-111724 | 128 | TAP-111760 |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 54 | 60 | Feature Estimation
TAP-112119 | 129 | TAP-111760 |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 | 160 | 1 hr | 1 hr | -160 | 0% | 20 | 40 | Feature Estimation
| 130 |  |  | 01.06.00.00.00.00.00.00 | [9 empty] | 134 | 160 | 1 hr | 1 hr | -26 | 1.194% | 184 | 295
TAP-94125 | 131 | TAP-111753, TAP-111760 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Instrument Homing Compatible with WS5 Structure | Feature | Accepted |  |  |  |  | 77 | 160 | 1 hr | 1 hr | -83 | 0% | 50 | 70 | Story Points
TAP-97747_SIRIUS | 132 |  |  | 01.06.01.01.00.00.00.00 | TAP-94125 | TAP-97747 | [TAP-97747_SIRIUS] ¦ [WS5][Homing][Sirius] Evaluate Homing Controller Architecture and Identify Improvements | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 5 | 160 | 1 hr | 1 hr | -155 | 0%
TAP-97748_SIRIUS | 133 |  |  | 01.06.01.02.00.00.00.00 | TAP-94125 | TAP-97748 | [TAP-97748_SIRIUS] ¦ [WS5][Homing][Sirius] Update DD for Homing Controller | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 4 | 160 | 1 hr | 1 hr | -156 | 0%
TAP-97749_SIRIUS | 134 |  |  | 01.06.01.03.00.00.00.00 | TAP-94125 | TAP-97749 | [TAP-97749_SIRIUS] ¦ [WS5][Homing][Sirius] Run and fix Static Analysis on Homing Controller | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 5 | 160 | 1 hr | 1 hr | -155 | 0%
TAP-97750_SIRIUS | 135 |  |  | 01.06.01.04.00.00.00.00 | TAP-94125 | TAP-97750 | [TAP-97750_SIRIUS] ¦ [WS5][Homing][Sirius] Create/Update Unit tests for Homing Controller | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 6 | 160 | 1 hr | 1 hr | -154 | 0%
TAP-97751_SIRIUS | 136 |  |  | 01.06.01.05.00.00.00.00 | TAP-94125 | TAP-97751 | [TAP-97751_SIRIUS] ¦ [WS5][Homing][Sirius] cFMEA Risk analysis for Homing Controller | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 5 | 160 | 1 hr | 1 hr | -155 | 0%
TAP-97752_SIRIUS | 137 |  |  | 01.06.01.06.00.00.00.00 | TAP-94125 | TAP-97752 | [TAP-97752_SIRIUS] ¦ [WS5][Homing][Sirius] Reserve for RCM creation | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 0%
TAP-97753_SIRIUS | 138 |  |  | 01.06.01.07.00.00.00.00 | TAP-94125 | TAP-97753 | [TAP-97753_SIRIUS] ¦ [WS5][Homing][Sirius] Develop requirements for homing controller (Part 1) | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 6 | 160 | 1 hr | 1 hr | -154 | 0%
TAP-97754_SIRIUS | 139 |  |  | 01.06.01.08.00.00.00.00 | TAP-94125 | TAP-97754 | [TAP-97754_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: ENGAGE_COUPLERS | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97755_SIRIUS | 140 |  |  | 01.06.01.09.00.00.00.00 | TAP-94125 | TAP-97755 | [TAP-97755_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_JAW | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97756_SIRIUS | 141 |  |  | 01.06.01.10.00.00.00.00 | TAP-94125 | TAP-97756 | [TAP-97756_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_TENSION | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97757_SIRIUS | 142 |  |  | 01.06.01.11.00.00.00.00 | TAP-94125 | TAP-97757 | [TAP-97757_SIRIUS] ¦ [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_YAW/HOME_PITCH | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 10 | 160 | 1 hr | 1 hr | -150 | 0%
TAP-97758_SIRIUS | 143 |  |  | 01.06.01.12.00.00.00.00 | TAP-94125 | TAP-97758 | [TAP-97758_SIRIUS] ¦ [WS5][Homing][Sirius] Develop requirements for homing controller (Part 2) | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 0%
TAP-95800 | 144 | TAP-111754, TAP-111760 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development Motor Controller Compatible with WS5 Structure | Feature | Accepted |  |  |  |  | 29 | 160 | 1 hr | 1 hr | -131 | 0% | 15 | 35 | Story Points
TAP-91185_SIRIUS | 145 |  |  | 01.06.02.01.00.00.00.00 | TAP-95800 | TAP-91185 | [TAP-91185_SIRIUS] ¦ [IRG][SW][WS5] Investigate alternative IDU motor position control approaches | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 4 | 160 | 1 hr | 1 hr | -156 | 0%
TAP-116475_SIRIUS | 146 |  |  | 01.06.02.03.00.00.00.00 | TAP-95800 | TAP-116475 | [TAP-116475_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Informal design review | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 53.33% | 0 | 0
TAP-116476_SIRIUS | 147 |  |  | 01.06.02.04.00.00.00.00 | TAP-95800 | TAP-116476 | [TAP-116476_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Decide on testing strategy | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 | 160 | 1 hr | 1 hr | -157 | 53.33% | 0 | 0
TAP-116477_SIRIUS | 148 |  |  | 01.06.02.05.00.00.00.00 | TAP-95800 | TAP-116477 | [TAP-116477_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Create MIL/Unit tests for motor controller | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 9 | 160 | 1 hr | 1 hr | -151 | 17.78% | 0 | 0
TAP-116478_SIRIUS | 149 |  |  | 01.06.02.06.00.00.00.00 | TAP-95800 | TAP-116478 | [TAP-116478_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Update and fix Static Analysis issues | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 | 162 | 1 hr | 1 hr | -160 | 100% | 0 | 0
TAP-116479_SIRIUS | 150 |  |  | 01.06.02.07.00.00.00.00 | TAP-95800 | TAP-116479 | [TAP-116479_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Develop requirements | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54% | 0 | 0
TAP-116480_SIRIUS | 151 |  |  | 01.06.02.08.00.00.00.00 | TAP-95800 | TAP-116480 | [TAP-116480_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Perform cFMEA | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 4 | 162 | 1 hr | 1 hr | -158 | 40.5% | 0 | 0
TAP-116482_SIRIUS | 152 |  |  | 01.06.02.09.00.00.00.00 | TAP-95800 | TAP-116482 | [TAP-116482_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Draft design documents | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 1 | 162 | 1 hr | 1 hr | -161 | 162% | 0 | 0
TAP-111740 | 153 | TAP-111756, TAP-111760 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 28 | 162 | 1 hr | 1 hr | -134 | 0% | 120 | 160 | Story Points
TAP-115106_HAPPYJAWS | 154 |  |  | 01.06.03.02.00.00.00.00 | TAP-111740 | TAP-115106 | [TAP-115106_HAPPYJAWS] ¦ [IRR][Phase 1b][Happy Jaws] Refactor teleoperation SWI to consolidate IK and improve architecture | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54% | 0 | 0
TAP-116483_HAPPYJAWS | 155 |  |  | 01.06.03.03.00.00.00.00 | TAP-111740 | TAP-116483 | [TAP-116483_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Informal design review | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54% | 0 | 0
TAP-116484_HAPPYJAWS | 156 |  |  | 01.06.03.04.00.00.00.00 | TAP-111740 | TAP-116484 | [TAP-116484_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Decide on testing strategy | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54% | 0 | 0
TAP-116485_HAPPYJAWS | 157 |  |  | 01.06.03.05.00.00.00.00 | TAP-111740 | TAP-116485 | [TAP-116485_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Create MIL/Unit tests for teleop SWI | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 9 | 162 | 1 hr | 1 hr | -153 | 18% | 0 | 0
TAP-116486_SIRIUS | 158 |  |  | 01.06.03.06.00.00.00.00 | TAP-111740 | TAP-116486 | [TAP-116486_SIRIUS] ¦ [IRR][Phase 1b][Teleoperation] Update and fix Static Analysis issues | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 | 162 | 1 hr | 1 hr | -160 | 81% | 0 | 0
TAP-116487_HAPPYJAWS | 159 |  |  | 01.06.03.07.00.00.00.00 | TAP-111740 | TAP-116487 | [TAP-116487_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Develop requirements | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 162 | 1 hr | 1 hr | -159 | 54% | 0 | 0
TAP-116488_HAPPYJAWS | 160 |  |  | 01.06.03.08.00.00.00.00 | TAP-111740 | TAP-116488 | [TAP-116488_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Perform cFMEA | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 4 | 162 | 1 hr | 1 hr | -158 | 40.5% | 0 | 0
TAP-116490_HAPPYJAWS | 161 |  |  | 01.06.03.09.00.00.00.00 | TAP-111740 | TAP-116490 | [TAP-116490_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Draft design documents | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 | 162 | 1 hr | 1 hr | -161 | 162% | 0 | 0
TAP-111749 | 162 | TAP-111757, TAP-111760 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 32 | 60 | Feature Estimation
TAP-112328_SIRIUS | 163 |  |  | 01.06.04.02.00.00.00.00 | TAP-111749 | TAP-112328 | [TAP-112328_SIRIUS] ¦ [IRR] Evaluate risk rank of alternate instrument hardware failure modes | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 0 | 0
TAP-111750 | 164 | TAP-111758, TAP-111760 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Procedure Manager SWI for IRR | Feature | Accepted |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 30 | 70 | Feature Estimation
TAP-111751 | 165 | TAP-111759, TAP-111760 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 56 | 90 | Feature Estimation
TAP-117678 | 166 | TAP-111760 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 0 | 0 | Feature Estimation
| 167 |  |  | 01.07.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 10 | 20
TAP-111834 | 168 | TAP-111760 | TAP-113995 | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 20 | 40 | Feature Estimation
| 169 |  |  | 02.00.00.00.00.00.00.00 | [9 empty] | 76 | 162 | 1 hr | 1 hr | -86 | 2.132% | 716 | 1266
| 170 |  |  | 02.01.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 2.132% | 50 | 100
TAP-111747 | 171 | TAP-113104 |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 100 | 200 | Feature Estimation
| 172 |  |  | 02.02.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 65 | 85
TAP-111772 | 173 | TAP-113104 |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 30 | 40 | Feature Estimation
TAP-111773 | 174 | TAP-113104 |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 100 | 130 | Feature Estimation
| 175 |  |  | 02.03.00.00.00.00.00.00 | [9 empty] | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 45 | 90
TAP-111838 | 176 | TAP-111842, TAP-113104 |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 20 | 30 | Feature Estimation
TAP-104213 | 177 | TAP-111842, TAP-113104 |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 30 | 90 | Feature Estimation
TAP-111842 | 178 | TAP-113104 | TAP-104213, TAP-111838 | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 | 162 | 1 hr | 1 hr | -162 | 0% | 40 | 60 | Feature Estimation
| 179 |  |  | 02.04.00.00.00.00.00.00 | [9 empty] | 25 | 162 | 1 hr | 1 hr | -137 | 6.48% | 102 | 172
TAP-111774 | 180 | TAP-111775, TAP-112080, TAP-113104 |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 10 | 162 | 1 hr | 1 hr | -152 | 0% | 28 | 47 | Story Points
TAP-116177_CASTLEBLACK | 181 |  |  | 02.04.01.04.00.00.00.00 | TAP-111774 | TAP-116177 | [TAP-116177_CASTLEBLACK] ¦ [Spike] Investigate Instrument Observer Mitigations | User Story | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 1 | 162 | 1 hr | 1 hr | -161 | 162% | 0 | 0
TAP-116194_PUPPETEERS | 182 |  |  | 02.04.01.05.00.00.00.00 | TAP-111774 | TAP-116194 | [TAP-116194_PUPPETEERS] ¦ [IRR][Puppeteers]cFMEA - Investigate risk analysis for MSO Joint Tracking Check- initial | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 5 | 167 | 1 hr | 1 hr | -162 | 100% | 0 | 0
TAP-116202_PUPPETEERS | 183 |  |  | 02.04.01.06.00.00.00.00 | TAP-111774 | TAP-116202 | [TAP-116202_PUPPETEERS] ¦ [IRR][Puppeteers] Create cFMEA draft in Excel Sheet for MSO Joint Tracking Check | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 3 | 170 | 1 hr | 1 hr | -167 | 100% | 0 | 0
TAP-116645_PUPPETEERS | 184 |  |  | 02.04.01.09.00.00.00.00 | TAP-111774 | TAP-116645 | [TAP-116645_PUPPETEERS] ¦ [Puppeteers] cFMEA and Polarian Training | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 100% | 0 | 0
TAP-112080 | 185 | TAP-111775, TAP-113104 | TAP-111774 | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 14 | 171 | 1 hr | 1 hr | -157 | 0% | 50 | 85 | Story Points
TAP-116414_PUPPETEERS | 186 |  |  | 02.04.02.05.00.00.00.00 | TAP-112080 | TAP-116414 | [TAP-116414_PUPPETEERS] ¦ [IRR][Puppeteers] Kinematics prototype for MSO joint check replacement | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 13 | 171 | 1 hr | 1 hr | -158 | 13.15% | 0 | 0
TAP-116211_PUPPETEERS | 187 |  |  | 02.04.02.06.00.00.00.00 | TAP-112080 | TAP-116211 | [TAP-116211_PUPPETEERS] ¦ [IRR][Puppeteers] Review, Approve and Release cFMEA in Polarian | User Story | Groomed | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 171% | 0 | 0
TAP-111775 | 188 | TAP-113104 | TAP-111774, TAP-112080 | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 0% | 61 | 99 | Feature Estimation
TAP-121472_PUPPETEERS | 189 |  |  | 02.04.03.05.00.00.00.00 | TAP-111775 | TAP-121472 | [TAP-121472_PUPPETEERS] ¦ [IRR][Puppeteers] Update Polarion | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 | 171 | 1 hr | 1 hr | -170 | 171% | 0 | 0
| 190 |  |  | 02.05.00.00.00.00.00.00 | [9 empty] | 0 | 171 | 1 hr | 1 hr | -171 | 171% | 321 | 603
TAP-123862 | 191 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 192 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR][MaybePnP] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 193 | TAP-113104 |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 320 | 625 | Feature Estimation
TAP-111656 | 194 | TAP-113104 |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 161 | 293 | Feature Estimation
| 195 |  |  | 02.06.00.00.00.00.00.00 | [9 empty] | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 15 | 30
TAP-111925 | 196 | TAP-113104 |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 30 | 60 | Feature Estimation
TAP-112113 | 197 | TAP-113104 |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
| 198 |  |  | 02.07.00.00.00.00.00.00 | [9 empty] | 51 | 171 | 1 hr | 1 hr | -120 | 3.353% | 118 | 186
TAP-111865 | 199 | TAP-113104 |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
| 200 |  |  | 02.07.02.00.00.00.00.00 | [9 empty] | 39 | 171 | 1 hr | 1 hr | -132 | 4.385% | 0 | 0
TAP-113111 | 201 | TAP-111689, TAP-111695 |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 202 | TAP-111687, TAP-111689, TAP-111695 |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 0 | 171 | 1 hr | 1 hr | -171 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 203 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 | 171 | 1 hr | 1 hr | -147 | 0% | 0 | 0 | Story Points
TAP-116170_CASTLEBLACK | 204 |  |  | 02.07.02.03.01.00.00.00 | TAP-114692 | TAP-116170 | [TAP-116170_CASTLEBLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK |  |  | 2 | 171 | 1 hr | 1 hr | -169 | 85.5% | 0 | 0
TAP-116199_PUPPETEERS | 205 |  |  | 02.07.02.03.02.00.00.00 | TAP-114692 | TAP-116199 | [TAP-116199_PUPPETEERS] ¦ [IRR][Puppeteers] Sree session | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 | 172 | 1 hr | 1 hr | -171 | 100% | 0 | 0
TAP-116198_PUPPETEERS | 206 |  |  | 02.07.02.03.03.00.00.00 | TAP-114692 | TAP-116198 | [TAP-116198_PUPPETEERS] ¦ [IRR][Puppeteers] testing protoype changes | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 3 | 172 | 1 hr | 1 hr | -169 | 57.33% | 0 | 0
TAP-116195_PUPPETEERS | 207 |  |  | 02.07.02.03.04.00.00.00 | TAP-114692 | TAP-116195 | [TAP-116195_PUPPETEERS] ¦ [IRR][Puppeteers] Architectual changes for use life calculations | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 5 | 177 | 1 hr | 1 hr | -172 | 100% | 0 | 0
TAP-116193_PUPPETEERS | 208 |  |  | 02.07.02.03.05.00.00.00 | TAP-114692 | TAP-116193 | [TAP-116193_PUPPETEERS] ¦ [IRR][Puppeteers] interface changes for use life | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 8 | 185 | 1 hr | 1 hr | -177 | 100% | 0 | 0
TAP-123411_PUPPETEERS | 209 |  |  | 02.07.02.03.06.00.00.00 | TAP-114692 | TAP-123411 | [TAP-123411_PUPPETEERS] ¦ [IRR][Puppeteers] Add notcode triggers to sra | User Story | In progress | Core Instruments - Puppeteers | PUPPETEERS |  |  | 3 | 185 | 1 hr | 1 hr | -182 | 61.67% | 0 | 0
TAP-123143_SIRIUS | 210 |  |  | 02.07.02.03.07.00.00.00 | TAP-114692 | TAP-123143 | [TAP-123143_SIRIUS] ¦ [IRR][Sirius] Manually update use life notcodes for staging/IRR-v3-control-development | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 | 187 | 1 hr | 1 hr | -185 | 100% | 0 | 0 | Feature Estimation
TAP-114689 | 211 | TAP-111687 |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Accepted |  |  |  |  | 15 | 187 | 1 hr | 1 hr | -172 | 0% | 0 | 0 | Story Points
TAP-115102_PIXELPOETS | 212 |  |  | 02.07.02.04.01.00.00.00 | TAP-114689 | TAP-115102 | [TAP-115102_PIXELPOETS] ¦ [MIRR][Pixel Poets] Finalize Design for Use Life Indicator | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 1 | 188 | 1 hr | 1 hr | -187 | 100% | 0 | 0
TAP-115105_PIXELPOETS | 213 |  |  | 02.07.02.04.02.00.00.00 | TAP-114689 | TAP-115105 | [TAP-115105_PIXELPOETS] ¦ [MIRR][Pixel Poets] Define DDS Interface Definitions | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 2 | 190 | 1 hr | 1 hr | -188 | 100% | 0 | 0
TAP-116036_PIXELPOETS | 214 |  |  | 02.07.02.04.03.00.00.00 | TAP-114689 | TAP-116036 | [TAP-116036_PIXELPOETS] ¦ [4.1][MIRR][Pixel Poets] MVP for Use Life Countdown Timer | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 10 | 200 | 1 hr | 1 hr | -190 | 100% | 0 | 0
TAP-116170_CASTLEBLACK | 215 |  |  | 02.07.02.04.04.00.00.00 | TAP-114689 | TAP-116170 | [TAP-116170_CASTLEBLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK |  |  | 2 | 200 | 1 hr | 1 hr | -198 | 100% | 0 | 0
| 216 |  |  | 02.07.03.00.00.00.00.00 | [9 empty] | 12 | 200 | 1 hr | 1 hr | -188 | 16.67% | 118 | 186
TAP-90375 | 217 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 | 200 | 1 hr | 1 hr | -191 | 0% |  |  | Story Points
TAP-96606_STELLARS | 218 |  |  | 02.07.03.01.01.00.00.00 | TAP-90375 | TAP-96606 | [TAP-96606_STELLARS] ¦ [Stellars] [TAP-90375] [Enabler] Identify Jama linking to be updated | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 1 | 200 | 1 hr | 1 hr | -199 | 0%
TAP-97208_STELLARS | 219 |  |  | 02.07.03.01.04.00.00.00 | TAP-90375 | TAP-97208 | [TAP-97208_STELLARS] ¦ [Stellars] [TAP-90375] [enabler]Jama Pull and merge | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 5 | 200 | 1 hr | 1 hr | -195 | 0%
TAP-97213_STELLARS | 220 |  |  | 02.07.03.01.05.00.00.00 | TAP-90375 | TAP-97213 | [TAP-97213_STELLARS] ¦ [Stellars] [TAP-90375] Implement, Test and Review UII updates | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0%
TAP-111861 | 221 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0% | 46 | 64 | Story Points
TAP-115871_PUPPETEERS | 222 |  |  | 02.07.03.02.04.00.00.00 | TAP-111861 | TAP-115871 | [TAP-115871_PUPPETEERS] ¦ [IRR] Increment Use count when instrument is expired | User Story | Groomed | Core Instruments - Puppeteers | PUPPETEERS |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 66.67% | 0 | 0
TAP-111687 | 223 |  | TAP-113123, TAP-114689 | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 48 | 80 | Feature Estimation
TAP-111689 | 224 |  | TAP-113111, TAP-113123 | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 49 | 76 | Feature Estimation
TAP-111695 | 225 |  | TAP-113111, TAP-113123 | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 35 | 72 | Feature Estimation
| 226 |  |  | 03.00.00.00.00.00.00.00 | [9 empty] | 6 | 200 | 1 hr | 1 hr | -194 | 33.33% | 396 | 678
| 227 |  |  | 03.01.00.00.00.00.00.00 | [9 empty] | 6 | 200 | 1 hr | 1 hr | -194 | 33.33% | 126 | 200
TAP-111753 | 228 | TAP-111761, TAP-111765 | TAP-94125 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 60 | 100 | Feature Estimation
TAP-111754 | 229 | TAP-110382, TAP-111765 | TAP-95800 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0% | 20 | 30 | Feature Estimation
TAP-116481_SIRIUS | 230 |  |  | 03.01.02.02.00.00.00.00 | TAP-111754 | TAP-116481 | [TAP-116481_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 66.67% | 0 | 0
TAP-111756 | 231 | TAP-111762, TAP-111765 | TAP-111740 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 0% | 70 | 90 | Feature Estimation
TAP-116489_HAPPYJAWS | 232 |  |  | 03.01.03.02.00.00.00.00 | TAP-111756 | TAP-116489 | [TAP-116489_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 | 200 | 1 hr | 1 hr | -197 | 66.67% | 0 | 0
TAP-111757 | 233 | TAP-111748, TAP-111765 | TAP-111749 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 32 | 60 | Feature Estimation
TAP-111758 | 234 | TAP-111764, TAP-111765 | TAP-111750 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 30 | 60 | Feature Estimation
TAP-111759 | 235 | TAP-111766, TAP-111765 | TAP-111751 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 40 | 60 | Feature Estimation
| 236 |  |  | 03.02.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 78 | 113
TAP-111761 | 237 | TAP-111765 | TAP-111753 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 50 | 60 | Feature Estimation
TAP-110382 | 238 | TAP-111765 | TAP-111754 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 10 | 16 | Feature Estimation
TAP-111762 | 239 | TAP-111765 | TAP-111756 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 30 | 50 | Feature Estimation
TAP-111748 | 240 | TAP-111765 | TAP-111757 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 16 | 30 | Feature Estimation
TAP-111764 | 241 | TAP-111765 | TAP-111758 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 20 | 30 | Feature Estimation
TAP-111766 | 242 | TAP-111765 | TAP-111759 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 30 | 40 | Feature Estimation
| 243 |  |  | 03.03.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 192 | 365
TAP-112082 | 244 | TAP-111765 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 65 | 185 | Feature Estimation
TAP-112093 | 245 | TAP-111765 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 110 | 140 | Feature Estimation
TAP-112094 | 246 | TAP-111765 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 174 | 340 | Feature Estimation
| 247 |  |  | 04.00.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 200 | 400
TAP-113100 | 248 | TAP-113101 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 400 | 800 | Feature Estimation
| 249 |  |  | 05.00.00.00.00.00.00.00 | [9 empty] | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 301 | 487
TAP-111900 | 250 | TAP-121104 | TAP-111767 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 109 | 212 | Feature Estimation
TAP-112042 | 251 | TAP-121104 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 44 | 60 | Feature Estimation
TAP-111692 | 252 | TAP-121104 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 150 | 220 | Feature Estimation
TAP-112231 | 253 | TAP-121104 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 80 | 100 | Feature Estimation
TAP-112233 | 254 | TAP-121104 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 20 | 40 | Feature Estimation
TAP-112234 | 255 | TAP-121104 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 40 | 80 | Feature Estimation
TAP-113127 | 256 | TAP-121104 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 | 200 | 1 hr | 1 hr | -200 | 0% | 0 | 0 | Feature Estimation
| 257 |  |  | 06.00.00.00.00.00.00.00 | [9 empty] | 241.25 | 200 | 1 hr | 1 hr | 41.25 | 0.829% | 0 | 0
| 258 |  |  | 06.01.00.00.00.00.00.00 | [9 empty] | 225.25 | 200 | 1 hr | 1 hr | 25.25 | 0.8879% | 0 | 0
| 259 |  |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 |  | Defect | Investigation |  |  |  |  | 30 | 200 | 1 hr | 1 hr | -170 | 6.667% | 0 | 0
TAP-115187 | 260 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 | 229 | 1 hr | 1 hr | -200 | 100% | 0 | 0
TAP-115835_STELLARS | 261 |  |  | 06.01.01.01.01.00.00.00 | TAP-115187 | TAP-115835 | [TAP-115835_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 1 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 5 | 234 | 1 hr | 1 hr | -229 | 100%
TAP-115839_STELLARS | 262 |  |  | 06.01.01.01.02.00.00.00 | TAP-115187 | TAP-115839 | [TAP-115839_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Draft Implementation changes - Part2 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 | 236 | 1 hr | 1 hr | -234 | 100% | 0 | 0
TAP-115837_STELLARS | 263 |  |  | 06.01.01.01.03.00.00.00 | TAP-115187 | TAP-115837 | [TAP-115837_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify FM/FMEA updates - Part 1 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 1 | 237 | 1 hr | 1 hr | -236 | 100%
TAP-115838_STELLARS | 264 |  |  | 06.01.01.01.04.00.00.00 | TAP-115187 | TAP-115838 | [TAP-115838_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Update CCB fields and Review - part 1 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 3 | 240 | 1 hr | 1 hr | -237 | 100%
TAP-115840_STELLARS | 265 |  |  | 06.01.01.01.05.00.00.00 | TAP-115187 | TAP-115840 | [TAP-115840_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Finalise and review Requirement Changes | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 | 242 | 1 hr | 1 hr | -240 | 100%
TAP-116265_STELLARS | 266 |  |  | 06.01.01.01.06.00.00.00 | TAP-115187 | TAP-116265 | [TAP-116265_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 2 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 | 244 | 1 hr | 1 hr | -242 | 100%
TAP-116278_SUNRISERS | 267 |  |  | 06.01.01.01.07.00.00.00 | TAP-115187 | TAP-116278 | [TAP-116278_SUNRISERS] ¦ [Sunrisers] [RAS-7203] [Enabler] Implementation changes review - SP2 | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS |  |  | 1 | 245 | 1 hr | 1 hr | -244 | 100% | 0 | 0
TAP-116308_STELLARS | 268 |  |  | 06.01.01.01.08.00.00.00 | TAP-115187 | TAP-116308 | [TAP-116308_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 3 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 | 247 | 1 hr | 1 hr | -245 | 100%
TAP-116316_STELLARS | 269 |  |  | 06.01.01.01.09.00.00.00 | TAP-115187 | TAP-116316 | [TAP-116316_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Draft and Review FM/FMEA updates | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 | 249 | 1 hr | 1 hr | -247 | 100%
TAP-116323_STELLARS | 270 |  |  | 06.01.01.01.10.00.00.00 | TAP-115187 | TAP-116323 | [TAP-116323_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify FM/FMEA updates - Part 2 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 3 | 252 | 1 hr | 1 hr | -249 | 100%
TAP-116535_SUNRISERS | 271 |  |  | 06.01.01.01.11.00.00.00 | TAP-115187 | TAP-116535 | [TAP-116535_SUNRISERS] ¦ [Sunrisers] [RAS-7203] [Enabler] Implementation changes review - SP3 | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS |  |  | 3 | 255 | 1 hr | 1 hr | -252 | 100% | 0 | 0
TAP-117468_STELLARS | 272 |  |  | 06.01.01.01.13.00.00.00 | TAP-115187 | TAP-117468 | [TAP-117468_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Draft Implementation changes - Part1 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 1 | 256 | 1 hr | 1 hr | -255 | 100% | 0 | 0
TAP-118097_STELLARS | 273 |  |  | 06.01.01.01.14.00.00.00 | TAP-115187 | TAP-118097 | [TAP-118097_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Update CCB fields and Review - part 2 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 | 258 | 1 hr | 1 hr | -256 | 100%
TAP-122269 | 274 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 1 | 258 | 1 hr | 1 hr | -257 | 0% | 0 | 0 | Feature Estimation
TAP-117467_STELLARS | 275 |  |  | 06.01.01.02.01.00.00.00 | TAP-122269 | TAP-117467 | [TAP-117467_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Attend CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 1 | 258 | 1 hr | 1 hr | -257 | 0%
| 276 |  |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 |  | Defect | Investigation |  |  |  |  | 108.25 | 258 | 1 hr | 1 hr | -149.75 | 0%
TAP-64314 | 277 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 | 290.25 |  | 1 hr | -258 | 100%
TAP-60617_JACOBIANS | 278 |  |  | 06.01.02.01.01.00.00.00 | TAP-64314 | TAP-60617 | [TAP-60617_JACOBIANS] ¦ [MBTI][Spike] Investigate Potential Causes of Roll Jump Discontinuity (RAS-7532) | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6.25 | 296.5 | 1 hr | 1 hr | -290.25 | 100%
TAP-67852_JACOBIANS | 279 |  |  | 06.01.02.01.04.00.00.00 | TAP-64314 | TAP-67852 | [TAP-67852_JACOBIANS] ¦ [CAPA][Jacobians] Technical Root Cause Analysis for CAPA | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 | 304.5 | 1 hr | 1 hr | -296.5 | 100%
TAP-67859_JACOBIANS | 280 |  |  | 06.01.02.01.05.00.00.00 | TAP-64314 | TAP-67859 | [TAP-67859_JACOBIANS] ¦ [CAPA][Jacobians] Process Root Cause Analysis for CAPA | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 | 312.5 | 1 hr | 1 hr | -304.5 | 100%
TAP-67866_JACOBIANS | 281 |  |  | 06.01.02.01.06.00.00.00 | TAP-64314 | TAP-67866 | [TAP-67866_JACOBIANS] ¦ [CAPA][Jacobians] Investigation Meetings, Discussions, and Cause Mapping (1 of 2) | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 3 | 315.5 | 1 hr | 1 hr | -312.5 | 100%
TAP-67873_JACOBIANS | 282 |  |  | 06.01.02.01.07.00.00.00 | TAP-64314 | TAP-67873 | [TAP-67873_JACOBIANS] ¦ [CAPA][Jacobians] Investigation Meetings, Discussions, and Cause Mapping (2 of 2) | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 3 | 318.5 | 1 hr | 1 hr | -315.5 | 100%
TAP-67880_JACOBIANS | 283 |  |  | 06.01.02.01.08.00.00.00 | TAP-64314 | TAP-67880 | [TAP-67880_JACOBIANS] ¦ [CAPA][Jacobians] Clearly Document Root Cause Analysis | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 319.5 | 1 hr | 1 hr | -318.5 | 100%
TAP-67881_JACOBIANS | 284 |  |  | 06.01.02.01.09.00.00.00 | TAP-64314 | TAP-67881 | [TAP-67881_JACOBIANS] ¦ [CAPA][Jacobians] Write Action Plan | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1.5 | 321 | 1 hr | 1 hr | -319.5 | 100%
TAP-67882_JACOBIANS | 285 |  |  | 06.01.02.01.10.00.00.00 | TAP-64314 | TAP-67882 | [TAP-67882_JACOBIANS] ¦ [CAPA][Jacobians] Write Effectiveness Plan | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1.5 | 322.5 | 1 hr | 1 hr | -321 | 100%
TAP-64315 | 286 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 347.5 |  | 1 hr | -322.5 | 100%
TAP-72807_JACOBIANS | 287 |  |  | 06.01.02.02.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-72807_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 | 355.5 | 1 hr | 1 hr | -347.5 | 100%
TAP-73681_JACOBIANS | 288 |  |  | 06.01.02.02.02.00.00.00 | TAP-64315 | TAP-73681 | [TAP-73681_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 4 | 359.5 | 1 hr | 1 hr | -355.5 | 100%
TAP-73690_JACOBIANS | 289 |  |  | 06.01.02.02.03.00.00.00 | TAP-64315 | TAP-73690 | [TAP-73690_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Document Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 | 361.5 | 1 hr | 1 hr | -359.5 | 100%
TAP-73736_JACOBIANS | 290 |  |  | 06.01.02.02.05.00.00.00 | TAP-64315 | TAP-73736 | [TAP-73736_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Action Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 362.5 | 1 hr | 1 hr | -361.5 | 100%
TAP-73732_JACOBIANS | 291 |  |  | 06.01.02.02.06.00.00.00 | TAP-64315 | TAP-73732 | [TAP-73732_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 363.5 | 1 hr | 1 hr | -362.5 | 100%
TAP-73752_JACOBIANS | 292 |  |  | 06.01.02.02.07.00.00.00 | TAP-64315 | TAP-73752 | [TAP-73752_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 364.5 | 1 hr | 1 hr | -363.5 | 100%
TAP-76433_REFLECT | 293 |  |  | 06.01.02.02.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-76433_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 3 | 367.5 | 1 hr | 1 hr | -364.5 | 100%
TAP-76437_REFLECT | 294 |  |  | 06.01.02.02.09.00.00.00 | TAP-64315 | TAP-76437 | [TAP-76437_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Write Action and Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 2 | 369.5 | 1 hr | 1 hr | -367.5 | 100%
TAP-76441_REFLECT | 295 |  |  | 06.01.02.02.10.00.00.00 | TAP-64315 | TAP-76441 | [TAP-76441_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 2 | 371.5 | 1 hr | 1 hr | -369.5 | 100%
TAP-79223_JACOBIANS | 296 |  |  | 06.01.02.02.11.00.00.00 | TAP-64315 | TAP-79223 | [TAP-79223_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Route CAPA in Agile | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 372.5 | 1 hr | 1 hr | -371.5 | 100%
TAP-64360_JACOBIANS | 297 |  |  | 06.01.02.03.01.00.00.00 | TAP-76243 | TAP-64360 | [TAP-64360_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 | 372.5 | 1 hr | 1 hr | -362.5 | 0%
TAP-64119_JACOBIANS | 298 |  |  | 06.01.02.03.02.00.00.00 | TAP-76243 | TAP-64119 | [TAP-64119_JACOBIANS] ¦ [Enabler] Create Large Set of Challenging Edge Cases for Kinematic Pipeline | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 372.5 | 1 hr | 1 hr | -367.5 | 0%
TAP-74719_JACOBIANS | 299 |  |  | 06.01.02.03.03.00.00.00 | TAP-76243 | TAP-74719 | [TAP-74719_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Develop Specifications for Kinematic Pipeline Behavior At Joint Limits | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6 | 372.5 | 1 hr | 1 hr | -366.5 | 0%
TAP-74721_JACOBIANS | 300 |  |  | 06.01.02.03.04.00.00.00 | TAP-76243 | TAP-74721 | [TAP-74721_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Design, prototype, and evaluate RCM that could have caught roll fix update | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 372.5 | 1 hr | 1 hr | -367.5 | 0%
TAP-73753_JACOBIANS | 301 |  |  | 06.01.02.03.05.00.00.00 | TAP-76243 | TAP-73753 | [TAP-73753_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 3 | 372.5 | 1 hr | 1 hr | -369.5 | 0%
TAP-83712 | 302 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 394.5 |  | 1 hr | -372.5 | 100%
TAP-86373_JACOBIANS | 303 |  |  | 06.01.02.04.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-86373_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 | 396.5 | 1 hr | 1 hr | -394.5 | 100%
TAP-86374_JACOBIANS | 304 |  |  | 06.01.02.04.02.00.00.00 | TAP-83712 | TAP-86374 | [TAP-86374_JACOBIANS] ¦ [CAPA][SWEEP] Fix Force Feedback issue at Static Limits | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 | 404.5 | 1 hr | 1 hr | -396.5 | 100%
TAP-86376_JACOBIANS | 305 |  |  | 06.01.02.04.04.00.00.00 | TAP-83712 | TAP-86376 | [TAP-86376_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Finalize Preliminary Prototypes | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 409.5 | 1 hr | 1 hr | -404.5 | 100%
TAP-89237_JACOBIANS | 306 |  |  | 06.01.02.04.05.00.00.00 | TAP-83712 | TAP-89237 | [TAP-89237_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User Studies Part 2 | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 410.5 | 1 hr | 1 hr | -409.5 | 100%
TAP-92875_JACOBIANS | 307 |  |  | 06.01.02.04.06.00.00.00 | TAP-83712 | TAP-92875 | [TAP-92875_JACOBIANS] ¦ [CAPA][SWEEP] Review MS Observer RCM | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 415.5 | 1 hr | 1 hr | -410.5 | 100%
TAP-93695_JACOBIANS | 308 |  |  | 06.01.02.04.08.00.00.00 | TAP-83712 | TAP-93695 | [TAP-93695_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Investigate Manual Mode Edge Case | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 416.5 | 1 hr | 1 hr | -415.5 | 100%
| 309 |  |  | 06.01.03.00.00.00.00.00 |  | RAS-9107 |  | Defect | Open |  |  |  |  | 76 | 416.5 | 1 hr | 1 hr | -340.5 | 0%
TAP-64315 | 310 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 441.5 |  | 1 hr | -416.5 | 100%
TAP-72807_JACOBIANS | 311 |  |  | 06.01.03.01.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-72807_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 | 449.5 | 1 hr | 1 hr | -441.5 | 100%
TAP-73681_JACOBIANS | 312 |  |  | 06.01.03.01.02.00.00.00 | TAP-64315 | TAP-73681 | [TAP-73681_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 4 | 453.5 | 1 hr | 1 hr | -449.5 | 100%
TAP-73690_JACOBIANS | 313 |  |  | 06.01.03.01.03.00.00.00 | TAP-64315 | TAP-73690 | [TAP-73690_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Document Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 | 455.5 | 1 hr | 1 hr | -453.5 | 100%
TAP-73736_JACOBIANS | 314 |  |  | 06.01.03.01.05.00.00.00 | TAP-64315 | TAP-73736 | [TAP-73736_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Action Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 456.5 | 1 hr | 1 hr | -455.5 | 100%
TAP-73732_JACOBIANS | 315 |  |  | 06.01.03.01.06.00.00.00 | TAP-64315 | TAP-73732 | [TAP-73732_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Write Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 457.5 | 1 hr | 1 hr | -456.5 | 100%
TAP-73752_JACOBIANS | 316 |  |  | 06.01.03.01.07.00.00.00 | TAP-64315 | TAP-73752 | [TAP-73752_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 458.5 | 1 hr | 1 hr | -457.5 | 100%
TAP-76433_REFLECT | 317 |  |  | 06.01.03.01.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-76433_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 3 | 461.5 | 1 hr | 1 hr | -458.5 | 100%
TAP-76437_REFLECT | 318 |  |  | 06.01.03.01.09.00.00.00 | TAP-64315 | TAP-76437 | [TAP-76437_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Write Action and Effectiveness Plan for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 2 | 463.5 | 1 hr | 1 hr | -461.5 | 100%
TAP-76441_REFLECT | 319 |  |  | 06.01.03.01.10.00.00.00 | TAP-64315 | TAP-76441 | [TAP-76441_REFLECT] ¦ [CAPA][UNWRAP][Reflect] Process and Technical Root Cause Analysis for Kinematics Unwrapping Discontinuity | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 2 | 465.5 | 1 hr | 1 hr | -463.5 | 100%
TAP-79223_JACOBIANS | 320 |  |  | 06.01.03.01.11.00.00.00 | TAP-64315 | TAP-79223 | [TAP-79223_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Route CAPA in Agile | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 466.5 | 1 hr | 1 hr | -465.5 | 100%
TAP-64360_JACOBIANS | 321 |  |  | 06.01.03.02.01.00.00.00 | TAP-76243 | TAP-64360 | [TAP-64360_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 | 466.5 | 1 hr | 1 hr | -456.5 | 0%
TAP-64119_JACOBIANS | 322 |  |  | 06.01.03.02.02.00.00.00 | TAP-76243 | TAP-64119 | [TAP-64119_JACOBIANS] ¦ [Enabler] Create Large Set of Challenging Edge Cases for Kinematic Pipeline | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 466.5 | 1 hr | 1 hr | -461.5 | 0%
TAP-74719_JACOBIANS | 323 |  |  | 06.01.03.02.03.00.00.00 | TAP-76243 | TAP-74719 | [TAP-74719_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Develop Specifications for Kinematic Pipeline Behavior At Joint Limits | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6 | 466.5 | 1 hr | 1 hr | -460.5 | 0%
TAP-74721_JACOBIANS | 324 |  |  | 06.01.03.02.04.00.00.00 | TAP-76243 | TAP-74721 | [TAP-74721_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Design, prototype, and evaluate RCM that could have caught roll fix update | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 466.5 | 1 hr | 1 hr | -461.5 | 0%
TAP-73753_JACOBIANS | 325 |  |  | 06.01.03.02.05.00.00.00 | TAP-76243 | TAP-73753 | [TAP-73753_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Implement Product Code Fix for Technical Root Cause | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 3 | 466.5 | 1 hr | 1 hr | -463.5 | 0%
TAP-83712 | 326 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 488.5 |  | 1 hr | -466.5 | 100%
TAP-86373_JACOBIANS | 327 |  |  | 06.01.03.03.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-86373_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 | 490.5 | 1 hr | 1 hr | -488.5 | 100%
TAP-86374_JACOBIANS | 328 |  |  | 06.01.03.03.02.00.00.00 | TAP-83712 | TAP-86374 | [TAP-86374_JACOBIANS] ¦ [CAPA][SWEEP] Fix Force Feedback issue at Static Limits | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 | 498.5 | 1 hr | 1 hr | -490.5 | 100%
TAP-86376_JACOBIANS | 329 |  |  | 06.01.03.03.04.00.00.00 | TAP-83712 | TAP-86376 | [TAP-86376_JACOBIANS] ¦ [CAPA][UNWRAP][Jacobians] Finalize Preliminary Prototypes | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 503.5 | 1 hr | 1 hr | -498.5 | 100%
TAP-89237_JACOBIANS | 330 |  |  | 06.01.03.03.05.00.00.00 | TAP-83712 | TAP-89237 | [TAP-89237_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User Studies Part 2 | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 504.5 | 1 hr | 1 hr | -503.5 | 100%
TAP-92875_JACOBIANS | 331 |  |  | 06.01.03.03.06.00.00.00 | TAP-83712 | TAP-92875 | [TAP-92875_JACOBIANS] ¦ [CAPA][SWEEP] Review MS Observer RCM | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 5 | 509.5 | 1 hr | 1 hr | -504.5 | 100%
TAP-93695_JACOBIANS | 332 |  |  | 06.01.03.03.08.00.00.00 | TAP-83712 | TAP-93695 | [TAP-93695_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Investigate Manual Mode Edge Case | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 510.5 | 1 hr | 1 hr | -509.5 | 100%
| 333 |  |  | 06.01.04.00.00.00.00.00 |  | RAS-10590 |  | Defect | Confirmed |  |  |  |  | 11 | 510.5 | 1 hr | 1 hr | -499.5 | 0%
TAP-86405_VISUAL | 334 |  |  | 06.01.04.01.00.00.00.00 |  | TAP-86405 | [TAP-86405_VISUAL] ¦ [CAPA] Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual | VISUAL |  |  | 3 | 513.5 | 1 hr | 1 hr | -510.5 | 100%
TAP-89386_VISUAL | 335 |  |  | 06.01.04.02.00.00.00.00 |  | TAP-89386 | [TAP-89386_VISUAL] ¦ [CAPA] Test support - Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual | VISUAL |  |  | 1 | 514.5 | 1 hr | 1 hr | -513.5 | 100%
TAP-90083_VISUAL | 336 |  |  | 06.01.04.03.00.00.00.00 |  | TAP-90083 | [TAP-90083_VISUAL] ¦ [CAPA] Test support - Storz Controller crash on second storz power cycle with endoscope connected v3.0 | User Story | Done | Foundation - Visual | VISUAL |  |  | 1 | 515.5 | 1 hr | 1 hr | -514.5 | 100%
TAP-90540_VISUAL | 337 |  |  | 06.01.04.04.00.00.00.00 |  | TAP-90540 | [TAP-90540_VISUAL] ¦ [CAPA] Dev support - Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual | VISUAL |  |  | 2 | 517.5 | 1 hr | 1 hr | -515.5 | 100%
TAP-90683_VISUAL | 338 |  |  | 06.01.04.05.00.00.00.00 |  | TAP-90683 | [TAP-90683_VISUAL] ¦ [CAPA][Enabler] Test support - Set up Valhalla ICG tower and KS for v2.0.3/v3.0API2 testing | User Story | Done | Foundation - Visual | VISUAL |  |  | 1 | 518.5 | 1 hr | 1 hr | -517.5 | 100%
TAP-91134_VISUAL | 339 |  |  | 06.01.04.06.00.00.00.00 |  | TAP-91134 | [TAP-91134_VISUAL] ¦ [CAPA] Test support - Storz Controller crash on second storz power cycle with endoscope connected v3.0 | User Story | Done | Foundation - Visual | VISUAL |  |  | 1 | 519.5 | 1 hr | 1 hr | -518.5 | 100%
TAP-91818_VISUAL | 340 |  |  | 06.01.04.07.00.00.00.00 |  | TAP-91818 | [TAP-91818_VISUAL] ¦ [CAPA] Dev support Sprint 4 - Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual | VISUAL |  |  | 2 | 521.5 | 1 hr | 1 hr | -519.5 | 100%
| 341 |  |  | 06.02.00.00.00.00.00.00 | [10 empty] | 521.5 | 1 hr | 1 hr | -519.5 | 0%
| 342 |  |  | 06.03.00.00.00.00.00.00 | [10 empty] | 521.5 | 1 hr | 1 hr | -519.5 | 0%
| 343 |  |  | 06.04.00.00.00.00.00.00 | [9 empty] | 16 | 521.5 | 1 hr | 1 hr | -505.5 | 32.59% | 0 | 0
| 344 |  |  | 06.04.01.00.00.00.00.00 | [9 empty] | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.59% | 0 | 0
| 345 |  |  | 06.04.01.01.00.00.00.00 |  | RAS-13292 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.59% | 0 | 0
| 346 |  |  | 06.04.02.00.00.00.00.00 | [9 empty] | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.59% | 0 | 0
| 347 |  |  | 06.04.02.01.00.00.00.00 |  | RAS-14234 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.59% | 0 | 0
| 348 |  |  | 06.04.02.02.00.00.00.00 |  | RAS-14305 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 32.59% | 0 | 0
| 349 |  |  | 06.04.02.03.00.00.00.00 |  | RAS-8707 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 350 |  |  | 06.04.02.04.00.00.00.00 |  | RAS-7177 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 351 |  |  | 06.04.03.00.00.00.00.00 | [9 empty] | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 352 |  |  | 06.04.03.01.00.00.00.00 |  | RAS-3230 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 353 |  |  | 06.04.03.02.00.00.00.00 |  | RAS-4262 |  | Defect | DEFERRED |  |  |  |  | 0 | 521.5 | 1 hr | 1 hr | -521.5 | 0%
| 354 |  |  | 06.04.04.00.00.00.00.00 | [9 empty] | 16 | 521.5 | 1 hr | 1 hr | -505.5 | 0%
| 355 |  |  | 06.04.04.01.00.00.00.00 |  | RAS-10357 |  | Defect | DEFERRED |  |  |  |  | 16 | 521.5 | 1 hr | 1 hr | -505.5 | 0%
TAP-94573 | 356 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 | 534.5 |  | 1 hr | -521.5 | 100%
TAP-96622_STELLARS | 357 |  |  | 06.04.04.01.01.01.00.00 | TAP-94573 | TAP-96622 | [TAP-96622_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Reproduce issue in SW 4.x | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 1 | 535.5 | 1 hr | 1 hr | -534.5 | 100%
TAP-96625_STELLARS | 358 |  |  | 06.04.04.01.01.02.00.00 | TAP-94573 | TAP-96625 | [TAP-96625_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Issue investigation through logs | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 5 | 540.5 | 1 hr | 1 hr | -535.5 | 100%
TAP-100121_STELLARS | 359 |  |  | 06.04.04.01.01.04.00.00 | TAP-94573 | TAP-100121 | [TAP-100121_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Reproduce issue - 2. x, 3.x Sw | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 | 542.5 | 1 hr | 1 hr | -540.5 | 100%
TAP-106195_STELLARS | 360 |  |  | 06.04.04.01.01.05.00.00 | TAP-94573 | TAP-106195 | [TAP-106195_STELLARS] ¦ {Stellars] [RAS-10357] [Spike] Identify possible solutions and impact set | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 | 546.5 | 1 hr | 1 hr | -542.5 | 100%
TAP-110875_STELLARS | 361 |  |  | 06.04.04.01.01.06.00.00 | TAP-94573 | TAP-110875 | [TAP-110875_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Complete SW impact assessment | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 1 | 547.5 | 1 hr | 1 hr | -546.5 | 100%
TAP-109680 | 362 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 | 547.5 | 1 hr | 1 hr | -544.5 | 0% |  |  | Feature Estimation
TAP-114754_STELLARS | 363 |  |  | 06.04.04.01.03.01.00.00 | TAP-109680 | TAP-114754 | [TAP-114754_STELLARS] ¦ [Stellars] [RAS-10357] CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 3 | 547.5 | 1 hr | 1 hr | -544.5 | 0%
TAP-114755_STELLARS | 364 |  |  | 06.04.04.01.03.02.00.00 | TAP-109680 | TAP-114755 | [TAP-114755_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify Requirement Changes | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114759_STELLARS | 365 |  |  | 06.04.04.01.03.03.00.00 | TAP-109680 | TAP-114759 | [TAP-114759_STELLARS] ¦ [Stellars] [RAS-10357] Implement, Test and Review - Incorrect Use Count update | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114758_STELLARS | 366 |  |  | 06.04.04.01.03.04.00.00 | TAP-109680 | TAP-114758 | [TAP-114758_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify FM Updates | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114756_STELLARS | 367 |  |  | 06.04.04.01.03.05.00.00 | TAP-109680 | TAP-114756 | [TAP-114756_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify Implementation Changes | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-114757_STELLARS | 368 |  |  | 06.04.04.01.03.06.00.00 | TAP-109680 | TAP-114757 | [TAP-114757_STELLARS] ¦ [Stellars] [RAS-10357] [Enabler] Identify Test Changes | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
| 369 |  |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 |  | Defect | In progress |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
| 370 |  |  | 07.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 40 | 60
TAP-111760 | 371 | TAP-111763 | TAP-94739, TAP-111559, TAP-111834, TAP-95800, TAP-120096, TAP-111719, TAP-117678, TAP-95983, TAP-111731, TAP-111555, TAP-111556, TAP-111751, TAP-111730, TAP-111554, TAP-116286, TAP-111750, TAP-111749, TAP-111724, TAP-111722, TAP-112119, TAP-111569, TAP-103448, TAP-111723, TAP-94966, TAP-112076, TAP-94125, TAP-111721, TAP-111740, TAP-111565, TAP-112012, TAP-112077, TAP-120097, TAP-123834 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 372 | TAP-113104 | TAP-111760 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30 | Feature Estimation
TAP-113104 | 373 | TAP-113105 | TAP-111747, TAP-111772, TAP-111838, TAP-111925, TAP-104213, TAP-111656, TAP-111865, TAP-112080, TAP-111775, TAP-111842, TAP-111773, TAP-111642, TAP-111774, TAP-112113, TAP-111763 | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 374 | TAP-111765 | TAP-113104 | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30 | Feature Estimation
TAP-111765 | 375 | TAP-111768 | TAP-111753, TAP-111754, TAP-111756, TAP-111757, TAP-111758, TAP-111759, TAP-111761, TAP-110382, TAP-111762, TAP-111748, TAP-111764, TAP-111766, TAP-112082, TAP-112093, TAP-112094, TAP-113105 | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 376 | TAP-111769 | TAP-111765 | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 377 | TAP-111767 | TAP-111768 | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 378 | TAP-111900 | TAP-111769 | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30 | Feature Estimation
TAP-113101 | 379 | TAP-113102 | TAP-113100 | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 380 | TAP-113103 | TAP-113101 | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 381 | TAP-121104 | TAP-113102 | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30 | Feature Estimation
TAP-121104 | 382 |  | TAP-111900, TAP-112042, TAP-111692, TAP-112231, TAP-112233, TAP-112234, TAP-113127, TAP-113103 | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 383 |  |  | 08.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30
| 384 |  |  | 08.01.00.00.00.00.00.00 | [10 empty] | 547.5 | 1 hr | 1 hr | -547.5 | 0%
| 385 |  |  | 08.02.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 30
TAP-94968 | 386 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% |  |  | Feature Estimation
TAP-111726 | 387 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 40 | 60 | Feature Estimation
TAP-111727 | 388 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111729 | 389 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-94967 | 390 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% |  |  | Feature Estimation
TAP-111733 | 391 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111734 | 392 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111735 | 393 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-111570 | 394 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 395 |  |  | 09.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 270 | 520
| 396 |  |  | 09.01.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 270 | 520
| 397 |  |  | 09.01.01.00.00.00.00.00 |  | MEMO:352 | [8 empty] | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-112107 | 398 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 30 | 60 | Feature Estimation
TAP-111934 | 399 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 400 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 20 | Feature Estimation
TAP-112084 | 401 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 20 | 20 | Feature Estimation
TAP-112101 | 402 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 320 | 640 | Feature Estimation
TAP-112086 | 403 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 50 | 100 | Feature Estimation
TAP-112087 | 404 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 100 | 200 | Feature Estimation
| 405 |  |  | 09.02.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0
TAP-112095 | 406 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% | 0 | 0 | Feature Estimation
| 407 |  |  | 00.00.00.00.00.00.00.00 | [9 empty] | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0%
TAP-106203 | 408 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 | 547.5 | 1 hr | 1 hr | -547.5 | 0% |  |  | Feature Estimation
TAP-100791 | 409 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 | 547.5 |  | 1 hr | -547.5 | 100%

## Log
DataTimeStamp | Event | Data

## Summary
Resource Names | Sum FDR
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
I2E
I2E
I2E
I2E
I2E
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
ANIMATORS
ANIMATORS
SIRIUS
PUPPETEERS
ANIMATORS
ANIMATORS
ANIMATORS
ANIMATORS
ANIMATORS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
I2E
I2E
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
PUPPETEERS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
CASTLEBLACK
PUPPETEERS
PUPPETEERS
PUPPETEERS
PUPPETEERS
PUPPETEERS
PUPPETEERS
CASTLEBLACK
PUPPETEERS
PUPPETEERS
PUPPETEERS
PUPPETEERS
PUPPETEERS
SIRIUS
PIXELPOETS
PIXELPOETS
PIXELPOETS
CASTLEBLACK
STELLARS
STELLARS
STELLARS
PUPPETEERS
SIRIUS
HAPPYJAWS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
SUNRISERS
STELLARS
STELLARS
STELLARS
SUNRISERS
STELLARS
STELLARS
STELLARS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
REFLECT
REFLECT
REFLECT
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
REFLECT
REFLECT
REFLECT
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
VISUAL
VISUAL
VISUAL
VISUAL
VISUAL
VISUAL
VISUAL
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS