## Project
Selector | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Index | Parent Feature | Key | Task Name | Issue Type | Status | ART | Resource Names | Task Type | Source | Σ Total SP | Σ Groom SP | Σ Done SP | Focus Duration | Low-Risk Duration | Remaining SP | % Complete | Σ Realistic Estimate | Σ Worst Case Estimate | RefinementLevel
TAP-94739 | 1 | TAP-97668, TAP-111760 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 |  | 12 | 1 hr | 1 hr | 0 | 100% | 40 | 50 | Story Points
TAP-94739_HAPPYJAWS | 2 |  |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-94739_HAPPYJAWS] ¦ [IRR][Arch] Describe wristed controller system functional architecture | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 |  | 17 |  | 1 hr | -12 | 100%
TAP-94739_SIRIUS
TAP-94739_CoreInstrument | 3 |  |  | 01.01.01.04.00.00.00.00 | TAP-94739 | TAP-97602 | [TAP-94739_SIRIUS] ¦ [IRR][Arch] Analyze requirement impact | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 3 |  | 20 |  | 1 hr | -17 | 100%
TAP-97668 | 4 | TAP-120097 | TAP-94739 |  |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | In progress |  |  |  |  | 32.5 |  | 20 | 1 hr | 1 hr | 12.5 | 1200% | 16 | 8 | Story Points
TAP-97668_HAPPYJAWS | 5 |  |  | 01.01.02.02.00.00.00.00 | TAP-97668 | TAP-97600 | [TAP-97668_HAPPYJAWS] ¦ [IRR][Arch] Identify impacts and opportunities on testing strategy | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3.5 |  | 23.5 |  | 1 hr | -20 | 100%
TAP-97668_SIRIUS | 6 |  |  | 01.01.02.04.00.00.00.00 | TAP-97668 | TAP-97586 | [TAP-97668_SIRIUS] ¦ [IRR][Arch] Migration and branch sync considerations | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 |  | 25.5 |  | 1 hr | -23.5 | 100%
TAP-120097 | 7 | TAP-111760 | TAP-97668 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture in SW | Feature | PROPOSED |  |  |  |  | 28.5 |  | 25.5 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Story Points
TAP-120097_HAPPYJAWS | 8 |  |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-97689 | [TAP-120097_HAPPYJAWS] ¦ [IRR][Arch] Update instrument data model for wristed instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 |  | 25.5 |  | 1 hr | -24.5 | 0%
TAP-111730 | 9 | TAP-111760, TAP-124062 | TAP-106315 | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 27 |  | 25.5 | 1 hr | 1 hr | 1.5 | 6000% | 80 | 40 | Story Points
TAP-111730_HAPPYJAWS | 10 |  |  | 01.02.01.02.00.00.00.00 | TAP-111730 | TAP-116458 | [TAP-111730_HAPPYJAWS] ¦ [IRR][Clamping] Update switching logic in jaw torque estimator | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 6 |  | 31.5 | 1 hr | 1 hr | -25.5 | 100% | 0 | 0
TAP-111731 | 11 | TAP-111760 |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 |  | 31.5 | 1 hr | 1 hr | -31.5 | 10000% | 100 | 50 | Feature Estimation
TAP-124062 | 12 |  | TAP-111730 | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 |  | 31.5 | 1 hr | 1 hr | -31.5 | 0% | 0 | 0 | Feature Estimation
TAP-112076 | 13 | TAP-111760 |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 |  | 31.5 | 1 hr | 1 hr | -31.5 | 2000% | 20 | 10 | Feature Estimation
TAP-94966 | 14 | TAP-111556, TAP-111760 | TAP-111562 | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | Accepted |  |  |  |  | 35 |  | 31.5 | 1 hr | 1 hr | 3.5 | 6500% | 111 | 78 | Story Points
TAP-94966_HAPPYJAWS | 15 |  |  | 01.03.02.03.00.00.00.00 | TAP-94966 | TAP-116502 | [TAP-94966_HAPPYJAWS] ¦ [IRR][Cutting] Reproduce position estimation failures & Investigate | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 4 |  | 35.5 | 1 hr | 1 hr | -31.5 | 100% | 0 | 0
TAP-94966_SIRIUS | 16 |  |  | 01.03.02.08.00.00.00.00 | TAP-94966 | TAP-116509 | [TAP-94966_SIRIUS] ¦ [IRR][Use-life] Identify dependent use-life parameters | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 8 |  | 43.5 | 1 hr | 1 hr | -35.5 | 100% | 0 | 0
TAP-111554 | 17 | TAP-111760 |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 |  | 43.5 | 1 hr | 1 hr | -36.5 | 4800% | 96 | 48 | Story Points
TAP-111554_HAPPYJAWS | 18 |  |  | 01.03.03.02.00.00.00.00 | TAP-111554 | TAP-116506 | [TAP-111554_HAPPYJAWS] ¦ [IRR][Cutting] Support Tissue Cutting investigation with Systems | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 5 |  | 43.5 | 1 hr | 1 hr | -38.5 | 8.7% | 0 | 0
TAP-111555 | 19 | TAP-111760 |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 |  | 43.5 | 1 hr | 1 hr | -43.5 | 2400% | 36 | 18 | Feature Estimation
TAP-112012 | 20 | TAP-111760 |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 |  | 43.5 | 1 hr | 1 hr | -43.5 | 2400% | 36 | 18 | Feature Estimation
TAP-111569 | 21 | TAP-111760 |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 |  | 43.5 | 1 hr | 1 hr | -43.5 | 1600% | 24 | 12 | Feature Estimation
TAP-111565 | 22 | TAP-111760 |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 |  | 43.5 | 1 hr | 1 hr | -43.5 | 1000% | 40 | 20 | Feature Estimation
TAP-111556 | 23 | TAP-111559, TAP-111760 | TAP-94966 | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 |  | 43.5 | 1 hr | 1 hr | -43.5 | 2000% | 30 | 15 | Feature Estimation
TAP-111559 | 24 | TAP-111760 | TAP-111556 | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 |  | 43.5 | 1 hr | 1 hr | -43.5 | 2000% | 30 | 15 | Feature Estimation
TAP-112077 | 25 | TAP-111760 | TAP-111562 | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 60 |  | 43.5 | 1 hr | 1 hr | 16.5 | 4000% | 60 | 30 | Story Points
TAP-112077_SIRIUS | 26 |  |  | 01.04.01.02.00.00.00.00 | TAP-112077 | TAP-115017 | [TAP-112077_SIRIUS] ¦ [IRR][Articulation] Finalize KPI/Simulation Script | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 7 |  | 50.5 |  | 1 hr | -43.5 | 100%
TAP-112077_HAPPYJAWS | 27 |  |  | 01.04.01.04.00.00.00.00 | TAP-112077 | TAP-116520 | [TAP-112077_HAPPYJAWS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in NoHa | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 |  | 50.5 | 1 hr | 1 hr | -47.5 | 16.83% | 0 | 0
TAP-120096 | 28 | TAP-111760 |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 |  | 50.5 | 1 hr | 1 hr | -50.5 | 0% | 0 | 0 | Feature Estimation
TAP-103448 | 29 | TAP-111760 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 |  | 50.5 | 1 hr | 1 hr | -36.5 | 0% | 0 | 0 | Story Points
TAP-103448_I2E | 30 |  |  | 01.05.01.01.00.00.00.00 | TAP-103448 | TAP-99022 | [TAP-103448_I2E] ¦ [v3.1][IRR][IDU CMD][I2E] Add Shears functionality to M-IRR's tool within Discrete Control Command | User Story | Done | Advanced Instruments - I2E | I2E |  |  | 5 |  | 55.5 |  | 1 hr | -50.5 | 100%
TAP-116286 | 31 | TAP-111760 |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 |  | 55.5 | 1 hr | 1 hr | -37.5 | 0% | 0 | 0 | Story Points
TAP-116286_SIRIUS | 32 |  |  | 01.05.03.02.00.00.00.00 | TAP-116286 | TAP-116514 | [TAP-116286_SIRIUS] ¦ [IRR][Analysis] Obtain brand new needle drivers | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 |  | 55.5 | 1 hr | 1 hr | -53.5 | 27.75% | 0 | 0
TAP-116286_HAPPYJAWS | 33 |  |  | 01.05.03.03.00.00.00.00 | TAP-116286 | TAP-116515 | [TAP-116286_HAPPYJAWS] ¦ [IRR][Analysis] Collect KPI data on a set of brand new instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 |  | 55.5 | 1 hr | 1 hr | -52.5 | 18.5% | 0 | 0
TAP-95983 | 34 | TAP-111760 |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 108 |  | 55.5 | 1 hr | 1 hr | 52.5 | 0% | 41 | 73 | Story Points
TAP-95983_HAPPYJAWS | 35 |  |  | 01.05.04.01.00.00.00.00 | TAP-95983 | TAP-88491 | [TAP-95983_HAPPYJAWS] ¦ [IRR][PlantSim][Happy Jaws] Introduce IDU Standalones to Modeling Team | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 |  | 56.5 |  | 1 hr | -55.5 | 100%
TAP-95983_SIRIUS | 36 |  |  | 01.05.04.02.00.00.00.00 | TAP-95983 | TAP-87610 | [TAP-95983_SIRIUS] ¦ [IRR][PlantSim][Sirius] Setup VM with Docker and git on Server in Mounds View | User Story | In progress | Core Instruments - Sirius | SIRIUS |  |  | 4 |  | 56.5 |  | 1 hr | -52.5 | 0%
TAP-95983_ANIMATORS | 37 |  |  | 01.05.04.07.00.00.00.00 | TAP-95983 | TAP-115103 | [TAP-95983_ANIMATORS] ¦ [IRR][PlantModels] Wristed Instrument Model Credibility and Risk Assessment (Validation) | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 0% | 0 | 0
TAP-95983_PUPPETEERS | 38 |  |  | 01.05.04.14.00.00.00.00 | TAP-95983 | TAP-116408 | [TAP-95983_PUPPETEERS] ¦ [IRR][Puppeteers] Support for framework for wristed testing | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 13 |  | 56.5 | 1 hr | 1 hr | -43.5 | 4.346% | 0 | 0
TAP-111719 | 39 | TAP-111562, TAP-111760 | TAP-124116 | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 |  | 56.5 | 1 hr | 1 hr | -51.5 | 0% | 15 | 22 | Story Points
TAP-111719_I2E | 40 |  |  | 01.05.05.04.00.00.00.00 | TAP-111719 | TAP-114445 | [TAP-111719_I2E] ¦ [MIRR][I2E][Spike] Support Sebastian in testing/configuring Galil | User Story | In progress | Advanced Instruments - I2E | I2E |  |  | 2 |  | 56.5 | 1 hr | 1 hr | -54.5 | 28.25% | 0 | 0
TAP-111721 | 41 | TAP-111760 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 |  | 56.5 | 1 hr | 1 hr | -32 | 5400% | 60 | 30 | Story Points
TAP-111721_SIRIUS | 42 |  |  | 01.05.06.02.00.00.00.00 | TAP-111721 | TAP-115880 | [TAP-111721_SIRIUS] ¦ [IRR][ORSI] Update Lab SW for Hard Stop recovery | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 |  | 56.5 | 1 hr | 1 hr | -53.5 | 18.83% | 0 | 0
TAP-111721_HAPPYJAWS | 43 |  |  | 01.05.06.09.00.00.00.00 | TAP-111721 | TAP-122340 | [TAP-111721_HAPPYJAWS] ¦ [IRR] Update Lab SW with Protection Against Slow Close | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 1 |  | 56.5 | 1 hr | 1 hr | -55.5 | 56.5% | 0 | 0
TAP-111721_PUPPETEERS | 44 |  |  | 01.05.06.12.00.00.00.00 | TAP-111721 | TAP-123066 | [TAP-111721_PUPPETEERS] ¦ [IRR][Puppeteers] Merge latest JBO updates to IRR staging branch for ORSI lab | User Story | In progress | Core Instruments - Puppeteers | PUPPETEERS |  |  | 2 |  | 56.5 | 1 hr | 1 hr | -54.5 | 28.25% | 0 | 0
TAP-111722 | 45 | TAP-111760 |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 5400% | 60 | 30 | Feature Estimation
TAP-111723 | 46 | TAP-111760 |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 5400% | 60 | 30 | Feature Estimation
TAP-111724 | 47 | TAP-111760 |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 5400% | 60 | 30 | Feature Estimation
TAP-112119 | 48 | TAP-111760 |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 2000% | 40 | 20 | Feature Estimation
TAP-94125 | 49 | TAP-111753, TAP-111760 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Instrument Homing Compatible with WS5 Structure | Feature | Accepted |  |  |  |  | 77 |  | 56.5 | 1 hr | 1 hr | 20.5 | 0% | 50 | 70 | Story Points
TAP-94125_SIRIUS | 50 |  |  | 01.06.01.01.00.00.00.00 | TAP-94125 | TAP-97747 | [TAP-94125_SIRIUS] ¦ [WS5][Homing][Sirius] Evaluate Homing Controller Architecture and Identify Improvements | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 5 |  | 56.5 |  | 1 hr | -51.5 | 0%
TAP-95800 | 51 | TAP-111754, TAP-111760 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development Motor Controller Compatible with WS5 Structure | Feature | Accepted |  |  |  |  | 29 |  | 56.5 | 1 hr | 1 hr | -27.5 | 0% | 15 | 35 | Story Points
TAP-95800_SIRIUS | 52 |  |  | 01.06.02.01.00.00.00.00 | TAP-95800 | TAP-91185 | [TAP-95800_SIRIUS] ¦ [IRG][SW][WS5] Investigate alternative IDU motor position control approaches | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 4 |  | 56.5 |  | 1 hr | -52.5 | 0%
TAP-111740 | 53 | TAP-111756, TAP-111760 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 28 |  | 56.5 | 1 hr | 1 hr | -28.5 | 12000% | 160 | 80 | Story Points
TAP-111740_HAPPYJAWS | 54 |  |  | 01.06.03.02.00.00.00.00 | TAP-111740 | TAP-115106 | [TAP-111740_HAPPYJAWS] ¦ [IRR][Phase 1b][Happy Jaws] Refactor teleoperation SWI to consolidate IK and improve architecture | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 |  | 56.5 | 1 hr | 1 hr | -53.5 | 18.83% | 0 | 0
TAP-111740_SIRIUS | 55 |  |  | 01.06.03.06.00.00.00.00 | TAP-111740 | TAP-116486 | [TAP-111740_SIRIUS] ¦ [IRR][Phase 1b][Teleoperation] Update and fix Static Analysis issues | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 2 |  | 56.5 | 1 hr | 1 hr | -54.5 | 28.25% | 0 | 0
TAP-111749 | 56 | TAP-111757, TAP-111760 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 3200% | 60 | 30 | Feature Estimation
TAP-111749_SIRIUS | 57 |  |  | 01.06.04.02.00.00.00.00 | TAP-111749 | TAP-112328 | [TAP-111749_SIRIUS] ¦ [IRR] Evaluate risk rank of alternate instrument hardware failure modes | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 0% | 0 | 0
TAP-111750 | 58 | TAP-111758, TAP-111760 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Procedure Manager SWI for IRR | Feature | Accepted |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 3000% | 70 | 35 | Feature Estimation
TAP-111751 | 59 | TAP-111759, TAP-111760 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 5600% | 90 | 45 | Feature Estimation
TAP-117678 | 60 | TAP-111760 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 0% | 0 | 0 | Feature Estimation
TAP-111834 | 61 | TAP-111760 | TAP-113995 | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 2000% | 40 | 20 | Feature Estimation
TAP-111747 | 62 | TAP-113104 |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 10000% | 200 | 100 | Feature Estimation
TAP-111772 | 63 | TAP-113104 |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 3000% | 40 | 20 | Feature Estimation
TAP-111773 | 64 | TAP-113104 |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 10000% | 130 | 65 | Feature Estimation
TAP-111838 | 65 | TAP-111842, TAP-113104 |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 2000% | 30 | 15 | Feature Estimation
TAP-104213 | 66 | TAP-111842, TAP-113104 |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 3000% | 90 | 45 | Feature Estimation
TAP-111842 | 67 | TAP-113104 | TAP-104213, TAP-111838 | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 |  | 56.5 | 1 hr | 1 hr | -56.5 | 4000% | 60 | 30 | Feature Estimation
TAP-111774 | 68 | TAP-111775, TAP-112080, TAP-113104 |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 10 |  | 56.5 | 1 hr | 1 hr | -46.5 | 2800% | 47 | 34 | Story Points
TAP-111774_CASTLEBLACK | 69 |  |  | 02.04.01.04.00.00.00.00 | TAP-111774 | TAP-116177 | [TAP-111774_CASTLEBLACK] ¦ [Spike] Investigate Instrument Observer Mitigations | User Story | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 1 |  | 56.5 | 1 hr | 1 hr | -55.5 | 56.5% | 0 | 0
TAP-111774_PUPPETEERS | 70 |  |  | 02.04.01.05.00.00.00.00 | TAP-111774 | TAP-116194 | [TAP-111774_PUPPETEERS] ¦ [IRR][Puppeteers]cFMEA - Investigate risk analysis for MSO Joint Tracking Check- initial | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 5 |  | 61.5 | 1 hr | 1 hr | -56.5 | 100% | 0 | 0
TAP-112080 | 71 | TAP-111775, TAP-113104 | TAP-111774 | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 14 |  | 61.5 | 1 hr | 1 hr | -47.5 | 5000% | 85 | 63 | Story Points
TAP-112080_PUPPETEERS | 72 |  |  | 02.04.02.05.00.00.00.00 | TAP-112080 | TAP-116414 | [TAP-112080_PUPPETEERS] ¦ [IRR][Puppeteers] Kinematics prototype for MSO joint check replacement | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 13 |  | 61.5 | 1 hr | 1 hr | -48.5 | 4.731% | 0 | 0
TAP-111775 | 73 | TAP-113104 | TAP-111774, TAP-112080 | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 |  | 61.5 | 1 hr | 1 hr | -60.5 | 6100% | 99 | 75 | Feature Estimation
TAP-111775_PUPPETEERS | 74 |  |  | 02.04.03.05.00.00.00.00 | TAP-111775 | TAP-121472 | [TAP-111775_PUPPETEERS] ¦ [IRR][Puppeteers] Update Polarion | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 |  | 61.5 | 1 hr | 1 hr | -60.5 | 61.5% | 0 | 0
TAP-123862 | 75 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 76 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR][MaybePnP] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 77 | TAP-113104 |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 32000% | 625 | 325 | Feature Estimation
TAP-111656 | 78 | TAP-113104 |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 16100% | 293 | 278 | Feature Estimation
TAP-111925 | 79 | TAP-113104 |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 3000% | 60 | 30 | Feature Estimation
TAP-112113 | 80 | TAP-113104 |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 0% | 0 | 0 | Feature Estimation
TAP-111865 | 81 | TAP-113104 |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 0% | 0 | 0 | Feature Estimation
TAP-113111 | 82 | TAP-111689, TAP-111695 |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 83 | TAP-111687, TAP-111689, TAP-111695 |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 0 |  | 61.5 | 1 hr | 1 hr | -61.5 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 84 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 |  | 61.5 | 1 hr | 1 hr | -37.5 | 0% | 0 | 0 | Story Points
TAP-114692_CASTLEBLACK | 85 |  |  | 02.07.02.03.01.00.00.00 | TAP-114692 | TAP-116170 | [TAP-114692_CASTLEBLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK |  |  | 2 |  | 61.5 | 1 hr | 1 hr | -59.5 | 30.75% | 0 | 0
TAP-114692_PUPPETEERS | 86 |  |  | 02.07.02.03.02.00.00.00 | TAP-114692 | TAP-116199 | [TAP-114692_PUPPETEERS] ¦ [IRR][Puppeteers] Sree session | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 |  | 62.5 | 1 hr | 1 hr | -61.5 | 100% | 0 | 0
TAP-114692_SIRIUS | 87 |  |  | 02.07.02.03.07.00.00.00 | TAP-114692 | TAP-123143 | [TAP-114692_SIRIUS] ¦ [IRR][Sirius] Manually update use life notcodes for staging/IRR-v3-control-development | User Story | Done | Core Instruments - Sirius | SIRIUS |  |  | 2 |  | 64.5 | 1 hr | 1 hr | -62.5 | 100% | 0 | 0 | Feature Estimation
TAP-114689 | 88 | TAP-111687 |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Accepted |  |  |  |  | 15 |  | 64.5 | 1 hr | 1 hr | -49.5 | 0% | 0 | 0 | Story Points
TAP-114689_PIXELPOETS | 89 |  |  | 02.07.02.04.01.00.00.00 | TAP-114689 | TAP-115102 | [TAP-114689_PIXELPOETS] ¦ [MIRR][Pixel Poets] Finalize Design for Use Life Indicator | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 1 |  | 65.5 | 1 hr | 1 hr | -64.5 | 100% | 0 | 0
TAP-114689_CASTLEBLACK | 90 |  |  | 02.07.02.04.04.00.00.00 | TAP-114689 | TAP-116170 | [TAP-114689_CASTLEBLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK |  |  | 2 |  | 65.5 | 1 hr | 1 hr | -63.5 | 32.75% | 0 | 0
TAP-90375 | 91 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 |  | 65.5 | 1 hr | 1 hr | -56.5 | 0% |  |  | Story Points
TAP-90375_STELLARS | 92 |  |  | 02.07.03.01.01.00.00.00 | TAP-90375 | TAP-96606 | [TAP-90375_STELLARS] ¦ [Stellars] [TAP-90375] [Enabler] Identify Jama linking to be updated | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 1 |  | 65.5 |  | 1 hr | -64.5 | 0%
TAP-111861 | 93 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 |  | 65.5 | 1 hr | 1 hr | -62.5 | 4600% | 64 | 46 | Story Points
TAP-111861_PUPPETEERS | 94 |  |  | 02.07.03.02.04.00.00.00 | TAP-111861 | TAP-115871 | [TAP-111861_PUPPETEERS] ¦ [IRR] Increment Use count when instrument is expired | User Story | Groomed | Core Instruments - Puppeteers | PUPPETEERS |  |  | 3 |  | 65.5 | 1 hr | 1 hr | -62.5 | 21.83% | 0 | 0
TAP-111687 | 95 |  | TAP-113123, TAP-114689 | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 4800% | 80 | 46 | Feature Estimation
TAP-111689 | 96 |  | TAP-113111, TAP-113123 | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 4900% | 76 | 48 | Feature Estimation
TAP-111695 | 97 |  | TAP-113111, TAP-113123 | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 3500% | 72 | 46 | Feature Estimation
TAP-111753 | 98 | TAP-111761, TAP-111765 | TAP-94125 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 6000% | 100 | 50 | Feature Estimation
TAP-111754 | 99 | TAP-110382, TAP-111765 | TAP-95800 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 |  | 65.5 | 1 hr | 1 hr | -62.5 | 2000% | 30 | 15 | Feature Estimation
TAP-111754_SIRIUS | 100 |  |  | 03.01.02.02.00.00.00.00 | TAP-111754 | TAP-116481 | [TAP-111754_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Sirius | SIRIUS |  |  | 3 |  | 65.5 | 1 hr | 1 hr | -62.5 | 21.83% | 0 | 0
TAP-111756 | 101 | TAP-111762, TAP-111765 | TAP-111740 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 |  | 65.5 | 1 hr | 1 hr | -62.5 | 7000% | 90 | 45 | Feature Estimation
TAP-111756_HAPPYJAWS | 102 |  |  | 03.01.03.02.00.00.00.00 | TAP-111756 | TAP-116489 | [TAP-111756_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS |  |  | 3 |  | 65.5 | 1 hr | 1 hr | -62.5 | 21.83% | 0 | 0
TAP-111757 | 103 | TAP-111748, TAP-111765 | TAP-111749 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 3200% | 60 | 30 | Feature Estimation
TAP-111758 | 104 | TAP-111764, TAP-111765 | TAP-111750 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 3000% | 60 | 30 | Feature Estimation
TAP-111759 | 105 | TAP-111766, TAP-111765 | TAP-111751 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 4000% | 60 | 30 | Feature Estimation
TAP-111761 | 106 | TAP-111765 | TAP-111753 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 5000% | 60 | 30 | Feature Estimation
TAP-110382 | 107 | TAP-111765 | TAP-111754 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 1000% | 16 | 8 | Feature Estimation
TAP-111762 | 108 | TAP-111765 | TAP-111756 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 3000% | 50 | 25 | Feature Estimation
TAP-111748 | 109 | TAP-111765 | TAP-111757 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 1600% | 30 | 15 | Feature Estimation
TAP-111764 | 110 | TAP-111765 | TAP-111758 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 2000% | 30 | 15 | Feature Estimation
TAP-111766 | 111 | TAP-111765 | TAP-111759 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 3000% | 40 | 20 | Feature Estimation
TAP-112082 | 112 | TAP-111765 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 6500% | 185 | 125 | Feature Estimation
TAP-112093 | 113 | TAP-111765 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 11000% | 140 | 70 | Feature Estimation
TAP-112094 | 114 | TAP-111765 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 17400% | 340 | 170 | Feature Estimation
TAP-113100 | 115 | TAP-113101 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 40000% | 800 | 400 | Feature Estimation
TAP-111900 | 116 | TAP-121104 | TAP-111767 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 10900% | 212 | 152 | Feature Estimation
TAP-112042 | 117 | TAP-121104 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 4400% | 60 | 30 | Feature Estimation
TAP-111692 | 118 | TAP-121104 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 15000% | 220 | 195 | Feature Estimation
TAP-112231 | 119 | TAP-121104 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 8000% | 100 | 50 | Feature Estimation
TAP-112233 | 120 | TAP-121104 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 2000% | 40 | 20 | Feature Estimation
TAP-112234 | 121 | TAP-121104 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 4000% | 80 | 40 | Feature Estimation
TAP-113127 | 122 | TAP-121104 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 |  | 65.5 | 1 hr | 1 hr | -65.5 | 0% | 0 | 0 | Feature Estimation
| 123 |  |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 |  | Defect | Investigation |  |  |  |  | 30 |  | 65.5 | 1 hr | 1 hr | -35.5 | 2.183% | 0 | 0
TAP-115187 | 124 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 |  | 94.5 | 1 hr | 1 hr | -65.5 | 100% | 0 | 0
TAP-115187_STELLARS | 125 |  |  | 06.01.01.01.01.00.00.00 | TAP-115187 | TAP-115835 | [TAP-115187_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 1 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 5 |  | 99.5 |  | 1 hr | -94.5 | 100%
TAP-115187_SUNRISERS | 126 |  |  | 06.01.01.01.07.00.00.00 | TAP-115187 | TAP-116278 | [TAP-115187_SUNRISERS] ¦ [Sunrisers] [RAS-7203] [Enabler] Implementation changes review - SP2 | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS |  |  | 1 |  | 100.5 | 1 hr | 1 hr | -99.5 | 100% | 0 | 0
TAP-122269 | 127 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 1 |  | 100.5 | 1 hr | 1 hr | -99.5 | 0% | 0 | 0 | Feature Estimation
TAP-122269_STELLARS | 128 |  |  | 06.01.01.02.01.00.00.00 | TAP-122269 | TAP-117467 | [TAP-122269_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Attend CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 1 |  | 100.5 |  | 1 hr | -99.5 | 0%
| 129 |  |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 |  | Defect | Investigation |  |  |  |  | 108.25 |  | 100.5 |  | 1 hr | 7.75 | 0%
TAP-64314 | 130 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 |  | 132.75 | 1 hr | 1 hr | -100.5 | 100%
TAP-64314_JACOBIANS | 131 |  |  | 06.01.02.01.01.00.00.00 | TAP-64314 | TAP-60617 | [TAP-64314_JACOBIANS] ¦ [MBTI][Spike] Investigate Potential Causes of Roll Jump Discontinuity (RAS-7532) | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6.25 |  | 139 |  | 1 hr | -132.75 | 100%
TAP-64315 | 132 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 |  | 164 | 1 hr | 1 hr | -139 | 100%
TAP-64315_JACOBIANS | 133 |  |  | 06.01.02.02.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-64315_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 |  | 172 |  | 1 hr | -164 | 100%
TAP-64315_REFLECT | 134 |  |  | 06.01.02.02.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-64315_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 3 |  | 175 |  | 1 hr | -172 | 100%
TAP-83712 | 135 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 |  | 197 | 1 hr | 1 hr | -175 | 100%
TAP-83712_JACOBIANS | 136 |  |  | 06.01.02.04.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-83712_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 199 |  | 1 hr | -197 | 100%
| 137 |  |  | 06.01.03.00.00.00.00.00 |  | RAS-9107 |  | Defect | Open |  |  |  |  | 76 |  | 199 |  | 1 hr | -123 | 0%
TAP-64315 | 138 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 |  | 224 | 1 hr | 1 hr | -199 | 100%
TAP-64315_JACOBIANS | 139 |  |  | 06.01.03.01.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-64315_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 |  | 232 |  | 1 hr | -224 | 100%
TAP-64315_REFLECT | 140 |  |  | 06.01.03.01.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-64315_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 3 |  | 235 |  | 1 hr | -232 | 100%
TAP-83712 | 141 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 |  | 257 | 1 hr | 1 hr | -235 | 100%
TAP-83712_JACOBIANS | 142 |  |  | 06.01.03.03.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-83712_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 259 |  | 1 hr | -257 | 100%
| 143 |  |  | 06.01.04.00.00.00.00.00 |  | RAS-10590 |  | Defect | Confirmed |  |  |  |  | 11 |  | 259 |  | 1 hr | -248 | 0%
TAP-83712_VISUAL | 144 |  |  | 06.01.04.01.00.00.00.00 |  | TAP-86405 | [TAP-83712_VISUAL] ¦ [CAPA] Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual | VISUAL |  |  | 3 |  | 262 |  | 1 hr | -259 | 100%
| 145 |  |  | 06.04.01.01.00.00.00.00 |  | RAS-13292 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 262 | 1 hr | 1 hr | -262 | 100% | 0 | 0
| 146 |  |  | 06.04.02.01.00.00.00.00 |  | RAS-14234 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 262 | 1 hr | 1 hr | -262 | 100% | 0 | 0
| 147 |  |  | 06.04.02.02.00.00.00.00 |  | RAS-14305 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 262 | 1 hr | 1 hr | -262 | 100% | 0 | 0
| 148 |  |  | 06.04.02.03.00.00.00.00 |  | RAS-8707 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 262 |  | 1 hr | -262 | 0%
| 149 |  |  | 06.04.02.04.00.00.00.00 |  | RAS-7177 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 262 |  | 1 hr | -262 | 0%
| 150 |  |  | 06.04.03.01.00.00.00.00 |  | RAS-3230 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 262 |  | 1 hr | -262 | 0%
| 151 |  |  | 06.04.03.02.00.00.00.00 |  | RAS-4262 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 262 |  | 1 hr | -262 | 0%
| 152 |  |  | 06.04.04.01.00.00.00.00 |  | RAS-10357 |  | Defect | DEFERRED |  |  |  |  | 16 |  | 262 |  | 1 hr | -246 | 0%
TAP-94573 | 153 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 |  | 275 | 1 hr | 1 hr | -262 | 100%
TAP-94573_STELLARS | 154 |  |  | 06.04.04.01.01.01.00.00 | TAP-94573 | TAP-96622 | [TAP-94573_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Reproduce issue in SW 4.x | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 1 |  | 276 |  | 1 hr | -275 | 100%
TAP-109680 | 155 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 |  | 276 | 1 hr | 1 hr | -273 | 0% |  |  | Feature Estimation
TAP-109680_STELLARS | 156 |  |  | 06.04.04.01.03.01.00.00 | TAP-109680 | TAP-114754 | [TAP-109680_STELLARS] ¦ [Stellars] [RAS-10357] CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 3 |  | 276 |  | 1 hr | -273 | 0%
| 157 |  |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 |  | Defect | In progress |  |  |  |  | 0 |  | 276 |  | 1 hr | -276 | 0%
TAP-111760 | 158 | TAP-111763 | TAP-94739, TAP-111559, TAP-111834, TAP-95800, TAP-120096, TAP-111719, TAP-117678, TAP-95983, TAP-111731, TAP-111555, TAP-111556, TAP-111751, TAP-111730, TAP-111554, TAP-116286, TAP-111750, TAP-111749, TAP-111724, TAP-111722, TAP-112119, TAP-111569, TAP-103448, TAP-111723, TAP-94966, TAP-112076, TAP-94125, TAP-111721, TAP-111740, TAP-111565, TAP-112012, TAP-112077, TAP-120097, TAP-123834 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 159 | TAP-113104 | TAP-111760 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 2000% | 30 | 15 | Feature Estimation
TAP-113104 | 160 | TAP-113105 | TAP-111747, TAP-111772, TAP-111838, TAP-111925, TAP-104213, TAP-111656, TAP-111865, TAP-112080, TAP-111775, TAP-111842, TAP-111773, TAP-111642, TAP-111774, TAP-112113, TAP-111763 | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 161 | TAP-111765 | TAP-113104 | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 2000% | 30 | 15 | Feature Estimation
TAP-111765 | 162 | TAP-111768 | TAP-111753, TAP-111754, TAP-111756, TAP-111757, TAP-111758, TAP-111759, TAP-111761, TAP-110382, TAP-111762, TAP-111748, TAP-111764, TAP-111766, TAP-112082, TAP-112093, TAP-112094, TAP-113105 | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 163 | TAP-111769 | TAP-111765 | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 164 | TAP-111767 | TAP-111768 | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 165 | TAP-111900 | TAP-111769 | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 2000% | 30 | 15 | Feature Estimation
TAP-113101 | 166 | TAP-113102 | TAP-113100 | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 167 | TAP-113103 | TAP-113101 | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 168 | TAP-121104 | TAP-113102 | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 2000% | 30 | 15 | Feature Estimation
TAP-121104 | 169 |  | TAP-111900, TAP-112042, TAP-111692, TAP-112231, TAP-112233, TAP-112234, TAP-113127, TAP-113103 | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-94968 | 170 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% |  |  | Feature Estimation
TAP-111726 | 171 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 4000% | 60 | 30 | Feature Estimation
TAP-111727 | 172 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111729 | 173 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-94967 | 174 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% |  |  | Feature Estimation
TAP-111733 | 175 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111734 | 176 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111735 | 177 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-111570 | 178 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-112107 | 179 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 3000% | 60 | 30 | Feature Estimation
TAP-111934 | 180 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 181 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 2000% | 20 | 10 | Feature Estimation
TAP-112084 | 182 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 2000% | 20 | 10 | Feature Estimation
TAP-112101 | 183 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 32000% | 640 | 320 | Feature Estimation
TAP-112086 | 184 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 5000% | 100 | 50 | Feature Estimation
TAP-112087 | 185 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 10000% | 200 | 100 | Feature Estimation
TAP-112095 | 186 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% | 0 | 0 | Feature Estimation
TAP-106203 | 187 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 0% |  |  | Feature Estimation
TAP-100791 | 188 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 |  | 276 | 1 hr | 1 hr | -276 | 100%

## Log
DataTimeStamp | Event | Data

## Summary
Resource Names | Sum FDR
HAPPYJAWS
SIRIUS
HAPPYJAWS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
SIRIUS
HAPPYJAWS
I2E
SIRIUS
HAPPYJAWS
HAPPYJAWS
SIRIUS
ANIMATORS
PUPPETEERS
I2E
SIRIUS
HAPPYJAWS
PUPPETEERS
SIRIUS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
CASTLEBLACK
PUPPETEERS
PUPPETEERS
PUPPETEERS
CASTLEBLACK
PUPPETEERS
SIRIUS
PIXELPOETS
CASTLEBLACK
STELLARS
PUPPETEERS
SIRIUS
HAPPYJAWS
STELLARS
SUNRISERS
STELLARS
JACOBIANS
JACOBIANS
REFLECT
JACOBIANS
JACOBIANS
REFLECT
JACOBIANS
VISUAL
STELLARS
STELLARS