## Project
Selector | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Index | Parent Feature | Key | Task Name | Issue Type | Status | ART | Resource Names | Task Type | Source | Σ Total SP | Σ Groom SP | Σ Done SP | Focus Duration | Low-Risk Duration | Remaining SP | % Complete | Σ Realistic Estimate | Σ Worst Case Estimate | RefinementLevel
TAP-94739 | 1 | TAP-97668, TAP-111760 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 |  | 24 | 1 hr | 1 hr | -12 | 100% | 40 | 50 | Story Points
TAP-94739_HAPPYJAWS | 2 |  |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-94739_HAPPYJAWS] ¦ [IRR][Arch] Describe wristed controller system functional architecture | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 5 |  | 10 |  | 1 hr | -5 | 100%
| 3 |  |  | 01.01.01.03.00.00.00.00 | TAP-94739 | TAP-99738 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
TAP-94739_SIRIUS | 4 |  |  | 01.01.01.04.00.00.00.00 | TAP-94739 | TAP-97602 | [TAP-94739_SIRIUS] ¦ [IRR][Arch] Analyze requirement impact | User Story | Done | Core Instruments | SIRIUS |  |  | 3 |  | 6 |  | 1 hr | -3 | 100%
| 5 |  |  | 01.01.01.05.00.00.00.00 | TAP-94739 | TAP-106673 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 6 |  |  | 01.01.01.06.00.00.00.00 | TAP-94739 | TAP-111973 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 40 | 50
TAP-97668 | 7 | TAP-120097 | TAP-94739 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  |  |  | 32.5 |  | 65 | 1 hr | 1 hr | -32.5 | 100% | 6 | 8 | Story Points
| 8 |  |  | 01.01.02.01.00.00.00.00 | TAP-97668 | TAP-111972 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 6 | 8
TAP-97668_HAPPYJAWS | 9 |  |  | 01.01.02.02.00.00.00.00 | TAP-97668 | TAP-97600 | [TAP-97668_HAPPYJAWS] ¦ [IRR][Arch] Identify impacts and opportunities on testing strategy | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 3.5 |  | 7 |  | 1 hr | -3.5 | 100%
| 10 |  |  | 01.01.02.03.00.00.00.00 | TAP-97668 | TAP-97595 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 6 |  | 12 |  | 1 hr | -6 | 100%
TAP-97668_SIRIUS | 11 |  |  | 01.01.02.04.00.00.00.00 | TAP-97668 | TAP-97586 | [TAP-97668_SIRIUS] ¦ [IRR][Arch] Migration and branch sync considerations | User Story | Done | Core Instruments | SIRIUS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 12 |  |  | 01.01.02.05.00.00.00.00 | TAP-97668 | TAP-97581 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 10 |  | 20 |  | 1 hr | -10 | 100%
| 13 |  |  | 01.01.02.06.00.00.00.00 | TAP-97668 | TAP-97568 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 14 |  | 28 |  | 1 hr | -14 | 100%
| 14 |  |  | 01.01.02.08.00.00.00.00 | TAP-97668 | TAP-114765 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 15 |  |  | 01.01.02.09.00.00.00.00 | TAP-97668 | TAP-114792 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 16 |  |  | 01.01.02.10.00.00.00.00 | TAP-97668 | TAP-114794 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
| 17 |  |  | 01.01.02.11.00.00.00.00 | TAP-97668 | TAP-123215 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 6 |  | 12 |  | 1 hr | -6 | 100%
TAP-120097 | 18 | TAP-111760 | TAP-97668 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | PROPOSED |  |  |  |  | 28.5 |  | 0 | 1 hr | 1 hr | 28.5 | 0% | 0 | 0 | Story Points
TAP-120097_HAPPYJAWS | 19 |  |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-97689 | [TAP-120097_HAPPYJAWS] ¦ [IRR][Arch] Update instrument data model for wristed instruments | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 1 |  | 0 |  | 1 hr | 1 | 0%
| 20 |  |  | 01.01.03.02.00.00.00.00 | TAP-120097 | TAP-106674 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 8 |  | 0 |  | 1 hr | 8 | 0%
| 21 |  |  | 01.01.03.03.00.00.00.00 | TAP-120097 | TAP-97598 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 4 |  | 0 |  | 1 hr | 4 | 0%
| 22 |  |  | 01.01.03.04.00.00.00.00 | TAP-120097 | TAP-114803 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
| 23 |  |  | 01.01.03.05.00.00.00.00 | TAP-120097 | TAP-115970 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 7 |  | 0 |  | 1 hr | 7 | 0%
| 24 |  |  | 01.01.03.06.00.00.00.00 | TAP-120097 | TAP-117147 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
| 25 |  |  | 01.01.03.07.00.00.00.00 | TAP-120097 | TAP-116501 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 20 |  | 0 | 1 hr | 1 hr | 20 | 0% | 0 | 0
| 26 |  |  | 01.01.03.08.00.00.00.00 | TAP-120097 | TAP-105494 |  | User Story | In progress | Core Instruments | HAPPYJAWS |  |  | 8 |  | 0 |  | 1 hr | 8 | 0%
TAP-111730 | 27 | TAP-111760, TAP-124062 | TAP-106315 | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 28 |  | 20 | 1 hr | 1 hr | 8 | 0% | 30 | 40 | Story Points
| 28 |  |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 30 | 40
TAP-111730_HAPPYJAWS | 29 |  |  | 01.02.01.02.00.00.00.00 | TAP-111730 | TAP-116458 | [TAP-111730_HAPPYJAWS] ¦ [IRR][Clamping] Update switching logic in jaw torque estimator | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 6 |  | 12 | 1 hr | 1 hr | -6 | 100% | 0 | 0
| 30 |  |  | 01.02.01.03.00.00.00.00 | TAP-111730 | TAP-116459 |  | User Story | In progress | Core Instruments | HAPPYJAWS |  |  | 16 |  | 0 | 1 hr | 1 hr | 16 | 0% | 0 | 0
| 31 |  |  | 01.02.01.07.00.00.00.00 | TAP-111730 | TAP-116463 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 32 |  |  | 01.02.01.08.00.00.00.00 | TAP-111730 | TAP-121692 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
| 33 |  |  | 01.02.01.09.00.00.00.00 | TAP-111730 | TAP-122144 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 12 |  | 24 | 1 hr | 1 hr | -12 | 100% | 0 | 0
| 34 |  |  | 01.02.01.10.00.00.00.00 | TAP-111730 | TAP-125005 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0 | Feature Estimation
TAP-111731 | 35 | TAP-111760 |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 50 | Feature Estimation
| 36 |  |  | 01.02.02.01.00.00.00.00 | TAP-111731 | TAP-111906 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 50
TAP-111731_ANIMATORS | 37 |  |  | 01.02.02.02.00.00.00.00 | TAP-111731 | TAP-112037 | [TAP-111731_ANIMATORS] ¦ [Animators] Reduce Force Variation when articulating during clamp | Feature Estimation | Open | Shared Services - Animators | ANIMATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
TAP-124062 | 38 |  | TAP-111730 | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112076 | 39 | TAP-111760 |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
| 40 |  |  | 01.03.01.01.00.00.00.00 | TAP-112076 | TAP-112078 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 10
TAP-94966 | 41 | TAP-111556, TAP-111760 | TAP-111562 | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | In progress |  |  |  |  | 37 |  | 25 | 1 hr | 1 hr | 12 | 0% | 45 | 78 | Story Points
| 42 |  |  | 01.03.02.01.00.00.00.00 | TAP-94966 | TAP-111781 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 33
| 43 |  |  | 01.03.02.02.00.00.00.00 | TAP-94966 | TAP-111786 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 25 | 45
TAP-94966_HAPPYJAWS | 44 |  |  | 01.03.02.03.00.00.00.00 | TAP-94966 | TAP-116502 | [TAP-94966_HAPPYJAWS] ¦ [IRR][Cutting] Reproduce position estimation failures & Investigate | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 45 |  |  | 01.03.02.04.00.00.00.00 | TAP-94966 | TAP-116503 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
| 46 |  |  | 01.03.02.05.00.00.00.00 | TAP-94966 | TAP-116504 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
| 47 |  |  | 01.03.02.06.00.00.00.00 | TAP-94966 | TAP-116505 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
| 48 |  |  | 01.03.02.07.00.00.00.00 | TAP-94966 | TAP-116508 |  | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
TAP-94966_SIRIUS | 49 |  |  | 01.03.02.08.00.00.00.00 | TAP-94966 | TAP-116509 | [TAP-94966_SIRIUS] ¦ [IRR][Use-life] Identify dependent use-life parameters | User Story | Done | Core Instruments | SIRIUS |  |  | 8 |  | 16 | 1 hr | 1 hr | -8 | 100% | 0 | 0
| 50 |  |  | 01.03.02.10.00.00.00.00 | TAP-94966 | TAP-116511 |  | User Story | In progress | Core Instruments | SIRIUS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 51 |  |  | 01.03.02.11.00.00.00.00 | TAP-94966 | TAP-116512 |  | User Story | In progress | Core Instruments | SIRIUS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 52 |  |  | 01.03.02.12.00.00.00.00 | TAP-94966 | TAP-124596 |  | User Story | In progress | Core Instruments | HAPPYJAWS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
TAP-111554 | 53 | TAP-111760 |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 |  | 0 | 1 hr | 1 hr | 7 | 0% | 24 | 48 | Story Points
| 54 |  |  | 01.03.03.01.00.00.00.00 | TAP-111554 | TAP-111782 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 24 | 48
TAP-111554_HAPPYJAWS | 55 |  |  | 01.03.03.02.00.00.00.00 | TAP-111554 | TAP-116506 | [TAP-111554_HAPPYJAWS] ¦ [IRR][Cutting] Support Tissue Cutting investigation with Systems | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 5 |  | 0 | 1 hr | 1 hr | 5 | 0% | 0 | 0
| 56 |  |  | 01.03.03.03.00.00.00.00 | TAP-111554 | TAP-116507 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
TAP-111555 | 57 | TAP-111760 |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
| 58 |  |  | 01.03.04.01.00.00.00.00 | TAP-111555 | TAP-111783 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 12 | 18
TAP-112012 | 59 | TAP-111760 |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
| 60 |  |  | 01.03.05.01.00.00.00.00 | TAP-112012 | TAP-112015 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 12 | 18
TAP-111569 | 61 | TAP-111760 |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 12 | Feature Estimation
| 62 |  |  | 01.03.07.01.00.00.00.00 | TAP-111569 | TAP-111797 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 12
TAP-111565 | 63 | TAP-111760 |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 20 | Feature Estimation
| 64 |  |  | 01.03.08.01.00.00.00.00 | TAP-111565 | TAP-111793 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 5 | 20
TAP-111556 | 65 | TAP-111559, TAP-111760 | TAP-94966 | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
| 66 |  |  | 01.03.09.01.00.00.00.00 | TAP-111556 | TAP-111784 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111559 | 67 | TAP-111760 | TAP-111556 | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
| 68 |  |  | 01.03.10.01.00.00.00.00 | TAP-111559 | TAP-111785 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-112077 | 69 | TAP-111760 | TAP-111562 | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 61 |  | 13 | 1 hr | 1 hr | 48 | 0% | 20 | 30 | Story Points
| 70 |  |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-112077_SIRIUS | 71 |  |  | 01.04.01.02.00.00.00.00 | TAP-112077 | TAP-115017 | [TAP-112077_SIRIUS] ¦ [IRR][Articulation] Finalize KPI/Simulation Script | User Story | Done | Core Instruments | SIRIUS |  |  | 7 |  | 14 |  | 1 hr | -7 | 100%
| 72 |  |  | 01.04.01.03.00.00.00.00 | TAP-112077 | TAP-116519 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 12 |  | 24 | 1 hr | 1 hr | -12 | 100% | 0 | 0
TAP-112077_HAPPYJAWS | 73 |  |  | 01.04.01.04.00.00.00.00 | TAP-112077 | TAP-116520 | [TAP-112077_HAPPYJAWS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in NoHa | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0
| 74 |  |  | 01.04.01.05.00.00.00.00 | TAP-112077 | TAP-116521 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 75 |  |  | 01.04.01.06.00.00.00.00 | TAP-112077 | TAP-116522 |  | User Story | Groomed | Core Instruments | SIRIUS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 76 |  |  | 01.04.01.07.00.00.00.00 | TAP-112077 | TAP-116523 |  | User Story | Groomed | Core Instruments | SIRIUS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 77 |  |  | 01.04.01.08.00.00.00.00 | TAP-112077 | TAP-116524 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 16 |  | 0 | 1 hr | 1 hr | 16 | 0% | 0 | 0
| 78 |  |  | 01.04.01.09.00.00.00.00 | TAP-112077 | TAP-116525 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
| 79 |  |  | 01.04.01.10.00.00.00.00 | TAP-112077 | TAP-116526 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 80 |  |  | 01.04.01.11.00.00.00.00 | TAP-112077 | TAP-116527 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 8 |  | 0 | 1 hr | 1 hr | 8 | 0% | 0 | 0
| 81 |  |  | 01.04.01.12.00.00.00.00 | TAP-112077 | TAP-116528 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 82 |  |  | 01.04.01.13.00.00.00.00 | TAP-112077 | TAP-116529 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
| 83 |  |  | 01.04.01.14.00.00.00.00 | TAP-112077 | TAP-116530 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
| 84 |  |  | 01.04.01.15.00.00.00.00 | TAP-112077 | TAP-116586 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 8 |  | 0 | 1 hr | 1 hr | 8 | 0% | 0 | 0
| 85 |  |  | 01.04.01.16.00.00.00.00 | TAP-112077 | TAP-118635 |  | User Story | In progress | Core Instruments | SIRIUS |  |  | 6 |  | 0 |  | 1 hr | 6 | 0%
| 86 |  |  | 01.04.01.17.00.00.00.00 | TAP-112077 | TAP-122341 |  | User Story | In progress | Core Instruments | SIRIUS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
TAP-120096 | 87 | TAP-111760 |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-103448 | 88 | TAP-111760 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 |  | 5 | 1 hr | 1 hr | 9 | 0% | 0 | 0 | Story Points
TAP-103448_I2E | 89 |  |  | 01.05.01.01.00.00.00.00 | TAP-103448 | TAP-99022 | [TAP-103448_I2E] ¦ [v3.1][IRR][IDU CMD][I2E] Add Shears functionality to M-IRR's tool within Discrete Control Command | User Story | Done | Advanced Instruments - I2E | I2E |  |  | 5 |  | 10 |  | 1 hr | -5 | 100%
| 90 |  |  | 01.05.01.02.00.00.00.00 | TAP-103448 | TAP-114885 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 91 |  |  | 01.05.01.03.00.00.00.00 | TAP-103448 | TAP-114886 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
| 92 |  |  | 01.05.01.04.00.00.00.00 | TAP-103448 | TAP-114887 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
| 93 |  |  | 01.05.01.05.00.00.00.00 | TAP-103448 | TAP-114892 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
TAP-116286 | 94 | TAP-111760 |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 |  | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0 | Story Points
TAP-116286_SIRIUS | 95 |  |  | 01.05.03.02.00.00.00.00 | TAP-116286 | TAP-116514 | [TAP-116286_SIRIUS] ¦ [IRR][Analysis] Obtain brand new needle drivers | User Story | Open | Core Instruments | SIRIUS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
TAP-116286_HAPPYJAWS | 96 |  |  | 01.05.03.03.00.00.00.00 | TAP-116286 | TAP-116515 | [TAP-116286_HAPPYJAWS] ¦ [IRR][Analysis] Collect KPI data on a set of brand new instruments | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0
| 97 |  |  | 01.05.03.04.00.00.00.00 | TAP-116286 | TAP-116516 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
| 98 |  |  | 01.05.03.05.00.00.00.00 | TAP-116286 | TAP-116517 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 99 |  |  | 01.05.03.06.00.00.00.00 | TAP-116286 | TAP-116518 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 16 |  | 0 | 1 hr | 1 hr | 16 | 0% | 0 | 0
TAP-95983 | 100 | TAP-111760 |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 106 |  | 35 | 1 hr | 1 hr | 71 | 0% | 41 | 73 | Story Points
TAP-95983_HAPPYJAWS | 101 |  |  | 01.05.04.01.00.00.00.00 | TAP-95983 | TAP-88491 | [TAP-95983_HAPPYJAWS] ¦ [IRR][PlantSim][Happy Jaws] Introduce IDU Standalones to Modeling Team | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 1 |  | 2 |  | 1 hr | -1 | 100%
TAP-95983_SIRIUS | 102 |  |  | 01.05.04.02.00.00.00.00 | TAP-95983 | TAP-87610 | [TAP-95983_SIRIUS] ¦ [IRR][PlantSim][Sirius] Setup VM with Docker and git on Server in Mounds View | User Story | In progress | Core Instruments | SIRIUS |  |  | 4 |  | 0 |  | 1 hr | 4 | 0%
| 103 |  |  | 01.05.04.03.00.00.00.00 | TAP-95983 | TAP-111914 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
| 104 |  |  | 01.05.04.05.00.00.00.00 | TAP-95983 | TAP-111921 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 3 | 5
| 105 |  |  | 01.05.04.06.00.00.00.00 | TAP-95983 | TAP-111725 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 30 |  | 60 | 1 hr | 1 hr | -30 | 100% | 0 | 0
TAP-95983_ANIMATORS | 106 |  |  | 01.05.04.07.00.00.00.00 | TAP-95983 | TAP-115103 | [TAP-95983_ANIMATORS] ¦ [IRR][PlantModels] Wristed Instrument Model Credibility and Risk Assessment (Validation) | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
| 107 |  |  | 01.05.04.08.00.00.00.00 | TAP-95983 | TAP-115108 |  | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
| 108 |  |  | 01.05.04.09.00.00.00.00 | TAP-95983 | TAP-111915 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 3 | 8
| 109 |  |  | 01.05.04.10.00.00.00.00 | TAP-95983 | TAP-111790 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 5 | 10
| 110 |  |  | 01.05.04.11.00.00.00.00 | TAP-95983 | TAP-111788 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-95983_FRED | 111 |  |  | 01.05.04.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_FRED] ¦ [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
| 112 |  |  | 01.05.04.13.00.00.00.00 | TAP-95983 | TAP-114540 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
TAP-95983_PUPPETEERS | 113 |  |  | 01.05.04.14.00.00.00.00 | TAP-95983 | TAP-116408 | [TAP-95983_PUPPETEERS] ¦ [IRR][Puppeteers] Support for framework for wristed testing | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 13 |  | 0 | 1 hr | 1 hr | 13 | 0% | 0 | 0
| 114 |  |  | 01.05.04.15.00.00.00.00 | TAP-95983 | TAP-116440 |  | User Story | Done | Shared Services - Animators | ANIMATORS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
| 115 |  |  | 01.05.04.16.00.00.00.00 | TAP-95983 | TAP-116441 |  | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 116 |  |  | 01.05.04.17.00.00.00.00 | TAP-95983 | TAP-116442 |  | User Story | In progress | Shared Services - Animators | ANIMATORS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 117 |  |  | 01.05.04.18.00.00.00.00 | TAP-95983 | TAP-116456 |  | User Story | Open | Shared Services - Animators | ANIMATORS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 118 |  |  | 01.05.04.19.00.00.00.00 | TAP-95983 | TAP-116457 |  | User Story | Done | Shared Services - Animators | ANIMATORS |  |  | 20 |  | 40 | 1 hr | 1 hr | -20 | 100% | 0 | 0
| 119 |  |  | 01.05.04.20.00.00.00.00 | TAP-95983 | TAP-116491 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0
| 120 |  |  | 01.05.04.21.00.00.00.00 | TAP-95983 | TAP-116492 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 8 |  | 0 | 1 hr | 1 hr | 8 | 0% | 0 | 0
| 121 |  |  | 01.05.04.22.00.00.00.00 | TAP-95983 | TAP-116493 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 14 |  | 0 | 1 hr | 1 hr | 14 | 0% | 0 | 0
| 122 |  |  | 01.05.04.23.00.00.00.00 | TAP-95983 | TAP-116494 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 12 |  | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0
| 123 |  |  | 01.05.04.24.00.00.00.00 | TAP-95983 | TAP-116495 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 124 |  |  | 01.05.04.25.00.00.00.00 | TAP-95983 | TAP-116496 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 14 |  | 0 | 1 hr | 1 hr | 14 | 0% | 0 | 0
| 125 |  |  | 01.05.04.26.00.00.00.00 | TAP-95983 | TAP-116497 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0
| 126 |  |  | 01.05.04.27.00.00.00.00 | TAP-95983 | TAP-116498 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
| 127 |  |  | 01.05.04.28.00.00.00.00 | TAP-95983 | TAP-116499 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
| 128 |  |  | 01.05.04.29.00.00.00.00 | TAP-95983 | TAP-116500 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
| 129 |  |  | 01.05.04.30.00.00.00.00 | TAP-95983 | TAP-118633 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
TAP-111719 | 130 | TAP-111562, TAP-111760 | TAP-124116 | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 |  | 2 | 1 hr | 1 hr | 3 | 0% | 15 | 22 | Story Points
| 131 |  |  | 01.05.05.01.00.00.00.00 | TAP-111719 | TAP-111916 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111719_FRED | 132 |  |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112039 | [TAP-111719_FRED] ¦ [IRR][Fred] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 1 | 2
TAP-111719_I2E | 133 |  |  | 01.05.05.03.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_I2E] ¦ [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 14 | 20
| 134 |  |  | 01.05.05.04.00.00.00.00 | TAP-111719 | TAP-114445 |  | User Story | Done | Advanced Instruments - I2E | I2E |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 135 |  |  | 01.05.05.05.00.00.00.00 | TAP-111719 | TAP-114446 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
TAP-111721 | 136 | TAP-111760 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 |  | 20.5 | 1 hr | 1 hr | 4 | 0% | 27 | 30 | Story Points
| 137 |  |  | 01.05.06.01.00.00.00.00 | TAP-111721 | TAP-111917 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 27 | 30
TAP-111721_SIRIUS | 138 |  |  | 01.05.06.03.00.00.00.00 | TAP-111721 | TAP-116464 | [TAP-111721_SIRIUS] ¦ [IRR][ORSI] Decide on parameters to derate with clinical | User Story | Done | Core Instruments | SIRIUS |  |  | 0.5 |  | 1 | 1 hr | 1 hr | -0.5 | 100% | 0 | 0
| 139 |  |  | 01.05.06.04.00.00.00.00 | TAP-111721 | TAP-116465 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
| 140 |  |  | 01.05.06.06.00.00.00.00 | TAP-111721 | TAP-116467 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 8 |  | 16 | 1 hr | 1 hr | -8 | 100% | 0 | 0
| 141 |  |  | 01.05.06.07.00.00.00.00 | TAP-111721 | TAP-121702 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 12 |  | 24 | 1 hr | 1 hr | -12 | 100% | 0 | 0
TAP-111721_HAPPYJAWS | 142 |  |  | 01.05.06.08.00.00.00.00 | TAP-111721 | TAP-122340 | [TAP-111721_HAPPYJAWS] ¦ [IRR] Update Lab SW with Protection Against Slow Close | User Story | Done | Core Instruments | HAPPYJAWS |  |  | 1 |  | 2 | 1 hr | 1 hr | -1 | 100% | 0 | 0
| 143 |  |  | 01.05.06.09.00.00.00.00 | TAP-111721 | TAP-122855 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 144 |  |  | 01.05.06.10.00.00.00.00 | TAP-111721 | TAP-122954 |  | User Story | In progress | Core Instruments | SIRIUS |  |  | 8 |  | 0 | 1 hr | 1 hr | 8 | 0% | 0 | 0
TAP-111721_PUPPETEERS | 145 |  |  | 01.05.06.11.00.00.00.00 | TAP-111721 | TAP-123066 | [TAP-111721_PUPPETEERS] ¦ [IRR][Puppeteers] Merge latest JBO updates to IRR staging branch for ORSI lab | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
TAP-111722 | 146 | TAP-111760 |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
| 147 |  |  | 01.05.07.01.00.00.00.00 | TAP-111722 | TAP-111918 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 27 | 30
TAP-111723 | 148 | TAP-111760 |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 27 | 30 | Feature Estimation
| 149 |  |  | 01.05.08.01.00.00.00.00 | TAP-111723 | TAP-111919 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 27 | 30
TAP-111723_SIRIUS | 150 |  |  | 01.05.08.02.00.00.00.00 | TAP-111723 | TAP-115880 | [TAP-111723_SIRIUS] ¦ [IRR][ORSI] Update Lab SW for Hard Stop recovery | User Story | Open | Core Instruments | SIRIUS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0
TAP-111724 | 151 | TAP-111760 |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
| 152 |  |  | 01.05.09.01.00.00.00.00 | TAP-111724 | TAP-111920 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 27 | 30
TAP-112119 | 153 | TAP-111760 |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
| 154 |  |  | 01.05.10.01.00.00.00.00 | TAP-112119 | TAP-112120 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-94125 | 155 | TAP-111753, TAP-111760 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | Accepted |  |  |  |  | 77 |  | 0 | 1 hr | 1 hr | 77 | 0% | 50 | 70 | Story Points
TAP-94125_SIRIUS | 156 |  |  | 01.06.01.01.00.00.00.00 | TAP-94125 | TAP-97747 | [TAP-94125_SIRIUS] ¦ [WS5][Homing][Sirius] Evaluate Homing Controller Architecture and Identify Improvements | User Story | Open | Core Instruments | SIRIUS |  |  | 5 |  | 0 |  | 1 hr | 5 | 0%
| 157 |  |  | 01.06.01.02.00.00.00.00 | TAP-94125 | TAP-97748 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 8 |  | 0 |  | 1 hr | 8 | 0%
| 158 |  |  | 01.06.01.03.00.00.00.00 | TAP-94125 | TAP-97749 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 10 |  | 0 |  | 1 hr | 10 | 0%
| 159 |  |  | 01.06.01.04.00.00.00.00 | TAP-94125 | TAP-97750 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 12 |  | 0 |  | 1 hr | 12 | 0%
| 160 |  |  | 01.06.01.05.00.00.00.00 | TAP-94125 | TAP-97751 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 10 |  | 0 |  | 1 hr | 10 | 0%
| 161 |  |  | 01.06.01.06.00.00.00.00 | TAP-94125 | TAP-97752 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 6 |  | 0 |  | 1 hr | 6 | 0%
| 162 |  |  | 01.06.01.07.00.00.00.00 | TAP-94125 | TAP-97753 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 12 |  | 0 |  | 1 hr | 12 | 0%
| 163 |  |  | 01.06.01.08.00.00.00.00 | TAP-94125 | TAP-97754 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 20 |  | 0 |  | 1 hr | 20 | 0%
| 164 |  |  | 01.06.01.09.00.00.00.00 | TAP-94125 | TAP-97755 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 20 |  | 0 |  | 1 hr | 20 | 0%
| 165 |  |  | 01.06.01.10.00.00.00.00 | TAP-94125 | TAP-97756 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 20 |  | 0 |  | 1 hr | 20 | 0%
| 166 |  |  | 01.06.01.11.00.00.00.00 | TAP-94125 | TAP-97757 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 20 |  | 0 |  | 1 hr | 20 | 0%
| 167 |  |  | 01.06.01.12.00.00.00.00 | TAP-94125 | TAP-97758 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 6 |  | 0 |  | 1 hr | 6 | 0%
| 168 |  |  | 01.06.01.14.00.00.00.00 | TAP-94125 | TAP-111778 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 70
TAP-95800 | 169 | TAP-111754, TAP-111760 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | Accepted |  |  |  |  | 31 |  | 2 | 1 hr | 1 hr | 29 | 0% | 15 | 35 | Story Points
TAP-95800_SIRIUS | 170 |  |  | 01.06.02.01.00.00.00.00 | TAP-95800 | TAP-91185 | [TAP-95800_SIRIUS] ¦ [IRG][SW][WS5] Investigate alternative IDU motor position control approaches | User Story | Open | Core Instruments | SIRIUS |  |  | 4 |  | 0 |  | 1 hr | 4 | 0%
| 171 |  |  | 01.06.02.02.00.00.00.00 | TAP-95800 | TAP-111779 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 35
| 172 |  |  | 01.06.02.03.00.00.00.00 | TAP-95800 | TAP-116475 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 173 |  |  | 01.06.02.04.00.00.00.00 | TAP-95800 | TAP-116476 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 174 |  |  | 01.06.02.05.00.00.00.00 | TAP-95800 | TAP-116477 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 18 |  | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0
| 175 |  |  | 01.06.02.06.00.00.00.00 | TAP-95800 | TAP-116478 |  | User Story | Done | Core Instruments | SIRIUS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 176 |  |  | 01.06.02.07.00.00.00.00 | TAP-95800 | TAP-116479 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 177 |  |  | 01.06.02.08.00.00.00.00 | TAP-95800 | TAP-116480 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 8 |  | 0 | 1 hr | 1 hr | 8 | 0% | 0 | 0
| 178 |  |  | 01.06.02.09.00.00.00.00 | TAP-95800 | TAP-116482 |  | User Story | Open | Core Instruments | SIRIUS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
| 179 |  |  | 01.06.02.10.00.00.00.00 | TAP-95800 | TAP-124660 |  | User Story | In progress | Core Instruments | SIRIUS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
TAP-111740 | 180 | TAP-111756, TAP-111760 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | PROPOSED |  |  |  |  | 28 |  | 0 | 1 hr | 1 hr | 28 | 0% | 60 | 80 | Story Points
| 181 |  |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 60 | 80
TAP-111740_HAPPYJAWS | 182 |  |  | 01.06.03.02.00.00.00.00 | TAP-111740 | TAP-115106 | [TAP-111740_HAPPYJAWS] ¦ [IRR][Phase 1b][Happy Jaws] Refactor teleoperation SWI to consolidate IK and improve architecture | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0
| 183 |  |  | 01.06.03.03.00.00.00.00 | TAP-111740 | TAP-116483 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 184 |  |  | 01.06.03.04.00.00.00.00 | TAP-111740 | TAP-116484 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 185 |  |  | 01.06.03.05.00.00.00.00 | TAP-111740 | TAP-116485 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 18 |  | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0
TAP-111740_SIRIUS | 186 |  |  | 01.06.03.06.00.00.00.00 | TAP-111740 | TAP-116486 | [TAP-111740_SIRIUS] ¦ [IRR][Phase 1b][Teleoperation] Update and fix Static Analysis issues | User Story | Open | Core Instruments | SIRIUS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
| 187 |  |  | 01.06.03.07.00.00.00.00 | TAP-111740 | TAP-116487 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 188 |  |  | 01.06.03.08.00.00.00.00 | TAP-111740 | TAP-116488 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 8 |  | 0 | 1 hr | 1 hr | 8 | 0% | 0 | 0
| 189 |  |  | 01.06.03.09.00.00.00.00 | TAP-111740 | TAP-116490 |  | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
TAP-111749 | 190 | TAP-111757, TAP-111760 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
| 191 |  |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 16 | 30
TAP-111749_SIRIUS | 192 |  |  | 01.06.04.02.00.00.00.00 | TAP-111749 | TAP-112328 | [TAP-111749_SIRIUS] ¦ [IRR] Evaluate risk rank of alternate instrument hardware failure modes | User Story | Open | Core Instruments | SIRIUS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
TAP-111750 | 193 | TAP-111758, TAP-111760 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 35 | Feature Estimation
| 194 |  |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 35
TAP-111751 | 195 | TAP-111759, TAP-111760 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 45 | Feature Estimation
| 196 |  |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 28 | 45
TAP-117678 | 197 | TAP-111760 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111834 | 198 | TAP-111760 | TAP-113995 | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-111834_JACOBIANS | 199 |  |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_JACOBIANS] ¦ Support Kinematic Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-111747 | 200 | TAP-113104 |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
| 201 |  |  | 02.01.01.01.00.00.00.00 | TAP-111747 | TAP-111913 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 100
TAP-111772 | 202 | TAP-113104 |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
| 203 |  |  | 02.02.01.01.00.00.00.00 | TAP-111772 | TAP-111965 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 20
TAP-111773 | 204 | TAP-113104 |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 65 | Feature Estimation
| 205 |  |  | 02.02.02.01.00.00.00.00 | TAP-111773 | TAP-111966 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 65
TAP-111838 | 206 | TAP-111842, TAP-113104 |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
| 207 |  |  | 02.03.01.01.00.00.00.00 | TAP-111838 | TAP-111967 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-104213 | 208 | TAP-111842, TAP-113104 |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 45 | Feature Estimation
| 209 |  |  | 02.03.02.01.00.00.00.00 | TAP-104213 | TAP-111968 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 45
TAP-111842 | 210 | TAP-113104 | TAP-104213, TAP-111838 | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
| 211 |  |  | 02.03.03.01.00.00.00.00 | TAP-111842 | TAP-111969 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-111774 | 212 | TAP-111775, TAP-112080, TAP-113104 |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 9 |  | 9 | 1 hr | 1 hr | 0 | 0% | 20 | 34 | Story Points
| 213 |  |  | 02.04.01.01.00.00.00.00 | TAP-111774 | TAP-111970 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 13
TAP-111774_JACOBIANS | 214 |  |  | 02.04.01.02.00.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 5 | 8
TAP-111774_CASTLEBLACK | 215 |  |  | 02.04.01.03.00.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774_CASTLEBLACK] ¦ [IRR][Castle Black] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 7 | 13
TAP-111774_PUPPETEERS | 216 |  |  | 02.04.01.04.00.00.00.00 | TAP-111774 | TAP-116202 | [TAP-111774_PUPPETEERS] ¦ [IRR][Puppeteers] Create cFMEA draft in Excel Sheet for MSO Joint Tracking Check | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 3 |  | 6 | 1 hr | 1 hr | -3 | 100% | 0 | 0
| 217 |  |  | 02.04.01.07.00.00.00.00 | TAP-111774 | TAP-116645 |  | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
| 218 |  |  | 02.04.01.08.00.00.00.00 | TAP-111774 | TAP-116194 |  | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
TAP-112080 | 219 | TAP-111775, TAP-113104 | TAP-111774 | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 15 |  | 0 | 1 hr | 1 hr | 15 | 0% | 37 | 63 | Story Points
| 220 |  |  | 02.04.02.01.00.00.00.00 | TAP-112080 | TAP-112081 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 13 | 22
TAP-112080_JACOBIANS | 221 |  |  | 02.04.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-112080_ORGANELLES | 222 |  |  | 02.04.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_ORGANELLES] ¦ [IRR][Organelles] UFSW - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 4 | 6
TAP-112080_INBETWEENERS | 223 |  |  | 02.04.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_INBETWEENERS] ¦ [IRR][Inbetweeners] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-112080_PUPPETEERS | 224 |  |  | 02.04.02.05.00.00.00.00 | TAP-112080 | TAP-116414 | [TAP-112080_PUPPETEERS] ¦ [IRR][Puppeteers] Kinematics prototype for MSO joint check replacement | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 13 |  | 0 | 1 hr | 1 hr | 13 | 0% | 0 | 0
| 225 |  |  | 02.04.02.06.00.00.00.00 | TAP-112080 | TAP-116211 |  | User Story | Groomed | Core Instruments - Puppeteers | PUPPETEERS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0
TAP-112080_CASTLEBLACK | 226 |  |  | 02.04.02.07.00.00.00.00 | TAP-112080 | TAP-116177 | [TAP-112080_CASTLEBLACK] ¦ [Spike] Investigate Instrument Observer Mitigations | User Story | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 1 |  | 0 | 1 hr | 1 hr | 1 | 0% | 0 | 0
TAP-111775 | 227 | TAP-113104 | TAP-111774, TAP-112080 | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 |  | 0 | 1 hr | 1 hr | 1 | 0% | 45 | 75 | Feature Estimation
| 228 |  |  | 02.04.03.01.00.00.00.00 | TAP-111775 | TAP-111971 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 16 | 24
TAP-111775_JACOBIANS | 229 |  |  | 02.04.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 25
TAP-111775_ORGANELLES | 230 |  |  | 02.04.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_ORGANELLES] ¦ [IRR][Organelles] UFSW - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 4 | 6
TAP-111775_INBETWEENERS | 231 |  |  | 02.04.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_INBETWEENERS] ¦ [IRR][Inbetweeners] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-111775_PUPPETEERS | 232 |  |  | 02.04.03.05.00.00.00.00 | TAP-111775 | TAP-121472 | [TAP-111775_PUPPETEERS] ¦ [IRR][Puppeteers] Update Polarion | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 |  | 0 | 1 hr | 1 hr | 1 | 0% | 0 | 0
TAP-123862 | 233 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 27 |  | 0 | 1 hr | 1 hr | 27 | 0% | 0 | 0 | Feature Estimation
TAP-123862_I2E | 234 |  |  | 02.05.01.01.00.00.00.00 | TAP-123862 | TAP-124413 | [TAP-123862_I2E] ¦ [I2E][IRR][Enabler] Determine memory to shmio mapping | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Feature Estimation
| 235 |  |  | 02.05.01.02.00.00.00.00 | TAP-123862 | TAP-124414 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 236 |  |  | 02.05.01.03.00.00.00.00 | TAP-123862 | TAP-124415 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 237 |  |  | 02.05.01.04.00.00.00.00 | TAP-123862 | TAP-124418 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0 | Feature Estimation
| 238 |  |  | 02.05.01.05.00.00.00.00 | TAP-123862 | TAP-124424 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 239 |  |  | 02.05.01.06.00.00.00.00 | TAP-123862 | TAP-124422 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0 | Feature Estimation
| 240 |  |  | 02.05.01.07.00.00.00.00 | TAP-123862 | TAP-124416 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Feature Estimation
| 241 |  |  | 02.05.01.08.00.00.00.00 | TAP-123862 | TAP-124763 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0 | Feature Estimation
| 242 |  |  | 02.05.01.09.00.00.00.00 | TAP-123862 | TAP-124833 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 243 |  |  | 02.05.01.10.00.00.00.00 | TAP-123862 | TAP-125080 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 244 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 26 |  | 0 | 1 hr | 1 hr | 26 | 0% | 0 | 0 | Feature Estimation
TAP-123863_I2E | 245 |  |  | 02.05.02.01.00.00.00.00 | TAP-123863 | TAP-124576 | [TAP-123863_I2E] ¦ [IRR][I2E][SRA HAL] Write behavioral UT that checks controller ID based on input Instrument ID + DSV | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 246 |  |  | 02.05.02.02.00.00.00.00 | TAP-123863 | TAP-124578 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 10 |  | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0 | Feature Estimation
| 247 |  |  | 02.05.02.03.00.00.00.00 | TAP-123863 | TAP-124577 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 248 |  |  | 02.05.02.04.00.00.00.00 | TAP-123863 | TAP-124579 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 249 |  |  | 02.05.02.05.00.00.00.00 | TAP-123863 | TAP-124580 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 250 |  |  | 02.05.02.06.00.00.00.00 | TAP-123863 | TAP-124581 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 251 |  |  | 02.05.02.07.00.00.00.00 | TAP-123863 | TAP-124582 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 252 |  |  | 02.05.02.08.00.00.00.00 | TAP-123863 | TAP-124584 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Feature Estimation
| 253 |  |  | 02.05.02.09.00.00.00.00 | TAP-123863 | TAP-124585 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 254 |  |  | 02.05.02.10.00.00.00.00 | TAP-123863 | TAP-124587 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 255 |  |  | 02.05.02.11.00.00.00.00 | TAP-123863 | TAP-124588 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 256 |  |  | 02.05.02.12.00.00.00.00 | TAP-123863 | TAP-124589 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Feature Estimation
| 257 |  |  | 02.05.02.13.00.00.00.00 | TAP-123863 | TAP-124590 |  | User Story | Open | Advanced Instruments - I2E | I2E |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 258 | TAP-113104 |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 170 | 325 | Feature Estimation
| 259 |  |  | 02.05.03.01.00.00.00.00 | TAP-111642 | TAP-111941 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 150 | 300
TAP-111642_I2E | 260 |  |  | 02.05.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111642_I2E] ¦ [IRR][I2E] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 17 | 20
TAP-111642_ORGANELLES | 261 |  |  | 02.05.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111642_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 3 | 5
TAP-111642_CASTLEBLACK | 262 |  |  | 02.05.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111642_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
TAP-111656 | 263 | TAP-113104 |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_CLASSY2 | 264 |  |  | 02.05.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_CLASSY2] ¦ [IRR][CLASSY 2] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111656_BOOSTERS | 265 |  |  | 02.05.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_BOOSTERS] ¦ [IRR][Boosters] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111656_INBETWEENERS | 266 |  |  | 02.05.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_INBETWEENERS] ¦ [IRR][Inbetweeners] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-111656_CASTLEBLACK | 267 |  |  | 02.05.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
TAP-111656_ORGANELLES | 268 |  |  | 02.05.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 3 | 5
TAP-111656_I2E | 269 |  |  | 02.05.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_I2E] ¦ [IRR][I2E] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 13
| 270 |  |  | 02.05.04.07.00.00.00.00 | TAP-111656 | TAP-111940 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 100 | 200
TAP-111925 | 271 | TAP-113104 |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
| 272 |  |  | 02.06.01.01.00.00.00.00 | TAP-111925 | TAP-111945 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 30
TAP-112113 | 273 | TAP-113104 |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 274 |  |  | 02.06.02.01.00.00.00.00 | TAP-112113 | TAP-112123 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111865 | 275 | TAP-113104 |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113111 | 276 | TAP-111689, TAP-111695 |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Accepted |  |  |  |  | 12 |  | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Feature Estimation
TAP-113111_BOOSTERS | 277 |  |  | 02.07.02.01.01.00.00.00 | TAP-113111 | TAP-124574 | [TAP-113111_BOOSTERS] ¦ [IRR][Boosters] Run data recorder auto gen script with new interfaces | User Story | Open | Foundation - Boosters | BOOSTERS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Feature Estimation
| 278 |  |  | 02.07.02.01.02.00.00.00 | TAP-113111 | TAP-124977 |  | User Story | Open | Foundation - Boosters | BOOSTERS |  |  | 12 |  | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Feature Estimation
| 279 |  |  | 02.07.02.01.03.00.00.00 | TAP-113111 | TAP-124976 |  | User Story | Open | Foundation - Boosters | BOOSTERS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 280 | TAP-111687, TAP-111689, TAP-111695 |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Feature Estimation
TAP-113123_PIXELPOETS | 281 |  |  | 02.07.02.02.01.00.00.00 | TAP-113123 | TAP-124452 | [TAP-113123_PIXELPOETS] ¦ [PixelPoets][MIRR] Placeholder for MIRR GUI Design | User Story | Open | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 282 |  |  | 02.07.02.02.02.00.00.00 | TAP-113123 | TAP-124572 |  | User Story | Open | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 4 |  | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Feature Estimation
| 283 |  |  | 02.07.02.02.03.00.00.00 | TAP-113123 | TAP-125033 |  | User Story | Open | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 2 |  | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 284 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 |  | 18 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-114692_CASTLEBLACK | 285 |  |  | 02.07.02.03.01.00.00.00 | TAP-114692 | TAP-116170 | [TAP-114692_CASTLEBLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | Done | Shared Services - Castle Black | CASTLEBLACK |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
TAP-114692_PUPPETEERS | 286 |  |  | 02.07.02.03.02.00.00.00 | TAP-114692 | TAP-116199 | [TAP-114692_PUPPETEERS] ¦ [IRR][Puppeteers] Sree session | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 1 |  | 2 | 1 hr | 1 hr | -1 | 100% | 0 | 0
| 287 |  |  | 02.07.02.03.03.00.00.00 | TAP-114692 | TAP-116198 |  | User Story | In progress | Core Instruments - Puppeteers | PUPPETEERS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
| 288 |  |  | 02.07.02.03.04.00.00.00 | TAP-114692 | TAP-116195 |  | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 10 |  | 20 | 1 hr | 1 hr | -10 | 100% | 0 | 0
| 289 |  |  | 02.07.02.03.05.00.00.00 | TAP-114692 | TAP-116193 |  | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS |  |  | 16 |  | 32 | 1 hr | 1 hr | -16 | 100% | 0 | 0
| 290 |  |  | 02.07.02.03.06.00.00.00 | TAP-114692 | TAP-123411 |  | User Story | In progress | Core Instruments - Puppeteers | PUPPETEERS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0
TAP-114692_SIRIUS | 291 |  |  | 02.07.02.03.07.00.00.00 | TAP-114692 | TAP-123143 | [TAP-114692_SIRIUS] ¦ [IRR][Sirius] Manually update use life notcodes for staging/IRR-v3-control-development | User Story | Done | Core Instruments | SIRIUS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0 | Feature Estimation
TAP-114689 | 292 | TAP-111687 |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  |  |  | 15 |  | 30 | 1 hr | 1 hr | -15 | 100% | 0 | 0 | Story Points
TAP-114689_PIXELPOETS | 293 |  |  | 02.07.02.04.01.00.00.00 | TAP-114689 | TAP-115102 | [TAP-114689_PIXELPOETS] ¦ [MIRR][Pixel Poets] Finalize Design for Use Life Indicator | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 1 |  | 2 | 1 hr | 1 hr | -1 | 100% | 0 | 0
| 294 |  |  | 02.07.02.04.02.00.00.00 | TAP-114689 | TAP-115105 |  | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 295 |  |  | 02.07.02.04.03.00.00.00 | TAP-114689 | TAP-116036 |  | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 20 |  | 40 | 1 hr | 1 hr | -20 | 100% | 0 | 0
TAP-114689_CASTLEBLACK | 296 |  |  | 02.07.02.04.04.00.00.00 | TAP-114689 | TAP-116170 | [TAP-114689_CASTLEBLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | Done | Shared Services - Castle Black | CASTLEBLACK |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
TAP-90375 | 297 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 |  | 0 | 1 hr | 1 hr | 9 | 0% |  |  | Story Points
TAP-90375_STELLARS | 298 |  |  | 02.07.03.01.01.00.00.00 | TAP-90375 | TAP-96606 | [TAP-90375_STELLARS] ¦ [Stellars] [TAP-90375] [Enabler] Identify Jama linking to be updated | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 1 |  | 0 |  | 1 hr | 1 | 0%
| 299 |  |  | 02.07.03.01.04.00.00.00 | TAP-90375 | TAP-97208 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 10 |  | 0 |  | 1 hr | 10 | 0%
| 300 |  |  | 02.07.03.01.05.00.00.00 | TAP-90375 | TAP-97213 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 6 |  | 0 |  | 1 hr | 6 | 0%
TAP-111861 | 301 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 34 | 46 | Story Points
TAP-111861_I2E | 302 |  |  | 02.07.03.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_I2E] ¦ [IRR][I2E] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 12 | 18
TAP-111861_ORGANELLES | 303 |  |  | 02.07.03.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_ORGANELLES] ¦ [IRR][Organelles] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 20
TAP-111861_DRUSHTI | 304 |  |  | 02.07.03.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_DRUSHTI] ¦ [IRR][Drushti] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 7 | 8
TAP-111861_PUPPETEERS | 305 |  |  | 02.07.03.02.04.00.00.00 | TAP-111861 | TAP-115871 | [TAP-111861_PUPPETEERS] ¦ [IRR] Increment Use count when instrument is expired | User Story | Groomed | Core Instruments - Puppeteers | PUPPETEERS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0
TAP-111687 | 306 |  | TAP-113123, TAP-114689 | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111687_PIXELPOETS | 307 |  |  | 02.07.03.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_PIXELPOETS] ¦ [IRR] [Pixel Poets] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 34
TAP-111687_ORGANELLES | 308 |  |  | 02.07.03.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_ORGANELLES] ¦ [IRR] [Organelles] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 12
TAP-111687_FRED | 309 |  |  | 02.07.03.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_FRED] ¦ [IRR] [Fred] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
TAP-111689 | 310 |  | TAP-113111, TAP-113123 | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 32 | 48 | Feature Estimation
TAP-111689_PIXELPOETS | 311 |  |  | 02.07.03.04.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111689_PIXELPOETS] ¦ [IRR] [Pixel Poets] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 17 | 28
TAP-111689_ORGANELLES | 312 |  |  | 02.07.03.04.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-111689_ORGANELLES] ¦ [IRR] [Organelles] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 12
TAP-111689_DRUSHTI | 313 |  |  | 02.07.03.04.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-111689_DRUSHTI] ¦ [IRR] [Drushti] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 7 | 8
TAP-111695 | 314 |  | TAP-113111, TAP-113123 | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 24 | 46 | Feature Estimation
TAP-111695_PIXELPOETS | 315 |  |  | 02.07.03.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_PIXELPOETS] ¦ [IRR][Pixel Poets] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 11 | 26
TAP-111695_ORGANELLES | 316 |  |  | 02.07.03.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_ORGANELLES] ¦ [IRR][Organelles] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 6 | 12
TAP-111695_DRUSHTI | 317 |  |  | 02.07.03.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_DRUSHTI] ¦ [IRR][Drushti] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 7 | 8
TAP-111753 | 318 | TAP-111761, TAP-111765 | TAP-94125 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 30 | 50 | Feature Estimation
| 319 |  |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 30 | 50
TAP-111754 | 320 | TAP-110382, TAP-111765 | TAP-95800 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 10 | 15 | Feature Estimation
| 321 |  |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111754_SIRIUS | 322 |  |  | 03.01.02.02.00.00.00.00 | TAP-111754 | TAP-116481 | [TAP-111754_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Create RCMs found in cFMEA | User Story | Open | Core Instruments | SIRIUS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0
TAP-111756 | 323 | TAP-111762, TAP-111765 | TAP-111740 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 35 | 45 | Feature Estimation
| 324 |  |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 35 | 45
TAP-111756_HAPPYJAWS | 325 |  |  | 03.01.03.02.00.00.00.00 | TAP-111756 | TAP-116489 | [TAP-111756_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Create RCMs found in cFMEA | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0
TAP-111757 | 326 | TAP-111748, TAP-111765 | TAP-111749 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
| 327 |  |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 16 | 30
TAP-111758 | 328 | TAP-111764, TAP-111765 | TAP-111750 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
| 329 |  |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 30
TAP-111759 | 330 | TAP-111766, TAP-111765 | TAP-111751 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
| 331 |  |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-111761 | 332 | TAP-111765 | TAP-111753 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 30 | Feature Estimation
| 333 |  |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 25 | 30
TAP-110382 | 334 | TAP-111765 | TAP-111754 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 8 | Feature Estimation
| 335 |  |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 5 | 8
TAP-111762 | 336 | TAP-111765 | TAP-111756 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 25 | Feature Estimation
| 337 |  |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 25
TAP-111748 | 338 | TAP-111765 | TAP-111757 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 15 | Feature Estimation
| 339 |  |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 15
TAP-111764 | 340 | TAP-111765 | TAP-111758 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
| 341 |  |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111766 | 342 | TAP-111765 | TAP-111759 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
| 343 |  |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 20
TAP-112082 | 344 | TAP-111765 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 125 | Feature Estimation
| 345 |  |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 60
TAP-112082_I2E | 346 |  |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_I2E] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-112082_ORGANELLES | 347 |  |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_ORGANELLES] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-112082_PIXELPOETS | 348 |  |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 15
TAP-112082_JACOBIANS | 349 |  |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 7 | 15
TAP-112093 | 350 | TAP-111765 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 55 | 70 | Feature Estimation
| 351 |  |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 55 | 70
TAP-112094 | 352 | TAP-111765 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 87 | 170 | Feature Estimation
| 353 |  |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 87 | 170
TAP-113100 | 354 | TAP-113101 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 200 | 400 | Feature Estimation
| 355 |  |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 200 | 400
TAP-111900 | 356 | TAP-121104 | TAP-111767 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 79 | 152 | Feature Estimation
| 357 |  |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 30 | 60
TAP-111900_BUGHUNTERS | 358 |  |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_BUGHUNTERS] ¦ [M-IRR][Bug Hunters] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Bug Hunters | BUGHUNTERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 1
TAP-111900_I2E | 359 |  |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-111900_I2E] ¦ [M-IRR][I2E] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111900_JACOBIANS | 360 |  |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_JACOBIANS] ¦ [M-IRR][Jacobians] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 13 | 20
TAP-111900_ORGANELLES | 361 |  |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_ORGANELLES] ¦ [M-IRR][Organelles] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 30
TAP-111900_SCRUMBLEDORES | 362 |  |  | 05.01.07.00.00.00.00.00 | TAP-111900 | TAP-112683 | [TAP-111900_SCRUMBLEDORES] ¦ [M-IRR][Scrumbledores] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 9 | 12
TAP-111900_SUNRISERS | 363 |  |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_SUNRISERS] ¦ [M-IRR][Sunrisers] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 3 | 6
TAP-111900_TEAMBD | 364 |  |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_TEAMBD] ¦ [M-IRR][TeamBD] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 3 | 5
TAP-111900_COSSACKS | 365 |  |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_COSSACKS] ¦ [M-IRR][Cossacks] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 1 | 3
TAP-112042 | 366 | TAP-121104 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 22 | 30 | Feature Estimation
TAP-112042_BUILDERS | 367 |  |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_BUILDERS] ¦ [V3.1][IRR][Builders] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 22 | 30
TAP-111692 | 368 | TAP-121104 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 130 | 195 | Feature Estimation
TAP-111692_ASTRANPSDEVELOPERS | 369 |  |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_ASTRANPSDEVELOPERS] ¦ [IRR][Astra NPS Developers] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 25
TAP-111692_TOOLSRULES | 370 |  |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_TOOLSRULES] ¦ [IRR][Tools Rules] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 25
TAP-111692_INBETWEENERS | 371 |  |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_INBETWEENERS] ¦ [IRR][Inbetweeners] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 65
TAP-111692_TRIPLETEA | 372 |  |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_TRIPLETEA] ¦ [IRR][Triple Tea] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 40 | 80
TAP-112231 | 373 | TAP-121104 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 40 | 50 | Feature Estimation
TAP-112231_ASTRANPSVALIDATORS | 374 |  |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 40 | 50
TAP-112233 | 375 | TAP-121104 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112233_ASTRANPSVALIDATORS | 376 |  |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-112234 | 377 | TAP-121104 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 40 | Feature Estimation
TAP-112234_TOOLSRULES | 378 |  |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 40
TAP-113127 | 379 | TAP-121104 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 380 |  |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 |  | Defect | Investigation |  |  |  |  | 40 |  | 29 | 1 hr | 1 hr | 11 | 0.725% | 0 | 0
TAP-115187 | 381 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 |  | 58 | 1 hr | 1 hr | -29 | 100% | 0 | 0
TAP-115187_STELLARS | 382 |  |  | 06.01.01.01.01.00.00.00 | TAP-115187 | TAP-115835 | [TAP-115187_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 1 | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 5 |  | 10 |  | 1 hr | -5 | 100%
| 383 |  |  | 06.01.01.01.02.00.00.00 | TAP-115187 | TAP-115839 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 8 | 1 hr | 1 hr | -4 | 100% | 0 | 0
| 384 |  |  | 06.01.01.01.03.00.00.00 | TAP-115187 | TAP-115837 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 385 |  |  | 06.01.01.01.04.00.00.00 | TAP-115187 | TAP-115838 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 6 |  | 12 |  | 1 hr | -6 | 100%
| 386 |  |  | 06.01.01.01.05.00.00.00 | TAP-115187 | TAP-115840 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 387 |  |  | 06.01.01.01.06.00.00.00 | TAP-115187 | TAP-116265 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
TAP-115187_SUNRISERS | 388 |  |  | 06.01.01.01.07.00.00.00 | TAP-115187 | TAP-116278 | [TAP-115187_SUNRISERS] ¦ [Sunrisers] [RAS-7203] [Enabler] Implementation changes review - SP2 | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS |  |  | 1 |  | 2 | 1 hr | 1 hr | -1 | 100% | 0 | 0
| 389 |  |  | 06.01.01.01.08.00.00.00 | TAP-115187 | TAP-116308 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 390 |  |  | 06.01.01.01.09.00.00.00 | TAP-115187 | TAP-116316 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 391 |  |  | 06.01.01.01.10.00.00.00 | TAP-115187 | TAP-116323 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 6 |  | 12 |  | 1 hr | -6 | 100%
| 392 |  |  | 06.01.01.01.11.00.00.00 | TAP-115187 | TAP-116535 |  | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS |  |  | 6 |  | 12 | 1 hr | 1 hr | -6 | 100% | 0 | 0
| 393 |  |  | 06.01.01.01.13.00.00.00 | TAP-115187 | TAP-117468 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 |  | 4 | 1 hr | 1 hr | -2 | 100% | 0 | 0
| 394 |  |  | 06.01.01.01.14.00.00.00 | TAP-115187 | TAP-118097 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
TAP-122269 | 395 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 11 |  | 0 | 1 hr | 1 hr | 11 | 0% | 0 | 0 | Feature Estimation
TAP-122269_STELLARS | 396 |  |  | 06.01.01.02.01.00.00.00 | TAP-122269 | TAP-117467 | [TAP-122269_STELLARS] ¦ [Stellars] [RAS-7203] Attend CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 1 |  | 0 |  | 1 hr | 1 | 0%
| 397 |  |  | 06.01.01.02.02.00.00.00 | TAP-122269 | TAP-124627 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 2 |  | 0 |  | 1 hr | 2 | 0%
| 398 |  |  | 06.01.01.02.03.00.00.00 | TAP-122269 | TAP-124628 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 2 |  | 0 |  | 1 hr | 2 | 0%
| 399 |  |  | 06.01.01.02.04.00.00.00 | TAP-122269 | TAP-124630 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 0 |  | 1 hr | 4 | 0%
| 400 |  |  | 06.01.01.02.05.00.00.00 | TAP-122269 | TAP-124632 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Feature Estimation
| 401 |  |  | 06.01.01.02.06.00.00.00 | TAP-122269 | TAP-124634 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 6 |  | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Feature Estimation
| 402 |  |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 |  | Defect | Investigation |  |  |  |  | 108.25 |  | 79.25 |  | 1 hr | 29 | 0%
TAP-64314 | 403 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 |  | 64.5 | 1 hr | 1 hr | -32.25 | 100%
TAP-64314_JACOBIANS | 404 |  |  | 06.01.02.01.01.00.00.00 | TAP-64314 | TAP-60617 | [TAP-64314_JACOBIANS] ¦ [MBTI][Spike] Investigate Potential Causes of Roll Jump Discontinuity (RAS-7532) | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6.25 |  | 12.5 |  | 1 hr | -6.25 | 100%
| 405 |  |  | 06.01.02.01.04.00.00.00 | TAP-64314 | TAP-67852 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 16 |  | 32 |  | 1 hr | -16 | 100%
| 406 |  |  | 06.01.02.01.05.00.00.00 | TAP-64314 | TAP-67859 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 16 |  | 32 |  | 1 hr | -16 | 100%
| 407 |  |  | 06.01.02.01.06.00.00.00 | TAP-64314 | TAP-67866 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6 |  | 12 |  | 1 hr | -6 | 100%
| 408 |  |  | 06.01.02.01.07.00.00.00 | TAP-64314 | TAP-67873 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6 |  | 12 |  | 1 hr | -6 | 100%
| 409 |  |  | 06.01.02.01.08.00.00.00 | TAP-64314 | TAP-67880 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 410 |  |  | 06.01.02.01.09.00.00.00 | TAP-64314 | TAP-67881 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 3 |  | 6 |  | 1 hr | -3 | 100%
| 411 |  |  | 06.01.02.01.10.00.00.00 | TAP-64314 | TAP-67882 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 3 |  | 6 |  | 1 hr | -3 | 100%
TAP-64315 | 412 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 |  | 50 | 1 hr | 1 hr | -25 | 100%
TAP-64315_JACOBIANS | 413 |  |  | 06.01.02.02.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-64315_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 |  | 16 |  | 1 hr | -8 | 100%
| 414 |  |  | 06.01.02.02.02.00.00.00 | TAP-64315 | TAP-73681 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 |  | 16 |  | 1 hr | -8 | 100%
| 415 |  |  | 06.01.02.02.03.00.00.00 | TAP-64315 | TAP-73690 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 416 |  |  | 06.01.02.02.05.00.00.00 | TAP-64315 | TAP-73736 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 417 |  |  | 06.01.02.02.06.00.00.00 | TAP-64315 | TAP-73732 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 418 |  |  | 06.01.02.02.07.00.00.00 | TAP-64315 | TAP-73752 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
TAP-64315_REFLECT | 419 |  |  | 06.01.02.02.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-64315_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 3 |  | 6 |  | 1 hr | -3 | 100%
| 420 |  |  | 06.01.02.02.09.00.00.00 | TAP-64315 | TAP-76437 |  | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 421 |  |  | 06.01.02.02.10.00.00.00 | TAP-64315 | TAP-76441 |  | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 422 |  |  | 06.01.02.02.11.00.00.00 | TAP-64315 | TAP-79223 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 423 |  |  | 06.01.02.03.01.00.00.00 | TAP-76243 | TAP-64360 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 20 |  | 0 |  | 1 hr | 20 | 0%
| 424 |  |  | 06.01.02.03.02.00.00.00 | TAP-76243 | TAP-64119 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 0 |  | 1 hr | 10 | 0%
| 425 |  |  | 06.01.02.03.03.00.00.00 | TAP-76243 | TAP-74719 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 12 |  | 0 |  | 1 hr | 12 | 0%
| 426 |  |  | 06.01.02.03.04.00.00.00 | TAP-76243 | TAP-74721 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 0 |  | 1 hr | 10 | 0%
| 427 |  |  | 06.01.02.03.05.00.00.00 | TAP-76243 | TAP-73753 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6 |  | 0 |  | 1 hr | 6 | 0%
TAP-83712 | 428 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 |  | 44 | 1 hr | 1 hr | -22 | 100%
TAP-83712_JACOBIANS | 429 |  |  | 06.01.02.04.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-83712_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 430 |  |  | 06.01.02.04.02.00.00.00 | TAP-83712 | TAP-86374 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 16 |  | 32 |  | 1 hr | -16 | 100%
| 431 |  |  | 06.01.02.04.04.00.00.00 | TAP-83712 | TAP-86376 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 20 |  | 1 hr | -10 | 100%
| 432 |  |  | 06.01.02.04.05.00.00.00 | TAP-83712 | TAP-89237 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 433 |  |  | 06.01.02.04.06.00.00.00 | TAP-83712 | TAP-92875 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 20 |  | 1 hr | -10 | 100%
| 434 |  |  | 06.01.02.04.08.00.00.00 | TAP-83712 | TAP-93695 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 435 |  |  | 06.01.03.00.00.00.00.00 |  | RAS-9107 |  | Defect | Open |  |  |  |  | 76 |  | 47 |  | 1 hr | 29 | 0%
TAP-64315 | 436 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 |  | 50 | 1 hr | 1 hr | -25 | 100%
TAP-64315_JACOBIANS | 437 |  |  | 06.01.03.01.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-64315_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 |  | 16 |  | 1 hr | -8 | 100%
| 438 |  |  | 06.01.03.01.02.00.00.00 | TAP-64315 | TAP-73681 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 8 |  | 16 |  | 1 hr | -8 | 100%
| 439 |  |  | 06.01.03.01.03.00.00.00 | TAP-64315 | TAP-73690 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 440 |  |  | 06.01.03.01.05.00.00.00 | TAP-64315 | TAP-73736 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 441 |  |  | 06.01.03.01.06.00.00.00 | TAP-64315 | TAP-73732 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 442 |  |  | 06.01.03.01.07.00.00.00 | TAP-64315 | TAP-73752 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
TAP-64315_REFLECT | 443 |  |  | 06.01.03.01.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-64315_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 3 |  | 6 |  | 1 hr | -3 | 100%
| 444 |  |  | 06.01.03.01.09.00.00.00 | TAP-64315 | TAP-76437 |  | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 445 |  |  | 06.01.03.01.10.00.00.00 | TAP-64315 | TAP-76441 |  | User Story | Done | Advanced Instruments - Reflect | REFLECT |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 446 |  |  | 06.01.03.01.11.00.00.00 | TAP-64315 | TAP-79223 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 447 |  |  | 06.01.03.02.01.00.00.00 | TAP-76243 | TAP-64360 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 20 |  | 0 |  | 1 hr | 20 | 0%
| 448 |  |  | 06.01.03.02.02.00.00.00 | TAP-76243 | TAP-64119 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 0 |  | 1 hr | 10 | 0%
| 449 |  |  | 06.01.03.02.03.00.00.00 | TAP-76243 | TAP-74719 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 12 |  | 0 |  | 1 hr | 12 | 0%
| 450 |  |  | 06.01.03.02.04.00.00.00 | TAP-76243 | TAP-74721 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 0 |  | 1 hr | 10 | 0%
| 451 |  |  | 06.01.03.02.05.00.00.00 | TAP-76243 | TAP-73753 |  | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 6 |  | 0 |  | 1 hr | 6 | 0%
TAP-83712 | 452 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 |  | 44 | 1 hr | 1 hr | -22 | 100%
TAP-83712_JACOBIANS | 453 |  |  | 06.01.03.03.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-83712_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 454 |  |  | 06.01.03.03.02.00.00.00 | TAP-83712 | TAP-86374 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 16 |  | 32 |  | 1 hr | -16 | 100%
| 455 |  |  | 06.01.03.03.04.00.00.00 | TAP-83712 | TAP-86376 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 20 |  | 1 hr | -10 | 100%
| 456 |  |  | 06.01.03.03.05.00.00.00 | TAP-83712 | TAP-89237 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 457 |  |  | 06.01.03.03.06.00.00.00 | TAP-83712 | TAP-92875 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 10 |  | 20 |  | 1 hr | -10 | 100%
| 458 |  |  | 06.01.03.03.08.00.00.00 | TAP-83712 | TAP-93695 |  | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 459 |  |  | 06.01.04.00.00.00.00.00 |  | RAS-10590 |  | Defect | Confirmed |  |  |  |  | 11 |  | 11 |  | 1 hr | 0 | 0%
TAP-83712_VISUAL | 460 |  |  | 06.01.04.01.00.00.00.00 |  | TAP-86405 | [TAP-83712_VISUAL] ¦ [CAPA] Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual | VISUAL |  |  | 3 |  | 6 |  | 1 hr | -3 | 100%
| 461 |  |  | 06.01.04.02.00.00.00.00 |  | TAP-89386 |  | User Story | Done | Foundation - Visual | VISUAL |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 462 |  |  | 06.01.04.03.00.00.00.00 |  | TAP-90083 |  | User Story | Done | Foundation - Visual | VISUAL |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 463 |  |  | 06.01.04.04.00.00.00.00 |  | TAP-90540 |  | User Story | Done | Foundation - Visual | VISUAL |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 464 |  |  | 06.01.04.05.00.00.00.00 |  | TAP-90683 |  | User Story | Done | Foundation - Visual | VISUAL |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 465 |  |  | 06.01.04.06.00.00.00.00 |  | TAP-91134 |  | User Story | Done | Foundation - Visual | VISUAL |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
| 466 |  |  | 06.01.04.07.00.00.00.00 |  | TAP-91818 |  | User Story | Done | Foundation - Visual | VISUAL |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 467 |  |  | 06.04.01.01.00.00.00.00 |  | RAS-13292 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
| 468 |  |  | 06.04.02.01.00.00.00.00 |  | RAS-14234 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
| 469 |  |  | 06.04.02.02.00.00.00.00 |  | RAS-14305 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0
| 470 |  |  | 06.04.02.03.00.00.00.00 |  | RAS-8707 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 471 |  |  | 06.04.02.04.00.00.00.00 |  | RAS-7177 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 472 |  |  | 06.04.03.01.00.00.00.00 |  | RAS-3230 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 473 |  |  | 06.04.03.02.00.00.00.00 |  | RAS-4262 |  | Defect | DEFERRED |  |  |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 474 |  |  | 06.04.04.01.00.00.00.00 |  | RAS-10357 |  | Defect | DEFERRED |  |  |  |  | 16 |  | 13 |  | 1 hr | 3 | 0%
TAP-94573 | 475 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 |  | 26 | 1 hr | 1 hr | -13 | 100%
TAP-94573_STELLARS | 476 |  |  | 06.04.04.01.01.01.00.00 | TAP-94573 | TAP-96622 | [TAP-94573_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Reproduce issue in SW 4.x | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 1 |  | 2 |  | 1 hr | -1 | 100%
| 477 |  |  | 06.04.04.01.01.02.00.00 | TAP-94573 | TAP-96625 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 10 |  | 20 |  | 1 hr | -10 | 100%
| 478 |  |  | 06.04.04.01.01.04.00.00 | TAP-94573 | TAP-100121 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 4 |  | 8 |  | 1 hr | -4 | 100%
| 479 |  |  | 06.04.04.01.01.05.00.00 | TAP-94573 | TAP-106195 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 8 |  | 16 |  | 1 hr | -8 | 100%
| 480 |  |  | 06.04.04.01.01.06.00.00 | TAP-94573 | TAP-110875 |  | User Story | Done | Released Product Engineering - Stellars | STELLARS |  |  | 2 |  | 4 |  | 1 hr | -2 | 100%
TAP-109680 | 481 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% |  |  | Feature Estimation
TAP-109680_STELLARS | 482 |  |  | 06.04.04.01.03.01.00.00 | TAP-109680 | TAP-114754 | [TAP-109680_STELLARS] ¦ [Stellars] [RAS-10357] CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 3 |  | 0 |  | 1 hr | 3 | 0%
| 483 |  |  | 06.04.04.01.03.02.00.00 | TAP-109680 | TAP-114755 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 484 |  |  | 06.04.04.01.03.03.00.00 | TAP-109680 | TAP-114759 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 485 |  |  | 06.04.04.01.03.04.00.00 | TAP-109680 | TAP-114758 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 486 |  |  | 06.04.04.01.03.05.00.00 | TAP-109680 | TAP-114756 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 487 |  |  | 06.04.04.01.03.06.00.00 | TAP-109680 | TAP-114757 |  | User Story | Open | Released Product Engineering - Stellars | STELLARS |  |  | 0 |  | 0 |  | 1 hr | 0 | 0%
| 488 |  |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 |  | Defect | In progress |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-124484 | 489 |  |  | 06.04.04.02.01.00.00.00 |  | TAP-124484 | [TAP-124484] ¦ [RAS-4536] [Stellars] Undefined response to SIM/Instrument Memory Error | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111760 | 490 | TAP-111763 | TAP-94739, TAP-111559, TAP-111834, TAP-95800, TAP-120096, TAP-111719, TAP-117678, TAP-95983, TAP-111731, TAP-111555, TAP-111556, TAP-111751, TAP-111730, TAP-111554, TAP-116286, TAP-111750, TAP-111749, TAP-111724, TAP-111722, TAP-112119, TAP-111569, TAP-103448, TAP-111723, TAP-94966, TAP-112076, TAP-94125, TAP-111721, TAP-111740, TAP-111565, TAP-112012, TAP-112077, TAP-120097, TAP-123834 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 491 | TAP-113104 | TAP-111760 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111763_SEAMLESS | 492 |  |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-113104 | 493 | TAP-113105 | TAP-111747, TAP-111772, TAP-111838, TAP-111925, TAP-104213, TAP-111656, TAP-111865, TAP-112080, TAP-111775, TAP-111842, TAP-111773, TAP-111642, TAP-111774, TAP-112113, TAP-111763 | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 494 | TAP-111765 | TAP-113104 | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113105_SEAMLESS | 495 |  |  | 07.04.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111765 | 496 | TAP-111768 | TAP-111753, TAP-111754, TAP-111756, TAP-111757, TAP-111758, TAP-111759, TAP-111761, TAP-110382, TAP-111762, TAP-111748, TAP-111764, TAP-111766, TAP-112082, TAP-112093, TAP-112094, TAP-113105 | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 497 | TAP-111769 | TAP-111765 | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 498 | TAP-111767 | TAP-111768 | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 499 | TAP-111900 | TAP-111769 | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111767_SEAMLESS | 500 |  |  | 07.08.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-113101 | 501 | TAP-113102 | TAP-113100 | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 502 | TAP-113103 | TAP-113101 | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 503 | TAP-121104 | TAP-113102 | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113103_SEAMLESS | 504 |  |  | 07.11.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-121104 | 505 |  | TAP-111900, TAP-112042, TAP-111692, TAP-112231, TAP-112233, TAP-112234, TAP-113127, TAP-113103 | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94968 | 506 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111726 | 507 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
| 508 |  |  | 08.02.02.01.00.00.00.00 | TAP-111726 | TAP-111947 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-111727 | 509 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 510 |  |  | 08.02.03.01.00.00.00.00 | TAP-111727 | TAP-111948 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111729 | 511 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 512 |  |  | 08.02.04.01.00.00.00.00 | TAP-111729 | TAP-111949 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-94967 | 513 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111733 | 514 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 515 |  |  | 08.03.01.00.00.00.00.00 | TAP-111733 | TAP-111908 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111734 | 516 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 517 |  |  | 08.04.01.00.00.00.00.00 | TAP-111734 | TAP-111911 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111735 | 518 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 519 |  |  | 08.05.01.00.00.00.00.00 | TAP-111735 | TAP-111912 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111570 | 520 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 521 |  |  | 08.06.01.00.00.00.00.00 | TAP-111570 | TAP-111798 |  | Feature Estimation | Open | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-112107 | 522 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
| 523 |  |  | 09.01.02.01.00.00.00.00 | TAP-112107 | TAP-112114 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 30
TAP-111934 | 524 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 525 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
| 526 |  |  | 09.01.04.01.00.00.00.00 | TAP-112085 | TAP-112090 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 10
TAP-112084 | 527 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
| 528 |  |  | 09.01.05.01.00.00.00.00 | TAP-112084 | TAP-112088 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 10
TAP-112101 | 529 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 160 | 320 | Feature Estimation
| 530 |  |  | 09.01.06.01.00.00.00.00 | TAP-112101 | TAP-112103 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 160 | 320
TAP-112086 | 531 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 50 | Feature Estimation
| 532 |  |  | 09.01.07.01.00.00.00.00 | TAP-112086 | TAP-112091 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 25 | 50
TAP-112087 | 533 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
| 534 |  |  | 09.01.08.01.00.00.00.00 | TAP-112087 | TAP-112092 |  | Feature Estimation | Done | Core Instruments | COREINSTRUMENT |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 100
TAP-112095 | 535 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112095_HAPPYJAWS | 536 |  |  | 09.02.01.01.00.00.00.00 | TAP-112095 | TAP-124573 | [TAP-112095_HAPPYJAWS] ¦ [IRR] Prototype 3-cable support for staging/irr-v3 | User Story | Open | Core Instruments | HAPPYJAWS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-106203 | 537 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-100791 | 538 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100%

## Log
DataTimeStamp | Event | Data

## Summary
Resource Names | Sum FDR
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
COREINSTRUMENT
COREINSTRUMENT
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
COREINSTRUMENT
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
COREINSTRUMENT
ANIMATORS
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
HAPPYJAWS
COREINSTRUMENT
HAPPYJAWS
HAPPYJAWS
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
SIRIUS
SIRIUS
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
I2E
I2E
I2E
I2E
I2E
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
SIRIUS
COREINSTRUMENT
COREINSTRUMENT
SIRIUS
ANIMATORS
ANIMATORS
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
FRED
SIRIUS
PUPPETEERS
ANIMATORS
ANIMATORS
ANIMATORS
ANIMATORS
ANIMATORS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
COREINSTRUMENT
FRED
I2E
I2E
I2E
COREINSTRUMENT
SIRIUS
SIRIUS
SIRIUS
SIRIUS
HAPPYJAWS
SIRIUS
SIRIUS
PUPPETEERS
COREINSTRUMENT
COREINSTRUMENT
SIRIUS
COREINSTRUMENT
COREINSTRUMENT
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
COREINSTRUMENT
SIRIUS
COREINSTRUMENT
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
SIRIUS
COREINSTRUMENT
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
SIRIUS
HAPPYJAWS
HAPPYJAWS
HAPPYJAWS
COREINSTRUMENT
SIRIUS
COREINSTRUMENT
COREINSTRUMENT
JACOBIANS
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
JACOBIANS
CASTLEBLACK
PUPPETEERS
PUPPETEERS
PUPPETEERS
COREINSTRUMENT
JACOBIANS
ORGANELLES
INBETWEENERS
PUPPETEERS
PUPPETEERS
CASTLEBLACK
COREINSTRUMENT
JACOBIANS
ORGANELLES
INBETWEENERS
PUPPETEERS
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
I2E
COREINSTRUMENT
I2E
ORGANELLES
CASTLEBLACK
CLASSY2
BOOSTERS
INBETWEENERS
CASTLEBLACK
ORGANELLES
I2E
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
BOOSTERS
BOOSTERS
BOOSTERS
PIXELPOETS
PIXELPOETS
PIXELPOETS
CASTLEBLACK
PUPPETEERS
PUPPETEERS
PUPPETEERS
PUPPETEERS
PUPPETEERS
SIRIUS
PIXELPOETS
PIXELPOETS
PIXELPOETS
CASTLEBLACK
STELLARS
STELLARS
STELLARS
I2E
ORGANELLES
DRUSHTI
PUPPETEERS
PIXELPOETS
ORGANELLES
FRED
PIXELPOETS
ORGANELLES
DRUSHTI
PIXELPOETS
ORGANELLES
DRUSHTI
COREINSTRUMENT
COREINSTRUMENT
SIRIUS
COREINSTRUMENT
HAPPYJAWS
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
I2E
ORGANELLES
PIXELPOETS
JACOBIANS
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
BUGHUNTERS
I2E
JACOBIANS
ORGANELLES
SCRUMBLEDORES
SUNRISERS
TEAMBD
COSSACKS
BUILDERS
ASTRANPSDEVELOPERS
TOOLSRULES
INBETWEENERS
TRIPLETEA
ASTRANPSVALIDATORS
ASTRANPSVALIDATORS
TOOLSRULES
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
SUNRISERS
STELLARS
STELLARS
STELLARS
SUNRISERS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
REFLECT
REFLECT
REFLECT
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
REFLECT
REFLECT
REFLECT
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
JACOBIANS
VISUAL
VISUAL
VISUAL
VISUAL
VISUAL
VISUAL
VISUAL
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
STELLARS
SEAMLESS
SEAMLESS
SEAMLESS
SEAMLESS
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
COREINSTRUMENT
HAPPYJAWS