## Project
Selector | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Index | Parent Feature | Key | Task Name | Issue Type | Status | ART | Resource Names | Task Type | Source | Σ Total SP | Σ Groom SP | Σ Done SP | Focus Duration | Low-Risk Duration | Remaining SP | % Complete | Σ Realistic Estimate | Σ Worst Case Estimate | RefinementLevel
TAP-94739 | 1 | TAP-97668, TAP-111760 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 |  | 24 | 1 hr | 1 hr | -12 | 100% | 40 | 50 | Story Points
TAP-97668 | 2 | TAP-120097 | TAP-94739 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  |  |  | 32.5 |  | 65 | 1 hr | 1 hr | -32.5 | 100% | 6 | 8 | Story Points
TAP-97668_COREINSTRUMENTS | 3 |  |  | 01.01.02.01.00.00.00.00 | TAP-97668 | TAP-111972 | [TAP-97668_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 32.5 |  | 97.5 | 1 hr | 1 hr | -65 | 100% | 6 | 8
TAP-120097 | 4 | TAP-111760 | TAP-97668 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | PROPOSED |  |  |  |  | 28.5 |  | 0 | 1 hr | 1 hr | 28.5 | 0% | 0 | 0 | Story Points
TAP-111730 | 5 | TAP-111760, TAP-124062 | TAP-106315 | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 28 |  | 20 | 1 hr | 1 hr | 8 | 0% | 30 | 40 | Story Points
TAP-111730_COREINSTRUMENTS | 6 |  |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 | [TAP-111730_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Fix force generation at clamp initiation | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 28 |  | 48 | 1 hr | 1 hr | -20 | 100% | 30 | 40
TAP-111731 | 7 | TAP-111760 |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 50 | Feature Estimation
TAP-111731_COREINSTRUMENTS | 8 |  |  | 01.02.02.01.00.00.00.00 | TAP-111731 | TAP-111906 | [TAP-111731_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce force variation when articulating during clamp | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 50
TAP-111731_SHAREDSERVICES-ANIMATORS | 9 |  |  | 01.02.02.02.00.00.00.00 | TAP-111731 | TAP-112037 | [TAP-111731_SHAREDSERVICES-ANIMATORS] ¦ [Animators] Reduce Force Variation when articulating during clamp | Feature Estimation | Open | SHARED SERVICES - ANIMATORS | SHAREDSERVICES-ANIMATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 50
TAP-124062 | 10 |  | TAP-111730 | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112076 | 11 | TAP-111760 |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112076_COREINSTRUMENTS | 12 |  |  | 01.03.01.01.00.00.00.00 | TAP-112076 | TAP-112078 | [TAP-112076_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Damage Modeling Documentation | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 10
TAP-94966 | 13 | TAP-111556, TAP-111760 | TAP-111562 | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | In progress |  |  |  |  | 37 |  | 25 | 1 hr | 1 hr | 12 | 0% | 45 | 78 | Story Points
TAP-94966_COREINSTRUMENTS | 14 |  |  | 01.03.02.01.00.00.00.00 | TAP-94966 | TAP-111781 | [TAP-94966_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Develop a Jaw Estimator for Shears | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 37 |  | 62 | 1 hr | 1 hr | -25 | 100% | 45 | 78
TAP-111554 | 15 | TAP-111760 |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 |  | 0 | 1 hr | 1 hr | 7 | 0% | 24 | 48 | Story Points
TAP-111554_COREINSTRUMENTS | 16 |  |  | 01.03.03.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I1 | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 7 |  | 7 | 1 hr | 1 hr | 0 | 100% | 24 | 48
TAP-111555 | 17 | TAP-111760 |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-111555_COREINSTRUMENTS | 18 |  |  | 01.03.04.01.00.00.00.00 | TAP-111555 | TAP-111783 | [TAP-111555_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I2 | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 12 | 18
TAP-112012 | 19 | TAP-111760 |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-112012_COREINSTRUMENTS | 20 |  |  | 01.03.05.01.00.00.00.00 | TAP-112012 | TAP-112015 | [TAP-112012_COREINSTRUMENTS] ¦ [IRR][Enhancement] Cutting Control Enhancements | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 12 | 18
TAP-111569 | 21 | TAP-111760 |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 12 | Feature Estimation
TAP-111569_COREINSTRUMENTS | 22 |  |  | 01.03.07.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Integration, Testing, Demo, Design Review | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 12
TAP-111565 | 23 | TAP-111760 |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 20 | Feature Estimation
TAP-111565_COREINSTRUMENTS | 24 |  |  | 01.03.08.01.00.00.00.00 | TAP-111565 | TAP-111793 | [TAP-111565_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 5 | 20
TAP-111556 | 25 | TAP-111559, TAP-111760 | TAP-94966 | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111556_COREINSTRUMENTS | 26 |  |  | 01.03.09.01.00.00.00.00 | TAP-111556 | TAP-111784 | [TAP-111556_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I1 | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111559 | 27 | TAP-111760 | TAP-111556 | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111559_COREINSTRUMENTS | 28 |  |  | 01.03.10.01.00.00.00.00 | TAP-111559 | TAP-111785 | [TAP-111559_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I2 | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-112077 | 29 | TAP-111760 | TAP-111562 | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 61 |  | 13 | 1 hr | 1 hr | 48 | 0% | 20 | 30 | Story Points
TAP-112077_COREINSTRUMENTS | 30 |  |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Articulation KPI generation and evaluation | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 61 |  | 74 | 1 hr | 1 hr | -13 | 100% | 20 | 30
TAP-120096 | 31 | TAP-111760 |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-103448 | 32 | TAP-111760 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 |  | 5 | 1 hr | 1 hr | 9 | 0% | 0 | 0 | Story Points
TAP-116286 | 33 | TAP-111760 |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 |  | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0 | Story Points
TAP-95983 | 34 | TAP-111760 |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 106 |  | 35 | 1 hr | 1 hr | 71 | 0% | 41 | 73 | Story Points
TAP-95983_FOUNDATION-FRED | 35 |  |  | 01.05.04.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_FOUNDATION-FRED] ¦ [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | Feature Estimation | Open | FOUNDATION - FRED | FOUNDATION-FRED |  |  | 125 |  | 156 | 1 hr | 1 hr | -31 | 1.248% | 82 | 146
TAP-111719 | 36 | TAP-111562, TAP-111760 | TAP-124116 | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 |  | 2 | 1 hr | 1 hr | 3 | 0% | 15 | 22 | Story Points
TAP-111719_COREINSTRUMENTS | 37 |  |  | 01.05.05.01.00.00.00.00 | TAP-111719 | TAP-111916 | [TAP-111719_COREINSTRUMENTS] ¦ [IRR][Core Instruments] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 5 |  | 2 | 1 hr | 1 hr | 3 | 0.4% | 15 | 22
TAP-111719_FOUNDATION-FRED | 38 |  |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112039 | [TAP-111719_FOUNDATION-FRED] ¦ [IRR][Fred] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | FOUNDATION - FRED | FOUNDATION-FRED |  |  | 5 |  | 2 | 1 hr | 1 hr | 3 | 0.4% | 15 | 22
TAP-111719_ADVANCEDINSTRUMENTS-I2E | 39 |  |  | 01.05.05.03.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_ADVANCEDINSTRUMENTS-I2E] ¦ [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | ADVANCED INSTRUMENTS - I2E | ADVANCEDINSTRUMENTS-I2E |  |  | 5 |  | 7 | 1 hr | 1 hr | -2 | 100% | 15 | 22
TAP-111721 | 40 | TAP-111760 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 |  | 20.5 | 1 hr | 1 hr | 4 | 0% | 27 | 30 | Story Points
TAP-111721_COREINSTRUMENTS | 41 |  |  | 01.05.06.01.00.00.00.00 | TAP-111721 | TAP-111917 | [TAP-111721_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI14) | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 24.5 |  | 45 | 1 hr | 1 hr | -20.5 | 100% | 27 | 30
TAP-111722 | 42 | TAP-111760 |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111722_COREINSTRUMENTS | 43 |  |  | 01.05.07.01.00.00.00.00 | TAP-111722 | TAP-111918 | [TAP-111722_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI15) | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 27 | 30
TAP-111723 | 44 | TAP-111760 |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 27 | 30 | Feature Estimation
TAP-111723_COREINSTRUMENTS | 45 |  |  | 01.05.08.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI16) | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 3 |  | 3 | 1 hr | 1 hr | 0 | 100% | 27 | 30
TAP-111724 | 46 | TAP-111760 |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111724_COREINSTRUMENTS | 47 |  |  | 01.05.09.01.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 27 | 30
TAP-112119 | 48 | TAP-111760 |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112119_COREINSTRUMENTS | 49 |  |  | 01.05.10.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119_COREINSTRUMENTS] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-94125 | 50 | TAP-111753, TAP-111760 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | Accepted |  |  |  |  | 77 |  | 0 | 1 hr | 1 hr | 77 | 0% | 50 | 70 | Story Points
TAP-95800 | 51 | TAP-111754, TAP-111760 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | Accepted |  |  |  |  | 31 |  | 2 | 1 hr | 1 hr | 29 | 0% | 15 | 35 | Story Points
TAP-111740 | 52 | TAP-111756, TAP-111760 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | PROPOSED |  |  |  |  | 28 |  | 0 | 1 hr | 1 hr | 28 | 0% | 60 | 80 | Story Points
TAP-111740_COREINSTRUMENTS | 53 |  |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 28 |  | 28 | 1 hr | 1 hr | 0 | 100% | 60 | 80
TAP-111749 | 54 | TAP-111757, TAP-111760 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111749_COREINSTRUMENTS | 55 |  |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Monitor SWI for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 16 | 30
TAP-111750 | 56 | TAP-111758, TAP-111760 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 35 | Feature Estimation
TAP-111750_COREINSTRUMENTS | 57 |  |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Procedure Manager SWI for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 35
TAP-111751 | 58 | TAP-111759, TAP-111760 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 45 | Feature Estimation
TAP-111751_COREINSTRUMENTS | 59 |  |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Estimator SWI for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 28 | 45
TAP-117678 | 60 | TAP-111760 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111834 | 61 | TAP-111760 | TAP-113995 | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-111834_ADVANCEDINSTRUMENTS-JACOBIANS | 62 |  |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_ADVANCEDINSTRUMENTS-JACOBIANS] ¦ Support Kinematic Updates for IRR Wristed Instruments | Feature Estimation | Done | ADVANCED INSTRUMENTS - JACOBIANS | ADVANCEDINSTRUMENTS-JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-111747 | 63 | TAP-113104 |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-111747_COREINSTRUMENTS | 64 |  |  | 02.01.01.01.00.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 100
TAP-111772 | 65 | TAP-113104 |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111772_COREINSTRUMENTS | 66 |  |  | 02.02.01.01.00.00.00.00 | TAP-111772 | TAP-111965 | [TAP-111772_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 20
TAP-111773 | 67 | TAP-113104 |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 65 | Feature Estimation
TAP-111773_COREINSTRUMENTS | 68 |  |  | 02.02.02.01.00.00.00.00 | TAP-111773 | TAP-111966 | [TAP-111773_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW + Test Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 65
TAP-111838 | 69 | TAP-111842, TAP-113104 |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111838_COREINSTRUMENTS | 70 |  |  | 02.03.01.01.00.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-104213 | 71 | TAP-111842, TAP-113104 |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 45 | Feature Estimation
TAP-104213_COREINSTRUMENTS | 72 |  |  | 02.03.02.01.00.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 45
TAP-111842 | 73 | TAP-113104 | TAP-104213, TAP-111838 | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111842_COREINSTRUMENTS | 74 |  |  | 02.03.03.01.00.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-111774 | 75 | TAP-111775, TAP-112080, TAP-113104 |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 9 |  | 9 | 1 hr | 1 hr | 0 | 0% | 20 | 34 | Story Points
TAP-111774_COREINSTRUMENTS | 76 |  |  | 02.04.01.01.00.00.00.00 | TAP-111774 | TAP-111970 | [TAP-111774_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 9 |  | 18 | 1 hr | 1 hr | -9 | 100% | 20 | 34
TAP-111774_ADVANCEDINSTRUMENTS-JACOBIANS | 77 |  |  | 02.04.01.02.00.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774_ADVANCEDINSTRUMENTS-JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | ADVANCED INSTRUMENTS - JACOBIANS | ADVANCEDINSTRUMENTS-JACOBIANS |  |  | 9 |  | 27 | 1 hr | 1 hr | -18 | 100% | 20 | 34
TAP-111774_SHAREDSERVICES-CASTLEBLACK | 78 |  |  | 02.04.01.03.00.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774_SHAREDSERVICES-CASTLEBLACK] ¦ [IRR][Castle Black] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Open | SHARED SERVICES - CASTLE BLACK | SHAREDSERVICES-CASTLEBLACK |  |  | 9 |  | 27 | 1 hr | 1 hr | -18 | 3% | 20 | 34
TAP-112080 | 79 | TAP-111775, TAP-113104 | TAP-111774 | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 15 |  | 0 | 1 hr | 1 hr | 15 | 0% | 37 | 63 | Story Points
TAP-112080_COREINSTRUMENTS | 80 |  |  | 02.04.02.01.00.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 15 |  | 15 | 1 hr | 1 hr | 0 | 100% | 37 | 63
TAP-112080_ADVANCEDINSTRUMENTS-JACOBIANS | 81 |  |  | 02.04.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_ADVANCEDINSTRUMENTS-JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | ADVANCED INSTRUMENTS - JACOBIANS | ADVANCEDINSTRUMENTS-JACOBIANS |  |  | 15 |  | 30 | 1 hr | 1 hr | -15 | 100% | 37 | 63
TAP-112080_ADVANCEDINSTRUMENTS-ORGANELLES | 82 |  |  | 02.04.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR][Organelles] UFSW - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 15 |  | 45 | 1 hr | 1 hr | -30 | 100% | 37 | 63
TAP-112080_SHAREDSERVICES-INBETWEENERS | 83 |  |  | 02.04.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_SHAREDSERVICES-INBETWEENERS] ¦ [IRR][Inbetweeners] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | SHARED SERVICES - INBETWEENERS | SHAREDSERVICES-INBETWEENERS |  |  | 15 |  | 60 | 1 hr | 1 hr | -45 | 100% | 37 | 63
TAP-111775 | 84 | TAP-113104 | TAP-111774, TAP-112080 | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 |  | 0 | 1 hr | 1 hr | 1 | 0% | 45 | 75 | Feature Estimation
TAP-111775_COREINSTRUMENTS | 85 |  |  | 02.04.03.01.00.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 1 |  | 1 | 1 hr | 1 hr | 0 | 100% | 45 | 75
TAP-111775_ADVANCEDINSTRUMENTS-JACOBIANS | 86 |  |  | 02.04.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_ADVANCEDINSTRUMENTS-JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | ADVANCED INSTRUMENTS - JACOBIANS | ADVANCEDINSTRUMENTS-JACOBIANS |  |  | 1 |  | 2 | 1 hr | 1 hr | -1 | 100% | 45 | 75
TAP-111775_ADVANCEDINSTRUMENTS-ORGANELLES | 87 |  |  | 02.04.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR][Organelles] UFSW - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 1 |  | 3 | 1 hr | 1 hr | -2 | 100% | 45 | 75
TAP-111775_SHAREDSERVICES-INBETWEENERS | 88 |  |  | 02.04.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_SHAREDSERVICES-INBETWEENERS] ¦ [IRR][Inbetweeners] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | SHARED SERVICES - INBETWEENERS | SHAREDSERVICES-INBETWEENERS |  |  | 1 |  | 4 | 1 hr | 1 hr | -3 | 100% | 45 | 75
TAP-123862 | 89 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 27 |  | 0 | 1 hr | 1 hr | 27 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 90 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 26 |  | 0 | 1 hr | 1 hr | 26 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 91 | TAP-113104 |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 170 | 325 | Feature Estimation
TAP-111642_COREINSTRUMENTS | 92 |  |  | 02.05.03.01.00.00.00.00 | TAP-111642 | TAP-111941 | [TAP-111642_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 170 | 325
TAP-111642_ADVANCEDINSTRUMENTS-I2E | 93 |  |  | 02.05.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111642_ADVANCEDINSTRUMENTS-I2E] ¦ [IRR][I2E] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | ADVANCED INSTRUMENTS - I2E | ADVANCEDINSTRUMENTS-I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 170 | 325
TAP-111642_ADVANCEDINSTRUMENTS-ORGANELLES | 94 |  |  | 02.05.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111642_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 170 | 325
TAP-111642_SHAREDSERVICES-CASTLEBLACK | 95 |  |  | 02.05.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111642_SHAREDSERVICES-CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | SHARED SERVICES - CASTLE BLACK | SHAREDSERVICES-CASTLEBLACK |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 170 | 325
TAP-111656 | 96 | TAP-113104 |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_FOUNDATION-CLASSY2 | 97 |  |  | 02.05.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_FOUNDATION-CLASSY2] ¦ [IRR][CLASSY 2] Controller Versioning: Productization | Feature Estimation | Done | FOUNDATION - CLASSY 2 | FOUNDATION-CLASSY2 |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 151 | 278
TAP-111656_FOUNDATION-BOOSTERS | 98 |  |  | 02.05.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_FOUNDATION-BOOSTERS] ¦ [IRR][Boosters] Controller Versioning: Productization | Feature Estimation | Done | FOUNDATION - BOOSTERS | FOUNDATION-BOOSTERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 151 | 278
TAP-111656_SHAREDSERVICES-INBETWEENERS | 99 |  |  | 02.05.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_SHAREDSERVICES-INBETWEENERS] ¦ [IRR][Inbetweeners] Controller Versioning: Productization | Feature Estimation | Done | SHARED SERVICES - INBETWEENERS | SHAREDSERVICES-INBETWEENERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 151 | 278
TAP-111656_SHAREDSERVICES-CASTLEBLACK | 100 |  |  | 02.05.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_SHAREDSERVICES-CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Productization | Feature Estimation | Open | SHARED SERVICES - CASTLE BLACK | SHAREDSERVICES-CASTLEBLACK |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 151 | 278
TAP-111656_ADVANCEDINSTRUMENTS-ORGANELLES | 101 |  |  | 02.05.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Productization | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 151 | 278
TAP-111656_ADVANCEDINSTRUMENTS-I2E | 102 |  |  | 02.05.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_ADVANCEDINSTRUMENTS-I2E] ¦ [IRR][I2E] Controller Versioning: Productization | Feature Estimation | Done | ADVANCED INSTRUMENTS - I2E | ADVANCEDINSTRUMENTS-I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 151 | 278
TAP-111656_COREINSTRUMENTS | 103 |  |  | 02.05.04.07.00.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Productization | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 151 | 278
TAP-111925 | 104 | TAP-113104 |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111925_COREINSTRUMENTS | 105 |  |  | 02.06.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 30
TAP-112113 | 106 | TAP-113104 |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112113_COREINSTRUMENTS | 107 |  |  | 02.06.02.01.00.00.00.00 | TAP-112113 | TAP-112123 | [TAP-112113_COREINSTRUMENTS] ¦ [IRR] Verification plan for regression on SKU's | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111865 | 108 | TAP-113104 |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113111 | 109 | TAP-111689, TAP-111695 |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Accepted |  |  |  |  | 12 |  | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 110 | TAP-111687, TAP-111689, TAP-111695 |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 111 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 |  | 18 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-114689 | 112 | TAP-111687 |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  |  |  | 15 |  | 30 | 1 hr | 1 hr | -15 | 100% | 0 | 0 | Story Points
TAP-90375 | 113 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 |  | 0 | 1 hr | 1 hr | 9 | 0% |  |  | Story Points
TAP-111861 | 114 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 34 | 46 | Story Points
TAP-111861_ADVANCEDINSTRUMENTS-I2E | 115 |  |  | 02.07.03.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_ADVANCEDINSTRUMENTS-I2E] ¦ [IRR][I2E] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | ADVANCED INSTRUMENTS - I2E | ADVANCEDINSTRUMENTS-I2E |  |  | 3 |  | 3 | 1 hr | 1 hr | 0 | 100% | 34 | 46
TAP-111861_ADVANCEDINSTRUMENTS-ORGANELLES | 116 |  |  | 02.07.03.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR][Organelles] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 3 |  | 6 | 1 hr | 1 hr | -3 | 100% | 34 | 46
TAP-111861_RELEASEDPRODUCTENGINEERING-DRUSHTI | 117 |  |  | 02.07.03.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_RELEASEDPRODUCTENGINEERING-DRUSHTI] ¦ [IRR][Drushti] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | RELEASED PRODUCT ENGINEERING - DRUSHTI | RELEASEDPRODUCTENGINEERING-DRUSHTI |  |  | 3 |  | 9 | 1 hr | 1 hr | -6 | 100% | 34 | 46
TAP-111687 | 118 |  | TAP-113123, TAP-114689 | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111687_ADVANCEDINSTRUMENTS-PIXELPOETS | 119 |  |  | 02.07.03.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_ADVANCEDINSTRUMENTS-PIXELPOETS] ¦ [IRR] [Pixel Poets] Instrument Use Life Count-Down Display | Feature Estimation | Done | ADVANCED INSTRUMENTS - PIXEL POETS | ADVANCEDINSTRUMENTS-PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 28 | 46
TAP-111687_ADVANCEDINSTRUMENTS-ORGANELLES | 120 |  |  | 02.07.03.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR] [Organelles] Instrument Use Life Count-Down Display | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 28 | 46
TAP-111687_FOUNDATION-FRED | 121 |  |  | 02.07.03.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_FOUNDATION-FRED] ¦ [IRR] [Fred] Instrument Use Life Count-Down Display | Feature Estimation | Open | FOUNDATION - FRED | FOUNDATION-FRED |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 28 | 46
TAP-111689 | 122 |  | TAP-113111, TAP-113123 | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 32 | 48 | Feature Estimation
TAP-111689_ADVANCEDINSTRUMENTS-PIXELPOETS | 123 |  |  | 02.07.03.04.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111689_ADVANCEDINSTRUMENTS-PIXELPOETS] ¦ [IRR] [Pixel Poets] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | ADVANCED INSTRUMENTS - PIXEL POETS | ADVANCEDINSTRUMENTS-PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 32 | 48
TAP-111689_ADVANCEDINSTRUMENTS-ORGANELLES | 124 |  |  | 02.07.03.04.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-111689_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR] [Organelles] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 32 | 48
TAP-111689_RELEASEDPRODUCTENGINEERING-DRUSHTI | 125 |  |  | 02.07.03.04.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-111689_RELEASEDPRODUCTENGINEERING-DRUSHTI] ¦ [IRR] [Drushti] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | RELEASED PRODUCT ENGINEERING - DRUSHTI | RELEASEDPRODUCTENGINEERING-DRUSHTI |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 32 | 48
TAP-111695 | 126 |  | TAP-113111, TAP-113123 | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 24 | 46 | Feature Estimation
TAP-111695_ADVANCEDINSTRUMENTS-PIXELPOETS | 127 |  |  | 02.07.03.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_ADVANCEDINSTRUMENTS-PIXELPOETS] ¦ [IRR][Pixel Poets] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | ADVANCED INSTRUMENTS - PIXEL POETS | ADVANCEDINSTRUMENTS-PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 24 | 46
TAP-111695_ADVANCEDINSTRUMENTS-ORGANELLES | 128 |  |  | 02.07.03.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR][Organelles] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 24 | 46
TAP-111695_RELEASEDPRODUCTENGINEERING-DRUSHTI | 129 |  |  | 02.07.03.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_RELEASEDPRODUCTENGINEERING-DRUSHTI] ¦ [IRR][Drushti] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | RELEASED PRODUCT ENGINEERING - DRUSHTI | RELEASEDPRODUCTENGINEERING-DRUSHTI |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 24 | 46
TAP-111753 | 130 | TAP-111761, TAP-111765 | TAP-94125 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 30 | 50 | Feature Estimation
TAP-111753_COREINSTRUMENTS | 131 |  |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 | [TAP-111753_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Homing Manager | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 30 | 50
TAP-111754 | 132 | TAP-110382, TAP-111765 | TAP-95800 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 10 | 15 | Feature Estimation
TAP-111754_COREINSTRUMENTS | 133 |  |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 | [TAP-111754_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Motor Controller | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 3 |  | 3 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111756 | 134 | TAP-111762, TAP-111765 | TAP-111740 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% | 35 | 45 | Feature Estimation
TAP-111756_COREINSTRUMENTS | 135 |  |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Teleoperation Controller | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 3 |  | 3 | 1 hr | 1 hr | 0 | 100% | 35 | 45
TAP-111757 | 136 | TAP-111748, TAP-111765 | TAP-111749 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111757_COREINSTRUMENTS | 137 |  |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 16 | 30
TAP-111758 | 138 | TAP-111764, TAP-111765 | TAP-111750 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111758_COREINSTRUMENTS | 139 |  |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 | [TAP-111758_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Procedure Manager SWI | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 30
TAP-111759 | 140 | TAP-111766, TAP-111765 | TAP-111751 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111759_COREINSTRUMENTS | 141 |  |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 | [TAP-111759_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Estimator SWI | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-111761 | 142 | TAP-111765 | TAP-111753 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 30 | Feature Estimation
TAP-111761_COREINSTRUMENTS | 143 |  |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Homing Manager Sub-SWI for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 25 | 30
TAP-110382 | 144 | TAP-111765 | TAP-111754 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 8 | Feature Estimation
TAP-110382_COREINSTRUMENTS | 145 |  |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 5 | 8
TAP-111762 | 146 | TAP-111765 | TAP-111756 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 25 | Feature Estimation
TAP-111762_COREINSTRUMENTS | 147 |  |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Teleoperation Controller for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 25
TAP-111748 | 148 | TAP-111765 | TAP-111757 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 15 | Feature Estimation
TAP-111748_COREINSTRUMENTS | 149 |  |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 8 | 15
TAP-111764 | 150 | TAP-111765 | TAP-111758 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111764_COREINSTRUMENTS | 151 |  |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Procedure Manager for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111766 | 152 | TAP-111765 | TAP-111759 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111766_COREINSTRUMENTS | 153 |  |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Estimator SWI for IRR | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 20
TAP-112082 | 154 | TAP-111765 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 125 | Feature Estimation
TAP-112082_COREINSTRUMENTS | 155 |  |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082_COREINSTRUMENTS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 125
TAP-112082_ADVANCEDINSTRUMENTS-I2E | 156 |  |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_ADVANCEDINSTRUMENTS-I2E] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | ADVANCED INSTRUMENTS - I2E | ADVANCEDINSTRUMENTS-I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 125
TAP-112082_ADVANCEDINSTRUMENTS-ORGANELLES | 157 |  |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 125
TAP-112082_ADVANCEDINSTRUMENTS-PIXELPOETS | 158 |  |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_ADVANCEDINSTRUMENTS-PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | ADVANCED INSTRUMENTS - PIXEL POETS | ADVANCEDINSTRUMENTS-PIXELPOETS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 125
TAP-112082_ADVANCEDINSTRUMENTS-JACOBIANS | 159 |  |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_ADVANCEDINSTRUMENTS-JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | ADVANCED INSTRUMENTS - JACOBIANS | ADVANCEDINSTRUMENTS-JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 125
TAP-112093 | 160 | TAP-111765 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 55 | 70 | Feature Estimation
TAP-112093_COREINSTRUMENTS | 161 |  |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093_COREINSTRUMENTS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 55 | 70
TAP-112094 | 162 | TAP-111765 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 87 | 170 | Feature Estimation
TAP-112094_COREINSTRUMENTS | 163 |  |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094_COREINSTRUMENTS] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 87 | 170
TAP-113100 | 164 | TAP-113101 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 200 | 400 | Feature Estimation
TAP-113100_COREINSTRUMENTS | 165 |  |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100_COREINSTRUMENTS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 200 | 400
TAP-111900 | 166 | TAP-121104 | TAP-111767 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 79 | 152 | Feature Estimation
TAP-111900_COREINSTRUMENTS | 167 |  |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900_COREINSTRUMENTS] ¦ [M-IRR][Core Instrument] Formal Software Verification activities | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_ADVANCEDINSTRUMENTS-BUGHUNTERS | 168 |  |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_ADVANCEDINSTRUMENTS-BUGHUNTERS] ¦ [M-IRR][Bug Hunters] Formal Software Verification activities | Feature Estimation | Open | ADVANCED INSTRUMENTS - BUG HUNTERS | ADVANCEDINSTRUMENTS-BUGHUNTERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_ADVANCEDINSTRUMENTS-I2E | 169 |  |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-111900_ADVANCEDINSTRUMENTS-I2E] ¦ [M-IRR][I2E] Formal Software Verification activities | Feature Estimation | Done | ADVANCED INSTRUMENTS - I2E | ADVANCEDINSTRUMENTS-I2E |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_ADVANCEDINSTRUMENTS-JACOBIANS | 170 |  |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_ADVANCEDINSTRUMENTS-JACOBIANS] ¦ [M-IRR][Jacobians] Formal Software Verification activities | Feature Estimation | Done | ADVANCED INSTRUMENTS - JACOBIANS | ADVANCEDINSTRUMENTS-JACOBIANS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_ADVANCEDINSTRUMENTS-ORGANELLES | 171 |  |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_ADVANCEDINSTRUMENTS-ORGANELLES] ¦ [M-IRR][Organelles] Formal Software Verification activities | Feature Estimation | Done | ADVANCED INSTRUMENTS - ORGANELLES | ADVANCEDINSTRUMENTS-ORGANELLES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_ADVANCEDINSTRUMENTS-SCRUMBLEDORES | 172 |  |  | 05.01.07.00.00.00.00.00 | TAP-111900 | TAP-112683 | [TAP-111900_ADVANCEDINSTRUMENTS-SCRUMBLEDORES] ¦ [M-IRR][Scrumbledores] Formal Software Verification activities | Feature Estimation | Done | ADVANCED INSTRUMENTS - SCRUMBLEDORES | ADVANCEDINSTRUMENTS-SCRUMBLEDORES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_ADVANCEDINSTRUMENTS-SUNRISERS | 173 |  |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_ADVANCEDINSTRUMENTS-SUNRISERS] ¦ [M-IRR][Sunrisers] Formal Software Verification activities | Feature Estimation | Done | ADVANCED INSTRUMENTS - SUNRISERS | ADVANCEDINSTRUMENTS-SUNRISERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_ADVANCEDINSTRUMENTS-TEAMBD | 174 |  |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_ADVANCEDINSTRUMENTS-TEAMBD] ¦ [M-IRR][TeamBD] Formal Software Verification activities | Feature Estimation | Done | ADVANCED INSTRUMENTS - TEAMBD | ADVANCEDINSTRUMENTS-TEAMBD |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-111900_SHAREDSERVICES-COSSACKS | 175 |  |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_SHAREDSERVICES-COSSACKS] ¦ [M-IRR][Cossacks] Formal Software Verification activities | Feature Estimation | Done | SHARED SERVICES - COSSACKS | SHAREDSERVICES-COSSACKS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 79 | 152
TAP-112042 | 176 | TAP-121104 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 22 | 30 | Feature Estimation
TAP-112042_SHAREDSERVICES-BUILDERS | 177 |  |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_SHAREDSERVICES-BUILDERS] ¦ [V3.1][IRR][Builders] Field Script Readiness Evaluation | Feature Estimation | Done | SHARED SERVICES - BUILDERS | SHAREDSERVICES-BUILDERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 22 | 30
TAP-111692 | 178 | TAP-121104 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 130 | 195 | Feature Estimation
TAP-111692_FOUNDATION-ASTRANPSDEVELOPERS | 179 |  |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_FOUNDATION-ASTRANPSDEVELOPERS] ¦ [IRR][Astra NPS Developers] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | FOUNDATION - ASTRA NPS DEVELOPERS | FOUNDATION-ASTRANPSDEVELOPERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 130 | 195
TAP-111692_FOUNDATION-TOOLSRULES | 180 |  |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_FOUNDATION-TOOLSRULES] ¦ [IRR][Tools Rules] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | FOUNDATION - TOOLS RULES | FOUNDATION-TOOLSRULES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 130 | 195
TAP-111692_SHAREDSERVICES-INBETWEENERS | 181 |  |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_SHAREDSERVICES-INBETWEENERS] ¦ [IRR][Inbetweeners] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | SHARED SERVICES - INBETWEENERS | SHAREDSERVICES-INBETWEENERS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 130 | 195
TAP-111692_SHAREDSERVICES-TRIPLETEA | 182 |  |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_SHAREDSERVICES-TRIPLETEA] ¦ [IRR][Triple Tea] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | SHARED SERVICES - TRIPLE TEA | SHAREDSERVICES-TRIPLETEA |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 130 | 195
TAP-112231 | 183 | TAP-121104 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 40 | 50 | Feature Estimation
TAP-112231_SHAREDSERVICES-ASTRANPSVALIDATORS | 184 |  |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_SHAREDSERVICES-ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | SHARED SERVICES - ASTRA NPS VALIDATORS | SHAREDSERVICES-ASTRANPSVALIDATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 40 | 50
TAP-112233 | 185 | TAP-121104 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112233_SHAREDSERVICES-ASTRANPSVALIDATORS | 186 |  |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_SHAREDSERVICES-ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | SHARED SERVICES - ASTRA NPS VALIDATORS | SHAREDSERVICES-ASTRANPSVALIDATORS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 20
TAP-112234 | 187 | TAP-121104 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 40 | Feature Estimation
TAP-112234_FOUNDATION-TOOLSRULES | 188 |  |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_FOUNDATION-TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | FOUNDATION - TOOLS RULES | FOUNDATION-TOOLSRULES |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 40
TAP-113127 | 189 | TAP-121104 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
| 190 |  |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 |  | Defect | Investigation |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-115187 | 191 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 |  | 58 | 1 hr | 1 hr | -29 | 100% | 0 | 0
TAP-122269 | 192 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 11 |  | 0 | 1 hr | 1 hr | 11 | 0% | 0 | 0 | Feature Estimation
| 193 |  |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 |  | Defect | Investigation |  |  |  |  | 21 |  | 0 | 1 hr | 1 hr | 21 | 0% | 0 | 0
TAP-64314 | 194 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 |  | 64.5 | 1 hr | 1 hr | -32.25 | 100%
TAP-64315 | 195 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 |  | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 196 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 |  | 44 | 1 hr | 1 hr | -22 | 100%
| 197 |  |  | 06.01.03.00.00.00.00.00 |  | RAS-9107 |  | Defect | Open |  |  |  |  | 42 |  | 86 |  | 1 hr | -44 | 0%
TAP-64315 | 198 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 |  | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 199 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 |  | 44 | 1 hr | 1 hr | -22 | 100%
| 200 |  |  | 06.01.04.00.00.00.00.00 |  | RAS-10590 |  | Defect | Confirmed |  |  |  |  | 42 |  | 86 |  | 1 hr | -44 | 0%
TAP-94573 | 201 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 |  | 26 | 1 hr | 1 hr | -13 | 100%
TAP-109680 | 202 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 |  | 0 | 1 hr | 1 hr | 3 | 0% |  |  | Feature Estimation
| 203 |  |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 |  | Defect | In progress |  |  |  |  | 3 |  | 0 |  | 1 hr | 3 | 0%
TAP-124484 | 204 |  |  | 06.04.04.02.01.00.00.00 |  | TAP-124484 | [TAP-124484] ¦ [RAS-4536] [Stellars] Undefined response to SIM/Instrument Memory Error | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111760 | 205 | TAP-111763 | TAP-94739, TAP-111559, TAP-111834, TAP-95800, TAP-120096, TAP-111719, TAP-117678, TAP-95983, TAP-111731, TAP-111555, TAP-111556, TAP-111751, TAP-111730, TAP-111554, TAP-116286, TAP-111750, TAP-111749, TAP-111724, TAP-111722, TAP-112119, TAP-111569, TAP-103448, TAP-111723, TAP-94966, TAP-112076, TAP-94125, TAP-111721, TAP-111740, TAP-111565, TAP-112012, TAP-112077, TAP-120097, TAP-123834 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 206 | TAP-113104 | TAP-111760 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111763_SHAREDSERVICES-SEAMLESS | 207 |  |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SHAREDSERVICES-SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | SHARED SERVICES - SEAMLESS | SHAREDSERVICES-SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-113104 | 208 | TAP-113105 | TAP-111747, TAP-111772, TAP-111838, TAP-111925, TAP-104213, TAP-111656, TAP-111865, TAP-112080, TAP-111775, TAP-111842, TAP-111773, TAP-111642, TAP-111774, TAP-112113, TAP-111763 | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 209 | TAP-111765 | TAP-113104 | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113105_SHAREDSERVICES-SEAMLESS | 210 |  |  | 07.04.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SHAREDSERVICES-SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | SHARED SERVICES - SEAMLESS | SHAREDSERVICES-SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-111765 | 211 | TAP-111768 | TAP-111753, TAP-111754, TAP-111756, TAP-111757, TAP-111758, TAP-111759, TAP-111761, TAP-110382, TAP-111762, TAP-111748, TAP-111764, TAP-111766, TAP-112082, TAP-112093, TAP-112094, TAP-113105 | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 212 | TAP-111769 | TAP-111765 | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 213 | TAP-111767 | TAP-111768 | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 214 | TAP-111900 | TAP-111769 | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111767_SHAREDSERVICES-SEAMLESS | 215 |  |  | 07.08.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SHAREDSERVICES-SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | SHARED SERVICES - SEAMLESS | SHAREDSERVICES-SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-113101 | 216 | TAP-113102 | TAP-113100 | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 217 | TAP-113103 | TAP-113101 | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 218 | TAP-121104 | TAP-113102 | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113103_SHAREDSERVICES-SEAMLESS | 219 |  |  | 07.11.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SHAREDSERVICES-SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | SHARED SERVICES - SEAMLESS | SHAREDSERVICES-SEAMLESS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 15
TAP-121104 | 220 |  | TAP-111900, TAP-112042, TAP-111692, TAP-112231, TAP-112233, TAP-112234, TAP-113127, TAP-113103 | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94968 | 221 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111726 | 222 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111726_COREINSTRUMENTS | 223 |  |  | 08.02.02.01.00.00.00.00 | TAP-111726 | TAP-111947 | [TAP-111726_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Bending radius | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 20 | 30
TAP-111727 | 224 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111727_COREINSTRUMENTS | 225 |  |  | 08.02.03.01.00.00.00.00 | TAP-111727 | TAP-111948 | [TAP-111727_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Validation | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111729 | 226 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111729_COREINSTRUMENTS | 227 |  |  | 08.02.04.01.00.00.00.00 | TAP-111729 | TAP-111949 | [TAP-111729_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Use-life count using damage model | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-94967 | 228 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111733 | 229 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111733_COREINSTRUMENTS | 230 |  |  | 08.03.01.00.00.00.00.00 | TAP-111733 | TAP-111908 | [TAP-111733_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore user clamp force setting | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111734 | 231 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111734_COREINSTRUMENTS | 232 |  |  | 08.04.01.00.00.00.00.00 | TAP-111734 | TAP-111911 | [TAP-111734_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore haptic force regulation / feedback for clamp force | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111735 | 233 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111735_COREINSTRUMENTS | 234 |  |  | 08.05.01.00.00.00.00.00 | TAP-111735 | TAP-111912 | [TAP-111735_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore clamp+cut control for Needle Cutting Grasper | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-111570 | 235 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111570_COREINSTRUMENTS | 236 |  |  | 08.06.01.00.00.00.00.00 | TAP-111570 | TAP-111798 | [TAP-111570_COREINSTRUMENTS] ¦ [IRR][Core Instruments] UX Update for Paddle to Cut Command Mapping | Feature Estimation | Open | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0
TAP-112107 | 237 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-112107_COREINSTRUMENTS | 238 |  |  | 09.01.02.01.00.00.00.00 | TAP-112107 | TAP-112114 | [TAP-112107_COREINSTRUMENTS] ¦ Grasper SKU Characterization at Frictional Max/Min | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 15 | 30
TAP-111934 | 239 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 240 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112085_COREINSTRUMENTS | 241 |  |  | 09.01.04.01.00.00.00.00 | TAP-112085 | TAP-112090 | [TAP-112085_COREINSTRUMENTS] ¦ Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 10
TAP-112084 | 242 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112084_COREINSTRUMENTS | 243 |  |  | 09.01.05.01.00.00.00.00 | TAP-112084 | TAP-112088 | [TAP-112084_COREINSTRUMENTS] ¦ Regress Articulation KPI's on Graspers for Pretension | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 10 | 10
TAP-112101 | 244 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 160 | 320 | Feature Estimation
TAP-112101_COREINSTRUMENTS | 245 |  |  | 09.01.06.01.00.00.00.00 | TAP-112101 | TAP-112103 | [TAP-112101_COREINSTRUMENTS] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 160 | 320
TAP-112086 | 246 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 50 | Feature Estimation
TAP-112086_COREINSTRUMENTS | 247 |  |  | 09.01.07.01.00.00.00.00 | TAP-112086 | TAP-112091 | [TAP-112086_COREINSTRUMENTS] ¦ Requirement and Verification Engineering for Multi-SKU Release | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 25 | 50
TAP-112087 | 248 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-112087_COREINSTRUMENTS | 249 |  |  | 09.01.08.01.00.00.00.00 | TAP-112087 | TAP-112092 | [TAP-112087_COREINSTRUMENTS] ¦ Product SW Development for Rest of Graspers | Feature Estimation | Done | CORE INSTRUMENTS | COREINSTRUMENTS |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100% | 50 | 100
TAP-112095 | 250 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-106203 | 251 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-100791 | 252 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 |  | 0 | 1 hr | 1 hr | 0 | 100%

## Log
DataTimeStamp | Event | Data

## Summary
Resource Names | Sum FDR
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
SHAREDSERVICES-ANIMATORS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
FOUNDATION-FRED
COREINSTRUMENTS
FOUNDATION-FRED
ADVANCEDINSTRUMENTS-I2E
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-JACOBIANS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-JACOBIANS
SHAREDSERVICES-CASTLEBLACK
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-JACOBIANS
ADVANCEDINSTRUMENTS-ORGANELLES
SHAREDSERVICES-INBETWEENERS
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-JACOBIANS
ADVANCEDINSTRUMENTS-ORGANELLES
SHAREDSERVICES-INBETWEENERS
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-I2E
ADVANCEDINSTRUMENTS-ORGANELLES
SHAREDSERVICES-CASTLEBLACK
FOUNDATION-CLASSY2
FOUNDATION-BOOSTERS
SHAREDSERVICES-INBETWEENERS
SHAREDSERVICES-CASTLEBLACK
ADVANCEDINSTRUMENTS-ORGANELLES
ADVANCEDINSTRUMENTS-I2E
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-I2E
ADVANCEDINSTRUMENTS-ORGANELLES
RELEASEDPRODUCTENGINEERING-DRUSHTI
ADVANCEDINSTRUMENTS-PIXELPOETS
ADVANCEDINSTRUMENTS-ORGANELLES
FOUNDATION-FRED
ADVANCEDINSTRUMENTS-PIXELPOETS
ADVANCEDINSTRUMENTS-ORGANELLES
RELEASEDPRODUCTENGINEERING-DRUSHTI
ADVANCEDINSTRUMENTS-PIXELPOETS
ADVANCEDINSTRUMENTS-ORGANELLES
RELEASEDPRODUCTENGINEERING-DRUSHTI
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-I2E
ADVANCEDINSTRUMENTS-ORGANELLES
ADVANCEDINSTRUMENTS-PIXELPOETS
ADVANCEDINSTRUMENTS-JACOBIANS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
ADVANCEDINSTRUMENTS-BUGHUNTERS
ADVANCEDINSTRUMENTS-I2E
ADVANCEDINSTRUMENTS-JACOBIANS
ADVANCEDINSTRUMENTS-ORGANELLES
ADVANCEDINSTRUMENTS-SCRUMBLEDORES
ADVANCEDINSTRUMENTS-SUNRISERS
ADVANCEDINSTRUMENTS-TEAMBD
SHAREDSERVICES-COSSACKS
SHAREDSERVICES-BUILDERS
FOUNDATION-ASTRANPSDEVELOPERS
FOUNDATION-TOOLSRULES
SHAREDSERVICES-INBETWEENERS
SHAREDSERVICES-TRIPLETEA
SHAREDSERVICES-ASTRANPSVALIDATORS
SHAREDSERVICES-ASTRANPSVALIDATORS
FOUNDATION-TOOLSRULES
SHAREDSERVICES-SEAMLESS
SHAREDSERVICES-SEAMLESS
SHAREDSERVICES-SEAMLESS
SHAREDSERVICES-SEAMLESS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS