## Project
Selector | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Index | Parent Feature | Key | Task Name | Issue Type | Status | ART | Resource Names | Task Type | Source | Σ Total SP | Σ Done SP | Focus Duration | Low-Risk Duration | Remaining SP | % Complete | Σ Realistic Estimate | Σ Worst Case Estimate | RefinementLevel
TAP-94739 | 3 | TAP-111760 not found!!! |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 | 24 | 1 hr | 1 hr | -12 | 100% | 40 | 50 | Story Points
TAP-97668 | 10 | TAP-120097 not found!!! | TAP-94739 not found!!! | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  |  |  | 32.5 | 65 | 1 hr | 1 hr | -32.5 | 100% | 6 | 8 | Story Points
TAP-120097 | 22 | TAP-111760 not found!!! | TAP-97668 not found!!! | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | PROPOSED |  |  |  |  | 28.5 | 0 | 1 hr | 1 hr | 28.5 | 0% | 0 | 0 | Story Points
TAP-111730 | 32 | TAP-124062 not found!!! | TAP-106315 not found!!! | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 28 | 20 | 1 hr | 1 hr | 8 | 0% | 30 | 40 | Story Points
TAP-111730_COREINSTRUMENTS | 33 | TAP-111730 not found!!! |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 | [TAP-111730_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Fix force generation at clamp initiation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 28 | 48 | 28 | 33.6 | -20 | 100% | 30 | 40 | Story Points
TAP-111731 | 43 | TAP-111760 not found!!! |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 50 | Feature Estimation
TAP-111731_COREINSTRUMENTS | 44 | TAP-111731 not found!!! |  | 01.02.02.01.00.00.00.00 | TAP-111731 | TAP-111906 | [TAP-111731_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce force variation when articulating during clamp | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 50 | 0 | 100% | 50 | 50 | Feature Estimation
TAP-111731_ANIMATORS | 45 | TAP-111731 not found!!! |  | 01.02.02.02.00.00.00.00 | TAP-111731 | TAP-112037 | [TAP-111731_ANIMATORS] ¦ [Animators] Reduce Force Variation when articulating during clamp | Feature Estimation | Open | Shared Services - Animators | ANIMATORS |  |  | 0 | 0 | 50 | 50 | 0 | 0% | 50 | 50 | Feature Estimation
TAP-124062 | 46 |  | TAP-111730 not found!!! | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112076 | 48 | TAP-111760 not found!!! |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112076_COREINSTRUMENTS | 49 | TAP-112076 not found!!! |  | 01.03.01.01.00.00.00.00 | TAP-112076 | TAP-112078 | [TAP-112076_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Damage Modeling Documentation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-94966 | 50 | TAP-111760 not found!!! | TAP-111562 not found!!! | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | In progress |  |  |  |  | 37 | 25 | 1 hr | 1 hr | 12 | 0% | 45 | 78 | Story Points
TAP-94966_COREINSTRUMENTS | 51 | TAP-94966 not found!!! |  | 01.03.02.01.00.00.00.00 | TAP-94966 | TAP-111781 | [TAP-94966_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Develop a Jaw Estimator for Shears | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 37 | 62 | 37 | 44.4 | -25 | 100% | 45 | 78 | Story Points
TAP-111554 | 63 | TAP-111760 not found!!! |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 | 0 | 1 hr | 1 hr | 7 | 0% | 24 | 48 | Story Points
TAP-111554_COREINSTRUMENTS | 64 | TAP-111554 not found!!! |  | 01.03.03.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 7 | 7 | 7 | 8.4 | 0 | 100% | 24 | 48 | Story Points
TAP-111555 | 67 | TAP-111760 not found!!! |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-111555_COREINSTRUMENTS | 68 | TAP-111555 not found!!! |  | 01.03.04.01.00.00.00.00 | TAP-111555 | TAP-111783 | [TAP-111555_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 12 | 18 | 0 | 100% | 12 | 18 | Feature Estimation
TAP-112012 | 69 | TAP-111760 not found!!! |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-112012_COREINSTRUMENTS | 70 | TAP-112012 not found!!! |  | 01.03.05.01.00.00.00.00 | TAP-112012 | TAP-112015 | [TAP-112012_COREINSTRUMENTS] ¦ [IRR][Enhancement] Cutting Control Enhancements | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 12 | 18 | 0 | 100% | 12 | 18 | Feature Estimation
TAP-111569 | 72 | TAP-111760 not found!!! |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 12 | Feature Estimation
TAP-111569_COREINSTRUMENTS | 73 | TAP-111569 not found!!! |  | 01.03.07.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Integration, Testing, Demo, Design Review | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 12 | 0 | 100% | 8 | 12 | Feature Estimation
TAP-111565 | 74 | TAP-111760 not found!!! |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 20 | Feature Estimation
TAP-111565_COREINSTRUMENTS | 75 | TAP-111565 not found!!! |  | 01.03.08.01.00.00.00.00 | TAP-111565 | TAP-111793 | [TAP-111565_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 5 | 20 | 0 | 100% | 5 | 20 | Feature Estimation
TAP-111556 | 77 | TAP-111760 not found!!! | TAP-94966 not found!!! | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111556_COREINSTRUMENTS | 78 | TAP-111556 not found!!! |  | 01.03.09.01.00.00.00.00 | TAP-111556 | TAP-111784 | [TAP-111556_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111559 | 79 | TAP-111760 not found!!! | TAP-111556 not found!!! | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111559_COREINSTRUMENTS | 80 | TAP-111559 not found!!! |  | 01.03.10.01.00.00.00.00 | TAP-111559 | TAP-111785 | [TAP-111559_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-112077 | 82 | TAP-111760 not found!!! | TAP-111562 not found!!! | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 61 | 13 | 1 hr | 1 hr | 48 | 0% | 20 | 30 | Story Points
TAP-112077_COREINSTRUMENTS | 83 | TAP-112077 not found!!! |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Articulation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 61 | 74 | 61 | 73.2 | -13 | 100% | 20 | 30 | Story Points
TAP-120096 | 100 | TAP-111760 not found!!! |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-103448 | 102 | TAP-111760 not found!!! |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 | 5 | 1 hr | 1 hr | 9 | 0% | 0 | 0 | Story Points
TAP-116286 | 109 | TAP-111760 not found!!! |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0 | Story Points
TAP-95983 | 116 | TAP-111760 not found!!! |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 106 | 35 | 1 hr | 1 hr | 71 | 0% | 41 | 73 | Story Points
TAP-95983_FRED | 128 | TAP-95983 not found!!! |  | 01.05.04.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_FRED] ¦ [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 125 | 156 | 125 | 150 | -31 | 124.8% | 82 | 146 | Story Points
TAP-111719 | 147 | TAP-111760 not found!!! | TAP-124116 not found!!! | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 | 2 | 1 hr | 1 hr | 3 | 0% | 15 | 22 | Story Points
TAP-111719_COREINSTRUMENTS | 148 | TAP-111719 not found!!! |  | 01.05.05.01.00.00.00.00 | TAP-111719 | TAP-111916 | [TAP-111719_COREINSTRUMENTS] ¦ [IRR][Core Instruments] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 5 | 2 | 5 | 6 | 3 | 40% | 15 | 22 | Story Points
TAP-111719_FRED | 149 | TAP-111719 not found!!! |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112039 | [TAP-111719_FRED] ¦ [IRR][Fred] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 5 | 2 | 5 | 6 | 3 | 40% | 15 | 22 | Story Points
TAP-111719_I2E | 150 | TAP-111719 not found!!! |  | 01.05.05.03.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_I2E] ¦ [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 5 | 7 | 5 | 6 | -2 | 100% | 15 | 22 | Story Points
TAP-111721 | 153 | TAP-111760 not found!!! |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 | 20.5 | 1 hr | 1 hr | 4 | 0% | 27 | 30 | Story Points
TAP-111721_COREINSTRUMENTS | 154 | TAP-111721 not found!!! |  | 01.05.06.01.00.00.00.00 | TAP-111721 | TAP-111917 | [TAP-111721_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI14) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 24.5 | 45 | 24.5 | 29.4 | -20.5 | 100% | 27 | 30 | Story Points
TAP-111722 | 165 | TAP-111760 not found!!! |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111722_COREINSTRUMENTS | 166 | TAP-111722 not found!!! |  | 01.05.07.01.00.00.00.00 | TAP-111722 | TAP-111918 | [TAP-111722_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI15) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-111723 | 167 | TAP-111760 not found!!! |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 27 | 30 | Feature Estimation
TAP-111723_COREINSTRUMENTS | 168 | TAP-111723 not found!!! |  | 01.05.08.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI16) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-111724 | 170 | TAP-111760 not found!!! |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111724_COREINSTRUMENTS | 171 | TAP-111724 not found!!! |  | 01.05.09.01.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-112119 | 172 | TAP-111760 not found!!! |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112119_COREINSTRUMENTS | 173 | TAP-112119 not found!!! |  | 01.05.10.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119_COREINSTRUMENTS] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-94125 | 175 | TAP-111760 not found!!! |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | Accepted |  |  |  |  | 77 | 0 | 1 hr | 1 hr | 77 | 0% | 50 | 70 | Story Points
TAP-95800 | 190 | TAP-111760 not found!!! |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | Accepted |  |  |  |  | 31 | 2 | 1 hr | 1 hr | 29 | 0% | 15 | 35 | Story Points
TAP-111740 | 201 | TAP-111760 not found!!! |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | PROPOSED |  |  |  |  | 28 | 0 | 1 hr | 1 hr | 28 | 0% | 60 | 80 | Story Points
TAP-111740_COREINSTRUMENTS | 202 | TAP-111740 not found!!! |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 28 | 28 | 28 | 33.6 | 0 | 100% | 60 | 80 | Story Points
TAP-111749 | 211 | TAP-111760 not found!!! |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111749_COREINSTRUMENTS | 212 | TAP-111749 not found!!! |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111750 | 214 | TAP-111760 not found!!! |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 35 | Feature Estimation
TAP-111750_COREINSTRUMENTS | 215 | TAP-111750 not found!!! |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Procedure Manager SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 35 | 0 | 100% | 15 | 35 | Feature Estimation
TAP-111751 | 216 | TAP-111760 not found!!! |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 45 | Feature Estimation
TAP-111751_COREINSTRUMENTS | 217 | TAP-111751 not found!!! |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 28 | 45 | 0 | 100% | 28 | 45 | Feature Estimation
TAP-117678 | 218 | TAP-111760 not found!!! |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111834 | 220 | TAP-111760 not found!!! | TAP-113995 not found!!! | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-111834_JACOBIANS | 221 | TAP-111834 not found!!! |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_JACOBIANS] ¦ Support Kinematic Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-111747 | 224 | TAP-113104 not found!!! |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-111747_COREINSTRUMENTS | 225 | TAP-111747 not found!!! |  | 02.01.01.01.00.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 100 | 0 | 100% | 50 | 100 | Feature Estimation
TAP-111772 | 227 | TAP-113104 not found!!! |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111772_COREINSTRUMENTS | 228 | TAP-111772 not found!!! |  | 02.02.01.01.00.00.00.00 | TAP-111772 | TAP-111965 | [TAP-111772_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-111773 | 229 | TAP-113104 not found!!! |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 65 | Feature Estimation
TAP-111773_COREINSTRUMENTS | 230 | TAP-111773 not found!!! |  | 02.02.02.01.00.00.00.00 | TAP-111773 | TAP-111966 | [TAP-111773_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW + Test Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 65 | 0 | 100% | 50 | 65 | Feature Estimation
TAP-111838 | 232 | TAP-113104 not found!!! |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111838_COREINSTRUMENTS | 233 | TAP-111838 not found!!! |  | 02.03.01.01.00.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-104213 | 234 | TAP-113104 not found!!! |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 45 | Feature Estimation
TAP-104213_COREINSTRUMENTS | 235 | TAP-104213 not found!!! |  | 02.03.02.01.00.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 45 | 0 | 100% | 15 | 45 | Feature Estimation
TAP-111842 | 236 | TAP-113104 not found!!! | TAP-111838 not found!!! | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111842_COREINSTRUMENTS | 237 | TAP-111842 not found!!! |  | 02.03.03.01.00.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111774 | 239 | TAP-113104 not found!!! |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 0% | 20 | 34 | Story Points
TAP-111774_COREINSTRUMENTS | 240 | TAP-111774 not found!!! |  | 02.04.01.01.00.00.00.00 | TAP-111774 | TAP-111970 | [TAP-111774_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 9 | 18 | 9 | 10.8 | -9 | 100% | 20 | 34 | Story Points
TAP-111774_JACOBIANS | 241 | TAP-111774 not found!!! |  | 02.04.01.02.00.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 9 | 27 | 9 | 10.8 | -18 | 100% | 20 | 34 | Story Points
TAP-111774_CASTLEBLACK | 242 | TAP-111774 not found!!! |  | 02.04.01.03.00.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774_CASTLEBLACK] ¦ [IRR][Castle Black] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 9 | 27 | 9 | 10.8 | -18 | 300% | 20 | 34 | Story Points
TAP-112080 | 248 | TAP-113104 not found!!! | TAP-111774 not found!!! | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 15 | 0 | 1 hr | 1 hr | 15 | 0% | 37 | 63 | Story Points
TAP-112080_COREINSTRUMENTS | 249 | TAP-112080 not found!!! |  | 02.04.02.01.00.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 15 | 15 | 15 | 18 | 0 | 100% | 37 | 63 | Story Points
TAP-112080_JACOBIANS | 250 | TAP-112080 not found!!! |  | 02.04.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 15 | 30 | 15 | 18 | -15 | 100% | 37 | 63 | Story Points
TAP-112080_ORGANELLES | 251 | TAP-112080 not found!!! |  | 02.04.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_ORGANELLES] ¦ [IRR][Organelles] UFSW - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 15 | 45 | 15 | 18 | -30 | 100% | 37 | 63 | Story Points
TAP-112080_INBETWEENERS | 252 | TAP-112080 not found!!! |  | 02.04.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_INBETWEENERS] ¦ [IRR][Inbetweeners] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 15 | 60 | 15 | 18 | -45 | 100% | 37 | 63 | Story Points
TAP-111775 | 256 | TAP-113104 not found!!! | TAP-112080 not found!!! | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 | 0 | 1 hr | 1 hr | 1 | 0% | 45 | 75 | Feature Estimation
TAP-111775_COREINSTRUMENTS | 257 | TAP-111775 not found!!! |  | 02.04.03.01.00.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 1 | 1 | 45 | 75 | 0 | 100% | 45 | 75 | Feature Estimation
TAP-111775_JACOBIANS | 258 | TAP-111775 not found!!! |  | 02.04.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 2 | 45 | 75 | -1 | 100% | 45 | 75 | Feature Estimation
TAP-111775_ORGANELLES | 259 | TAP-111775 not found!!! |  | 02.04.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_ORGANELLES] ¦ [IRR][Organelles] UFSW - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 1 | 3 | 45 | 75 | -2 | 100% | 45 | 75 | Feature Estimation
TAP-111775_INBETWEENERS | 260 | TAP-111775 not found!!! |  | 02.04.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_INBETWEENERS] ¦ [IRR][Inbetweeners] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 1 | 4 | 45 | 75 | -3 | 100% | 45 | 75 | Feature Estimation
TAP-123862 | 263 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 27 | 0 | 1 hr | 1 hr | 27 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 274 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 26 | 0 | 1 hr | 1 hr | 26 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 288 | TAP-113104 not found!!! |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 170 | 325 | Feature Estimation
TAP-111642_COREINSTRUMENTS | 289 | TAP-111642 not found!!! |  | 02.05.03.01.00.00.00.00 | TAP-111642 | TAP-111941 | [TAP-111642_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_I2E | 290 | TAP-111642 not found!!! |  | 02.05.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111642_I2E] ¦ [IRR][I2E] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_ORGANELLES | 291 | TAP-111642 not found!!! |  | 02.05.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111642_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_CASTLEBLACK | 292 | TAP-111642 not found!!! |  | 02.05.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111642_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 170 | 325 | 0 | 0% | 170 | 325 | Feature Estimation
TAP-111656 | 293 | TAP-113104 not found!!! |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_CLASSY2 | 294 | TAP-111656 not found!!! |  | 02.05.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_CLASSY2] ¦ [IRR][CLASSY 2] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_BOOSTERS | 295 | TAP-111656 not found!!! |  | 02.05.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_BOOSTERS] ¦ [IRR][Boosters] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_INBETWEENERS | 296 | TAP-111656 not found!!! |  | 02.05.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_INBETWEENERS] ¦ [IRR][Inbetweeners] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_CASTLEBLACK | 297 | TAP-111656 not found!!! |  | 02.05.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 151 | 278 | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_ORGANELLES | 298 | TAP-111656 not found!!! |  | 02.05.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_I2E | 299 | TAP-111656 not found!!! |  | 02.05.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_I2E] ¦ [IRR][I2E] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_COREINSTRUMENTS | 300 | TAP-111656 not found!!! |  | 02.05.04.07.00.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Productization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111925 | 302 | TAP-113104 not found!!! |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111925_COREINSTRUMENTS | 303 | TAP-111925 not found!!! |  | 02.06.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-112113 | 304 | TAP-113104 not found!!! |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112113_COREINSTRUMENTS | 305 | TAP-112113 not found!!! |  | 02.06.02.01.00.00.00.00 | TAP-112113 | TAP-112123 | [TAP-112113_COREINSTRUMENTS] ¦ [IRR] Verification plan for regression on SKU's | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111865 | 307 | TAP-113104 not found!!! |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113111 | 309 | TAP-111695 not found!!! |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 313 | TAP-111695 not found!!! |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 317 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 | 18 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-114689 | 325 | TAP-111687 not found!!! |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  |  |  | 15 | 30 | 1 hr | 1 hr | -15 | 100% | 0 | 0 | Story Points
TAP-90375 | 332 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 | 0 | 1 hr | 1 hr | 9 | 0% |  |  | Story Points
TAP-111861 | 338 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 34 | 46 | Story Points
TAP-111861_I2E | 339 | TAP-111861 not found!!! |  | 02.07.03.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_I2E] ¦ [IRR][I2E] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 3 | 3 | 3 | 3.6 | 0 | 100% | 34 | 46 | Story Points
TAP-111861_ORGANELLES | 340 | TAP-111861 not found!!! |  | 02.07.03.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_ORGANELLES] ¦ [IRR][Organelles] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 3 | 6 | 3 | 3.6 | -3 | 100% | 34 | 46 | Story Points
TAP-111861_DRUSHTI | 341 | TAP-111861 not found!!! |  | 02.07.03.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_DRUSHTI] ¦ [IRR][Drushti] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 3 | 9 | 3 | 3.6 | -6 | 100% | 34 | 46 | Story Points
TAP-111687 | 343 |  | TAP-114689 not found!!! | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111687_PIXELPOETS | 344 | TAP-111687 not found!!! |  | 02.07.03.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_PIXELPOETS] ¦ [IRR] [Pixel Poets] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 28 | 46 | 0 | 100% | 28 | 46 | Feature Estimation
TAP-111687_ORGANELLES | 345 | TAP-111687 not found!!! |  | 02.07.03.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_ORGANELLES] ¦ [IRR] [Organelles] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 28 | 46 | 0 | 100% | 28 | 46 | Feature Estimation
TAP-111687_FRED | 346 | TAP-111687 not found!!! |  | 02.07.03.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_FRED] ¦ [IRR] [Fred] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 0 | 0 | 28 | 46 | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111689 | 347 |  | TAP-113123 not found!!! | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 32 | 48 | Feature Estimation
TAP-111689_PIXELPOETS | 348 | TAP-111689 not found!!! |  | 02.07.03.04.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111689_PIXELPOETS] ¦ [IRR] [Pixel Poets] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111689_ORGANELLES | 349 | TAP-111689 not found!!! |  | 02.07.03.04.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-111689_ORGANELLES] ¦ [IRR] [Organelles] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111689_DRUSHTI | 350 | TAP-111689 not found!!! |  | 02.07.03.04.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-111689_DRUSHTI] ¦ [IRR] [Drushti] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111695 | 351 |  | TAP-113123 not found!!! | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 24 | 46 | Feature Estimation
TAP-111695_PIXELPOETS | 352 | TAP-111695 not found!!! |  | 02.07.03.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_PIXELPOETS] ¦ [IRR][Pixel Poets] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111695_ORGANELLES | 353 | TAP-111695 not found!!! |  | 02.07.03.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_ORGANELLES] ¦ [IRR][Organelles] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111695_DRUSHTI | 354 | TAP-111695 not found!!! |  | 02.07.03.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_DRUSHTI] ¦ [IRR][Drushti] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111753 | 357 | TAP-111765 not found!!! | TAP-94125 not found!!! | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 30 | 50 | Feature Estimation
TAP-111753_COREINSTRUMENTS | 358 | TAP-111753 not found!!! |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 | [TAP-111753_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Homing Manager | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 30 | 50 | 0 | 100% | 30 | 50 | Feature Estimation
TAP-111754 | 359 | TAP-111765 not found!!! | TAP-95800 not found!!! | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 10 | 15 | Feature Estimation
TAP-111754_COREINSTRUMENTS | 360 | TAP-111754 not found!!! |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 | [TAP-111754_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111756 | 362 | TAP-111765 not found!!! | TAP-111740 not found!!! | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 35 | 45 | Feature Estimation
TAP-111756_COREINSTRUMENTS | 363 | TAP-111756 not found!!! |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Teleoperation Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 35 | 45 | 0 | 100% | 35 | 45 | Feature Estimation
TAP-111757 | 365 | TAP-111765 not found!!! | TAP-111749 not found!!! | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111757_COREINSTRUMENTS | 366 | TAP-111757 not found!!! |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111758 | 367 | TAP-111765 not found!!! | TAP-111750 not found!!! | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111758_COREINSTRUMENTS | 368 | TAP-111758 not found!!! |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 | [TAP-111758_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Procedure Manager SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-111759 | 369 | TAP-111765 not found!!! | TAP-111751 not found!!! | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111759_COREINSTRUMENTS | 370 | TAP-111759 not found!!! |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 | [TAP-111759_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Estimator SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111761 | 372 | TAP-111765 not found!!! | TAP-111753 not found!!! | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 30 | Feature Estimation
TAP-111761_COREINSTRUMENTS | 373 | TAP-111761 not found!!! |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Homing Manager Sub-SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 25 | 30 | 0 | 100% | 25 | 30 | Feature Estimation
TAP-110382 | 374 | TAP-111765 not found!!! | TAP-111754 not found!!! | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 8 | Feature Estimation
TAP-110382_COREINSTRUMENTS | 375 | TAP-110382 not found!!! |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 5 | 8 | 0 | 100% | 5 | 8 | Feature Estimation
TAP-111762 | 376 | TAP-111765 not found!!! | TAP-111756 not found!!! | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 25 | Feature Estimation
TAP-111762_COREINSTRUMENTS | 377 | TAP-111762 not found!!! |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Teleoperation Controller for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 25 | 0 | 100% | 15 | 25 | Feature Estimation
TAP-111748 | 378 | TAP-111765 not found!!! | TAP-111757 not found!!! | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 15 | Feature Estimation
TAP-111748_COREINSTRUMENTS | 379 | TAP-111748 not found!!! |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 15 | 0 | 100% | 8 | 15 | Feature Estimation
TAP-111764 | 380 | TAP-111765 not found!!! | TAP-111758 not found!!! | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111764_COREINSTRUMENTS | 381 | TAP-111764 not found!!! |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Procedure Manager for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111766 | 382 | TAP-111765 not found!!! | TAP-111759 not found!!! | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111766_COREINSTRUMENTS | 383 | TAP-111766 not found!!! |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-112082 | 385 | TAP-111765 not found!!! |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 125 | Feature Estimation
TAP-112082_COREINSTRUMENTS | 386 | TAP-112082 not found!!! |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082_COREINSTRUMENTS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_I2E | 387 | TAP-112082 not found!!! |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_I2E] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_ORGANELLES | 388 | TAP-112082 not found!!! |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_ORGANELLES] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_PIXELPOETS | 389 | TAP-112082 not found!!! |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_JACOBIANS | 390 | TAP-112082 not found!!! |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112093 | 391 | TAP-111765 not found!!! |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 55 | 70 | Feature Estimation
TAP-112093_COREINSTRUMENTS | 392 | TAP-112093 not found!!! |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093_COREINSTRUMENTS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 55 | 70 | 0 | 100% | 55 | 70 | Feature Estimation
TAP-112094 | 393 | TAP-111765 not found!!! |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 87 | 170 | Feature Estimation
TAP-112094_COREINSTRUMENTS | 394 | TAP-112094 not found!!! |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094_COREINSTRUMENTS] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 87 | 170 | 0 | 100% | 87 | 170 | Feature Estimation
TAP-113100 | 396 | TAP-113101 not found!!! |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 200 | 400 | Feature Estimation
TAP-113100_COREINSTRUMENTS | 397 | TAP-113100 not found!!! |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100_COREINSTRUMENTS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 200 | 400 | 0 | 100% | 200 | 400 | Feature Estimation
TAP-111900 | 399 | TAP-121104 not found!!! | TAP-111767 not found!!! | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 79 | 152 | Feature Estimation
TAP-111900_COREINSTRUMENTS | 400 | TAP-111900 not found!!! |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900_COREINSTRUMENTS] ¦ [M-IRR][Core Instrument] Formal Software Verification activities | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_BUGHUNTERS | 401 | TAP-111900 not found!!! |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_BUGHUNTERS] ¦ [M-IRR][Bug Hunters] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Bug Hunters | BUGHUNTERS |  |  | 0 | 0 | 79 | 152 | 0 | 0% | 79 | 152 | Feature Estimation
TAP-111900_I2E | 402 | TAP-111900 not found!!! |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-111900_I2E] ¦ [M-IRR][I2E] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_JACOBIANS | 403 | TAP-111900 not found!!! |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_JACOBIANS] ¦ [M-IRR][Jacobians] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_ORGANELLES | 404 | TAP-111900 not found!!! |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_ORGANELLES] ¦ [M-IRR][Organelles] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_SCRUMBLEDORES | 406 | TAP-111900 not found!!! |  | 05.01.07.00.00.00.00.00 | TAP-111900 | TAP-112683 | [TAP-111900_SCRUMBLEDORES] ¦ [M-IRR][Scrumbledores] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_SUNRISERS | 407 | TAP-111900 not found!!! |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_SUNRISERS] ¦ [M-IRR][Sunrisers] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_TEAMBD | 408 | TAP-111900 not found!!! |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_TEAMBD] ¦ [M-IRR][TeamBD] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_COSSACKS | 410 | TAP-111900 not found!!! |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_COSSACKS] ¦ [M-IRR][Cossacks] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-112042 | 412 | TAP-121104 not found!!! |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 22 | 30 | Feature Estimation
TAP-112042_BUILDERS | 413 | TAP-112042 not found!!! |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_BUILDERS] ¦ [V3.1][IRR][Builders] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS |  |  | 0 | 0 | 22 | 30 | 0 | 100% | 22 | 30 | Feature Estimation
TAP-111692 | 414 | TAP-121104 not found!!! |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 130 | 195 | Feature Estimation
TAP-111692_ASTRANPSDEVELOPERS | 415 | TAP-111692 not found!!! |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_ASTRANPSDEVELOPERS] ¦ [IRR][Astra NPS Developers] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TOOLSRULES | 416 | TAP-111692 not found!!! |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_TOOLSRULES] ¦ [IRR][Tools Rules] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_INBETWEENERS | 417 | TAP-111692 not found!!! |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_INBETWEENERS] ¦ [IRR][Inbetweeners] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TRIPLETEA | 418 | TAP-111692 not found!!! |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_TRIPLETEA] ¦ [IRR][Triple Tea] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-112231 | 419 | TAP-121104 not found!!! |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 40 | 50 | Feature Estimation
TAP-112231_ASTRANPSVALIDATORS | 420 | TAP-112231 not found!!! |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 40 | 50 | 0 | 100% | 40 | 50 | Feature Estimation
TAP-112233 | 421 | TAP-121104 not found!!! |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112233_ASTRANPSVALIDATORS | 422 | TAP-112233 not found!!! |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-112234 | 423 | TAP-121104 not found!!! |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 40 | Feature Estimation
TAP-112234_TOOLSRULES | 424 | TAP-112234 not found!!! |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 20 | 40 | 0 | 100% | 20 | 40 | Feature Estimation
TAP-113127 | 425 | TAP-121104 not found!!! |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113127 | 428 | TAP-113127 not found!!! |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Defect | Investigation |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-115187 | 429 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 | 58 | 1 hr | 1 hr | -29 | 100% | 0 | 0
TAP-122269 | 444 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 11 | 0 | 1 hr | 1 hr | 11 | 0% | 0 | 0 | Feature Estimation
TAP-122269 | 451 | TAP-122269 not found!!! |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Defect | Investigation |  |  |  |  | 21 | 0 | 0 | 0 | 21 | 0% | 0 | 0 | Feature Estimation
TAP-64314 | 452 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 | 64.5 | 1 hr | 1 hr | -32.25 | 100%
TAP-64315 | 463 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 481 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 44 | 1 hr | 1 hr | -22 | 100%
TAP-64315 | 491 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 509 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 44 | 1 hr | 1 hr | -22 | 100%
TAP-94573 | 542 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 | 26 | 1 hr | 1 hr | -13 | 100%
TAP-109680 | 550 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% |  |  | Feature Estimation
TAP-109680 | 557 | TAP-109680 not found!!! |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Defect | In progress |  |  |  |  | 3 | 0 |  |  | 3 | 0% |  |  | Feature Estimation
TAP-124484 | 558 |  |  | 06.04.04.02.01.00.00.00 |  | TAP-124484 | [TAP-124484] ¦ [RAS-4536] [Stellars] Undefined response to SIM/Instrument Memory Error | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111760 | 560 | TAP-111763 not found!!! | TAP-123834 not found!!! | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 561 | TAP-113104 not found!!! | TAP-111760 not found!!! | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111763_SEAMLESS | 562 | TAP-111763 not found!!! |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-113104 | 563 | TAP-113105 not found!!! | TAP-111763 not found!!! | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 564 | TAP-111765 not found!!! | TAP-113104 not found!!! | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113105_SEAMLESS | 565 | TAP-113105 not found!!! |  | 07.04.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111765 | 566 | TAP-111768 not found!!! | TAP-113105 not found!!! | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 567 | TAP-111769 not found!!! | TAP-111765 not found!!! | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 568 | TAP-111767 not found!!! | TAP-111768 not found!!! | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 569 | TAP-111900 not found!!! | TAP-111769 not found!!! | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111767_SEAMLESS | 570 | TAP-111767 not found!!! |  | 07.08.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-113101 | 571 | TAP-113102 not found!!! | TAP-113100 not found!!! | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 572 | TAP-113103 not found!!! | TAP-113101 not found!!! | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 573 | TAP-121104 not found!!! | TAP-113102 not found!!! | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113103_SEAMLESS | 574 | TAP-113103 not found!!! |  | 07.11.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-121104 | 575 |  | TAP-113103 not found!!! | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94968 | 579 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111726 | 582 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111726_COREINSTRUMENTS | 583 | TAP-111726 not found!!! |  | 08.02.02.01.00.00.00.00 | TAP-111726 | TAP-111947 | [TAP-111726_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Bending radius | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111727 | 584 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111727_COREINSTRUMENTS | 585 | TAP-111727 not found!!! |  | 08.02.03.01.00.00.00.00 | TAP-111727 | TAP-111948 | [TAP-111727_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Validation | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111729 | 586 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111729_COREINSTRUMENTS | 587 | TAP-111729 not found!!! |  | 08.02.04.01.00.00.00.00 | TAP-111729 | TAP-111949 | [TAP-111729_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Use-life count using damage model | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94967 | 588 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111733 | 589 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111733_COREINSTRUMENTS | 590 | TAP-111733 not found!!! |  | 08.03.01.00.00.00.00.00 | TAP-111733 | TAP-111908 | [TAP-111733_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore user clamp force setting | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111734 | 591 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111734_COREINSTRUMENTS | 592 | TAP-111734 not found!!! |  | 08.04.01.00.00.00.00.00 | TAP-111734 | TAP-111911 | [TAP-111734_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore haptic force regulation / feedback for clamp force | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111735 | 593 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111735_COREINSTRUMENTS | 594 | TAP-111735 not found!!! |  | 08.05.01.00.00.00.00.00 | TAP-111735 | TAP-111912 | [TAP-111735_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore clamp+cut control for Needle Cutting Grasper | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111570 | 595 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111570_COREINSTRUMENTS | 596 | TAP-111570 not found!!! |  | 08.06.01.00.00.00.00.00 | TAP-111570 | TAP-111798 | [TAP-111570_COREINSTRUMENTS] ¦ [IRR][Core Instruments] UX Update for Paddle to Cut Command Mapping | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112107 | 600 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-112107_COREINSTRUMENTS | 601 | TAP-112107 not found!!! |  | 09.01.02.01.00.00.00.00 | TAP-112107 | TAP-112114 | [TAP-112107_COREINSTRUMENTS] ¦ Grasper SKU Characterization at Frictional Max/Min | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-111934 | 602 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 603 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112085_COREINSTRUMENTS | 604 | TAP-112085 not found!!! |  | 09.01.04.01.00.00.00.00 | TAP-112085 | TAP-112090 | [TAP-112085_COREINSTRUMENTS] ¦ Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-112084 | 605 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112084_COREINSTRUMENTS | 606 | TAP-112084 not found!!! |  | 09.01.05.01.00.00.00.00 | TAP-112084 | TAP-112088 | [TAP-112084_COREINSTRUMENTS] ¦ Regress Articulation KPI's on Graspers for Pretension | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-112101 | 607 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 160 | 320 | Feature Estimation
TAP-112101_COREINSTRUMENTS | 608 | TAP-112101 not found!!! |  | 09.01.06.01.00.00.00.00 | TAP-112101 | TAP-112103 | [TAP-112101_COREINSTRUMENTS] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 160 | 320 | 0 | 100% | 160 | 320 | Feature Estimation
TAP-112086 | 609 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 50 | Feature Estimation
TAP-112086_COREINSTRUMENTS | 610 | TAP-112086 not found!!! |  | 09.01.07.01.00.00.00.00 | TAP-112086 | TAP-112091 | [TAP-112086_COREINSTRUMENTS] ¦ Requirement and Verification Engineering for Multi-SKU Release | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 25 | 50 | 0 | 100% | 25 | 50 | Feature Estimation
TAP-112087 | 611 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-112087_COREINSTRUMENTS | 612 | TAP-112087 not found!!! |  | 09.01.08.01.00.00.00.00 | TAP-112087 | TAP-112092 | [TAP-112087_COREINSTRUMENTS] ¦ Product SW Development for Rest of Graspers | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 100 | 0 | 100% | 50 | 100 | Feature Estimation
TAP-112095 | 614 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-106203 | 617 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-100791 | 624 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100%

## Log
DataTimeStamp | Event | Data

## Summary
Resource Names | Sum FDR
COREINSTRUMENTS
COREINSTRUMENTS
ANIMATORS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
FRED
COREINSTRUMENTS
FRED
I2E
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
JACOBIANS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
JACOBIANS
CASTLEBLACK
COREINSTRUMENTS
JACOBIANS
ORGANELLES
INBETWEENERS
COREINSTRUMENTS
JACOBIANS
ORGANELLES
INBETWEENERS
COREINSTRUMENTS
I2E
ORGANELLES
CASTLEBLACK
CLASSY2
BOOSTERS
INBETWEENERS
CASTLEBLACK
ORGANELLES
I2E
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
I2E
ORGANELLES
DRUSHTI
PIXELPOETS
ORGANELLES
FRED
PIXELPOETS
ORGANELLES
DRUSHTI
PIXELPOETS
ORGANELLES
DRUSHTI
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
I2E
ORGANELLES
PIXELPOETS
JACOBIANS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
BUGHUNTERS
I2E
JACOBIANS
ORGANELLES
SCRUMBLEDORES
SUNRISERS
TEAMBD
COSSACKS
BUILDERS
ASTRANPSDEVELOPERS
TOOLSRULES
INBETWEENERS
TRIPLETEA
ASTRANPSVALIDATORS
ASTRANPSVALIDATORS
TOOLSRULES
SEAMLESS
SEAMLESS
SEAMLESS
SEAMLESS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS