## Project
Selector | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Index | Parent Feature | Key | Task Name | Issue Type | Status | ART | Resource Names | Task Type | Source | Text19 | Text20 | Duration | Duration1 | Remaining SP | %Complete | Text22 | Text23 | Text24
TAP-94739 | 1 | 2, 202 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 | 24 | 1 hr | 1 hr | -12 | 100% | 40 | 50 | Story Points
TAP-97668 | 2 | 3 | 1 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  |  |  | 32.5 | 65 | 1 hr | 1 hr | -32.5 | 100% | 6 | 8 | Story Points
TAP-120097 | 3 | 202 | 2 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | PROPOSED |  |  |  |  | 28.5 | 0 | 1 hr | 1 hr | 28.5 | 0% | 0 | 0 | Story Points
TAP-111730 | 4 | 202, 9 | TAP-106315 not found | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 28 | 20 | 1 hr | 1 hr | 8 | 0% | 30 | 40 | Story Points
TAP-111730_COREINSTRUMENTS | 5 | 4 |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 | [TAP-111730_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Fix force generation at clamp initiation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 28 | 48 | 28 | 33.6 | -20 | 100% | 30 | 40 | Story Points
TAP-111731 | 6 | 202 |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 50 | Feature Estimation
TAP-111731_COREINSTRUMENTS | 7 | 6 |  | 01.02.02.01.00.00.00.00 | TAP-111731 | TAP-111906 | [TAP-111731_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce force variation when articulating during clamp | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 50 | 0 | 100% | 50 | 50 | Feature Estimation
TAP-111731_ANIMATORS | 8 | 6 |  | 01.02.02.02.00.00.00.00 | TAP-111731 | TAP-112037 | [TAP-111731_ANIMATORS] ¦ [Animators] Reduce Force Variation when articulating during clamp | Feature Estimation | Open | Shared Services - Animators | ANIMATORS |  |  | 0 | 0 | 50 | 50 | 0 | 0% | 50 | 50 | Feature Estimation
TAP-124062 | 9 |  | 4 | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112076 | 10 | 202 |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112076_COREINSTRUMENTS | 11 | 10 |  | 01.03.01.01.00.00.00.00 | TAP-112076 | TAP-112078 | [TAP-112076_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Damage Modeling Documentation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-94966 | 12 | 24, 202 | TAP-111562 not found | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | In progress |  |  |  |  | 37 | 25 | 1 hr | 1 hr | 12 | 0% | 45 | 78 | Story Points
TAP-94966_COREINSTRUMENTS | 13 | 12 |  | 01.03.02.01.00.00.00.00 | TAP-94966 | TAP-111781 | [TAP-94966_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Develop a Jaw Estimator for Shears | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 37 | 62 | 37 | 44.4 | -25 | 100% | 45 | 78 | Story Points
TAP-111554 | 14 | 202 |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 | 0 | 1 hr | 1 hr | 7 | 0% | 24 | 48 | Story Points
TAP-111554_COREINSTRUMENTS | 15 | 14 |  | 01.03.03.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 7 | 7 | 7 | 8.4 | 0 | 100% | 24 | 48 | Story Points
TAP-111555 | 16 | 202 |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-111555_COREINSTRUMENTS | 17 | 16 |  | 01.03.04.01.00.00.00.00 | TAP-111555 | TAP-111783 | [TAP-111555_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 12 | 18 | 0 | 100% | 12 | 18 | Feature Estimation
TAP-112012 | 18 | 202 |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-112012_COREINSTRUMENTS | 19 | 18 |  | 01.03.05.01.00.00.00.00 | TAP-112012 | TAP-112015 | [TAP-112012_COREINSTRUMENTS] ¦ [IRR][Enhancement] Cutting Control Enhancements | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 12 | 18 | 0 | 100% | 12 | 18 | Feature Estimation
TAP-111569 | 20 | 202 |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 12 | Feature Estimation
TAP-111569_COREINSTRUMENTS | 21 | 20 |  | 01.03.07.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Integration, Testing, Demo, Design Review | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 12 | 0 | 100% | 8 | 12 | Feature Estimation
TAP-111565 | 22 | 202 |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 20 | Feature Estimation
TAP-111565_COREINSTRUMENTS | 23 | 22 |  | 01.03.08.01.00.00.00.00 | TAP-111565 | TAP-111793 | [TAP-111565_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 5 | 20 | 0 | 100% | 5 | 20 | Feature Estimation
TAP-111556 | 24 | 26, 202 | 12 | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111556_COREINSTRUMENTS | 25 | 24 |  | 01.03.09.01.00.00.00.00 | TAP-111556 | TAP-111784 | [TAP-111556_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111559 | 26 | 202 | 24 | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111559_COREINSTRUMENTS | 27 | 26 |  | 01.03.10.01.00.00.00.00 | TAP-111559 | TAP-111785 | [TAP-111559_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-112077 | 28 | 202 | TAP-111562 not found | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 61 | 13 | 1 hr | 1 hr | 48 | 0% | 20 | 30 | Story Points
TAP-112077_COREINSTRUMENTS | 29 | 28 |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Articulation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 61 | 74 | 61 | 73.2 | -13 | 100% | 20 | 30 | Story Points
TAP-120096 | 30 | 202 |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-103448 | 31 | 202 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 | 5 | 1 hr | 1 hr | 9 | 0% | 0 | 0 | Story Points
TAP-116286 | 32 | 202 |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0 | Story Points
TAP-95983 | 33 | 202 |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 106 | 35 | 1 hr | 1 hr | 71 | 0% | 41 | 73 | Story Points
TAP-95983_FRED | 34 | 33 |  | 01.05.04.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_FRED] ¦ [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 125 | 156 | 125 | 150 | -31 | 124.8% | 82 | 146 | Story Points
TAP-111719 | 35 | TAP-111562 not found, 202 | TAP-124116 not found | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 | 2 | 1 hr | 1 hr | 3 | 0% | 15 | 22 | Story Points
TAP-111719_COREINSTRUMENTS | 36 | 35 |  | 01.05.05.01.00.00.00.00 | TAP-111719 | TAP-111916 | [TAP-111719_COREINSTRUMENTS] ¦ [IRR][Core Instruments] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 5 | 2 | 5 | 6 | 3 | 40% | 15 | 22 | Story Points
TAP-111719_FRED | 37 | 35 |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112039 | [TAP-111719_FRED] ¦ [IRR][Fred] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 5 | 2 | 5 | 6 | 3 | 40% | 15 | 22 | Story Points
TAP-111719_I2E | 38 | 35 |  | 01.05.05.03.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_I2E] ¦ [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 5 | 7 | 5 | 6 | -2 | 100% | 15 | 22 | Story Points
TAP-111721 | 39 | 202 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 | 20.5 | 1 hr | 1 hr | 4 | 0% | 27 | 30 | Story Points
TAP-111721_COREINSTRUMENTS | 40 | 39 |  | 01.05.06.01.00.00.00.00 | TAP-111721 | TAP-111917 | [TAP-111721_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI14) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 24.5 | 45 | 24.5 | 29.4 | -20.5 | 100% | 27 | 30 | Story Points
TAP-111722 | 41 | 202 |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111722_COREINSTRUMENTS | 42 | 41 |  | 01.05.07.01.00.00.00.00 | TAP-111722 | TAP-111918 | [TAP-111722_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI15) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-111723 | 43 | 202 |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 27 | 30 | Feature Estimation
TAP-111723_COREINSTRUMENTS | 44 | 43 |  | 01.05.08.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI16) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-111724 | 45 | 202 |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111724_COREINSTRUMENTS | 46 | 45 |  | 01.05.09.01.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-112119 | 47 | 202 |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112119_COREINSTRUMENTS | 48 | 47 |  | 01.05.10.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119_COREINSTRUMENTS] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-94125 | 49 | 129, 202 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | Accepted |  |  |  |  | 77 | 0 | 1 hr | 1 hr | 77 | 0% | 50 | 70 | Story Points
TAP-95800 | 50 | 131, 202 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | Accepted |  |  |  |  | 31 | 2 | 1 hr | 1 hr | 29 | 0% | 15 | 35 | Story Points
TAP-111740 | 51 | 133, 202 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | PROPOSED |  |  |  |  | 28 | 0 | 1 hr | 1 hr | 28 | 0% | 60 | 80 | Story Points
TAP-111740_COREINSTRUMENTS | 52 | 51 |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 28 | 28 | 28 | 33.6 | 0 | 100% | 60 | 80 | Story Points
TAP-111749 | 53 | 135, 202 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111749_COREINSTRUMENTS | 54 | 53 |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111750 | 55 | 137, 202 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 35 | Feature Estimation
TAP-111750_COREINSTRUMENTS | 56 | 55 |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Procedure Manager SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 35 | 0 | 100% | 15 | 35 | Feature Estimation
TAP-111751 | 57 | 139, 202 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 45 | Feature Estimation
TAP-111751_COREINSTRUMENTS | 58 | 57 |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 28 | 45 | 0 | 100% | 28 | 45 | Feature Estimation
TAP-117678 | 59 | 202 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111834 | 60 | 202 | TAP-113995 not found | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-111834_JACOBIANS | 61 | 60 |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_JACOBIANS] ¦ Support Kinematic Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-111747 | 62 | 205 |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-111747_COREINSTRUMENTS | 63 | 62 |  | 02.01.01.01.00.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 100 | 0 | 100% | 50 | 100 | Feature Estimation
TAP-111772 | 64 | 205 |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111772_COREINSTRUMENTS | 65 | 64 |  | 02.02.01.01.00.00.00.00 | TAP-111772 | TAP-111965 | [TAP-111772_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-111773 | 66 | 205 |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 65 | Feature Estimation
TAP-111773_COREINSTRUMENTS | 67 | 66 |  | 02.02.02.01.00.00.00.00 | TAP-111773 | TAP-111966 | [TAP-111773_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW + Test Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 65 | 0 | 100% | 50 | 65 | Feature Estimation
TAP-111838 | 68 | 72, 205 |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111838_COREINSTRUMENTS | 69 | 68 |  | 02.03.01.01.00.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-104213 | 70 | 72, 205 |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 45 | Feature Estimation
TAP-104213_COREINSTRUMENTS | 71 | 70 |  | 02.03.02.01.00.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 45 | 0 | 100% | 15 | 45 | Feature Estimation
TAP-111842 | 72 | 205 | 70, 68 | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111842_COREINSTRUMENTS | 73 | 72 |  | 02.03.03.01.00.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111774 | 74 | 83, 78, 205 |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 0% | 20 | 34 | Story Points
TAP-111774_COREINSTRUMENTS | 75 | 74 |  | 02.04.01.01.00.00.00.00 | TAP-111774 | TAP-111970 | [TAP-111774_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 9 | 18 | 9 | 10.8 | -9 | 100% | 20 | 34 | Story Points
TAP-111774_JACOBIANS | 76 | 74 |  | 02.04.01.02.00.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 9 | 27 | 9 | 10.8 | -18 | 100% | 20 | 34 | Story Points
TAP-111774_CASTLEBLACK | 77 | 74 |  | 02.04.01.03.00.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774_CASTLEBLACK] ¦ [IRR][Castle Black] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 9 | 27 | 9 | 10.8 | -18 | 300% | 20 | 34 | Story Points
TAP-112080 | 78 | 83, 205 | 74 | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 15 | 0 | 1 hr | 1 hr | 15 | 0% | 37 | 63 | Story Points
TAP-112080_COREINSTRUMENTS | 79 | 78 |  | 02.04.02.01.00.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 15 | 15 | 15 | 18 | 0 | 100% | 37 | 63 | Story Points
TAP-112080_JACOBIANS | 80 | 78 |  | 02.04.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 15 | 30 | 15 | 18 | -15 | 100% | 37 | 63 | Story Points
TAP-112080_ORGANELLES | 81 | 78 |  | 02.04.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_ORGANELLES] ¦ [IRR][Organelles] UFSW - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 15 | 45 | 15 | 18 | -30 | 100% | 37 | 63 | Story Points
TAP-112080_INBETWEENERS | 82 | 78 |  | 02.04.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_INBETWEENERS] ¦ [IRR][Inbetweeners] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 15 | 60 | 15 | 18 | -45 | 100% | 37 | 63 | Story Points
TAP-111775 | 83 | 205 | 74, 78 | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 | 0 | 1 hr | 1 hr | 1 | 0% | 45 | 75 | Feature Estimation
TAP-111775_COREINSTRUMENTS | 84 | 83 |  | 02.04.03.01.00.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 1 | 1 | 45 | 75 | 0 | 100% | 45 | 75 | Feature Estimation
TAP-111775_JACOBIANS | 85 | 83 |  | 02.04.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 2 | 45 | 75 | -1 | 100% | 45 | 75 | Feature Estimation
TAP-111775_ORGANELLES | 86 | 83 |  | 02.04.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_ORGANELLES] ¦ [IRR][Organelles] UFSW - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 1 | 3 | 45 | 75 | -2 | 100% | 45 | 75 | Feature Estimation
TAP-111775_INBETWEENERS | 87 | 83 |  | 02.04.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_INBETWEENERS] ¦ [IRR][Inbetweeners] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 1 | 4 | 45 | 75 | -3 | 100% | 45 | 75 | Feature Estimation
TAP-123862 | 88 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 27 | 0 | 1 hr | 1 hr | 27 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 89 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 26 | 0 | 1 hr | 1 hr | 26 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 90 | 205 |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 170 | 325 | Feature Estimation
TAP-111642_COREINSTRUMENTS | 91 | 90 |  | 02.05.03.01.00.00.00.00 | TAP-111642 | TAP-111941 | [TAP-111642_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_I2E | 92 | 90 |  | 02.05.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111642_I2E] ¦ [IRR][I2E] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_ORGANELLES | 93 | 90 |  | 02.05.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111642_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_CASTLEBLACK | 94 | 90 |  | 02.05.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111642_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 170 | 325 | 0 | 0% | 170 | 325 | Feature Estimation
TAP-111656 | 95 | 205 |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_CLASSY2 | 96 | 95 |  | 02.05.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_CLASSY2] ¦ [IRR][CLASSY 2] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_BOOSTERS | 97 | 95 |  | 02.05.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_BOOSTERS] ¦ [IRR][Boosters] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_INBETWEENERS | 98 | 95 |  | 02.05.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_INBETWEENERS] ¦ [IRR][Inbetweeners] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_CASTLEBLACK | 99 | 95 |  | 02.05.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 151 | 278 | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_ORGANELLES | 100 | 95 |  | 02.05.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_I2E | 101 | 95 |  | 02.05.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_I2E] ¦ [IRR][I2E] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_COREINSTRUMENTS | 102 | 95 |  | 02.05.04.07.00.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Productization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111925 | 103 | 205 |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111925_COREINSTRUMENTS | 104 | 103 |  | 02.06.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-112113 | 105 | 205 |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112113_COREINSTRUMENTS | 106 | 105 |  | 02.06.02.01.00.00.00.00 | TAP-112113 | TAP-112123 | [TAP-112113_COREINSTRUMENTS] ¦ [IRR] Verification plan for regression on SKU's | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111865 | 107 | 205 |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113111 | 108 | 121, 125 |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 109 | 117, 121, 125 |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 110 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 | 18 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-114689 | 111 | 117 |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  |  |  | 15 | 30 | 1 hr | 1 hr | -15 | 100% | 0 | 0 | Story Points
TAP-90375 | 112 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 | 0 | 1 hr | 1 hr | 9 | 0% |  |  | Story Points
TAP-111861 | 113 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 34 | 46 | Story Points
TAP-111861_I2E | 114 | 113 |  | 02.07.03.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_I2E] ¦ [IRR][I2E] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 3 | 3 | 3 | 3.6 | 0 | 100% | 34 | 46 | Story Points
TAP-111861_ORGANELLES | 115 | 113 |  | 02.07.03.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_ORGANELLES] ¦ [IRR][Organelles] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 3 | 6 | 3 | 3.6 | -3 | 100% | 34 | 46 | Story Points
TAP-111861_DRUSHTI | 116 | 113 |  | 02.07.03.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_DRUSHTI] ¦ [IRR][Drushti] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 3 | 9 | 3 | 3.6 | -6 | 100% | 34 | 46 | Story Points
TAP-111687 | 117 |  | 109, 111 | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111687_PIXELPOETS | 118 | 117 |  | 02.07.03.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_PIXELPOETS] ¦ [IRR] [Pixel Poets] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 28 | 46 | 0 | 100% | 28 | 46 | Feature Estimation
TAP-111687_ORGANELLES | 119 | 117 |  | 02.07.03.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_ORGANELLES] ¦ [IRR] [Organelles] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 28 | 46 | 0 | 100% | 28 | 46 | Feature Estimation
TAP-111687_FRED | 120 | 117 |  | 02.07.03.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_FRED] ¦ [IRR] [Fred] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 0 | 0 | 28 | 46 | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111689 | 121 |  | 108, 109 | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 32 | 48 | Feature Estimation
TAP-111689_PIXELPOETS | 122 | 121 |  | 02.07.03.04.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111689_PIXELPOETS] ¦ [IRR] [Pixel Poets] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111689_ORGANELLES | 123 | 121 |  | 02.07.03.04.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-111689_ORGANELLES] ¦ [IRR] [Organelles] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111689_DRUSHTI | 124 | 121 |  | 02.07.03.04.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-111689_DRUSHTI] ¦ [IRR] [Drushti] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111695 | 125 |  | 108, 109 | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 24 | 46 | Feature Estimation
TAP-111695_PIXELPOETS | 126 | 125 |  | 02.07.03.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_PIXELPOETS] ¦ [IRR][Pixel Poets] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111695_ORGANELLES | 127 | 125 |  | 02.07.03.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_ORGANELLES] ¦ [IRR][Organelles] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111695_DRUSHTI | 128 | 125 |  | 02.07.03.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_DRUSHTI] ¦ [IRR][Drushti] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111753 | 129 | 141, 208 | 49 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 30 | 50 | Feature Estimation
TAP-111753_COREINSTRUMENTS | 130 | 129 |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 | [TAP-111753_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Homing Manager | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 30 | 50 | 0 | 100% | 30 | 50 | Feature Estimation
TAP-111754 | 131 | 143, 208 | 50 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 10 | 15 | Feature Estimation
TAP-111754_COREINSTRUMENTS | 132 | 131 |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 | [TAP-111754_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111756 | 133 | 145, 208 | 51 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 35 | 45 | Feature Estimation
TAP-111756_COREINSTRUMENTS | 134 | 133 |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Teleoperation Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 35 | 45 | 0 | 100% | 35 | 45 | Feature Estimation
TAP-111757 | 135 | 147, 208 | 53 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111757_COREINSTRUMENTS | 136 | 135 |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111758 | 137 | 149, 208 | 55 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111758_COREINSTRUMENTS | 138 | 137 |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 | [TAP-111758_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Procedure Manager SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-111759 | 139 | 151, 208 | 57 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111759_COREINSTRUMENTS | 140 | 139 |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 | [TAP-111759_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Estimator SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111761 | 141 | 208 | 129 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 30 | Feature Estimation
TAP-111761_COREINSTRUMENTS | 142 | 141 |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Homing Manager Sub-SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 25 | 30 | 0 | 100% | 25 | 30 | Feature Estimation
TAP-110382 | 143 | 208 | 131 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 8 | Feature Estimation
TAP-110382_COREINSTRUMENTS | 144 | 143 |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 5 | 8 | 0 | 100% | 5 | 8 | Feature Estimation
TAP-111762 | 145 | 208 | 133 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 25 | Feature Estimation
TAP-111762_COREINSTRUMENTS | 146 | 145 |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Teleoperation Controller for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 25 | 0 | 100% | 15 | 25 | Feature Estimation
TAP-111748 | 147 | 208 | 135 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 15 | Feature Estimation
TAP-111748_COREINSTRUMENTS | 148 | 147 |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 15 | 0 | 100% | 8 | 15 | Feature Estimation
TAP-111764 | 149 | 208 | 137 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111764_COREINSTRUMENTS | 150 | 149 |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Procedure Manager for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111766 | 151 | 208 | 139 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111766_COREINSTRUMENTS | 152 | 151 |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-112082 | 153 | 208 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 125 | Feature Estimation
TAP-112082_COREINSTRUMENTS | 154 | 153 |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082_COREINSTRUMENTS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_I2E | 155 | 153 |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_I2E] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_ORGANELLES | 156 | 153 |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_ORGANELLES] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_PIXELPOETS | 157 | 153 |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_JACOBIANS | 158 | 153 |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112093 | 159 | 208 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 55 | 70 | Feature Estimation
TAP-112093_COREINSTRUMENTS | 160 | 159 |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093_COREINSTRUMENTS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 55 | 70 | 0 | 100% | 55 | 70 | Feature Estimation
TAP-112094 | 161 | 208 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 87 | 170 | Feature Estimation
TAP-112094_COREINSTRUMENTS | 162 | 161 |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094_COREINSTRUMENTS] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 87 | 170 | 0 | 100% | 87 | 170 | Feature Estimation
TAP-113100 | 163 | 213 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 200 | 400 | Feature Estimation
TAP-113100_COREINSTRUMENTS | 164 | 163 |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100_COREINSTRUMENTS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 200 | 400 | 0 | 100% | 200 | 400 | Feature Estimation
TAP-111900 | 165 | 217 | 211 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 79 | 152 | Feature Estimation
TAP-111900_COREINSTRUMENTS | 166 | 165 |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900_COREINSTRUMENTS] ¦ [M-IRR][Core Instrument] Formal Software Verification activities | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_BUGHUNTERS | 167 | 165 |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_BUGHUNTERS] ¦ [M-IRR][Bug Hunters] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Bug Hunters | BUGHUNTERS |  |  | 0 | 0 | 79 | 152 | 0 | 0% | 79 | 152 | Feature Estimation
TAP-111900_I2E | 168 | 165 |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-111900_I2E] ¦ [M-IRR][I2E] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_JACOBIANS | 169 | 165 |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_JACOBIANS] ¦ [M-IRR][Jacobians] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_ORGANELLES | 170 | 165 |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_ORGANELLES] ¦ [M-IRR][Organelles] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_SCRUMBLEDORES | 171 | 165 |  | 05.01.07.00.00.00.00.00 | TAP-111900 | TAP-112683 | [TAP-111900_SCRUMBLEDORES] ¦ [M-IRR][Scrumbledores] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_SUNRISERS | 172 | 165 |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_SUNRISERS] ¦ [M-IRR][Sunrisers] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_TEAMBD | 173 | 165 |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_TEAMBD] ¦ [M-IRR][TeamBD] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_COSSACKS | 174 | 165 |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_COSSACKS] ¦ [M-IRR][Cossacks] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-112042 | 175 | 217 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 22 | 30 | Feature Estimation
TAP-112042_BUILDERS | 176 | 175 |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_BUILDERS] ¦ [V3.1][IRR][Builders] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS |  |  | 0 | 0 | 22 | 30 | 0 | 100% | 22 | 30 | Feature Estimation
TAP-111692 | 177 | 217 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 130 | 195 | Feature Estimation
TAP-111692_ASTRANPSDEVELOPERS | 178 | 177 |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_ASTRANPSDEVELOPERS] ¦ [IRR][Astra NPS Developers] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TOOLSRULES | 179 | 177 |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_TOOLSRULES] ¦ [IRR][Tools Rules] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_INBETWEENERS | 180 | 177 |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_INBETWEENERS] ¦ [IRR][Inbetweeners] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TRIPLETEA | 181 | 177 |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_TRIPLETEA] ¦ [IRR][Triple Tea] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-112231 | 182 | 217 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 40 | 50 | Feature Estimation
TAP-112231_ASTRANPSVALIDATORS | 183 | 182 |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 40 | 50 | 0 | 100% | 40 | 50 | Feature Estimation
TAP-112233 | 184 | 217 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112233_ASTRANPSVALIDATORS | 185 | 184 |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-112234 | 186 | 217 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 40 | Feature Estimation
TAP-112234_TOOLSRULES | 187 | 186 |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 20 | 40 | 0 | 100% | 20 | 40 | Feature Estimation
TAP-113127 | 188 | 217 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113127 | 189 | 188 |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Defect | Investigation |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-115187 | 190 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 | 58 | 1 hr | 1 hr | -29 | 100% | 0 | 0
TAP-122269 | 191 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 11 | 0 | 1 hr | 1 hr | 11 | 0% | 0 | 0 | Feature Estimation
TAP-122269 | 192 | 191 |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Defect | Investigation |  |  |  |  | 21 | 0 | 0 | 0 | 21 | 0% | 0 | 0 | Feature Estimation
TAP-64314 | 193 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 | 64.5 | 1 hr | 1 hr | -32.25 | 100%
TAP-64315 | 194 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 195 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 44 | 1 hr | 1 hr | -22 | 100%
TAP-64315 | 196 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 197 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 44 | 1 hr | 1 hr | -22 | 100%
TAP-94573 | 198 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 | 26 | 1 hr | 1 hr | -13 | 100%
TAP-109680 | 199 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% |  |  | Feature Estimation
TAP-109680 | 200 | 199 |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Defect | In progress |  |  |  |  | 3 | 0 |  |  | 3 | 0% |  |  | Feature Estimation
TAP-124484 | 201 |  |  | 06.04.04.02.01.00.00.00 |  | TAP-124484 | [TAP-124484] ¦ [RAS-4536] [Stellars] Undefined response to SIM/Instrument Memory Error | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111760 | 202 | 203 | TAP-123834 not found | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 203 | 205 | 202 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111763_SEAMLESS | 204 | 203 |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-113104 | 205 | 206 | 62, 64, 68, 103, 70, 95, 107, 78, 83, 72, 66, 90, 74, 105, 203 | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 206 | 208 | 205 | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113105_SEAMLESS | 207 | 206 |  | 07.04.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111765 | 208 | 209 | 129, 131, 133, 135, 137, 139, 141, 143, 145, 147, 149, 151, 153, 159, 161, 206 | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 209 | 210 | 208 | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 210 | 211 | 209 | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 211 | 165 | 210 | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111767_SEAMLESS | 212 | 211 |  | 07.08.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-113101 | 213 | 214 | 163 | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 214 | 215 | 213 | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 215 | 217 | 214 | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113103_SEAMLESS | 216 | 215 |  | 07.11.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-121104 | 217 |  | 165, 175, 177, 182, 184, 186, 188, 215 | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94968 | 218 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111726 | 219 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111726_COREINSTRUMENTS | 220 | 219 |  | 08.02.02.01.00.00.00.00 | TAP-111726 | TAP-111947 | [TAP-111726_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Bending radius | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111727 | 221 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111727_COREINSTRUMENTS | 222 | 221 |  | 08.02.03.01.00.00.00.00 | TAP-111727 | TAP-111948 | [TAP-111727_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Validation | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111729 | 223 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111729_COREINSTRUMENTS | 224 | 223 |  | 08.02.04.01.00.00.00.00 | TAP-111729 | TAP-111949 | [TAP-111729_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Use-life count using damage model | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94967 | 225 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111733 | 226 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111733_COREINSTRUMENTS | 227 | 226 |  | 08.03.01.00.00.00.00.00 | TAP-111733 | TAP-111908 | [TAP-111733_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore user clamp force setting | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111734 | 228 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111734_COREINSTRUMENTS | 229 | 228 |  | 08.04.01.00.00.00.00.00 | TAP-111734 | TAP-111911 | [TAP-111734_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore haptic force regulation / feedback for clamp force | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111735 | 230 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111735_COREINSTRUMENTS | 231 | 230 |  | 08.05.01.00.00.00.00.00 | TAP-111735 | TAP-111912 | [TAP-111735_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore clamp+cut control for Needle Cutting Grasper | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111570 | 232 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111570_COREINSTRUMENTS | 233 | 232 |  | 08.06.01.00.00.00.00.00 | TAP-111570 | TAP-111798 | [TAP-111570_COREINSTRUMENTS] ¦ [IRR][Core Instruments] UX Update for Paddle to Cut Command Mapping | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112107 | 234 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-112107_COREINSTRUMENTS | 235 | 234 |  | 09.01.02.01.00.00.00.00 | TAP-112107 | TAP-112114 | [TAP-112107_COREINSTRUMENTS] ¦ Grasper SKU Characterization at Frictional Max/Min | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-111934 | 236 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 237 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112085_COREINSTRUMENTS | 238 | 237 |  | 09.01.04.01.00.00.00.00 | TAP-112085 | TAP-112090 | [TAP-112085_COREINSTRUMENTS] ¦ Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-112084 | 239 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112084_COREINSTRUMENTS | 240 | 239 |  | 09.01.05.01.00.00.00.00 | TAP-112084 | TAP-112088 | [TAP-112084_COREINSTRUMENTS] ¦ Regress Articulation KPI's on Graspers for Pretension | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-112101 | 241 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 160 | 320 | Feature Estimation
TAP-112101_COREINSTRUMENTS | 242 | 241 |  | 09.01.06.01.00.00.00.00 | TAP-112101 | TAP-112103 | [TAP-112101_COREINSTRUMENTS] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 160 | 320 | 0 | 100% | 160 | 320 | Feature Estimation
TAP-112086 | 243 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 50 | Feature Estimation
TAP-112086_COREINSTRUMENTS | 244 | 243 |  | 09.01.07.01.00.00.00.00 | TAP-112086 | TAP-112091 | [TAP-112086_COREINSTRUMENTS] ¦ Requirement and Verification Engineering for Multi-SKU Release | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 25 | 50 | 0 | 100% | 25 | 50 | Feature Estimation
TAP-112087 | 245 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-112087_COREINSTRUMENTS | 246 | 245 |  | 09.01.08.01.00.00.00.00 | TAP-112087 | TAP-112092 | [TAP-112087_COREINSTRUMENTS] ¦ Product SW Development for Rest of Graspers | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 100 | 0 | 100% | 50 | 100 | Feature Estimation
TAP-112095 | 247 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-106203 | 248 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-100791 | 249 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100%

## Log
DataTimeStamp | Event | Data

## Summary
Resource Names | Sum FDR
COREINSTRUMENTS
COREINSTRUMENTS
ANIMATORS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
FRED
COREINSTRUMENTS
FRED
I2E
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
JACOBIANS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
JACOBIANS
CASTLEBLACK
COREINSTRUMENTS
JACOBIANS
ORGANELLES
INBETWEENERS
COREINSTRUMENTS
JACOBIANS
ORGANELLES
INBETWEENERS
COREINSTRUMENTS
I2E
ORGANELLES
CASTLEBLACK
CLASSY2
BOOSTERS
INBETWEENERS
CASTLEBLACK
ORGANELLES
I2E
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
I2E
ORGANELLES
DRUSHTI
PIXELPOETS
ORGANELLES
FRED
PIXELPOETS
ORGANELLES
DRUSHTI
PIXELPOETS
ORGANELLES
DRUSHTI
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
I2E
ORGANELLES
PIXELPOETS
JACOBIANS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
BUGHUNTERS
I2E
JACOBIANS
ORGANELLES
SCRUMBLEDORES
SUNRISERS
TEAMBD
COSSACKS
BUILDERS
ASTRANPSDEVELOPERS
TOOLSRULES
INBETWEENERS
TRIPLETEA
ASTRANPSVALIDATORS
ASTRANPSVALIDATORS
TOOLSRULES
SEAMLESS
SEAMLESS
SEAMLESS
SEAMLESS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS
COREINSTRUMENTS