## Project
Text10 | Unique ID | Unique ID Successors | Unique ID Predecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Number10 | Number11 | Duration | Duration1 | Number12 | % Complete | Number13 | Number14 | Text24
TAP-94739 | 1 | 2, 202 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 | 24 | 1 hr | 1 hr | -12 | 100% | 40 | 50 | Story Points
TAP-97668 | 2 | 3 | 1 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  |  |  | 32.5 | 65 | 1 hr | 1 hr | -32.5 | 100% | 6 | 8 | Story Points
TAP-120097 | 3 | 202 | 2 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | PROPOSED |  |  |  |  | 28.5 | 0 | 1 hr | 1 hr | 28.5 | 0% | 0 | 0 | Story Points
TAP-111730 | 4 | 202, 9 |  | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | In progress |  |  |  |  | 28 | 20 | 1 hr | 1 hr | 8 | 0% | 30 | 40 | Story Points
TAP-111730_COREINSTRUMENTS | 5 | 4 |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 | [TAP-111730_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Fix force generation at clamp initiation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 28 | 48 | 28 | 33.6 | -20 | 100% | 30 | 40 | Story Points
TAP-111731 | 6 | 202 |  | 01.02.02.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 50 | Feature Estimation
TAP-111731_COREINSTRUMENTS | 7 | 6 |  | 01.02.02.01.00.00.00.00 | TAP-111731 | TAP-111906 | [TAP-111731_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce force variation when articulating during clamp | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 50 | 0 | 100% | 50 | 50 | Feature Estimation
TAP-111731_ANIMATORS | 8 | 6 |  | 01.02.02.02.00.00.00.00 | TAP-111731 | TAP-112037 | [TAP-111731_ANIMATORS] ¦ [Animators] Reduce Force Variation when articulating during clamp | Feature Estimation | Open | Shared Services - Animators | ANIMATORS |  |  | 0 | 0 | 50 | 50 | 0 | 0% | 50 | 50 | Feature Estimation
TAP-124062 | 9 |  | 4 | 01.02.03.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112076 | 10 | 202 |  | 01.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112076_COREINSTRUMENTS | 11 | 10 |  | 01.03.01.01.00.00.00.00 | TAP-112076 | TAP-112078 | [TAP-112076_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Damage Modeling Documentation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-94966 | 12 | 24, 202 |  | 01.03.02.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | In progress |  |  |  |  | 37 | 25 | 1 hr | 1 hr | 12 | 0% | 45 | 78 | Story Points
TAP-94966_COREINSTRUMENTS | 13 | 12 |  | 01.03.02.01.00.00.00.00 | TAP-94966 | TAP-111781 | [TAP-94966_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Develop a Jaw Estimator for Shears | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 37 | 62 | 37 | 44.4 | -25 | 100% | 45 | 78 | Story Points
TAP-111554 | 14 | 202 |  | 01.03.03.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I1 | Feature | PROPOSED |  |  |  |  | 7 | 0 | 1 hr | 1 hr | 7 | 0% | 24 | 48 | Story Points
TAP-111554_COREINSTRUMENTS | 15 | 14 |  | 01.03.03.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 7 | 7 | 7 | 8.4 | 0 | 100% | 24 | 48 | Story Points
TAP-111555 | 16 | 202 |  | 01.03.04.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-111555_COREINSTRUMENTS | 17 | 16 |  | 01.03.04.01.00.00.00.00 | TAP-111555 | TAP-111783 | [TAP-111555_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 12 | 18 | 0 | 100% | 12 | 18 | Feature Estimation
TAP-112012 | 18 | 202 |  | 01.03.05.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 12 | 18 | Feature Estimation
TAP-112012_COREINSTRUMENTS | 19 | 18 |  | 01.03.05.01.00.00.00.00 | TAP-112012 | TAP-112015 | [TAP-112012_COREINSTRUMENTS] ¦ [IRR][Enhancement] Cutting Control Enhancements | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 12 | 18 | 0 | 100% | 12 | 18 | Feature Estimation
TAP-111569 | 20 | 202 |  | 01.03.07.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 12 | Feature Estimation
TAP-111569_COREINSTRUMENTS | 21 | 20 |  | 01.03.07.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Integration, Testing, Demo, Design Review | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 12 | 0 | 100% | 8 | 12 | Feature Estimation
TAP-111565 | 22 | 202 |  | 01.03.08.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 20 | Feature Estimation
TAP-111565_COREINSTRUMENTS | 23 | 22 |  | 01.03.08.01.00.00.00.00 | TAP-111565 | TAP-111793 | [TAP-111565_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 5 | 20 | 0 | 100% | 5 | 20 | Feature Estimation
TAP-111556 | 24 | 26, 202 | 12 | 01.03.09.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111556_COREINSTRUMENTS | 25 | 24 |  | 01.03.09.01.00.00.00.00 | TAP-111556 | TAP-111784 | [TAP-111556_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111559 | 26 | 202 | 24 | 01.03.10.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111559_COREINSTRUMENTS | 27 | 26 |  | 01.03.10.01.00.00.00.00 | TAP-111559 | TAP-111785 | [TAP-111559_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Reduce use-life impact from cutting I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-112077 | 28 | 202 |  | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 61 | 13 | 1 hr | 1 hr | 48 | 0% | 20 | 30 | Story Points
TAP-112077_COREINSTRUMENTS | 29 | 28 |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Articulation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 61 | 74 | 61 | 73.2 | -13 | 100% | 20 | 30 | Story Points
TAP-120096 | 30 | 202 |  | 01.04.02.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-103448 | 31 | 202 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 | 5 | 1 hr | 1 hr | 9 | 0% | 0 | 0 | Story Points
TAP-116286 | 32 | 202 |  | 01.05.03.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | Accepted |  |  |  |  | 18 | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0 | Story Points
TAP-95983 | 33 | 202 |  | 01.05.04.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 106 | 35 | 1 hr | 1 hr | 71 | 0% | 41 | 73 | Story Points
TAP-95983_FRED | 34 | 33 |  | 01.05.04.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_FRED] ¦ [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 125 | 156 | 125 | 150 | -31 | 100% | 82 | 146 | Story Points
TAP-111719 | 35 | 202 |  | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 | 2 | 1 hr | 1 hr | 3 | 0% | 15 | 22 | Story Points
TAP-111719_COREINSTRUMENTS | 36 | 35 |  | 01.05.05.01.00.00.00.00 | TAP-111719 | TAP-111916 | [TAP-111719_COREINSTRUMENTS] ¦ [IRR][Core Instruments] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 5 | 2 | 5 | 6 | 3 | 40% | 15 | 22 | Story Points
TAP-111719_FRED | 37 | 35 |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112039 | [TAP-111719_FRED] ¦ [IRR][Fred] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 5 | 2 | 5 | 6 | 3 | 40% | 15 | 22 | Story Points
TAP-111719_I2E | 38 | 35 |  | 01.05.05.03.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_I2E] ¦ [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 5 | 7 | 5 | 6 | -2 | 100% | 15 | 22 | Story Points
TAP-111721 | 39 | 202 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | In progress |  |  |  |  | 24.5 | 20.5 | 1 hr | 1 hr | 4 | 0% | 27 | 30 | Story Points
TAP-111721_COREINSTRUMENTS | 40 | 39 |  | 01.05.06.01.00.00.00.00 | TAP-111721 | TAP-111917 | [TAP-111721_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI14) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 24.5 | 45 | 24.5 | 29.4 | -20.5 | 100% | 27 | 30 | Story Points
TAP-111722 | 41 | 202 |  | 01.05.07.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111722_COREINSTRUMENTS | 42 | 41 |  | 01.05.07.01.00.00.00.00 | TAP-111722 | TAP-111918 | [TAP-111722_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI15) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-111723 | 43 | 202 |  | 01.05.08.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 27 | 30 | Feature Estimation
TAP-111723_COREINSTRUMENTS | 44 | 43 |  | 01.05.08.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI16) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-111724 | 45 | 202 |  | 01.05.09.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111724_COREINSTRUMENTS | 46 | 45 |  | 01.05.09.01.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-112119 | 47 | 202 |  | 01.05.10.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112119_COREINSTRUMENTS | 48 | 47 |  | 01.05.10.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119_COREINSTRUMENTS] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-94125 | 49 | 129, 202 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | Accepted |  |  |  |  | 77 | 0 | 1 hr | 1 hr | 77 | 0% | 50 | 70 | Story Points
TAP-95800 | 50 | 131, 202 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | Accepted |  |  |  |  | 31 | 2 | 1 hr | 1 hr | 29 | 0% | 15 | 35 | Story Points
TAP-111740 | 51 | 133, 202 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | PROPOSED |  |  |  |  | 28 | 0 | 1 hr | 1 hr | 28 | 0% | 60 | 80 | Story Points
TAP-111740_COREINSTRUMENTS | 52 | 51 |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 28 | 28 | 28 | 33.6 | 0 | 100% | 60 | 80 | Story Points
TAP-111749 | 53 | 135, 202 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111749_COREINSTRUMENTS | 54 | 53 |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111750 | 55 | 137, 202 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 35 | Feature Estimation
TAP-111750_COREINSTRUMENTS | 56 | 55 |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Procedure Manager SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 35 | 0 | 100% | 15 | 35 | Feature Estimation
TAP-111751 | 57 | 139, 202 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 45 | Feature Estimation
TAP-111751_COREINSTRUMENTS | 58 | 57 |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 28 | 45 | 0 | 100% | 28 | 45 | Feature Estimation
TAP-117678 | 59 | 202 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111834 | 60 | 202 |  | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-111834_JACOBIANS | 61 | 60 |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_JACOBIANS] ¦ Support Kinematic Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-111747 | 62 | 205 |  | 02.01.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-111747_COREINSTRUMENTS | 63 | 62 |  | 02.01.01.01.00.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 100 | 0 | 100% | 50 | 100 | Feature Estimation
TAP-111772 | 64 | 205 |  | 02.02.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111772_COREINSTRUMENTS | 65 | 64 |  | 02.02.01.01.00.00.00.00 | TAP-111772 | TAP-111965 | [TAP-111772_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-111773 | 66 | 205 |  | 02.02.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 65 | Feature Estimation
TAP-111773_COREINSTRUMENTS | 67 | 66 |  | 02.02.02.01.00.00.00.00 | TAP-111773 | TAP-111966 | [TAP-111773_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW + Test Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 65 | 0 | 100% | 50 | 65 | Feature Estimation
TAP-111838 | 68 | 72, 205 |  | 02.03.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111838_COREINSTRUMENTS | 69 | 68 |  | 02.03.01.01.00.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-104213 | 70 | 72, 205 |  | 02.03.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 45 | Feature Estimation
TAP-104213_COREINSTRUMENTS | 71 | 70 |  | 02.03.02.01.00.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 45 | 0 | 100% | 15 | 45 | Feature Estimation
TAP-111842 | 72 | 205 | 70, 68 | 02.03.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111842_COREINSTRUMENTS | 73 | 72 |  | 02.03.03.01.00.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111774 | 74 | 83, 78, 205 |  | 02.04.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | In progress |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 0% | 20 | 34 | Story Points
TAP-111774_COREINSTRUMENTS | 75 | 74 |  | 02.04.01.01.00.00.00.00 | TAP-111774 | TAP-111970 | [TAP-111774_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 9 | 18 | 9 | 10.8 | -9 | 100% | 20 | 34 | Story Points
TAP-111774_JACOBIANS | 76 | 74 |  | 02.04.01.02.00.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 9 | 27 | 9 | 10.8 | -18 | 100% | 20 | 34 | Story Points
TAP-111774_CASTLEBLACK | 77 | 74 |  | 02.04.01.03.00.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774_CASTLEBLACK] ¦ [IRR][Castle Black] Analysis of Need and Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 9 | 27 | 9 | 10.8 | -18 | 100% | 20 | 34 | Story Points
TAP-112080 | 78 | 83, 205 | 74 | 02.04.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature | Accepted |  |  |  |  | 15 | 0 | 1 hr | 1 hr | 15 | 0% | 37 | 63 | Story Points
TAP-112080_COREINSTRUMENTS | 79 | 78 |  | 02.04.02.01.00.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 15 | 15 | 15 | 18 | 0 | 100% | 37 | 63 | Story Points
TAP-112080_JACOBIANS | 80 | 78 |  | 02.04.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 15 | 30 | 15 | 18 | -15 | 100% | 37 | 63 | Story Points
TAP-112080_ORGANELLES | 81 | 78 |  | 02.04.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_ORGANELLES] ¦ [IRR][Organelles] UFSW - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 15 | 45 | 15 | 18 | -30 | 100% | 37 | 63 | Story Points
TAP-112080_INBETWEENERS | 82 | 78 |  | 02.04.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_INBETWEENERS] ¦ [IRR][Inbetweeners] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 15 | 60 | 15 | 18 | -45 | 100% | 37 | 63 | Story Points
TAP-111775 | 83 | 205 | 74, 78 | 02.04.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 | 0 | 1 hr | 1 hr | 1 | 0% | 45 | 75 | Feature Estimation
TAP-111775_COREINSTRUMENTS | 84 | 83 |  | 02.04.03.01.00.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 1 | 1 | 45 | 75 | 0 | 100% | 45 | 75 | Feature Estimation
TAP-111775_JACOBIANS | 85 | 83 |  | 02.04.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 2 | 45 | 75 | -1 | 100% | 45 | 75 | Feature Estimation
TAP-111775_ORGANELLES | 86 | 83 |  | 02.04.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_ORGANELLES] ¦ [IRR][Organelles] UFSW - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 1 | 3 | 45 | 75 | -2 | 100% | 45 | 75 | Feature Estimation
TAP-111775_INBETWEENERS | 87 | 83 |  | 02.04.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_INBETWEENERS] ¦ [IRR][Inbetweeners] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 1 | 4 | 45 | 75 | -3 | 100% | 45 | 75 | Feature Estimation
TAP-123862 | 88 |  |  | 02.05.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Versioning and Expiration | Feature | PROPOSED |  |  |  |  | 27 | 0 | 1 hr | 1 hr | 27 | 0% | 0 | 0 | Feature Estimation
TAP-123863 | 89 |  |  | 02.05.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Controller Versioning Architecture Design With Data Consolidation | Feature | PROPOSED |  |  |  |  | 26 | 0 | 1 hr | 1 hr | 26 | 0% | 0 | 0 | Feature Estimation
TAP-111642 | 90 | 205 |  | 02.05.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 170 | 325 | Feature Estimation
TAP-111642_COREINSTRUMENTS | 91 | 90 |  | 02.05.03.01.00.00.00.00 | TAP-111642 | TAP-111941 | [TAP-111642_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_I2E | 92 | 90 |  | 02.05.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111642_I2E] ¦ [IRR][I2E] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_ORGANELLES | 93 | 90 |  | 02.05.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111642_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 170 | 325 | 0 | 100% | 170 | 325 | Feature Estimation
TAP-111642_CASTLEBLACK | 94 | 90 |  | 02.05.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111642_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 170 | 325 | 0 | 0% | 170 | 325 | Feature Estimation
TAP-111656 | 95 | 205 |  | 02.05.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_CLASSY2 | 96 | 95 |  | 02.05.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_CLASSY2] ¦ [IRR][CLASSY 2] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_BOOSTERS | 97 | 95 |  | 02.05.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_BOOSTERS] ¦ [IRR][Boosters] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_INBETWEENERS | 98 | 95 |  | 02.05.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_INBETWEENERS] ¦ [IRR][Inbetweeners] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_CASTLEBLACK | 99 | 95 |  | 02.05.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 151 | 278 | 0 | 0% | 151 | 278 | Feature Estimation
TAP-111656_ORGANELLES | 100 | 95 |  | 02.05.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_ORGANELLES] ¦ [IRR][Organelles] UFSW Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_I2E | 101 | 95 |  | 02.05.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_I2E] ¦ [IRR][I2E] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111656_COREINSTRUMENTS | 102 | 95 |  | 02.05.04.07.00.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Productization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 151 | 278 | 0 | 100% | 151 | 278 | Feature Estimation
TAP-111925 | 103 | 205 |  | 02.06.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111925_COREINSTRUMENTS | 104 | 103 |  | 02.06.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-112113 | 105 | 205 |  | 02.06.02.00.00.00.00.00 |  | TAP-112113 | [TAP-112113] ¦ [IRR] Verification plan for regression on SKU's | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112113_COREINSTRUMENTS | 106 | 105 |  | 02.06.02.01.00.00.00.00 | TAP-112113 | TAP-112123 | [TAP-112113_COREINSTRUMENTS] ¦ [IRR] Verification plan for regression on SKU's | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111865 | 107 | 205 |  | 02.07.01.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113111 | 108 | 121, 125 |  | 02.07.02.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike][Foundation] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Feature Estimation
TAP-113123 | 109 | 117, 121, 125 |  | 02.07.02.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Feature Estimation
TAP-114692 | 110 |  |  | 02.07.02.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | In progress |  |  |  |  | 24 | 18 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-114689 | 111 | 117 |  | 02.07.02.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  |  |  | 15 | 30 | 1 hr | 1 hr | -15 | 100% | 0 | 0 | Story Points
TAP-90375 | 112 |  |  | 02.07.03.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 | 0 | 1 hr | 1 hr | 9 | 0% |  |  | Story Points
TAP-111861 | 113 |  |  | 02.07.03.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 34 | 46 | Story Points
TAP-111861_I2E | 114 | 113 |  | 02.07.03.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_I2E] ¦ [IRR][I2E] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 3 | 3 | 3 | 3.6 | 0 | 100% | 34 | 46 | Story Points
TAP-111861_ORGANELLES | 115 | 113 |  | 02.07.03.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_ORGANELLES] ¦ [IRR][Organelles] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 3 | 6 | 3 | 3.6 | -3 | 100% | 34 | 46 | Story Points
TAP-111861_DRUSHTI | 116 | 113 |  | 02.07.03.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_DRUSHTI] ¦ [IRR][Drushti] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 3 | 9 | 3 | 3.6 | -6 | 100% | 34 | 46 | Story Points
TAP-111687 | 117 |  | 109, 111 | 02.07.03.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111687_PIXELPOETS | 118 | 117 |  | 02.07.03.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_PIXELPOETS] ¦ [IRR] [Pixel Poets] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 28 | 46 | 0 | 100% | 28 | 46 | Feature Estimation
TAP-111687_ORGANELLES | 119 | 117 |  | 02.07.03.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_ORGANELLES] ¦ [IRR] [Organelles] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 28 | 46 | 0 | 100% | 28 | 46 | Feature Estimation
TAP-111687_FRED | 120 | 117 |  | 02.07.03.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_FRED] ¦ [IRR] [Fred] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 0 | 0 | 28 | 46 | 0 | 0% | 28 | 46 | Feature Estimation
TAP-111689 | 121 |  | 108, 109 | 02.07.03.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 32 | 48 | Feature Estimation
TAP-111689_PIXELPOETS | 122 | 121 |  | 02.07.03.04.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111689_PIXELPOETS] ¦ [IRR] [Pixel Poets] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111689_ORGANELLES | 123 | 121 |  | 02.07.03.04.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-111689_ORGANELLES] ¦ [IRR] [Organelles] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111689_DRUSHTI | 124 | 121 |  | 02.07.03.04.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-111689_DRUSHTI] ¦ [IRR] [Drushti] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 32 | 48 | 0 | 100% | 32 | 48 | Feature Estimation
TAP-111695 | 125 |  | 108, 109 | 02.07.03.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 24 | 46 | Feature Estimation
TAP-111695_PIXELPOETS | 126 | 125 |  | 02.07.03.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_PIXELPOETS] ¦ [IRR][Pixel Poets] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111695_ORGANELLES | 127 | 125 |  | 02.07.03.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_ORGANELLES] ¦ [IRR][Organelles] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111695_DRUSHTI | 128 | 125 |  | 02.07.03.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_DRUSHTI] ¦ [IRR][Drushti] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 24 | 46 | 0 | 100% | 24 | 46 | Feature Estimation
TAP-111753 | 129 | 141, 208 | 49 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 30 | 50 | Feature Estimation
TAP-111753_COREINSTRUMENTS | 130 | 129 |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 | [TAP-111753_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Homing Manager | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 30 | 50 | 0 | 100% | 30 | 50 | Feature Estimation
TAP-111754 | 131 | 143, 208 | 50 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 10 | 15 | Feature Estimation
TAP-111754_COREINSTRUMENTS | 132 | 131 |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 | [TAP-111754_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111756 | 133 | 145, 208 | 51 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 35 | 45 | Feature Estimation
TAP-111756_COREINSTRUMENTS | 134 | 133 |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Teleoperation Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 3 | 35 | 45 | 0 | 100% | 35 | 45 | Feature Estimation
TAP-111757 | 135 | 147, 208 | 53 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111757_COREINSTRUMENTS | 136 | 135 |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111758 | 137 | 149, 208 | 55 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111758_COREINSTRUMENTS | 138 | 137 |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 | [TAP-111758_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Procedure Manager SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-111759 | 139 | 151, 208 | 57 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111759_COREINSTRUMENTS | 140 | 139 |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 | [TAP-111759_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Estimator SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111761 | 141 | 208 | 129 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 30 | Feature Estimation
TAP-111761_COREINSTRUMENTS | 142 | 141 |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Homing Manager Sub-SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 25 | 30 | 0 | 100% | 25 | 30 | Feature Estimation
TAP-110382 | 143 | 208 | 131 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 8 | Feature Estimation
TAP-110382_COREINSTRUMENTS | 144 | 143 |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 5 | 8 | 0 | 100% | 5 | 8 | Feature Estimation
TAP-111762 | 145 | 208 | 133 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 25 | Feature Estimation
TAP-111762_COREINSTRUMENTS | 146 | 145 |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Teleoperation Controller for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 25 | 0 | 100% | 15 | 25 | Feature Estimation
TAP-111748 | 147 | 208 | 135 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 15 | Feature Estimation
TAP-111748_COREINSTRUMENTS | 148 | 147 |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 15 | 0 | 100% | 8 | 15 | Feature Estimation
TAP-111764 | 149 | 208 | 137 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111764_COREINSTRUMENTS | 150 | 149 |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Procedure Manager for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111766 | 151 | 208 | 139 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111766_COREINSTRUMENTS | 152 | 151 |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-112082 | 153 | 208 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 125 | Feature Estimation
TAP-112082_COREINSTRUMENTS | 154 | 153 |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082_COREINSTRUMENTS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_I2E | 155 | 153 |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_I2E] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_ORGANELLES | 156 | 153 |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_ORGANELLES] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_PIXELPOETS | 157 | 153 |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_JACOBIANS | 158 | 153 |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112093 | 159 | 208 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 55 | 70 | Feature Estimation
TAP-112093_COREINSTRUMENTS | 160 | 159 |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093_COREINSTRUMENTS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 55 | 70 | 0 | 100% | 55 | 70 | Feature Estimation
TAP-112094 | 161 | 208 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 87 | 170 | Feature Estimation
TAP-112094_COREINSTRUMENTS | 162 | 161 |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094_COREINSTRUMENTS] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 87 | 170 | 0 | 100% | 87 | 170 | Feature Estimation
TAP-113100 | 163 | 213 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 200 | 400 | Feature Estimation
TAP-113100_COREINSTRUMENTS | 164 | 163 |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100_COREINSTRUMENTS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 200 | 400 | 0 | 100% | 200 | 400 | Feature Estimation
TAP-111900 | 165 | 217 | 211 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 79 | 152 | Feature Estimation
TAP-111900_COREINSTRUMENTS | 166 | 165 |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900_COREINSTRUMENTS] ¦ [M-IRR][Core Instrument] Formal Software Verification activities | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_BUGHUNTERS | 167 | 165 |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_BUGHUNTERS] ¦ [M-IRR][Bug Hunters] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Bug Hunters | BUGHUNTERS |  |  | 0 | 0 | 79 | 152 | 0 | 0% | 79 | 152 | Feature Estimation
TAP-111900_I2E | 168 | 165 |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-111900_I2E] ¦ [M-IRR][I2E] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_JACOBIANS | 169 | 165 |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_JACOBIANS] ¦ [M-IRR][Jacobians] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_ORGANELLES | 170 | 165 |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_ORGANELLES] ¦ [M-IRR][Organelles] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_SCRUMBLEDORES | 171 | 165 |  | 05.01.07.00.00.00.00.00 | TAP-111900 | TAP-112683 | [TAP-111900_SCRUMBLEDORES] ¦ [M-IRR][Scrumbledores] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_SUNRISERS | 172 | 165 |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_SUNRISERS] ¦ [M-IRR][Sunrisers] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_TEAMBD | 173 | 165 |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_TEAMBD] ¦ [M-IRR][TeamBD] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-111900_COSSACKS | 174 | 165 |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_COSSACKS] ¦ [M-IRR][Cossacks] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS |  |  | 0 | 0 | 79 | 152 | 0 | 100% | 79 | 152 | Feature Estimation
TAP-112042 | 175 | 217 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 22 | 30 | Feature Estimation
TAP-112042_BUILDERS | 176 | 175 |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_BUILDERS] ¦ [V3.1][IRR][Builders] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS |  |  | 0 | 0 | 22 | 30 | 0 | 100% | 22 | 30 | Feature Estimation
TAP-111692 | 177 | 217 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 130 | 195 | Feature Estimation
TAP-111692_ASTRANPSDEVELOPERS | 178 | 177 |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_ASTRANPSDEVELOPERS] ¦ [IRR][Astra NPS Developers] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TOOLSRULES | 179 | 177 |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_TOOLSRULES] ¦ [IRR][Tools Rules] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_INBETWEENERS | 180 | 177 |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_INBETWEENERS] ¦ [IRR][Inbetweeners] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TRIPLETEA | 181 | 177 |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_TRIPLETEA] ¦ [IRR][Triple Tea] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-112231 | 182 | 217 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 40 | 50 | Feature Estimation
TAP-112231_ASTRANPSVALIDATORS | 183 | 182 |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 40 | 50 | 0 | 100% | 40 | 50 | Feature Estimation
TAP-112233 | 184 | 217 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112233_ASTRANPSVALIDATORS | 185 | 184 |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-112234 | 186 | 217 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 40 | Feature Estimation
TAP-112234_TOOLSRULES | 187 | 186 |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 20 | 40 | 0 | 100% | 20 | 40 | Feature Estimation
TAP-113127 | 188 | 217 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113127 | 189 | 188 |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Defect | Investigation |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-115187 | 190 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 | 58 | 1 hr | 1 hr | -29 | 100% | 0 | 0
TAP-122269 | 191 |  |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Feature | PROPOSED |  |  |  |  | 11 | 0 | 1 hr | 1 hr | 11 | 0% | 0 | 0 | Feature Estimation
TAP-122269 | 192 | 191 |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 | [TAP-122269] ¦ {CAPA2023-019237} update Z-slide brake check test - Develop | Defect | Investigation |  |  |  |  | 21 | 0 | 0 | 0 | 21 | 0% | 0 | 0 | Feature Estimation
TAP-64314 | 193 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 | 64.5 | 1 hr | 1 hr | -32.25 | 100%
TAP-64315 | 194 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 195 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 44 | 1 hr | 1 hr | -22 | 100%
TAP-64315 | 196 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 50 | 1 hr | 1 hr | -25 | 100%
TAP-83712 | 197 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 44 | 1 hr | 1 hr | -22 | 100%
TAP-94573 | 198 |  |  | 06.04.04.01.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 | 26 | 1 hr | 1 hr | -13 | 100%
TAP-109680 | 199 |  |  | 06.04.04.01.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% |  |  | Feature Estimation
TAP-109680 | 200 | 199 |  | 06.04.04.02.00.00.00.00 |  | RAS-4536 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Defect | In progress |  |  |  |  | 3 | 0 |  |  | 3 | 0% |  |  | Feature Estimation
TAP-124484 | 201 |  |  | 06.04.04.02.01.00.00.00 |  | TAP-124484 | [TAP-124484] ¦ [RAS-4536] [Stellars] Undefined response to SIM/Instrument Memory Error | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111760 | 202 | 203 |  | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 203 | 205 | 202 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111763_SEAMLESS | 204 | 203 |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-113104 | 205 | 206 | 62, 64, 68, 103, 70, 95, 107, 78, 83, 72, 66, 90, 74, 105, 203 | 07.03.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 206 | 208 | 205 | 07.04.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113105_SEAMLESS | 207 | 206 |  | 07.04.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111765 | 208 | 209 | 129, 131, 133, 135, 137, 139, 141, 143, 145, 147, 149, 151, 153, 159, 161, 206 | 07.05.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 209 | 210 | 208 | 07.06.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 210 | 211 | 209 | 07.07.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 211 | 165 | 210 | 07.08.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111767_SEAMLESS | 212 | 211 |  | 07.08.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-113101 | 213 | 214 | 163 | 07.09.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 214 | 215 | 213 | 07.10.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 215 | 217 | 214 | 07.11.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113103_SEAMLESS | 216 | 215 |  | 07.11.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-121104 | 217 |  | 165, 175, 177, 182, 184, 186, 188, 215 | 07.12.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94968 | 218 |  |  | 08.02.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111726 | 219 |  |  | 08.02.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111726_COREINSTRUMENTS | 220 | 219 |  | 08.02.02.01.00.00.00.00 | TAP-111726 | TAP-111947 | [TAP-111726_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Bending radius | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111727 | 221 |  |  | 08.02.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111727_COREINSTRUMENTS | 222 | 221 |  | 08.02.03.01.00.00.00.00 | TAP-111727 | TAP-111948 | [TAP-111727_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Wristed Damage Modelling: Validation | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111729 | 223 |  |  | 08.02.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111729_COREINSTRUMENTS | 224 | 223 |  | 08.02.04.01.00.00.00.00 | TAP-111729 | TAP-111949 | [TAP-111729_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Use-life count using damage model | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-94967 | 225 |  |  | 08.02.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-111733 | 226 |  |  | 08.03.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111733_COREINSTRUMENTS | 227 | 226 |  | 08.03.01.00.00.00.00.00 | TAP-111733 | TAP-111908 | [TAP-111733_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore user clamp force setting | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111734 | 228 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111734_COREINSTRUMENTS | 229 | 228 |  | 08.04.01.00.00.00.00.00 | TAP-111734 | TAP-111911 | [TAP-111734_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore haptic force regulation / feedback for clamp force | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111735 | 230 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111735_COREINSTRUMENTS | 231 | 230 |  | 08.05.01.00.00.00.00.00 | TAP-111735 | TAP-111912 | [TAP-111735_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Explore clamp+cut control for Needle Cutting Grasper | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111570 | 232 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111570_COREINSTRUMENTS | 233 | 232 |  | 08.06.01.00.00.00.00.00 | TAP-111570 | TAP-111798 | [TAP-111570_COREINSTRUMENTS] ¦ [IRR][Core Instruments] UX Update for Paddle to Cut Command Mapping | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112107 | 234 |  |  | 09.01.02.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-112107_COREINSTRUMENTS | 235 | 234 |  | 09.01.02.01.00.00.00.00 | TAP-112107 | TAP-112114 | [TAP-112107_COREINSTRUMENTS] ¦ Grasper SKU Characterization at Frictional Max/Min | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-111934 | 236 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-112085 | 237 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112085_COREINSTRUMENTS | 238 | 237 |  | 09.01.04.01.00.00.00.00 | TAP-112085 | TAP-112090 | [TAP-112085_COREINSTRUMENTS] ¦ Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-112084 | 239 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 10 | Feature Estimation
TAP-112084_COREINSTRUMENTS | 240 | 239 |  | 09.01.05.01.00.00.00.00 | TAP-112084 | TAP-112088 | [TAP-112084_COREINSTRUMENTS] ¦ Regress Articulation KPI's on Graspers for Pretension | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 10 | 0 | 100% | 10 | 10 | Feature Estimation
TAP-112101 | 241 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 160 | 320 | Feature Estimation
TAP-112101_COREINSTRUMENTS | 242 | 241 |  | 09.01.06.01.00.00.00.00 | TAP-112101 | TAP-112103 | [TAP-112101_COREINSTRUMENTS] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 160 | 320 | 0 | 100% | 160 | 320 | Feature Estimation
TAP-112086 | 243 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 50 | Feature Estimation
TAP-112086_COREINSTRUMENTS | 244 | 243 |  | 09.01.07.01.00.00.00.00 | TAP-112086 | TAP-112091 | [TAP-112086_COREINSTRUMENTS] ¦ Requirement and Verification Engineering for Multi-SKU Release | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 25 | 50 | 0 | 100% | 25 | 50 | Feature Estimation
TAP-112087 | 245 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-112087_COREINSTRUMENTS | 246 | 245 |  | 09.01.08.01.00.00.00.00 | TAP-112087 | TAP-112092 | [TAP-112087_COREINSTRUMENTS] ¦ Product SW Development for Rest of Graspers | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 100 | 0 | 100% | 50 | 100 | Feature Estimation
TAP-112095 | 247 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-106203 | 248 |  |  | 00.01.00.00.00.00.00.00 |  | TAP-106203 | [TAP-106203] ¦ [IRR] Wristed Instrument Model | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  |  | Feature Estimation
TAP-100791 | 249 |  |  | 00.04.00.00.00.00.00.00 |  | TAP-100791 | [TAP-100791] ¦ [IRR] Build WS5 controller with lower lead and higher efficiency for Joe Eisenger | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100%

## Log
DataTimeStamp | Event | Data
TAP-106315 not found
TAP-111562 not found
TAP-111562 not found
TAP-111562 not found | TAP-124116 not found
TAP-113995 not found
TAP-123834 not found

## Summary
1 hr
1 hr
1 hr
COREINSTRUMENTS | 28.5
1 hr
COREINSTRUMENTS | 28
1 hr
COREINSTRUMENTS | 50
ANIMATORS | 50
1 hr
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 37
1 hr
COREINSTRUMENTS | 7
1 hr
COREINSTRUMENTS | 12
1 hr
COREINSTRUMENTS | 12
1 hr
COREINSTRUMENTS | 8
1 hr
COREINSTRUMENTS | 5
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 61
1 hr
1 hr
I2E | 14
1 hr
COREINSTRUMENTS | 18
1 hr
COREINSTRUMENTS | 106
ANIMATORS | 125
FRED | 125
PUPPETEERS | 127
1 hr
COREINSTRUMENTS | 5
FRED | 5
I2E | 5
1 hr
COREINSTRUMENTS | 24.5
PUPPETEERS | 47
1 hr
COREINSTRUMENTS | 27
1 hr
COREINSTRUMENTS | 27
1 hr
COREINSTRUMENTS | 27
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 77
1 hr
COREINSTRUMENTS | 31
1 hr
COREINSTRUMENTS | 28
1 hr
COREINSTRUMENTS | 16
1 hr
COREINSTRUMENTS | 15
1 hr
COREINSTRUMENTS | 28
1 hr
1 hr
JACOBIANS | 10
1 hr
COREINSTRUMENTS | 50
1 hr
COREINSTRUMENTS | 15
1 hr
COREINSTRUMENTS | 50
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 15
1 hr
COREINSTRUMENTS | 20
1 hr
COREINSTRUMENTS | 9
JACOBIANS | 9
CASTLEBLACK | 9
PUPPETEERS | 9
1 hr
COREINSTRUMENTS | 15
JACOBIANS | 15
ORGANELLES | 15
INBETWEENERS | 15
PUPPETEERS | 15
CASTLEBLACK | 16
1 hr
COREINSTRUMENTS | 45
JACOBIANS | 45
ORGANELLES | 45
INBETWEENERS | 45
PUPPETEERS | 45
1 hr
I2E | 0
1 hr
I2E | 0
1 hr
COREINSTRUMENTS | 170
I2E | 170
ORGANELLES | 170
CASTLEBLACK | 170
1 hr
CLASSY2 | 151
BOOSTERS | 151
INBETWEENERS | 151
CASTLEBLACK | 151
ORGANELLES | 151
I2E | 151
COREINSTRUMENTS | 151
1 hr
COREINSTRUMENTS | 15
1 hr
COREINSTRUMENTS | 0
1 hr
1 hr
BOOSTERS | 0
1 hr
PIXELPOETS | 0
1 hr
CASTLEBLACK | 24
PUPPETEERS | 24
COREINSTRUMENTS | 43
1 hr
1 hr
STELLARS | 9
1 hr
I2E | 3
ORGANELLES | 3
DRUSHTI | 3
PUPPETEERS | 3
1 hr
PIXELPOETS | 28
ORGANELLES | 28
FRED | 28
1 hr
PIXELPOETS | 32
ORGANELLES | 32
DRUSHTI | 32
1 hr
PIXELPOETS | 24
ORGANELLES | 24
DRUSHTI | 24
1 hr
COREINSTRUMENTS | 30
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 35
1 hr
COREINSTRUMENTS | 16
1 hr
COREINSTRUMENTS | 15
1 hr
COREINSTRUMENTS | 20
1 hr
COREINSTRUMENTS | 25
1 hr
COREINSTRUMENTS | 5
1 hr
COREINSTRUMENTS | 15
1 hr
COREINSTRUMENTS | 8
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 15
1 hr
COREINSTRUMENTS | 50
I2E | 50
ORGANELLES | 50
PIXELPOETS | 50
JACOBIANS | 50
1 hr
COREINSTRUMENTS | 55
1 hr
COREINSTRUMENTS | 87
1 hr
COREINSTRUMENTS | 200
1 hr
COREINSTRUMENTS | 79
BUGHUNTERS | 79
I2E | 79
JACOBIANS | 79
ORGANELLES | 79
SCRUMBLEDORES | 79
SUNRISERS | 79
TEAMBD | 79
COSSACKS | 79
1 hr
BUILDERS | 22
1 hr
ASTRANPSDEVELOPERS | 130
TOOLSRULES | 130
INBETWEENERS | 130
TRIPLETEA | 130
1 hr
ASTRANPSVALIDATORS | 40
1 hr
ASTRANPSVALIDATORS | 10
1 hr
TOOLSRULES | 20
1 hr
0
1 hr
1 hr
STELLARS | 0
0
1 hr
1 hr
1 hr
1 hr
1 hr
1 hr
1 hr
STELLARS
1 hr
1 hr
1 hr
SEAMLESS | 10
1 hr
1 hr
SEAMLESS | 10
1 hr
1 hr
1 hr
1 hr
SEAMLESS | 10
1 hr
1 hr
1 hr
SEAMLESS | 10
1 hr
1 hr
1 hr
COREINSTRUMENTS | 20
1 hr
COREINSTRUMENTS | 0
1 hr
COREINSTRUMENTS | 0
1 hr
1 hr
COREINSTRUMENTS | 0
1 hr
COREINSTRUMENTS | 0
1 hr
COREINSTRUMENTS | 0
1 hr
COREINSTRUMENTS | 0
1 hr
COREINSTRUMENTS | 15
1 hr
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 10
1 hr
COREINSTRUMENTS | 160
1 hr
COREINSTRUMENTS | 25
1 hr
COREINSTRUMENTS | 50
1 hr
COREINSTRUMENTS | 0
1 hr
1 hr