## Project
Text10 | Unique ID | Unique ID Successors | Unique ID Predecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Number10 | Number11 | Duration | Duration1 | Number12 | % Complete | Number13 | Number14 | Text24
TAP-94739 | 1 | 2, 194 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 40 | 50 | Story Points
TAP-97668 | 2 | 3 | 1 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  |  |  | 32.5 | 32.5 | 1 hr | 1 hr | 0 | 100% | 6 | 8 | Story Points
TAP-120097 | 3 | 194 | 2 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | Accepted |  |  |  |  | 34.5 | 0 | 1 hr | 1 hr | 34.5 | 0% | 0 | 0 | Story Points
TAP-111730 | 4 | 194, 5 |  | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | Done |  |  |  |  | 20 | 20 | 1 hr | 1 hr | 0 | 100% | 30 | 40 | Story Points
TAP-124062 | 5 | 194 | 4 | 01.02.02.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | Accepted |  |  |  |  | 31 | 8 | 1 hr | 1 hr | 23 | 25.81% | 0 | 0 | Story Points
TAP-94966 | 6 | 194 |  | 01.03.01.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | Done |  |  |  |  | 37 | 37 | 1 hr | 1 hr | 0 | 100% | 45 | 78 | Story Points
TAP-111554 | 7 | 194 |  | 01.03.02.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness | Feature | Accepted |  |  |  |  | 18 | 0 | 1 hr | 1 hr | 18 | 0% | 24 | 48 | Story Points
TAP-111554_COREINSTRUMENTS | 8 | 7 |  | 01.03.02.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Improve Cutting Control Robustness I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 18 | 0 | 18 | 21.6 | 18 | 100% | 24 | 48 | Story Points
TAP-111569 | 9 | 194 |  | 01.03.04.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] Integration, Testing, Demo, Design Review | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 12 | Feature Estimation
TAP-111569_COREINSTRUMENTS | 10 | 9 |  | 01.03.04.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Integration, Testing, Demo, Design Review | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 12 | 0 | 100% | 8 | 12 | Feature Estimation
TAP-112077 | 11 | 194 |  | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  |  |  | 49 | 14 | 1 hr | 1 hr | 35 | 28.57% | 20 | 30 | Story Points
TAP-112077_COREINSTRUMENTS | 12 | 11 |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Articulation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 49 | 14 | 49 | 58.8 | 35 | 100% | 20 | 30 | Story Points
TAP-103448 | 13 | 194 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  |  |  | 14 | 5 | 1 hr | 1 hr | 9 | 35.71% | 0 | 0 | Story Points
TAP-95983 | 14 | 194 |  | 01.05.03.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  |  |  | 80 | 40 | 1 hr | 1 hr | 40 | 50% | 41 | 73 | Story Points
TAP-95983_FRED | 15 | 14 |  | 01.05.03.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_FRED] ¦ [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 99 | 40 | 99 | 118.8 | 59 | 40.4% | 82 | 146 | Story Points
TAP-124116 | 16 | 17 |  | 01.05.04.00.00.00.00.00 |  | TAP-124116 | [TAP-124116] ¦ [IRR][Enabler] Setup of EtherCAT DAQ module for Synchronized Data Acquisition | Feature | Accepted |  |  |  |  | 13 | 0 | 1 hr | 1 hr | 13 | 0% | 1 | 2 | Story Points
TAP-111719 | 17 | 194 | 16 | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  |  |  | 5 | 2 | 1 hr | 1 hr | 3 | 40% | 14 | 20 | Feature Estimation
TAP-111719_I2E | 18 | 17 |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_I2E] ¦ [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 5 | 2 | 14 | 20 | 3 | 100% | 14 | 20 | Feature Estimation
TAP-111721 | 19 | 194 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | Done |  |  |  |  | 24.5 | 24.5 | 1 hr | 1 hr | 0 | 100% | 27 | 30 | Story Points
TAP-111723 | 20 | 194 |  | 01.05.07.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 27 | 30 | Feature Estimation
TAP-111723_COREINSTRUMENTS | 21 | 20 |  | 01.05.07.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI16) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 0 | 27 | 30 | 3 | 100% | 27 | 30 | Feature Estimation
TAP-112119 | 22 | 194 |  | 01.05.08.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112119_COREINSTRUMENTS | 23 | 22 |  | 01.05.08.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119_COREINSTRUMENTS] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-123914 | 24 | 194 |  | 01.05.09.00.00.00.00.00 |  | TAP-123914 | [TAP-123914] ¦ [IRR] Create standardized test tools for data collection and analysis | Feature | Accepted |  |  |  |  | 37 | 0 | 1 hr | 1 hr | 37 | 0% | 0 | 0 | Story Points
TAP-94125 | 25 | 108, 194 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | PROPOSED |  |  |  |  | 77 | 0 | 1 hr | 1 hr | 77 | 0% | 50 | 70 | Story Points
TAP-95800 | 26 | 110, 194 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | Accepted |  |  |  |  | 61 | 2 | 1 hr | 1 hr | 59 | 3.279% | 15 | 35 | Story Points
TAP-95800_COREINSTRUMENTS | 27 | 26 |  | 01.06.02.02.00.00.00.00 | TAP-95800 | TAP-111779 | [TAP-95800_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 61 | 2 | 61 | 73.2 | 59 | 100% | 15 | 35 | Story Points
TAP-111740 | 28 | 112, 194 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | Accepted |  |  |  |  | 73 | 3 | 1 hr | 1 hr | 70 | 4.11% | 60 | 80 | Story Points
TAP-111740_COREINSTRUMENTS | 29 | 28 |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Teloperation SWI Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 73 | 3 | 73 | 87.6 | 70 | 100% | 60 | 80 | Story Points
TAP-111749 | 30 | 114, 194 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111749_COREINSTRUMENTS | 31 | 30 |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111750 | 32 | 116, 194 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 35 | Feature Estimation
TAP-111750_COREINSTRUMENTS | 33 | 32 |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Procedure Manager SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 35 | 0 | 100% | 15 | 35 | Feature Estimation
TAP-111751 | 34 | 118, 194 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 28 | 45 | Feature Estimation
TAP-111751_COREINSTRUMENTS | 35 | 34 |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751_COREINSTRUMENTS] ¦ [IRR][Core Instruments] First Phase SW Development of Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 28 | 45 | 0 | 100% | 28 | 45 | Feature Estimation
TAP-117678 | 36 | 194 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 35 | Feature Estimation
TAP-117678_COREINSTRUMENTS | 37 | 36 |  | 01.06.07.01.00.00.00.00 | TAP-117678 | TAP-127786 | [TAP-117678_COREINSTRUMENTS] ¦ [IRR][Core Instruments][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 35 | 0 | 0% | 20 | 35 | Feature Estimation
TAP-111834 | 38 | 194 |  | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | Accepted |  |  |  |  | 50.5 | 0 | 1 hr | 1 hr | 50.5 | 0% | 10 | 20 | Story Points
TAP-111834_JACOBIANS | 39 | 38 |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_JACOBIANS] ¦ Support Kinematic Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 50.5 | 0 | 50.5 | 60.6 | 50.5 | 100% | 10 | 20 | Story Points
TAP-125255 | 40 | 194 |  | 01.08.00.00.00.00.00.00 |  | TAP-125255 | [TAP-125255] ¦ [IRR] Update/Automate Data Recorder V&V for IRR Interface Changes | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Story Points
TAP-123834 | 41 | 194 |  | 01.09.00.00.00.00.00.00 |  | TAP-123834 | [TAP-123834] ¦ [IRR] Migrate IRR SW to Post-Cyber Branch | Feature | Accepted |  |  |  |  | 17 | 0 | 1 hr | 1 hr | 17 | 0% | 0 | 0 | Story Points
TAP-111724 | 42 | 198 |  | 02.01.00.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 27 | 30 | Feature Estimation
TAP-111724_COREINSTRUMENTS | 43 | 42 |  | 02.01.01.00.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 27 | 30 | 0 | 100% | 27 | 30 | Feature Estimation
TAP-123818 | 44 | 198 |  | 02.02.00.00.00.00.00.00 |  | TAP-123818 | [TAP-123818] ¦ [IRR] Adapt SW Tools with new Polarion API | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-111747 | 45 | 198 |  | 02.03.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 100 | Feature Estimation
TAP-111747_COREINSTRUMENTS | 46 | 45 |  | 02.03.01.01.00.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 100 | 0 | 100% | 50 | 100 | Feature Estimation
TAP-111772 | 47 | 198 |  | 02.04.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111772_COREINSTRUMENTS | 48 | 47 |  | 02.04.01.01.00.00.00.00 | TAP-111772 | TAP-111965 | [TAP-111772_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Algorithm Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-111773 | 49 | 198 |  | 02.04.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 65 | Feature Estimation
TAP-111773_COREINSTRUMENTS | 50 | 49 |  | 02.04.02.01.00.00.00.00 | TAP-111773 | TAP-111966 | [TAP-111773_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW + Test Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 65 | 0 | 100% | 50 | 65 | Feature Estimation
TAP-111838 | 51 | 55, 198 |  | 02.05.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111838_COREINSTRUMENTS | 52 | 51 |  | 02.05.01.01.00.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-104213 | 53 | 55, 198 |  | 02.05.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 45 | Feature Estimation
TAP-104213_COREINSTRUMENTS | 54 | 53 |  | 02.05.02.01.00.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 45 | 0 | 100% | 15 | 45 | Feature Estimation
TAP-111842 | 55 | 198 | 53, 51 | 02.05.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 40 | 60 | Feature Estimation
TAP-111842_COREINSTRUMENTS | 56 | 55 |  | 02.05.03.01.00.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842_COREINSTRUMENTS] ¦ [IRR][Core Instruments] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 40 | 60 | 0 | 100% | 40 | 60 | Feature Estimation
TAP-111842_USERFLOWSW | 57 | 55 |  | 02.05.03.02.00.00.00.00 | TAP-111842 | TAP-127787 | [TAP-111842_USERFLOWSW] ¦ [IRR][UFSW] SW Development of HALT Recovery/Prevention | Feature Estimation | Open | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 40 | 60 | 0 | 0% | 40 | 60 | Feature Estimation
TAP-111774 | 58 | 64, 59, 198 |  | 02.06.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 20 | 34 | Story Points
TAP-112080 | 59 | 64, 198 | 58 | 02.06.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature | PROPOSED |  |  |  |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | 37 | 63 | Feature Estimation
TAP-112080_COREINSTRUMENTS | 60 | 59 |  | 02.06.02.01.00.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 14 | 0 | 37 | 63 | 14 | 100% | 37 | 63 | Feature Estimation
TAP-112080_JACOBIANS | 61 | 59 |  | 02.06.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 14 | 0 | 37 | 63 | 14 | 100% | 37 | 63 | Feature Estimation
TAP-112080_USERFLOWSW | 62 | 59 |  | 02.06.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_USERFLOWSW] ¦ [IRR][Organelles] UFSW - Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 14 | 0 | 37 | 63 | 14 | 100% | 37 | 63 | Feature Estimation
TAP-112080_INBETWEENERS | 63 | 59 |  | 02.06.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_INBETWEENERS] ¦ [IRR][Inbetweeners] Prototype Replacement for MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 14 | 0 | 37 | 63 | 14 | 100% | 37 | 63 | Feature Estimation
TAP-111775 | 64 | 198 | 58, 59 | 02.06.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  |  |  | 1 | 0 | 1 hr | 1 hr | 1 | 0% | 45 | 75 | Feature Estimation
TAP-111775_COREINSTRUMENTS | 65 | 64 |  | 02.06.03.01.00.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 1 | 0 | 45 | 75 | 1 | 100% | 45 | 75 | Feature Estimation
TAP-111775_JACOBIANS | 66 | 64 |  | 02.06.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_JACOBIANS] ¦ [IRR][Jacobians] Kinematics - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 1 | 0 | 45 | 75 | 1 | 100% | 45 | 75 | Feature Estimation
TAP-111775_USERFLOWSW | 67 | 64 |  | 02.06.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_USERFLOWSW] ¦ [IRR][Organelles] UFSW - Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 1 | 0 | 45 | 75 | 1 | 100% | 45 | 75 | Feature Estimation
TAP-111775_INBETWEENERS | 68 | 64 |  | 02.06.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_INBETWEENERS] ¦ [IRR][Inbetweeners] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 1 | 0 | 45 | 75 | 1 | 100% | 45 | 75 | Feature Estimation
TAP-123862 | 69 | 198 |  | 02.07.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | Feature | Accepted |  |  |  |  | 24 | 0 | 1 hr | 1 hr | 24 | 0% | 0 | 0 | Story Points
TAP-123863 | 70 | 198 |  | 02.07.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | Feature | Accepted |  |  |  |  | 29 | 0 | 1 hr | 1 hr | 29 | 0% | 0 | 0 | Story Points
TAP-111642 | 71 | 198 |  | 02.07.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 33 | 50 | Feature Estimation
TAP-111642_COREINSTRUMENTS | 72 | 71 |  | 02.07.03.01.00.00.00.00 | TAP-111642 | TAP-111941 | [TAP-111642_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 33 | 50 | 0 | 100% | 33 | 50 | Feature Estimation
TAP-111642_I2E | 73 | 71 |  | 02.07.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111642_I2E] ¦ [IRR][I2E] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 33 | 50 | 0 | 100% | 33 | 50 | Feature Estimation
TAP-111642_USERFLOWSW | 74 | 71 |  | 02.07.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111642_USERFLOWSW] ¦ [IRR][Organelles] UFSW Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 33 | 50 | 0 | 100% | 33 | 50 | Feature Estimation
TAP-111642_CASTLEBLACK | 75 | 71 |  | 02.07.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111642_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 33 | 50 | 0 | 0% | 33 | 50 | Feature Estimation
TAP-111656 | 76 | 198 |  | 02.07.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 70 | 115 | Feature Estimation
TAP-111656_CLASSY2 | 77 | 76 |  | 02.07.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_CLASSY2] ¦ [IRR][CLASSY 2] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 |  |  | 0 | 0 | 70 | 115 | 0 | 100% | 70 | 115 | Feature Estimation
TAP-111656_BOOSTERS | 78 | 76 |  | 02.07.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_BOOSTERS] ¦ [IRR][Boosters] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS |  |  | 0 | 0 | 70 | 115 | 0 | 100% | 70 | 115 | Feature Estimation
TAP-111656_INBETWEENERS | 79 | 76 |  | 02.07.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_INBETWEENERS] ¦ [IRR][Inbetweeners] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 70 | 115 | 0 | 100% | 70 | 115 | Feature Estimation
TAP-111656_CASTLEBLACK | 80 | 76 |  | 02.07.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_CASTLEBLACK] ¦ [IRR][Castle Black] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK |  |  | 0 | 0 | 70 | 115 | 0 | 0% | 70 | 115 | Feature Estimation
TAP-111656_USERFLOWSW | 81 | 76 |  | 02.07.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_USERFLOWSW] ¦ [IRR][Organelles] UFSW Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 70 | 115 | 0 | 100% | 70 | 115 | Feature Estimation
TAP-111656_I2E | 82 | 76 |  | 02.07.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_I2E] ¦ [IRR][I2E] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 70 | 115 | 0 | 100% | 70 | 115 | Feature Estimation
TAP-111656_COREINSTRUMENTS | 83 | 76 |  | 02.07.04.07.00.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Controller Versioning: Productization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 70 | 115 | 0 | 100% | 70 | 115 | Feature Estimation
TAP-111925 | 84 | 198 |  | 02.08.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111925_COREINSTRUMENTS | 85 | 84 |  | 02.08.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-113111 | 86 | 99, 104 |  | 02.09.01.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Accepted |  |  |  |  | 21 | 0 | 1 hr | 1 hr | 21 | 0% | 0 | 0 | Story Points
TAP-113123 | 87 | 95, 99, 104 |  | 02.09.01.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | Accepted |  |  |  |  | 4 | 0 | 1 hr | 1 hr | 4 | 0% | 0 | 0 | Story Points
TAP-114692 | 88 |  |  | 02.09.01.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | Done |  |  |  |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-114689 | 89 | 95 |  | 02.09.01.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-90375 | 90 | 198 |  | 02.09.02.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  |  |  | 9 | 0 | 1 hr | 1 hr | 9 | 0% |  |  | Story Points
TAP-111861 | 91 | 198 |  | 02.09.02.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  |  |  | 19 | 0 | 1 hr | 1 hr | 19 | 0% | 34 | 46 | Feature Estimation
TAP-111861_I2E | 92 | 91 |  | 02.09.02.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_I2E] ¦ [IRR][I2E] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 19 | 0 | 34 | 46 | 19 | 100% | 34 | 46 | Feature Estimation
TAP-111861_USERFLOWSW | 93 | 91 |  | 02.09.02.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_USERFLOWSW] ¦ [IRR][Organelles] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 19 | 0 | 34 | 46 | 19 | 100% | 34 | 46 | Feature Estimation
TAP-111861_DRUSHTI | 94 | 91 |  | 02.09.02.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_DRUSHTI] ¦ [IRR][Drushti] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 19 | 0 | 34 | 46 | 19 | 100% | 34 | 46 | Feature Estimation
TAP-111687 | 95 | 198 | 87, 89 | 02.09.02.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 33 | 61 | Feature Estimation
TAP-111687_PIXELPOETS | 96 | 95 |  | 02.09.02.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_PIXELPOETS] ¦ [IRR] [Pixel Poets] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 3 | 0 | 33 | 61 | 3 | 100% | 33 | 61 | Feature Estimation
TAP-111687_USERFLOWSW | 97 | 95 |  | 02.09.02.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_USERFLOWSW] ¦ [IRR] [Organelles] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 3 | 0 | 33 | 61 | 3 | 100% | 33 | 61 | Feature Estimation
TAP-111687_FRED | 98 | 95 |  | 02.09.02.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_FRED] ¦ [IRR] [Fred] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | FRED |  |  | 3 | 0 | 33 | 61 | 3 | 0% | 33 | 61 | Feature Estimation
TAP-111689 | 99 | 198 | 86, 87 | 02.09.02.04.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 54 | 101 | Feature Estimation
TAP-111689_PIXELPOETS | 100 | 99 |  | 02.09.02.04.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111689_PIXELPOETS] ¦ [IRR] [Pixel Poets] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 54 | 101 | 0 | 100% | 54 | 101 | Feature Estimation
TAP-111689_USERFLOWSW | 101 | 99 |  | 02.09.02.04.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-111689_USERFLOWSW] ¦ [IRR] [Organelles] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 54 | 101 | 0 | 100% | 54 | 101 | Feature Estimation
TAP-111689_DRUSHTI | 102 | 99 |  | 02.09.02.04.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-111689_DRUSHTI] ¦ [IRR] [Drushti] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 54 | 101 | 0 | 100% | 54 | 101 | Feature Estimation
TAP-111689_BOOSTERS | 103 | 99 |  | 02.09.02.04.04.00.00.00 | TAP-111689 | TAP-127789 | [TAP-111689_BOOSTERS] ¦ [IRR] [Boosters] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Open | Foundation - Boosters | BOOSTERS |  |  | 0 | 0 | 54 | 101 | 0 | 0% | 54 | 101 | Feature Estimation
TAP-111695 | 104 | 198 | 86, 87 | 02.09.02.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 48 | 84 | Feature Estimation
TAP-111695_PIXELPOETS | 105 | 104 |  | 02.09.02.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_PIXELPOETS] ¦ [IRR][Pixel Poets] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 48 | 84 | 0 | 100% | 48 | 84 | Feature Estimation
TAP-111695_USERFLOWSW | 106 | 104 |  | 02.09.02.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_USERFLOWSW] ¦ [IRR][Organelles] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 48 | 84 | 0 | 100% | 48 | 84 | Feature Estimation
TAP-111695_DRUSHTI | 107 | 104 |  | 02.09.02.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_DRUSHTI] ¦ [IRR][Drushti] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 0 | 0 | 48 | 84 | 0 | 100% | 48 | 84 | Feature Estimation
TAP-111753 | 108 | 120, 202 | 25 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 30 | 50 | Feature Estimation
TAP-111753_COREINSTRUMENTS | 109 | 108 |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 | [TAP-111753_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Homing Manager | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 30 | 50 | 0 | 100% | 30 | 50 | Feature Estimation
TAP-111754 | 110 | 122, 202 | 26 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 10 | 15 | Feature Estimation
TAP-111754_COREINSTRUMENTS | 111 | 110 |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 | [TAP-111754_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 0 | 10 | 15 | 3 | 100% | 10 | 15 | Feature Estimation
TAP-111756 | 112 | 124, 202 | 28 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 35 | 45 | Feature Estimation
TAP-111756_COREINSTRUMENTS | 113 | 112 |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Teleoperation Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 3 | 0 | 35 | 45 | 3 | 100% | 35 | 45 | Feature Estimation
TAP-111757 | 114 | 126, 202 | 30 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 16 | 30 | Feature Estimation
TAP-111757_COREINSTRUMENTS | 115 | 114 |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 16 | 30 | 0 | 100% | 16 | 30 | Feature Estimation
TAP-111758 | 116 | 128, 202 | 32 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 30 | Feature Estimation
TAP-111758_COREINSTRUMENTS | 117 | 116 |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 | [TAP-111758_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Procedure Manager SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 30 | 0 | 100% | 15 | 30 | Feature Estimation
TAP-111759 | 118 | 130, 202 | 34 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 30 | Feature Estimation
TAP-111759_COREINSTRUMENTS | 119 | 118 |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 | [TAP-111759_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Requirements and SW Verification of IRR Estimator SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 20 | 30 | 0 | 100% | 20 | 30 | Feature Estimation
TAP-111761 | 120 | 202 | 108 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 25 | 30 | Feature Estimation
TAP-111761_COREINSTRUMENTS | 121 | 120 |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Homing Manager Sub-SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 25 | 30 | 0 | 100% | 25 | 30 | Feature Estimation
TAP-110382 | 122 | 202 | 110 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 5 | 8 | Feature Estimation
TAP-110382_COREINSTRUMENTS | 123 | 122 |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 5 | 8 | 0 | 100% | 5 | 8 | Feature Estimation
TAP-111762 | 124 | 202 | 112 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 25 | Feature Estimation
TAP-111762_COREINSTRUMENTS | 125 | 124 |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Teleoperation Controller for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 25 | 0 | 100% | 15 | 25 | Feature Estimation
TAP-111748 | 126 | 202 | 114 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 8 | 15 | Feature Estimation
TAP-111748_COREINSTRUMENTS | 127 | 126 |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 8 | 15 | 0 | 100% | 8 | 15 | Feature Estimation
TAP-111764 | 128 | 202 | 116 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111764_COREINSTRUMENTS | 129 | 128 |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Procedure Manager for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-111766 | 130 | 202 | 118 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 20 | Feature Estimation
TAP-111766_COREINSTRUMENTS | 131 | 130 |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766_COREINSTRUMENTS] ¦ [IRR][Core Instruments] Product SW Development Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 20 | 0 | 100% | 15 | 20 | Feature Estimation
TAP-112082 | 132 | 202 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 50 | 125 | Feature Estimation
TAP-112082_COREINSTRUMENTS | 133 | 132 |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082_COREINSTRUMENTS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_I2E | 134 | 132 |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_I2E] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_USERFLOWSW | 135 | 132 |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_USERFLOWSW] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_PIXELPOETS | 136 | 132 |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112082_JACOBIANS | 137 | 132 |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 50 | 125 | 0 | 100% | 50 | 125 | Feature Estimation
TAP-112093 | 138 | 202 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 135 | 230 | Feature Estimation
TAP-112093_COREINSTRUMENTS | 139 | 138 |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093_COREINSTRUMENTS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 135 | 230 | 0 | 100% | 135 | 230 | Feature Estimation
TAP-112093_I2E | 140 | 138 |  | 03.03.02.02.00.00.00.00 | TAP-112093 | TAP-127793 | [TAP-112093_I2E] ¦ [IRR][I2E] BRR/TRR prep and finalization | Feature Estimation | Open | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 135 | 230 | 0 | 0% | 135 | 230 | Feature Estimation
TAP-112093_USERFLOWSW | 141 | 138 |  | 03.03.02.03.00.00.00.00 | TAP-112093 | TAP-127794 | [TAP-112093_USERFLOWSW] ¦ [IRR][UFSW] BRR/TRR prep and finalization | Feature Estimation | Open | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 135 | 230 | 0 | 0% | 135 | 230 | Feature Estimation
TAP-112093_PIXELPOETS | 142 | 138 |  | 03.03.02.04.00.00.00.00 | TAP-112093 | TAP-127795 | [TAP-112093_PIXELPOETS] ¦ [IRR][Pixel Poets] BRR/TRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 135 | 230 | 0 | 0% | 135 | 230 | Feature Estimation
TAP-112093_JACOBIANS | 143 | 138 |  | 03.03.02.05.00.00.00.00 | TAP-112093 | TAP-127796 | [TAP-112093_JACOBIANS] ¦ [IRR][Jacobians] BRR/TRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 135 | 230 | 0 | 0% | 135 | 230 | Feature Estimation
TAP-112094 | 144 | 202 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 87 | 170 | Feature Estimation
TAP-112094_COREINSTRUMENTS | 145 | 144 |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094_COREINSTRUMENTS] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 87 | 170 | 0 | 100% | 87 | 170 | Feature Estimation
TAP-113100 | 146 | 208 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 250 | 500 | Feature Estimation
TAP-113100_COREINSTRUMENTS | 147 | 146 |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100_COREINSTRUMENTS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 250 | 500 | 0 | 100% | 250 | 500 | Feature Estimation
TAP-113100_JACOBIANS | 148 | 146 |  | 04.01.02.00.00.00.00.00 | TAP-113100 | TAP-127797 | [TAP-113100_JACOBIANS] ¦ [IRR][Jacobians] RC2 Code Freeze | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 250 | 500 | 0 | 0% | 250 | 500 | Feature Estimation
TAP-111900 | 149 | 213 | 205 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 116 | 188 | Feature Estimation
TAP-111900_COREINSTRUMENTS | 150 | 149 |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900_COREINSTRUMENTS] ¦ [M-IRR][Core Instrument] Formal Software Verification activities | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 116 | 188 | 0 | 100% | 116 | 188 | Feature Estimation
TAP-111900_BUGHUNTERS | 151 | 149 |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_BUGHUNTERS] ¦ [M-IRR][Bug Hunters] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS |  |  | 0 | 0 | 116 | 188 | 0 | 100% | 116 | 188 | Feature Estimation
TAP-111900_I2E | 152 | 149 |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-111900_I2E] ¦ [M-IRR][I2E] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - I2E | I2E |  |  | 0 | 0 | 116 | 188 | 0 | 100% | 116 | 188 | Feature Estimation
TAP-111900_JACOBIANS | 153 | 149 |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_JACOBIANS] ¦ [M-IRR][Jacobians] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS |  |  | 0 | 0 | 116 | 188 | 0 | 100% | 116 | 188 | Feature Estimation
TAP-111900_USERFLOWSW | 154 | 149 |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_USERFLOWSW] ¦ [M-IRR][Romulus] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 116 | 188 | 0 | 100% | 116 | 188 | Feature Estimation
TAP-111900_PIXELPOETS | 155 | 149 |  | 05.01.06.00.00.00.00.00 | TAP-111900 | TAP-112682 | [TAP-111900_PIXELPOETS] ¦ [M-IRR][Pixel Poets] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 0 | 0 | 116 | 188 | 0 | 0% | 116 | 188 | Feature Estimation
TAP-111900_SUNRISERS | 156 | 149 |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_SUNRISERS] ¦ [M-IRR][Sunrisers] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS |  |  | 0 | 0 | 131 | 208 | 0 | 100% | 131 | 208 | Feature Estimation
TAP-111900_TEAMBD | 157 | 149 |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_TEAMBD] ¦ [M-IRR][TeamBD] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD |  |  | 0 | 0 | 131 | 208 | 0 | 100% | 131 | 208 | Feature Estimation
TAP-111900_COSSACKS | 158 | 149 |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_COSSACKS] ¦ [M-IRR][Cossacks] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS |  |  | 0 | 0 | 131 | 208 | 0 | 100% | 131 | 208 | Feature Estimation
TAP-112042 | 159 | 213 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V3.1][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 22 | 30 | Feature Estimation
TAP-112042_BUILDERS | 160 | 159 |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_BUILDERS] ¦ [V3.1][IRR][Builders] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS |  |  | 0 | 0 | 22 | 30 | 0 | 100% | 22 | 30 | Feature Estimation
TAP-111692 | 161 | 213 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 130 | 195 | Feature Estimation
TAP-111692_ASTRANPSDEVELOPERS | 162 | 161 |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_ASTRANPSDEVELOPERS] ¦ [IRR][Astra NPS Developers] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TOOLSRULES | 163 | 161 |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_TOOLSRULES] ¦ [IRR][Tools Rules] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_INBETWEENERS | 164 | 161 |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_INBETWEENERS] ¦ [IRR][Inbetweeners] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-111692_TRIPLETEA | 165 | 161 |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_TRIPLETEA] ¦ [IRR][Triple Tea] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA |  |  | 0 | 0 | 130 | 195 | 0 | 100% | 130 | 195 | Feature Estimation
TAP-112231 | 166 | 213 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 40 | 50 | Feature Estimation
TAP-112231_ASTRANPSVALIDATORS | 167 | 166 |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 40 | 50 | 0 | 100% | 40 | 50 | Feature Estimation
TAP-112233 | 168 | 213 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 20 | Feature Estimation
TAP-112233_ASTRANPSVALIDATORS | 169 | 168 |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS |  |  | 0 | 0 | 10 | 20 | 0 | 100% | 10 | 20 | Feature Estimation
TAP-112234 | 170 | 213 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 20 | 40 | Feature Estimation
TAP-112234_TOOLSRULES | 171 | 170 |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 0 | 0 | 20 | 40 | 0 | 100% | 20 | 40 | Feature Estimation
TAP-113127 | 172 | 213 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113127 | 173 | 172 |  | 06.01.01.00.00.00.00.00 |  | RAS-7203 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Defect | Investigation |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Feature Estimation
TAP-115187 | 174 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0
TAP-122269 | 175 | 202 |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ [CAPA2023-019237] update Z-slide brake check test - Develop | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Story Points
TAP-122269 | 176 | 175 |  | 06.01.02.00.00.00.00.00 |  | RAS-7532 | [TAP-122269] ¦ [CAPA2023-019237] update Z-slide brake check test - Develop | Defect | Investigation |  |  |  |  | 23 | 0 | 23 | 27.6 | 23 | 0% | 0 | 0 | Story Points
TAP-64314 | 177 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  |  |  | 32.25 | 32.25 | 1 hr | 1 hr | 0 | 100%
TAP-64315 | 178 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 25 | 1 hr | 1 hr | 0 | 100%
TAP-83712 | 179 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100%
TAP-64315 | 180 |  |  | 06.01.03.01.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  |  |  | 25 | 25 | 1 hr | 1 hr | 0 | 100%
TAP-83712 | 181 |  |  | 06.01.03.03.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100%
TAP-125315 | 182 | 202 |  | 06.04.01.03.01.00.00.00 |  | TAP-125315 | [TAP-125315] ¦ [Spike] [RAS-7177] Investigate Instrument Insertion without Internal Calibration | Feature | PROPOSED |  |  |  |  | 16 | 0 | 1 hr | 1 hr | 16 | 0% | 0 | 0 | Story Points
TAP-127798 | 183 | 202 |  | 06.04.01.04.00.00.00.00 |  | TAP-127798 | [TAP-127798] ¦ Attachment workflow fix for use count updates | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 45 | 80 | Feature Estimation
TAP-127798_COREINSTRUMENTS | 184 | 183 |  | 06.04.01.04.01.00.00.00 | TAP-127798 | TAP-127799 | [TAP-127798_COREINSTRUMENTS] ¦ [Core Instruments] Attachment workflow fix for multiple defects | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 45 | 80 | 0 | 0% | 45 | 80 | Feature Estimation
TAP-127798_USERFLOWSW | 185 | 183 |  | 06.04.01.04.02.00.00.00 | TAP-127798 | TAP-127800 | [TAP-127798_USERFLOWSW] ¦ [UFSW] Attachment workflow fix for multiple defects | Feature Estimation | Open | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 45 | 80 | 0 | 0% | 45 | 80 | Feature Estimation
TAP-127878 | 186 |  |  | 06.04.01.05.00.00.00.00 |  | TAP-127878 | [TAP-127878] ¦ [IRR] HALT workflow improvements | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 15 | 35 | Feature Estimation
TAP-127878_COREINSTRUMENTS | 187 | 186 |  | 06.04.01.05.01.00.00.00 | TAP-127878 | TAP-127879 | [TAP-127878_COREINSTRUMENTS] ¦ [IRR][Core Instruments] HALT workflow improvements | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS |  |  | 0 | 0 | 15 | 35 | 0 | 0% | 15 | 35 | Feature Estimation
TAP-127878_USERFLOWSW | 188 | 186 |  | 06.04.01.05.02.00.00.00 | TAP-127878 | TAP-127880 | [TAP-127878_USERFLOWSW] ¦ [IRR][UFSW] HALT workflow improvements | Feature Estimation | Open | Advanced Instruments - User Flow SW | USERFLOWSW |  |  | 0 | 0 | 15 | 35 | 0 | 0% | 15 | 35 | Feature Estimation
TAP-127878_USERFLOWSW | 189 | 186 |  | 06.04.02.01.00.00.00.00 |  | RAS-13292 | [TAP-127878_USERFLOWSW] ¦ [IRR][UFSW] HALT workflow improvements | Defect | DEFERRED |  |  |  |  | 0 | 0 | 15 | 35 | 0 | 0% | 15 | 35 | Feature Estimation
TAP-94573 | 190 |  |  | 06.04.03.02.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-109680 | 191 | 202 |  | 06.04.03.02.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  |  |  | 18 | 0 | 1 hr | 1 hr | 18 | 0% |  |  | Story Points
TAP-109680 | 192 | 191 |  | 06.04.03.03.00.00.00.00 |  | RAS-4536 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Defect | In progress |  |  |  |  | 33 | 0 | 33 | 39.6 | 33 | 0% |  |  | Story Points
TAP-124484 | 193 | 202 |  | 06.04.03.03.01.00.00.00 |  | TAP-124484 | [TAP-124484] ¦ [RAS-4536] [Stellars] Undefined response to SIM/Instrument Memory Error | Feature | PROPOSED |  |  |  |  | 31 | 0 | 1 hr | 1 hr | 31 | 0% | 0 | 0 | Story Points
TAP-111760 | 194 | 195 | 1, 38, 26, 17, 36, 14, 34, 4, 7, 32, 30, 22, 9, 13, 20, 6, 25, 19, 28, 11, 3, 41, 5, 24, 40 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111763 | 195 | 198, 197 | 194 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111763_SEAMLESS | 196 | 195 |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-127945 | 197 |  | 195 | 07.03.00.00.00.00.00.00 |  | TAP-127945 | [TAP-127945] ¦ [Prochain][IRR] EC1 Prochain Endpoint | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113104 | 198 | 199 | 195, 44, 42, 99, 90, 70, 95, 69, 91, 104 | 07.04.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113105 | 199 | 202, 201 | 198 | 07.05.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113105_SEAMLESS | 200 | 199 |  | 07.05.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-127946 | 201 |  | 199 | 07.06.00.00.00.00.00.00 |  | TAP-127946 | [TAP-127946] ¦ [Prochain][IRR] EC2 Prochain Endpoint | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111765 | 202 | 203 | 108, 110, 112, 114, 116, 118, 120, 122, 124, 126, 128, 130, 132, 138, 144, 199, 193, 191, 175, 182, 183 | 07.07.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111768 | 203 | 204 | 202 | 07.08.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111769 | 204 | 205 | 203 | 07.09.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-111767 | 205 | 149, 207 | 204 | 07.10.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-111767_SEAMLESS | 206 | 205 |  | 07.10.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-127947 | 207 |  | 205 | 07.11.00.00.00.00.00.00 |  | TAP-127947 | [TAP-127947] ¦ [Prochain][IRR] RC1 Prochain Endpoint | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113101 | 208 | 209 | 146 | 07.12.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113102 | 209 | 210 | 208 | 07.13.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-113103 | 210 | 213, 212 | 209 | 07.14.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 10 | 15 | Feature Estimation
TAP-113103_SEAMLESS | 211 | 210 |  | 07.14.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS |  |  | 0 | 0 | 10 | 15 | 0 | 100% | 10 | 15 | Feature Estimation
TAP-127948 | 212 |  | 210 | 07.15.00.00.00.00.00.00 |  | TAP-127948 | [TAP-127948] ¦ [Prochain][IRR] RC2 Prochain Endpoint | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation
TAP-121104 | 213 |  | 149, 159, 161, 166, 168, 170, 172, 210 | 07.16.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Feature Estimation

## Log
DataTimeStamp (?) | Event (?) | Data (?) | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
|  |  | TAP-121104 |  | TAP-112113

## Summary
Resource Names | Sum FDR
COREINSTRUMENTS | 1987
I2E | 519
ANIMATORS | 99
FRED | 145
PUPPETEERS | 336.5
JACOBIANS | 683.5
CASTLEBLACK | 259.5
BOOSTERS | 136
USERFLOWSW | 755
INBETWEENERS | 282
ZENITH | 93
CLASSY2 | 70
PIXELPOETS | 440
STELLARS | 86
DRUSHTI | 136
BUGHUNTERS | 116
SUNRISERS | 131
TEAMBD | 131
COSSACKS | 131
BUILDERS | 22
ASTRANPSDEVELOPERS | 130
TOOLSRULES | 150
TRIPLETEA | 130
ASTRANPSVALIDATORS | 50
SEAMLESS | 59522.5