## Project
Text10 | Unique ID | Unique ID Successors | Unique ID Predecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Number10 | Number11 | Duration | Duration1 | Number12 | % Complete | Number13 | Number14 | Text24
TAP-79978 | 1 | 3, 2 | 206, 260, 96, 237, 243, 246, 255, 351, 146 | 03.02.00.00.00.00.00.00 |  | TAP-79978 | [TAP-79978] ¦ [Milestone][V4.0] (EC1) Engineering Candidate 1 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85787 | 2 |  | 1 | 03.03.00.00.00.00.00.00 |  | TAP-85787 | [TAP-85787] ¦ [Prochain][V4.0] (EC1) Engineering Candidate 1 Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79979 | 3 | 4, 5, 408, 411 | 380, 358, 386, 396, 352, 387, 385, 1, 404, 403, 402, 37, 397, 381, 97, 367, 322, 264, 454, 240, 453, 131, 332, 319, 470, 471, 473, 462, 463, 465, 467, 474, 472 | 03.04.00.00.00.00.00.00 |  | TAP-79979 | [TAP-79979] ¦ [Milestone][V4.0] (EC2) Engineering Candidate 2 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85788 | 4 |  | 3 | 03.05.00.00.00.00.00.00 |  | TAP-85788 | [TAP-85788] ¦ [Prochain][V4.0] (EC2) Engineering Candidate 2 Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79981 | 5 | 6, 9 | 398, 256, 249, 455, 326, 405, 325, 3, 273, 205, 280, 324, 456, 55, 364, 363, 362, 29, 93, 388, 128, 35, 27, 53, 323, 248, 272, 320, 328, 375, 377, 468, 46 | 03.06.00.00.00.00.00.00 |  | TAP-79981 | [TAP-79981] ¦ [Milestone][V4.0] (EC3) Engineering Candidate 3 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104120 | 6 |  | 5 | 03.07.00.00.00.00.00.00 |  | TAP-104120 | [TAP-104120] ¦ [Prochain][V4.0] (EC3) Engineering Candidate 3 Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104131 | 7 | 8, 9 | 148 | 03.08.00.00.00.00.00.00 |  | TAP-104131 | [TAP-104131] ¦ [Milestone][V4.0] (RC1) Release Candidate 1 Finalized Test Code and NPS | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104132 | 8 |  | 7 | 03.09.00.00.00.00.00.00 |  | TAP-104132 | [TAP-104132] ¦ [Prochain][V4.0] (RC1) Release Candidate 1 Finalized Test Code and NPS Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79982 | 9 | 11, 10 | 101, 327, 376 | 03.10.00.00.00.00.00.00 |  | TAP-79982 | [TAP-79982] ¦ [Milestone][V4.0] (BRR) Build Readiness Review | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104121 | 10 |  | 9 | 03.11.00.00.00.00.00.00 |  | TAP-104121 | [TAP-104121] ¦ [Prochain][V4.0] (BRR) Build Readiness Review Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79983 | 11 | 15, 12, 183, 184 |  | 03.12.00.00.00.00.00.00 |  | TAP-79983 | [TAP-79983] ¦ [Milestone][V4.0] (TRR) Test Readiness Review | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85789 | 12 |  | 11 | 03.13.00.00.00.00.00.00 |  | TAP-85789 | [TAP-85789] ¦ [Prochain][V4.0] (TRR) Test Readiness Review Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83580 | 13 | 14 | 84 | 03.14.00.00.00.00.00.00 |  | TAP-83580 | [TAP-83580] ¦ [Milestone][V4.0] (RC2) Release Candidate 2 USA Launch Service and Manufacturing Support | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104122 | 14 |  | 13 | 03.15.00.00.00.00.00.00 |  | TAP-104122 | [TAP-104122] ¦ [Prochain][V4.0] (RC2) Release Candidate 2 USA Launch Service and Manufacturing Support Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-79984 | 15 | 17, 16 | 189, 190, 215, 217, 225 | 03.16.00.00.00.00.00.00 |  | TAP-79984 | [TAP-79984] ¦ [Milestone][V4.0] V&V Complete | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104178 | 16 |  | 15 | 03.17.00.00.00.00.00.00 |  | TAP-104178 | [TAP-104178] ¦ [Prochain][V4.0] V&V Complete Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-79985 | 17 | 18 | 15, 365, 218, 219, 228, 222, 229, 226, 227, 220, 223, 224, 221, 196, 216 | 03.18.00.00.00.00.00.00 |  | TAP-79985 | [TAP-79985] ¦ [Milestone][V4.0] (DVR) Design Verification Review | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104179 | 18 |  | 17 | 03.19.00.00.00.00.00.00 |  | TAP-104179 | [TAP-104179] ¦ [Prochain][V4.0] (DVR) Design Verification Review Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104128 | 19 | 20 | 435, 436 | 03.20.00.00.00.00.00.00 |  | TAP-104128 | [TAP-104128] ¦ [Milestone][V4.0] (RC3-Manufacturing) Release Candidate 3 Full Plexus Transfer Code | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104173 | 20 |  | 19 | 03.21.00.00.00.00.00.00 |  | TAP-104173 | [TAP-104173] ¦ [Prochain][V4.0] (RC3-Manufacturing) Release Candidate 3 Full Plexus Transfer Code Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-87766 | 21 | 22 | 73, 439, 438, 437, 440, 441, 447, 448, 449 | 03.22.00.00.00.00.00.00 |  | TAP-87766 | [TAP-87766] ¦ [Milestone][V4.0] NPS Manufacturing SW Complete | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104180 | 22 |  | 21 | 03.23.00.00.00.00.00.00 |  | TAP-104180 | [TAP-104180] ¦ [Prochain][V4.0] NPS Manufacturing SW Complete Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-83590 | 23 | 24 | 444 | 03.24.00.00.00.00.00.00 |  | TAP-83590 | [TAP-83590] ¦ [Milestone][V4.0] NPS Service Software | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104181 | 24 |  | 23 | 03.25.00.00.00.00.00.00 |  | TAP-104181 | [TAP-104181] ¦ [Prochain][V4.0] NPS Service Software Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104181 | 25 | 24 |  | 04.01.00.00.00.00.00.00 |  | RAS-11338 | [TAP-104181] ¦ [Prochain][V4.0] NPS Service Software Prochain Buffer | Enhancement | Confirmed |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-86327 | 26 | 1 |  | 04.01.01.00.00.00.00.00 |  | TAP-86327 | [TAP-86327] ¦ (RAS-11338) Log Event and notify user when no LLM is detected on ACA | Feature | Done |  |  |  |  | 25 | 25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104062 | 27 | 5 |  | 04.02.01.00.00.00.00.00 |  | TAP-104062 | [TAP-104062] ¦ [v4.0] (RAS-11933) Add torque stable logging to IDU startup | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47497 | 28 | 1 |  | 04.06.01.00.00.00.00.00 |  | TAP-47497 | [TAP-47497] ¦ [MTBI] (Batch B) Allow setup joints to be manual controllable after ACA hot swap | Feature | Done |  |  |  |  | 23 | 23 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95751 | 29 | 5 |  | 04.08.01.00.00.00.00.00 |  | TAP-95751 | [TAP-95751] ¦ [RAS-12678][v4.0] Add instrument use life limit as a event | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79084 | 30 | 1 |  | 04.10.01.00.00.00.00.00 |  | TAP-79084 | [TAP-79084] ¦ [iSim][v4.0] Add system deactivation functionality to the iSim + SC Configuration | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86325 | 31 | 1 |  | 04.12.01.00.00.00.00.00 |  | TAP-86325 | [TAP-86325] ¦ (RAS-7054) Allow Wristed instrument fails calibration retries without detaching the instrument | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86030 | 32 | 1 |  | 04.13.01.00.00.00.00.00 |  | TAP-86030 | [TAP-86030] ¦ (RAS-7239) Avoid flooding of UPS_manager tmp logs | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95635 | 33 | 1 |  | 04.15.01.00.00.00.00.00 |  | TAP-95635 | [TAP-95635] ¦ [RAS-11445] Add SMC Encode Initialization offsets to sqlite database | Feature | Done |  |  |  |  | 11.5 | 11.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84571 | 34 | 1 |  | 04.18.01.00.00.00.00.00 |  | TAP-84571 | [TAP-84571] ¦ (Close RAS-10913) Improve peripheral compat robustness by retrying after a wait period | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97497 | 35 | 5 |  | 04.20.01.00.00.00.00.00 |  | TAP-97497 | [TAP-97497] ¦ [Drushti][RAS-1210] Change ACAD Error state color | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-6975 | 36 | 1 |  | 04.21.02.00.00.00.00.00 |  | TAP-6975 | [TAP-6975] ¦ [GUI](RAS-1818) Align behavior to match ergonomics when clutching and firing energy | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71016 | 37 | 3 |  | 04.27.01.00.00.00.00.00 |  | TAP-71016 | [TAP-71016] ¦ [iSim][v4.0] Update Surgical Science Trainer build | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94703 | 38 | 1 |  | 04.29.01.00.00.00.00.00 |  | TAP-94703 | [TAP-94703] ¦ [RAS-11307] Indication of system deactivation from Tower startup failures | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58230 | 39 | 1 |  | 04.31.01.00.00.00.00.00 |  | TAP-58230 | [TAP-58230] ¦ [Tech Debt] Initial Build Variant Work | Feature | Done |  |  |  |  | 49 | 49 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-61982 | 40 | 1 |  | 04.31.02.00.00.00.00.00 |  | TAP-61982 | [TAP-61982] ¦ Merge gated derating infrastructure to develop | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-68699 | 41 | 1 |  | 04.31.04.00.00.00.00.00 |  | TAP-68699 | [TAP-68699] ¦ [Croc] Implement Twitch de-rating in iSim for user studies | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83329 | 42 | 1 |  | 04.31.08.00.00.00.00.00 |  | TAP-83329 | [TAP-83329] ¦ [Croc] [Tech Debt] Finalize Croc Variants Merge to Develop | Feature | Done |  |  |  |  | 43.75 | 43.75 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-6337 | 43 | 1 |  | 04.31.10.00.00.00.00.00 |  | TAP-6337 | [TAP-6337] ¦ [TechDebt] SPIKE - Consolidate instrument angle sign conventions across SRA and IDU | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86333 | 44 | 1 |  | 04.32.01.00.00.00.00.00 |  | TAP-86333 | [TAP-86333] ¦ complete pending work for RAS-6750, RAS-6239 | Feature | Done |  |  |  |  | 10.75 | 10.75 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86312 | 45 | 1 |  | 04.33.01.00.00.00.00.00 |  | TAP-86312 | [TAP-86312] ¦ (RAS-6961)Retry ACA calibration in the instance when calibration times out during an arm hotswap | Feature | Done |  |  |  |  | 50 | 50 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-114212 | 46 | 5 |  | 04.39.01.00.00.00.00.00 |  | TAP-114212 | [TAP-114212] ¦ [V4.0][EC3][SC2] Fix RAS-13574 | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84573 | 47 | 1 |  | 04.45.01.00.00.00.00.00 |  | TAP-84573 | [TAP-84573] ¦ [Drushti](RAS-9521) GUI Stuck Calibrate Arms Screen | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81873 | 48 | 1 |  | 04.49.01.00.00.00.00.00 |  | TAP-81873 | [TAP-81873] ¦ [US URO] De-rating Prototype Jaw Opening & Closing Forces | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81874 | 49 | 1 |  | 04.49.02.00.00.00.00.00 |  | TAP-81874 | [TAP-81874] ¦ [US URO] De-rating Prototype Tracking Errors | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81924 | 50 | 1 |  | 04.49.03.00.00.00.00.00 |  | TAP-81924 | [TAP-81924] ¦ [US URO] De-rating Prototype Range Of Motion | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81925 | 51 | 1 |  | 04.49.04.00.00.00.00.00 |  | TAP-81925 | [TAP-81925] ¦ [US URO] De-rating Prototype Endoscope Directional Accuracy | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81926 | 52 | 1 |  | 04.49.05.00.00.00.00.00 |  | TAP-81926 | [TAP-81926] ¦ [US URO] De-rating Prototype Translation Distance in Time | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-91222 | 53 | 5 |  | 04.49.06.00.00.00.00.00 |  | TAP-91222 | [TAP-91222] ¦ [IRR][US URO] Set and Lock Out Articulation and Roll in De-Rating Tool | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96638 | 54 | 1 |  | 04.49.09.00.00.00.00.00 |  | TAP-96638 | [TAP-96638] ¦ [US URO] - Update URO Derating Tools to Address TMD Feedback | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104444 | 55 | 5 |  | 04.49.10.00.00.00.00.00 |  | TAP-104444 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113408 | 56 | 9 |  | 04.56.01.00.00.00.00.00 |  | TAP-113408 | [TAP-113408] ¦ [Foundation] Fix Design Documentation | Feature | Done |  |  |  |  | 50.8 | 50.8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113410 | 57 | 9 |  | 04.56.03.00.00.00.00.00 |  | TAP-113410 | [TAP-113410] ¦ [Core Instr] Fix Design Documentation | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-125059 | 58 | 13 |  | 04.57.01.00.00.00.00.00 |  | TAP-125059 | [TAP-125059] ¦ [V4.0][Cyber] Upgrade from Staging GSO to Production GSO for build signing | Feature | Accepted |  |  |  |  | 24 | 2 | 1 hr | 1 hr | 22 | 8.333% | 0 | 0 | Story Points
TAP-125059 | 59 | 58 |  | 04.58.00.00.00.00.00.00 |  | RAS-15043 | [TAP-125059] ¦ [V4.0][Cyber] Upgrade from Staging GSO to Production GSO for build signing | Defect | In progress |  |  |  |  | 34.5 | 2 | 34.5 | 41.4 | 32.5 | 5.797% | 0 | 0 | Story Points
TAP-125059 | 60 | 58 |  | 04.59.00.00.00.00.00.00 |  | RAS-13563 | [TAP-125059] ¦ [V4.0][Cyber] Upgrade from Staging GSO to Production GSO for build signing | Enhancement | In progress |  |  |  |  | 37.5 | 2 | 37.5 | 45 | 35.5 | 5.333% | 0 | 0 | Story Points
TAP-93577 | 61 | 13 |  | 04.59.01.00.00.00.00.00 |  | TAP-93577 | [TAP-93577] ¦ {GUI}(v4.0) [Cyber] Package and send translation package to GDS | Feature | Done |  |  |  |  | 20 | 20 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96537 | 62 | 13 |  | 04.59.03.00.00.00.00.00 |  | TAP-96537 | [TAP-96537] ¦ {GUI} (RAS-7008) v3.0 Language Formals and Release | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-116321 | 63 | 13 |  | 04.59.08.00.00.00.00.00 |  | TAP-116321 | [TAP-116321] ¦ {GUI} (RAS-13563) v4.0 Language Formals and Release | Feature | Accepted |  |  |  |  | 18 | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0 | Story Points
TAP-116321 | 64 | 63 |  | 04.60.00.00.00.00.00.00 |  | RAS-15162 | [TAP-116321] ¦ {GUI} (RAS-13563) v4.0 Language Formals and Release | Defect | In progress |  |  |  |  | 35 | 0 | 35 | 42 | 35 | 0% | 0 | 0 | Story Points
TAP-126027 | 65 | 13 |  | 04.60.01.00.00.00.00.00 |  | TAP-126027 | [TAP-126027] ¦ [V4.0][RC1][Cyber] Implement penetration testing findings for WolfSSH 1.4.17 | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58674 | 66 | 13 |  | 04.61.01.00.00.00.00.00 |  | TAP-58674 | [TAP-58674] ¦ [Cyber] Implement Fixes for Findings in Micro Penetration Testing for DDS/UDP | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-109870 | 67 | 13 |  | 04.63.01.00.00.00.00.00 |  | TAP-109870 | [TAP-109870] ¦ [Cyber] ESAT v2, Support Field Service Use of CyberArk P2 | Feature | Accepted |  |  |  |  | 121 | 85 | 1 hr | 1 hr | 36 | 70.25% | 0 | 0 | Story Points
TAP-122714 | 68 | 13 |  | 04.63.02.00.00.00.00.00 |  | TAP-122714 | [TAP-122714] ¦ [V4.0][RC2] ESAT v2: Additional ESAT and NPS content for V4 RC2 | Feature | Accepted |  |  |  |  | 130 | 59 | 1 hr | 1 hr | 71 | 45.38% | 0 | 0 | Story Points
TAP-122714 | 69 | 68 |  | 04.63.02.08.00.00.00.00 | TAP-122714 | TAP-81292 | [TAP-122714] ¦ [V4.0][RC2] ESAT v2: Additional ESAT and NPS content for V4 RC2 | Issue | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 155 | 59 | 155 | 186 | 96 | 100% | 0 | 0 | Story Points
TAP-122714 | 70 | 68 |  | 04.63.02.13.01.00.00.00 | TAP-122714 | TAP-126254 | [TAP-122714] ¦ [V4.0][RC2] ESAT v2: Additional ESAT and NPS content for V4 RC2 | Sub Task | In progress |  |  |  |  | 176 | 59 | 176 | 211.2 | 117 | 33.52% | 0 | 0 | Story Points
TAP-102220 | 71 | 13 |  | 04.63.02.16.00.00.00.00 | TAP-122714 | TAP-102220 | [TAP-102220] ¦ [V4] [Cyber] ESAT Laptop certificate installation | Feature | Done |  |  |  |  | 38 | 38 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84375 | 72 | 13 |  | 04.64.01.00.00.00.00.00 |  | TAP-84375 | [TAP-84375] ¦ [Cyber] US FRU Replacement Script/Procedure Updates | Feature | Done |  |  |  |  | 78 | 78 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87778 | 73 | 21 |  | 04.64.02.00.00.00.00.00 |  | TAP-87778 | [TAP-87778] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 2 (validation) | Feature | In progress |  |  |  |  | 42 | 0 | 1 hr | 1 hr | 42 | 0% | 0 | 0 | Story Points
TAP-115441 | 74 | 13 |  | 04.64.05.00.00.00.00.00 |  | TAP-115441 | [TAP-115441] ¦ [Cyber] Ubuntu BSP To support Plexus Programming | Feature | Accepted |  |  |  |  | 48.5 | 20 | 1 hr | 1 hr | 28.5 | 41.24% | 0 | 0 | Story Points
TAP-115441 | 75 | 74 |  | 04.65.00.00.00.00.00.00 |  | RAS-15282 | [TAP-115441] ¦ [Cyber] Ubuntu BSP To support Plexus Programming | Enhancement | In progress |  |  |  |  | 85 | 20 | 85 | 102 | 65 | 23.53% | 0 | 0 | Story Points
TAP-86043 | 76 | 13 |  | 04.65.01.00.00.00.00.00 |  | TAP-86043 | [TAP-86043] ¦ [Cyber] Enable ARM production security features | Feature | Accepted |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Story Points
TAP-86043 | 77 | 76 |  | 04.66.00.00.00.00.00.00 |  | RAS-15141 | [TAP-86043] ¦ [Cyber] Enable ARM production security features | Enhancement | In progress |  |  |  |  | 3 | 0 | 3 | 3.6 | 3 | 0% | 0 | 0 | Story Points
TAP-111218 | 78 | 13 |  | 04.66.01.00.00.00.00.00 |  | TAP-111218 | [TAP-111218] ¦ [Cyber] Non Production Boot Deployment | Feature | In progress |  |  |  |  | 64 | 59 | 1 hr | 1 hr | 5 | 92.19% | 0 | 0 | Story Points
TAP-111218 | 79 | 78 |  | 04.67.00.00.00.00.00.00 |  | RAS-15154 | [TAP-111218] ¦ [Cyber] Non Production Boot Deployment | Defect | In progress |  |  |  |  | 122 | 59 | 122 | 146.4 | 63 | 48.36% | 0 | 0 | Story Points
TAP-125598 | 80 | 13 |  | 04.67.01.00.00.00.00.00 |  | TAP-125598 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Feature | Accepted |  |  |  |  | 12.5 | 0 | 1 hr | 1 hr | 12.5 | 0% | 0 | 0 | Story Points
TAP-125598 | 81 | 80 |  | 04.68.00.00.00.00.00.00 |  | RAS-15284 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Defect | In progress |  |  |  |  | 22 | 0 | 22 | 26.4 | 22 | 0% | 0 | 0 | Story Points
TAP-125598 | 82 | 80 |  | 04.68.01.00.00.00.00.00 |  | TAP-124550 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Issue | Open | Released Product Engineering - Drushti | DRUSHTI |  |  | 22 | 0 | 22 | 26.4 | 22 | 0% | 0 | 0 | Story Points
TAP-125598 | 83 | 80 |  | 04.70.00.00.00.00.00.00 |  | RAS-15286 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Enhancement | In progress |  |  |  |  | 22 | 0 | 22 | 26.4 | 22 | 0% | 0 | 0 | Story Points
TAP-128136 | 84 | 13 |  | 04.71.02.00.00.00.00.00 |  | TAP-128136 | [TAP-128136] ¦ {v4 RC2} RAS-15283 - Radio Button Misalignment in Visualization Screen for Non-English Languages | Feature | PROPOSED |  |  |  |  | 5 | 0 | 1 hr | 1 hr | 5 | 0% | 0 | 0 | Story Points
TAP-128136 | 85 | 84 |  | 04.72.00.00.00.00.00.00 |  | RAS-10734 | [TAP-128136] ¦ {v4 RC2} RAS-15283 - Radio Button Misalignment in Visualization Screen for Non-English Languages | Enhancement | In progress |  |  |  |  | 5 | 0 | 5 | 6 | 5 | 0% | 0 | 0 | Story Points
TAP-94626 | 86 | 1 |  | 04.72.04.00.00.00.00.00 |  | TAP-94626 | [TAP-94626] ¦ Reduce SW Verification dependency on test setup and tools - implementation | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115657 | 87 | 11 |  | 04.72.08.00.00.00.00.00 |  | TAP-115657 | [TAP-115657] ¦ [Cyber] Tracking Documentation For Design Outputs - EIN V4.0 Testability Detailed Designs | Feature | Done |  |  |  |  | 18.5 | 18.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-125101 | 88 | 13 |  | 04.72.12.00.00.00.00.00 |  | TAP-125101 | [TAP-125101] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - Foundation | Feature | Accepted |  |  |  |  | 79 | 17 | 1 hr | 1 hr | 62 | 21.52% | 0 | 0 | Story Points
TAP-125113 | 89 | 13 |  | 04.72.13.00.00.00.00.00 |  | TAP-125113 | [TAP-125113] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - AdvancedInstr | Feature | Accepted |  |  |  |  | 8.25 | 0 | 1 hr | 1 hr | 8.25 | 0% | 0 | 0 | Story Points
TAP-125114 | 90 | 13 |  | 04.72.14.00.00.00.00.00 |  | TAP-125114 | [TAP-125114] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - CoreInstr | Feature | Accepted |  |  |  |  | 6 | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-125114 | 91 | 90 |  | 04.72.16.00.00.00.00.00 |  | TAP-127952 | [TAP-125114] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - CoreInstr | Issue | In progress | Foundation - Storm Chasers | STORMCHASERS |  |  | 6 | 0 | 6 | 7.2 | 6 | 0% | 0 | 0 | Story Points
TAP-95509 | 92 | 1 |  | 05.01.00.00.00.00.00.00 |  | TAP-95509 | [TAP-95509] ¦ [IDP] Generate Doxygen documentation for every mainline. | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103380 | 93 | 5 |  | 05.02.00.00.00.00.00.00 |  | TAP-103380 | [TAP-103380] ¦ [IDP][Enabler] CMake clean-up | Feature | Done |  |  |  |  | 18.5 | 18.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-102422 | 94 | 9 |  | 05.03.00.00.00.00.00.00 |  | TAP-102422 | [TAP-102422] ¦ [IDP][Foundation] Support integration of the design documents into the code repository | Feature | Done |  |  |  |  | 17.2 | 17.2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95500 | 95 | 1 |  | 05.04.00.00.00.00.00.00 |  | TAP-95500 | [TAP-95500] ¦ [IDP] Use Code Change Impact Analysis Tool in Production | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95095 | 96 | 1 |  | 05.05.00.00.00.00.00.00 |  | TAP-95095 | [TAP-95095] ¦ [Tech Debt] PI12 - Improve Unit Tests (Foundation) | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-73233 | 97 | 3 |  | 05.06.00.00.00.00.00.00 |  | TAP-73233 | [TAP-73233] ¦ [Architecture][Infrastructure] Improve KPI collection and processing software | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87661 | 98 | 1 |  | 05.07.00.00.00.00.00.00 |  | TAP-87661 | [TAP-87661] ¦ [V&V Enabler] SW Verification - Improvements Batch2 - Foundation | Feature | Done |  |  |  |  | 9.5 | 9.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55705 | 99 | 1 |  | 05.08.00.00.00.00.00.00 |  | TAP-55705 | [TAP-55705] ¦ Refactor logging library | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55471 | 100 | 1 |  | 05.09.00.00.00.00.00.00 |  | TAP-55471 | [TAP-55471] ¦ [V4.0] Keep alarms, errors, safety, communication SW verification tests up to date | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-117503 | 101 | 9 |  | 05.10.00.00.00.00.00.00 |  | TAP-117503 | [TAP-117503] ¦ [Shared Services] [v4.0] sFMEA update and review | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83615 | 102 | 1 |  | 05.11.00.00.00.00.00.00 |  | TAP-83615 | [TAP-83615] ¦ [Architecture][Enabler] GECAT for Instruments Data Transportation - Foundation Support | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82932 | 103 | 1 |  | 05.12.00.00.00.00.00.00 |  | TAP-82932 | [TAP-82932] ¦ [V4.0] Stability issue investigation and resolution - PI11 | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-93110 | 104 | 1 |  | 05.13.00.00.00.00.00.00 |  | TAP-93110 | [TAP-93110] ¦ [V4.0][Architecture] Improve SW Virtualization Platform | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86330 | 105 | 1 |  | 05.14.00.00.00.00.00.00 |  | TAP-86330 | [TAP-86330] ¦ [v4.0](TAP-66316) Add SMC data recorder bfbs schema file to SMC Application package | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83225 | 106 | 1 |  | 05.15.00.00.00.00.00.00 |  | TAP-83225 | [TAP-83225] ¦ [v4.0] Expanding ENDOSW tests to perform integration testing with GUI | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70472 | 107 | 1 |  | 05.16.00.00.00.00.00.00 |  | TAP-70472 | [TAP-70472] ¦ [V4.0] Implement EDID based detection of S3D and use Intel UHD graphics driver for SCDC Windows installation | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-16423 | 108 | 1 |  | 05.17.00.00.00.00.00.00 |  | TAP-16423 | [TAP-16423] ¦ [Infra] SW Integration Framework Prototype | Feature | Done |  |  |  |  | 139 | 139 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2693 | 109 | 1 |  | 05.18.00.00.00.00.00.00 |  | TAP-2693 | [TAP-2693] ¦ [Tech Debt][platformers][V&V] test infrastructure improvements Batch 1 | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-6886 | 110 | 1 |  | 05.19.00.00.00.00.00.00 |  | TAP-6886 | [TAP-6886] ¦ [Compliance] Establish Controlled Process for log data specification in JAMA | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115484 | 111 | 7 |  | 05.20.00.00.00.00.00.00 |  | TAP-115484 | [TAP-115484] ¦ QNX 7.1 BSP for FSE test fixture | Feature | Done |  |  |  |  | 4.1 | 4.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-64261 | 112 | 7 |  | 05.21.00.00.00.00.00.00 |  | TAP-64261 | [TAP-64261] ¦ [v4.0 SW][Arch][Enabler] Improve Unit Tests (Foundation) | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76479 | 113 | 1 |  | 05.22.00.00.00.00.00.00 |  | TAP-76479 | [TAP-76479] ¦ [Architecture][Spike] Future Software Item Breakdown - Align SWI, Repository, and Requirements - PI12 | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-48935 | 114 | 1 |  | 05.23.00.00.00.00.00.00 |  | TAP-48935 | [TAP-48935] ¦ [TechDebt]Refactor EtherCAT communication | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47057 | 115 | 1 |  | 05.24.00.00.00.00.00.00 |  | TAP-47057 | [TAP-47057] ¦ [Tech Debt] Integrate log_clock into product | Feature | Done |  |  |  |  | 49 | 49 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83342 | 116 | 1 |  | 05.25.00.00.00.00.00.00 |  | TAP-83342 | [TAP-83342] ¦ ESAT v2 Stability and Usability Enhancements | Feature | Done |  |  |  |  | 130 | 130 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71137 | 117 | 1 |  | 05.26.00.00.00.00.00.00 |  | TAP-71137 | [TAP-71137] ¦ [v4.0] GUI codebase cleanup | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-99176 | 118 | 7 |  | 05.27.00.00.00.00.00.00 |  | TAP-99176 | [TAP-99176] ¦ Update Failing Tests and Static Analysis | Feature | Done |  |  |  |  | 95 | 95 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95508 | 119 | 7 |  | 05.28.00.00.00.00.00.00 |  | TAP-95508 | [TAP-95508] ¦ [IDP] Improve build system - Batch 1 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95505 | 120 | 1 |  | 05.29.00.00.00.00.00.00 |  | TAP-95505 | [TAP-95505] ¦ [IDP] Support Unit Verification Process Improvement - Batch 1 | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72843 | 121 | 1 |  | 05.30.00.00.00.00.00.00 |  | TAP-72843 | [TAP-72843] ¦ Support collapse of develop-next back to develop | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70775 | 122 | 1 |  | 05.31.00.00.00.00.00.00 |  | TAP-70775 | [TAP-70775] ¦ [Infrastructure] Setup Minimal Simulink Projects for Impact Analysis Verification | Feature | Done |  |  |  |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-54303 | 123 | 1 |  | 05.32.00.00.00.00.00.00 |  | TAP-54303 | [TAP-54303] ¦ [Architecture][Spike] Future Software Item Breakdown - Align SWI, Repository, and Requirements | Feature | Done |  |  |  |  | 57.9 | 57.9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85444 | 124 | 1 |  | 05.33.00.00.00.00.00.00 |  | TAP-85444 | [TAP-85444] ¦ [V4.0][Visual] Tests and development process improvements after the new codebase merge | Feature | Done |  |  |  |  | 23.5 | 23.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81827 | 125 | 1 |  | 05.34.00.00.00.00.00.00 |  | TAP-81827 | [TAP-81827] ¦ [Infrastructure] Reduce Simulink Verification Runtime | Feature | Done |  |  |  |  | 53.5 | 53.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-66620 | 126 | 1 |  | 05.35.00.00.00.00.00.00 |  | TAP-66620 | [TAP-66620] ¦ [Tech Debt] Remove Testability Branch for Simulink Tools | Feature | Done |  |  |  |  | 53 | 53 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97622 | 127 | 7 |  | 05.36.00.00.00.00.00.00 |  | TAP-97622 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Feature | Done |  |  |  |  | 72 | 72 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104009 | 128 | 5 |  | 05.37.00.00.00.00.00.00 |  | TAP-104009 | [TAP-104009] ¦ [V2.2] Field Script Readiness Evaluation | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-49649 | 129 | 1 |  | 05.38.00.00.00.00.00.00 |  | TAP-49649 | [TAP-49649] ¦ [Tech Debt] Complete ACS Rework | Feature | Done |  |  |  |  | 47 | 47 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113409 | 130 | 197, 9 |  | 05.39.00.00.00.00.00.00 |  | TAP-113409 | [TAP-113409] ¦ [V4][Adv Instr] Fix Design Documentation | Feature | Done |  |  |  |  | 28.5 | 28.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-68411 | 131 | 3 |  | 05.40.00.00.00.00.00.00 |  | TAP-68411 | [TAP-68411] ¦ [TechDebt] [v4.0] Remove sphlib | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76424 | 132 | 1 |  | 05.41.00.00.00.00.00.00 |  | TAP-76424 | [TAP-76424] ¦ [Tech Debt] Improve Unit Tests (Foundation) | Feature | Done |  |  |  |  | 28 | 28 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-69437 | 133 | 1 |  | 05.42.00.00.00.00.00.00 |  | TAP-69437 | [TAP-69437] ¦ [Architecture] Improve alarm code generator workflow | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72858 | 134 | 1 |  | 05.43.00.00.00.00.00.00 |  | TAP-72858 | [TAP-72858] ¦ [V4.0][Inogeni][TechDebt] Post-release support and software refactoring | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72842 | 135 | 1 |  | 05.44.00.00.00.00.00.00 |  | TAP-72842 | [TAP-72842] ¦ Support collapse of develop-next back to develop | Feature | Done |  |  |  |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-61255 | 136 | 1 |  | 05.45.00.00.00.00.00.00 |  | TAP-61255 | [TAP-61255] ¦ [V4.0] Improve performance of Data Access software to allow support of more logs collection | Feature | Done |  |  |  |  | 79 | 79 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-53969 | 137 | 1 |  | 05.46.00.00.00.00.00.00 |  | TAP-53969 | [TAP-53969] ¦ [v4.0 SW][Tech Debt] Migrate C++ Unit Tests to new process/framework | Feature | Done |  |  |  |  | 72 | 72 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84311 | 138 | 1 |  | 05.47.00.00.00.00.00.00 |  | TAP-84311 | [TAP-84311] ¦ [Architecture][Infrastructure] Use Code Change Impact Analysis Tool to run only affected unit-tests | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-37832 | 139 | 1 |  | 05.48.00.00.00.00.00.00 |  | TAP-37832 | [TAP-37832] ¦ [v4.0 SW][techDebt] Fix remaining coverity findings for v4.0 software (PI7 Platform) | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-36556 | 140 | 1 |  | 05.49.00.00.00.00.00.00 |  | TAP-36556 | [TAP-36556] ¦ [Arch]Cleanup EtherCAT communication | Feature | Done |  |  |  |  | 40.25 | 40.25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47543 | 141 | 1 |  | 05.50.00.00.00.00.00.00 |  | TAP-47543 | [TAP-47543] ¦ [Arch][Enabler] Rework ACS Core | Feature | Done |  |  |  |  | 100.5 | 100.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-63938 | 142 | 1 |  | 05.51.00.00.00.00.00.00 |  | TAP-63938 | [TAP-63938] ¦ [V4.0][DFS] Logging update to better connect events with procedures - implementation | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-60608 | 143 | 1 |  | 05.52.00.00.00.00.00.00 |  | TAP-60608 | [TAP-60608] ¦ Replace Ripdraw SOUP library with in-house implementation | Feature | Done |  |  |  |  | 165 | 165 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47915 | 144 | 1 |  | 05.53.00.00.00.00.00.00 |  | TAP-47915 | [TAP-47915] ¦ [Arch][Enabler] Refine RASA Applications | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-69540 | 145 | 1 |  | 05.54.00.00.00.00.00.00 |  | TAP-69540 | [TAP-69540] ¦ [Tech Debt][Simulink] Update unit tests to be compatible with Simulink SIL/PIL Testing | Feature | Done |  |  |  |  | 53.5 | 53.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71958 | 146 | 1 |  | 05.55.00.00.00.00.00.00 |  | TAP-71958 | [TAP-71958] ¦ [v3.0][Enabler] IDU Standalones Automation Enhancements - Part 1 | Feature | Done |  |  |  |  | 32.25 | 32.25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113411 | 147 | 9 |  | 05.56.00.00.00.00.00.00 |  | TAP-113411 | [TAP-113411] ¦ [RPE] Fix Design Documentation | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-122378 | 148 | 7 |  | 05.57.00.00.00.00.00.00 |  | TAP-122378 | [TAP-122378] ¦ [V4][RC1] Update Setup Arm Latency test duration as per new requirement | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113539 | 149 | 7 |  | 05.58.00.00.00.00.00.00 |  | TAP-113539 | [TAP-113539] ¦ ESAT v2 - Continued Improvement ESAT v2 (PI14) - Product Security | Feature | Done |  |  |  |  | 101 | 101 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-114202 | 150 | 7 |  | 05.59.00.00.00.00.00.00 |  | TAP-114202 | [TAP-114202] ¦ [IDP][Enabler] Infrastructure maintenance PI14 | Feature | Done |  |  |  |  | 66.5 | 66.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106648 | 151 | 7 |  | 05.60.00.00.00.00.00.00 |  | TAP-106648 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Feature | Done |  |  |  |  | 64.1 | 64.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95494 | 152 | 7 |  | 05.61.00.00.00.00.00.00 |  | TAP-95494 | [TAP-95494] ¦ [IDP][V4.0] SW Integration QNX_x86_64 Ecosystem into Production | Feature | Done |  |  |  |  | 230 | 230 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-111461 | 153 | 7 |  | 06.01.01.00.00.00.00.00 |  | TAP-111461 | [TAP-111461] ¦ [V4.0] [Cyber] Peripheral deployment cleanup | Feature | Done |  |  |  |  | 47.5 | 47.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105342 | 154 | 7 |  | 06.01.02.00.00.00.00.00 |  | TAP-105342 | [TAP-105342] ¦ [Cyber][V4.0] Define and Create Test Build to support formal SW VV | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-111460 | 155 | 7 |  | 06.01.03.00.00.00.00.00 |  | TAP-111460 | [TAP-111460] ¦ [V4.0][V&V] Test User Notification when running non clinical software | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87417 | 156 | 7 |  | 06.01.04.00.00.00.00.00 |  | TAP-87417 | [TAP-87417] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun Batch2 and Test Fix - Foundation | Feature | Done |  |  |  |  | 207.5 | 207.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84549 | 157 | 7 |  | 06.01.05.00.00.00.00.00 |  | TAP-84549 | [TAP-84549] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun and Test Fix - AdvancedInstruments | Feature | Done |  |  |  |  | 140.125 | 140.125 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83547 | 158 | 7 |  | 06.01.06.00.00.00.00.00 |  | TAP-83547 | [TAP-83547] ¦ [Cyber][V4.0][V&V] pre-EC1 Dryrun - Foundation | Feature | Done |  |  |  |  | 52 | 52 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85483 | 159 | 7 |  | 06.01.07.00.00.00.00.00 |  | TAP-85483 | [TAP-85483] ¦ [Cyber][V4.0][Advanced Instruments] SW Verification - Improvements | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-57120 | 160 | 7 |  | 06.01.08.00.00.00.00.00 |  | TAP-57120 | [TAP-57120] ¦ [Cyber][V4.0][V&V] Investigation of DDS Secure and UDP Secure Impact on SW Testing - Foundation | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84563 | 161 | 7 |  | 06.01.09.00.00.00.00.00 |  | TAP-84563 | [TAP-84563] ¦ [Cyber][V4.0][V&V] Investigation of DDS Secure and UDP Secure Impact on SW Testing - AdvancedInstruments | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85482 | 162 | 7 |  | 06.01.10.00.00.00.00.00 |  | TAP-85482 | [TAP-85482] ¦ [V4.0][Foundation][Cyber] SW Verification - Improvements | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85484 | 163 | 7 |  | 06.01.11.00.00.00.00.00 |  | TAP-85484 | [TAP-85484] ¦ [V4.0][V&V][Cyber][Core Instruments] SW Verification - Improvements | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94634 | 164 | 7 |  | 06.01.12.00.00.00.00.00 |  | TAP-94634 | [TAP-94634] ¦ [Cyber][V4.0][V&V] Test TOOLS and Test Environment Update | Feature | Done |  |  |  |  | 113.5 | 113.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-67835 | 165 | 7 |  | 06.01.13.00.00.00.00.00 |  | TAP-67835 | [TAP-67835] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - CoreInstruments | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-67834 | 166 | 7 |  | 06.01.14.00.00.00.00.00 |  | TAP-67834 | [TAP-67834] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - Foundation | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84546 | 167 | 7 |  | 06.01.15.00.00.00.00.00 |  | TAP-84546 | [TAP-84546] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - AdvancedInstruments | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105122 | 168 | 11 |  | 06.01.16.00.00.00.00.00 |  | TAP-105122 | [TAP-105122] ¦ [V4][RC1][V&V][Cyber] Test TOOLS and Test Environment Update Preparing for Formal V&V | Feature | Done |  |  |  |  | 103 | 103 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88236 | 169 | 7 |  | 06.01.17.00.00.00.00.00 |  | TAP-88236 | [TAP-88236] ¦ [Cyber][V4.0][V&V] Engineering Candidate EC1 SW Test Dryrun and Test Failure Fix - Foundation | Feature | Done |  |  |  |  | 322.5 | 322.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-111448 | 170 | 7 |  | 06.01.18.00.00.00.00.00 |  | TAP-111448 | [TAP-111448] ¦ [Cyber][V4.0][V&V] Secure Deployment V&V | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88387 | 171 | 7 |  | 06.01.19.00.00.00.00.00 |  | TAP-88387 | [TAP-88387] ¦ [Cyber][V4.0][V&V] Engineering Candidate EC1 SW Test Dryrun and Test Failure Fix - AdvancedInstruments | Feature | Done |  |  |  |  | 277.55 | 277.55 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87440 | 172 | 7 |  | 06.01.20.00.00.00.00.00 |  | TAP-87440 | [TAP-87440] ¦ [Cyber][V4.0][V&V] Update Test Items to Support Authenticated Communication - Foundation | Feature | Done |  |  |  |  | 96 | 96 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86973 | 173 | 7 |  | 06.01.21.00.00.00.00.00 |  | TAP-86973 | [TAP-86973] ¦ [Cyber][V4.0][V&V] Update Test Items to Support Authenticated Communication - AdvancedInstruments | Feature | Done |  |  |  |  | 57.5 | 57.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106162 | 174 | 7 |  | 06.01.22.00.00.00.00.00 |  | TAP-106162 | [TAP-106162] ¦ [Cyber][V&V] Test certificate expiration notifications | Feature | Done |  |  |  |  | 59 | 59 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88231 | 175 | 7 |  | 06.01.23.00.00.00.00.00 |  | TAP-88231 | [TAP-88231] ¦ [V4][RC1][V&V] [Cyber] Post-EC1 SW Test Dryrun and Test Failure Fix on Test Build - Foundation | Feature | Done |  |  |  |  | 398 | 398 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88386 | 176 | 7 |  | 06.01.24.00.00.00.00.00 |  | TAP-88386 | [TAP-88386] ¦ [V4][RC1][V&V] [Cyber] Post-EC1 SW Test Dryrun and Test Failure Fix on Test Build - AdvancedInstruments | Feature | Done |  |  |  |  | 156.45 | 156.45 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105883 | 177 | 7 |  | 06.01.25.00.00.00.00.00 |  | TAP-105883 | [TAP-105883] ¦ [Cyber][V4.0][V&V] Test Automation of Controls Nominal Behavior SSRs | Feature | Done |  |  |  |  | 88.25 | 88.25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88384 | 178 | 11 |  | 06.01.26.00.00.00.00.00 |  | TAP-88384 | [TAP-88384] ¦ [Cyber][V4.0][V&V] TRR Deliverables Preparation - AdvancedInstruments | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87425 | 179 | 11 |  | 06.01.27.00.00.00.00.00 |  | TAP-87425 | [TAP-87425] ¦ [Cyber][V4.0][V&V] TRR Deliverables Preparation - Foundation | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105169 | 180 | 7 |  | 06.01.28.00.00.00.00.00 |  | TAP-105169 | [TAP-105169] ¦ [Cyber][Platformers][V&V] V&V for Ethercat CM and expiration notifications | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-108089 | 181 | 11 |  | 06.01.29.00.00.00.00.00 |  | TAP-108089 | [TAP-108089] ¦ [V4][RC1][V&V] TRR Project Wide Documents Release | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87421 | 182 | 11 |  | 06.01.30.00.00.00.00.00 |  | TAP-87421 | [TAP-87421] ¦ [V4][RC1][V&V] [Cyber] TRR Deliverables Release - Foundation | Feature | Done |  |  |  |  | 201 | 201 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88385 | 183 | 15 | 11 | 06.01.31.00.00.00.00.00 |  | TAP-88385 | [TAP-88385] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - AdvancedInstruments | Feature | Groomed |  |  |  |  | 245.75 | 1.5 | 1 hr | 1 hr | 244.25 | 0.6104% | 0 | 0 | Story Points
TAP-87426 | 184 | 15 | 11 | 06.01.32.00.00.00.00.00 |  | TAP-87426 | [TAP-87426] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - Foundation | Feature | Groomed |  |  |  |  | 202 | 19 | 1 hr | 1 hr | 183 | 9.406% | 0 | 0 | Story Points
TAP-113928 | 185 | 15 |  | 06.01.33.00.00.00.00.00 |  | TAP-113928 | [TAP-113928] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - CoreInstruments | Feature | Groomed |  |  |  |  | 61 | 1 | 1 hr | 1 hr | 60 | 1.639% | 0 | 0 | Story Points
TAP-88621 | 186 | 11 |  | 06.01.34.00.00.00.00.00 |  | TAP-88621 | [TAP-88621] ¦ [V4][RC1][V&V] [Cyber] TRR Deliverables Release - AdvancedInstruments | Feature | Done |  |  |  |  | 152 | 152 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-125121 | 187 | 13 |  | 06.01.35.00.00.00.00.00 |  | TAP-125121 | [TAP-125121] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - AdvancedInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125126 | 188 | 15 |  | 06.01.36.00.00.00.00.00 |  | TAP-125126 | [TAP-125126] ¦ [V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - AdvancedInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125127 | 189 | 15 |  | 06.01.38.00.00.00.00.00 |  | TAP-125127 | [TAP-125127] ¦ [V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - CoreInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125125 | 190 | 15 |  | 06.01.39.00.00.00.00.00 |  | TAP-125125 | [TAP-125125] ¦ 🚩[V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - Foundation | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125120 | 191 | 13 |  | 06.01.41.00.00.00.00.00 |  | TAP-125120 | [TAP-125120] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - Foundation | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125122 | 192 | 13 |  | 06.01.42.00.00.00.00.00 |  | TAP-125122 | [TAP-125122] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - CoreInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125122 | 193 | 192 |  | 06.02.00.00.00.00.00.00 |  | LOT-6109 | [TAP-125122] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - CoreInstr | FX | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-115485 | 194 | 9 |  | 06.02.01.01.00.00.00.00 |  | TAP-115485 | [TAP-115485] ¦ [Cyber] Tracking Documentation For Design Planning | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-115498 | 195 | 9 |  | 06.02.01.02.00.00.00.00 |  | TAP-115498 | [TAP-115498] ¦ [Cyber] Tracking Documentation For Design Inputs | Feature | PROPOSED |  |  |  |  | 4.5 | 4.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115511 | 196 | 17 |  | 06.02.01.03.00.00.00.00 |  | TAP-115511 | [TAP-115511] ¦ [V4.0][RC1][Cyber][Project Wide V&V Reports] Tracking Documentation For Design Verification | Feature | Accepted |  |  |  |  | 28 | 3 | 1 hr | 1 hr | 25 | 10.71% | 0 | 0 | Story Points
TAP-115768 | 197 | 9 | 130 | 06.02.01.04.00.00.00.00 |  | TAP-115768 | [TAP-115768] ¦ [V4][RC1] BRR Deliverables Release - AdvancedInstruments | Feature | Done |  |  |  |  | 45 | 45 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115637 | 198 | 9 |  | 06.02.01.05.00.00.00.00 |  | TAP-115637 | [TAP-115637] ¦ [Cyber] Tracking Documentation For Design Outputs | Feature | PROPOSED |  |  |  |  | 2 | 1 | 1 hr | 1 hr | 1 | 50% | 0 | 0 | Story Points
TAP-115695 | 199 | 11 |  | 06.02.01.06.00.00.00.00 |  | TAP-115695 | [TAP-115695] ¦ [Cyber] Tracking Documentation For Design Outputs - EIN V4.0 Unit Verification Checklists | Feature | Done |  |  |  |  | 37 | 37 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115718 | 200 | 11 |  | 06.02.01.07.00.00.00.00 |  | TAP-115718 | [TAP-115718] ¦ [Cyber] Tracking Documentation For EIN V4.0 Readiness Reviews BOM | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115722 | 201 | 9 |  | 06.02.01.08.00.00.00.00 |  | TAP-115722 | [TAP-115722] ¦ [Cyber] Tracking Documentation For EIN V4.0 SW Design Reviews | Feature | Done |  |  |  |  | 41 | 41 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115735 | 202 | 9 |  | 06.02.01.09.00.00.00.00 |  | TAP-115735 | [TAP-115735] ¦ [Cyber] Tracking Documentation For EIN V4.0 Product Risk Management | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-115742 | 203 | 9 |  | 06.02.01.10.00.00.00.00 |  | TAP-115742 | [TAP-115742] ¦ [Cyber] Tracking Documentation For Design Transfer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-115742 | 204 | 203 |  | 06.02.02.00.00.00.00.00 |  | LOT-6179 | [TAP-115742] ¦ [Cyber] Tracking Documentation For Design Transfer | FX | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-105163 | 205 | 5 |  | 06.02.02.01.00.00.00.00 |  | TAP-105163 | [TAP-105163] ¦ [v4.0][Cyber] NPS development for Advanced Instruments scrum teams in PI13 | Feature | Done |  |  |  |  | 40 | 40 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96204 | 206 | 1 |  | 06.02.02.02.00.00.00.00 |  | TAP-96204 | [TAP-96204] ¦ [v4.0][Cyber] NPS development for I2E, Jacobians, Scrumbledores, TeamBD, Pixel Poets - PI12 | Feature | Done |  |  |  |  | 27 | 27 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83444 | 207 | 7 |  | 06.02.02.03.00.00.00.00 |  | TAP-83444 | [TAP-83444] ¦ [v4.0] [Cyber] NPS Validation for BRR/TRR - PI11 | Feature | Done |  |  |  |  | 1 | 1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105160 | 208 | 7 |  | 06.02.02.04.00.00.00.00 |  | TAP-105160 | [TAP-105160] ¦ [Cyber][V4.0] NPS development for Triple tea - PI13 | Feature | Done |  |  |  |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96051 | 209 | 7 |  | 06.02.02.05.00.00.00.00 |  | TAP-96051 | [TAP-96051] ¦ [Cyber][V4.0] NPS development for Inbetweeners - PI12 | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105534 | 210 | 7 |  | 06.02.02.06.00.00.00.00 |  | TAP-105534 | [TAP-105534] ¦ [Cyber][V4.0] NPS development for FRED team | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94624 | 211 | 1 |  | 06.02.02.07.00.00.00.00 |  | TAP-94624 | [TAP-94624] ¦ [Cyber][V4.0] NPS development for CLASSY team - PI12 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105053 | 212 | 7 |  | 06.02.02.08.00.00.00.00 |  | TAP-105053 | [TAP-105053] ¦ [Cyber][V4.0] NPS development for Inbetweeners - PI13 | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-90275 | 213 | 11 |  | 06.02.02.09.00.00.00.00 |  | TAP-90275 | [TAP-90275] ¦ [v4.0] NPS validation for BRR/TRR - RC1 | Feature | Done |  |  |  |  | 361 | 361 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96135 | 214 | 7 |  | 06.02.02.10.00.00.00.00 |  | TAP-96135 | [TAP-96135] ¦ [Cyber][V4.0] NPS development for Tools Rules team - PI12 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-116341 | 215 | 15 |  | 06.02.03.01.00.00.00.00 |  | TAP-116341 | [TAP-116341] ¦ [SOUP][v4.0][Cyber] [IW] SOUP SQR Agile Release | Feature | Accepted |  |  |  |  | 100 | 0 | 1 hr | 1 hr | 100 | 0% | 0 | 0 | Story Points
TAP-123260 | 216 | 17 |  | 06.02.03.02.00.00.00.00 |  | TAP-123260 | [TAP-123260] ¦ [SOUP][V4.0][DVR] SOUP Verification activities | Feature | Accepted |  |  |  |  | 13 | 0 | 1 hr | 1 hr | 13 | 0% | 0 | 0 | Story Points
TAP-116345 | 217 | 15 |  | 06.02.03.03.00.00.00.00 |  | TAP-116345 | [TAP-116345] ¦ [V4.0][PI15] SOUP complete analysis - Foundation ART | Feature | Accepted |  |  |  |  | 23 | 3 | 1 hr | 1 hr | 20 | 13.04% | 0 | 0 | Story Points
TAP-96719 | 218 | 17 |  | 06.02.03.04.00.00.00.00 |  | TAP-96719 | [TAP-96719] ¦ [v4.0][Cyber][PI13] SOUP Initial analysis | Feature | Done |  |  |  |  | 140 | 140 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96675 | 219 | 17 |  | 06.02.03.05.00.00.00.00 |  | TAP-96675 | [TAP-96675] ¦ [v4.0][Cyber][PI13] SOUP complete analysis - Foundation ART | Feature | Done |  |  |  |  | 46 | 46 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83010 | 220 | 17 |  | 06.02.03.06.00.00.00.00 |  | TAP-83010 | [TAP-83010] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - Advanced Instruments ART | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95434 | 221 | 17 |  | 06.02.03.07.00.00.00.00 |  | TAP-95434 | [TAP-95434] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - Foundation ART | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106670 | 222 | 17 |  | 06.02.03.08.00.00.00.00 |  | TAP-106670 | [TAP-106670] ¦ [v4.0][Cyber][PI14] SOUP complete analysis - Foundation ART | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95432 | 223 | 17 |  | 06.02.03.09.00.00.00.00 |  | TAP-95432 | [TAP-95432] ¦ [v4.0][Cyber][PI12] SOUP Initial analysis | Feature | Done |  |  |  |  | 101 | 101 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72332 | 224 | 17 |  | 06.02.03.10.00.00.00.00 |  | TAP-72332 | [TAP-72332] ¦ [V4.0][Cyber][PI13] SOUP V&V Tasks | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113388 | 225 | 15 |  | 06.02.03.11.00.00.00.00 |  | TAP-113388 | [TAP-113388] ¦ [V4.0][Cyber][PI14] SOUP V&V Tasks [BRR/TRR] | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103997 | 226 | 17 |  | 06.02.03.13.00.00.00.00 |  | TAP-103997 | [TAP-103997] ¦ [v4.0][Cyber][PI13] SOUP complete analysis - Advanced Instruments ART | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97857 | 227 | 17 |  | 06.02.03.14.00.00.00.00 |  | TAP-97857 | [TAP-97857] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - RPE ART | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95435 | 228 | 17 |  | 06.02.03.15.00.00.00.00 |  | TAP-95435 | [TAP-95435] ¦ [v4.0][Cyber][PI13] SOUP SQR Agile Release | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106240 | 229 | 17 |  | 06.02.03.16.00.00.00.00 |  | TAP-106240 | [TAP-106240] ¦ [v4.0][Cyber][PI14] SOUP SQR Agile Release | Feature | Done |  |  |  |  | 65.5 | 65.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2133 | 230 | 237, 1 |  | 06.05.02.01.01.00.00.00 |  | TAP-2133 | [TAP-2133] ¦ [Cyber] Prototype Chain of Trust boot up for QNX x86 platform on 7.1 OS | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12357 | 231 | 237, 1 |  | 06.05.02.01.02.00.00.00 |  | TAP-12357 | [TAP-12357] ¦ [Cyber] Implement chain of trust on QNX x86 platform | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-17155 | 232 | 237, 1 |  | 06.05.02.01.03.00.00.00 |  | TAP-17155 | [TAP-17155] ¦ [Cyber] SPIKE Investigate needs for Unique/Non-Unique BIOS passwords on each system | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12358 | 233 | 237, 1 |  | 06.05.02.01.04.00.00.00 |  | TAP-12358 | [TAP-12358] ¦ [Cyber] Implement fallback mechanism for verification failures for QNX x86 | Feature | Done |  |  |  |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12361 | 234 | 237, 1 |  | 06.05.02.01.05.00.00.00 |  | TAP-12361 | [TAP-12361] ¦ [Cyber] Investigate Hard coded secrets in QNX x86 platforms | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2135 | 235 | 237, 1 |  | 06.05.02.01.06.00.00.00 |  | TAP-2135 | [TAP-2135] ¦ [Cyber] Hardware failure handling enhancement for QNX 7.1 x86 OS | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12360 | 236 | 237, 1 |  | 06.05.02.01.07.00.00.00 |  | TAP-12360 | [TAP-12360] ¦ [Cyber] Implement TPM usage in QNX x86 | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58662 | 237 | 238, 1 | 230, 231, 232, 233, 234, 235, 236 | 06.05.02.01.08.00.00.00 |  | TAP-58662 | [TAP-58662] ¦ [Cyber] Micro-Penetration Test by 3rd Party for QNX x86 Secure Boot | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13749 | 238 | 1 | 237 | 06.05.02.01.09.00.00.00 |  | TAP-13749 | [TAP-13749] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 - chain of trust | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70864 | 239 | 1 |  | 06.05.02.01.11.00.00.00 |  | TAP-70864 | [TAP-70864] ¦ [Cyber] Operations and Service support planning for bsp changes | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72558 | 240 | 3 |  | 06.05.02.01.12.00.00.00 |  | TAP-72558 | [TAP-72558] ¦ [Boosters][Cyber] Integrate WolfSSH in Data Access and miscellaneous logging improvement | Feature | Done |  |  |  |  | 59 | 59 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13750 | 241 | 9 |  | 06.05.02.01.13.00.00.00 |  | TAP-13750 | [TAP-13750] ¦ [Cyber] Finish the QA, V&V tasks related to QNX x86 OS for Cyber release | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2134 | 242 | 243, 1 |  | 06.05.02.02.01.00.00.00 |  | TAP-2134 | [TAP-2134] ¦ [Cyber] Implement secure storage for QNX x86 7.1 OS platform | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58909 | 243 | 244, 1 | 242 | 06.05.02.02.02.00.00.00 |  | TAP-58909 | [TAP-58909] ¦ [Cyber] Micro-Penetration Test by 3rd Party for QNX x86 Data Protection | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58919 | 244 | 1 | 243 | 06.05.02.02.03.00.00.00 |  | TAP-58919 | [TAP-58919] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 Data Protections | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-4982 | 245 | 1 |  | 06.05.02.03.01.00.00.00 |  | TAP-4982 | [TAP-4982] ¦ [Cyber] Least privilege mechanism on QNX x86 node | Feature | Done |  |  |  |  | 194 | 194 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58840 | 246 | 247, 1 |  | 06.05.02.03.02.00.00.00 |  | TAP-58840 | [TAP-58840] ¦ [Cyber] QNX x86: WolfSSH Integration | Feature | Done |  |  |  |  | 73 | 73 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12359 | 247 | 1 | 246 | 06.05.02.03.03.00.00.00 |  | TAP-12359 | [TAP-12359] ¦ [Cyber] Implement OS Hardening of QNX x86 nodes (SSH, SFTP, USB, etc) | Feature | Done |  |  |  |  | 137.5 | 137.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70489 | 248 | 249, 5 |  | 06.05.02.03.04.00.00.00 |  | TAP-70489 | [TAP-70489] ¦ [Cyber] Micro-Penetration Test Readiness and Support by 3rd Party for QNX x86 OS Hardening | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70490 | 249 | 5 | 248 | 06.05.02.03.05.00.00.00 |  | TAP-70490 | [TAP-70490] ¦ 🚩[Cyber] Implement Fixes for Findings in Micro Penetration Testing for QNX x86 OS Hardening | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1005 | 250 | 255, 1 |  | 06.05.03.01.01.00.00.00 |  | TAP-1005 | [TAP-1005] ¦ [Cyber] Create obfuscated secret key during run time | Feature | Done |  |  |  |  | 90 | 90 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1182 | 251 | 255, 1 |  | 06.05.03.01.02.00.00.00 |  | TAP-1182 | [TAP-1182] ¦ [Cyber] [Enabler] Define road map for Zynq Authenticated boot | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-7423 | 252 | 255, 1 |  | 06.05.03.01.03.00.00.00 |  | TAP-7423 | [TAP-7423] ¦ [Cyber] Establish Chain of trust on zynq platform | Feature | Done |  |  |  |  | 167.5 | 167.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12362 | 253 | 255, 1 |  | 06.05.03.01.04.00.00.00 |  | TAP-12362 | [TAP-12362] ¦ [Cyber] Implement fallback for qnx armv7 nodes | Feature | Done |  |  |  |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83759 | 254 | 1, 255 |  | 06.05.03.01.05.00.00.00 |  | TAP-83759 | [TAP-83759] ¦ [Critical][Cyber][V4.0] Investigate and Fix Backup OS | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58663 | 255 | 256, 1 | 250, 251, 252, 253, 258, 254 | 06.05.03.01.06.00.00.00 |  | TAP-58663 | [TAP-58663] ¦ [Cyber] Micro-Penetration Readiness and Test by 3rd Party for QNX Zynq | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13752 | 256 | 5 | 255 | 06.05.03.01.07.00.00.00 |  | TAP-13752 | [TAP-13752] ¦ [Cyber] Implementation penetration testing finding for QNX armv7 nodes | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13753 | 257 | 9 |  | 06.05.03.01.08.00.00.00 |  | TAP-13753 | [TAP-13753] ¦ [Cyber] Finish cyber analysis, V&V, and QA related tasks for QNX Armv7 OS | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13751 | 258 | 255, 1 |  | 06.05.03.02.01.00.00.00 |  | TAP-13751 | [TAP-13751] ¦ [Cyber] Implement secure key storage for QNX armv7 | Feature | Done |  |  |  |  | 82 | 82 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84498 | 259 | 1 |  | 06.05.03.03.01.00.00.00 |  | TAP-84498 | [TAP-84498] ¦ [Cyber]User Separation for Zynq nodes | Feature | Done |  |  |  |  | 33.5 | 33.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105165 | 260 | 1 |  | 06.05.03.03.02.00.00.00 |  | TAP-105165 | [TAP-105165] ¦ Improvements for Finalizing Cyber Development | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76492 | 261 | 1 |  | 06.05.03.03.03.00.00.00 |  | TAP-76492 | [TAP-76492] ¦ [Cyber] Increase Security of Key exchange | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-7424 | 262 | 1 |  | 06.05.03.03.04.00.00.00 |  | TAP-7424 | [TAP-7424] ¦ [Cyber] QNX7 Arm OS hardening | Feature | Done |  |  |  |  | 133.5 | 133.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58839 | 263 | 1 |  | 06.05.03.03.05.00.00.00 |  | TAP-58839 | [TAP-58839] ¦ [Cyber] QNX Zynq: WolfSSH Integration | Feature | Done |  |  |  |  | 25.5 | 25.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-73977 | 264 | 3 |  | 06.05.03.03.06.00.00.00 |  | TAP-73977 | [TAP-73977] ¦ [Cyber] PL key obfuscation and storage hardening | Feature | Done |  |  |  |  | 89.5 | 89.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1743 | 265 | 272, 1 |  | 06.05.04.01.01.00.00.00 |  | TAP-1743 | [TAP-1743] ¦ [Cyber] Certificate(s) to install as PK onWindows systems | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1744 | 266 | 272, 1 |  | 06.05.04.01.02.00.00.00 |  | TAP-1744 | [TAP-1744] ¦ [Cyber] 3 versions of UEFI firmware for testing Windows secure boot | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2423 | 267 | 272, 1 |  | 06.05.04.01.03.00.00.00 |  | TAP-2423 | [TAP-2423] ¦ [Cyber] Update 3rd party libraries and components on Windows Bamboo agents for v2.0 | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1745 | 268 | 272, 1 |  | 06.05.04.01.04.00.00.00 |  | TAP-1745 | [TAP-1745] ¦ [Cyber] Kontron specific instructions on updating the TPM certificate stores | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1742 | 269 | 272, 1 |  | 06.05.04.01.05.00.00.00 |  | TAP-1742 | [TAP-1742] ¦ [Cyber] Define Strategy and Architecture for Windows Cyber Security | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12365 | 270 | 272, 1 |  | 06.05.04.01.06.00.00.00 |  | TAP-12365 | [TAP-12365] ¦ [Cyber] Implement chain of trust on the Windows Platform | Feature | Done |  |  |  |  | 52.5 | 52.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-63713 | 271 | 1, 272 |  | 06.05.04.01.07.00.00.00 |  | TAP-63713 | [TAP-63713] ¦ [Cyber] Implement Authentic Code Execution on the Windows Platform | Feature | Done |  |  |  |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58664 | 272 | 273, 5 | 265, 266, 267, 268, 269, 270, 271 | 06.05.04.01.08.00.00.00 |  | TAP-58664 | [TAP-58664] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Windows x86 | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13756 | 273 | 5 | 272 | 06.05.04.01.09.00.00.00 |  | TAP-13756 | [TAP-13756] ¦ [Cyber] Implement penetration testing findings for Windows OS | Feature | Done |  |  |  |  | 52.5 | 52.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13758 | 274 | 9 |  | 06.05.04.01.10.00.00.00 |  | TAP-13758 | [TAP-13758] ¦ [Cyber] Finish the QA tasks related to Windows for Cyber release | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12370 | 275 | 1 |  | 06.05.04.02.01.00.00.00 |  | TAP-12370 | [TAP-12370] ¦ [Cyber] Implement secure storage on windows platform | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12367 | 276 | 1 |  | 06.05.04.03.01.00.00.00 |  | TAP-12367 | [TAP-12367] ¦ [Cyber] Implement least privilege strategy for the windows platform | Feature | Done |  |  |  |  | 83 | 83 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12368 | 277 | 1 |  | 06.05.04.03.02.00.00.00 |  | TAP-12368 | [TAP-12368] ¦ [Cyber] Windows OS Interface Hardening | Feature | Done |  |  |  |  | 110 | 110 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12369 | 278 | 1 |  | 06.05.04.03.03.00.00.00 |  | TAP-12369 | [TAP-12369] ¦ [Cyber] Investigate hard coded secrets on Windows Platform | Feature | Done |  |  |  |  | 1 | 1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58837 | 279 | 1 |  | 06.05.04.03.04.00.00.00 |  | TAP-58837 | [TAP-58837] ¦ [Cyber] Windows: WolfSSH Integration | Feature | Done |  |  |  |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104858 | 280 | 5 |  | 06.05.04.03.05.00.00.00 |  | TAP-104858 | [TAP-104858] ¦ [Cyber] WinOS Data and network protection | Feature | Done |  |  |  |  | 14.1 | 14.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76410 | 281 | 291, 1 |  | 06.05.05.01.01.00.00.00 |  | TAP-76410 | [TAP-76410] ¦ [Cyber] Integrate secure EtherCAT into system | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58458 | 282 | 291, 1 |  | 06.05.05.01.02.00.00.00 |  | TAP-58458 | [TAP-58458] ¦ [Cyber] Update Secure Communication Library | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-177 | 283 | 291, 1 |  | 06.05.05.01.03.00.00.00 |  | TAP-177 | [TAP-177] ¦ [Cyber] Design Secure EtherCAT Communication | Feature | Done |  |  |  |  | 66 | 66 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-4936 | 284 | 291, 1 |  | 06.05.05.01.04.00.00.00 |  | TAP-4936 | [TAP-4936] ¦ [Cyber] Implement Secure EtherCAT cyclic communication and cybersecurity framework | Feature | Done |  |  |  |  | 46 | 46 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55077 | 285 | 291, 1 |  | 06.05.05.01.05.00.00.00 |  | TAP-55077 | [TAP-55077] ¦ [Cyber] SPIKE Investigate and Architect the Solution to Authenticate File Over Ethercat Communications Risk: R021 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71075 | 286 | 291, 1 |  | 06.05.05.01.06.00.00.00 |  | TAP-71075 | [TAP-71075] ¦ [Cyber] Implement Authenticated File Over Ethercat Communications | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71074 | 287 | 291, 1 |  | 06.05.05.01.07.00.00.00 |  | TAP-71074 | [TAP-71074] ¦ [v4.0][Cyber] Implement EtherCAT security for the acyclic communication path | Feature | Done |  |  |  |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83828 | 288 | 1 |  | 06.05.05.01.08.00.00.00 |  | TAP-83828 | [TAP-83828] ¦ [Cyber] Ethercat Master updates to support RASA Testers and Manufacturing | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83633 | 289 | 7 |  | 06.05.05.01.09.00.00.00 |  | TAP-83633 | [TAP-83633] ¦ [V4.0][Cyber][Tech Debt] Complete Test Infrastructure for Secure EtherCAT | Feature | Done |  |  |  |  | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95486 | 290 | 7 |  | 06.05.05.01.10.00.00.00 |  | TAP-95486 | [TAP-95486] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Authentication Tests for FoE and Cyclic | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58669 | 291 | 292, 13 | 284, 286, 283, 285, 287, 282, 281 | 06.05.05.01.11.00.00.00 |  | TAP-58669 | [TAP-58669] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Ethercat/SSL | Feature | Done |  |  |  |  | 5.5 | 5.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58670 | 292 | 13 | 291 | 06.05.05.01.12.00.00.00 |  | TAP-58670 | [TAP-58670] ¦ [Cyber] Correct penetration testing findings for Ethercat/SSL | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106190 | 293 | 7 |  | 06.05.05.01.13.00.00.00 |  | TAP-106190 | [TAP-106190] ¦ 🚩[v4.0][Cyber] EtherCAT SSC<->Master Anti-Replay Tests for Ayclic | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106193 | 294 | 7 |  | 06.05.05.01.14.00.00.00 |  | TAP-106193 | [TAP-106193] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Anti-Replay Tests for FoE | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97725 | 295 | 7 |  | 06.05.05.01.15.00.00.00 |  | TAP-97725 | [TAP-97725] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Authentication Tests for Ayclic | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95051 | 296 | 7 |  | 06.05.05.01.16.00.00.00 |  | TAP-95051 | [TAP-95051] ¦ [v4.0][Sentinel][Cyber] EtherCAT Stability Improvements + Test Fixes | Feature | Done |  |  |  |  | 85 | 85 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-149 | 297 | 321, 1 |  | 06.05.05.02.01.00.00.00 |  | TAP-149 | [TAP-149] ¦ [Cyber] Secure UDP | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-141 | 298 | 321, 1 |  | 06.05.05.02.02.00.00.00 |  | TAP-141 | [TAP-141] ¦ [Cyber] UDP library new features | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-158 | 299 | 321, 1 |  | 06.05.05.02.03.00.00.00 |  | TAP-158 | [TAP-158] ¦ [Cyber] Secure Communication Library | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-193 | 300 | 321, 1 |  | 06.05.05.02.04.00.00.00 |  | TAP-193 | [TAP-193] ¦ [Cyber] Investigate DDS Domains | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-178 | 301 | 321, 1 |  | 06.05.05.02.05.00.00.00 |  | TAP-178 | [TAP-178] ¦ [Cyber] Communication Library New Interface Phase 1 | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115 | 302 | 321, 1 |  | 06.05.05.02.06.00.00.00 |  | TAP-115 | [TAP-115] ¦ [Cyber] Communication Middleware Layer Phase 2 | Feature | Done |  |  |  |  | 57 | 57 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-133 | 303 | 321, 1 |  | 06.05.05.02.07.00.00.00 |  | TAP-133 | [TAP-133] ¦ [Cyber] [Spike] DDS Secure Feasibility | Feature | Done |  |  |  |  | 23 | 23 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-125 | 304 | 321, 1 |  | 06.05.05.02.08.00.00.00 |  | TAP-125 | [TAP-125] ¦ [Cyber] Integrate Communication Library Interface in Alarms | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1010 | 305 | 321, 1 |  | 06.05.05.02.09.00.00.00 |  | TAP-1010 | [TAP-1010] ¦ [Cyber] Cleanup usage of DDS Domains | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-25137 | 306 | 321, 1 |  | 06.05.05.02.10.00.00.00 |  | TAP-25137 | [TAP-25137] ¦ [Cyber][Arch]Improve Testability of New Communication Libraries (UDP) | Feature | Done |  |  |  |  | 89 | 89 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55466 | 307 | 321, 1 |  | 06.05.05.02.11.00.00.00 |  | TAP-55466 | [TAP-55466] ¦ [Cyber][Arch]Improve Testability of New Communication Libraries (DDS) (Phase 1) | Feature | Done |  |  |  |  | 43 | 43 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55473 | 308 | 321, 1 |  | 06.05.05.02.12.00.00.00 |  | TAP-55473 | [TAP-55473] ¦ [Cyber] [Arch] [Enabler] [Storm Chasers] Communication library update: head tracking | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55557 | 309 | 321, 1 |  | 06.05.05.02.13.00.00.00 |  | TAP-55557 | [TAP-55557] ¦ [Cyber] [Arch] [Enabler] Supporting integration of new communication library | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55463 | 310 | 321, 1 |  | 06.05.05.02.14.00.00.00 |  | TAP-55463 | [TAP-55463] ¦ [Cyber] [Arch] [Enabler][Fred] Integrate new communication library into ACS communication | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55464 | 311 | 321, 1 |  | 06.05.05.02.15.00.00.00 |  | TAP-55464 | [TAP-55464] ¦ [Cyber] [Arch] [Enabler] [Boosters] Communication library update: configuration | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71118 | 312 | 321, 1 |  | 06.05.05.02.16.00.00.00 |  | TAP-71118 | [TAP-71118] ¦ [V4.0][Cyber] PI10 New Communication Library Wrapper (Foundation) | Feature | Done |  |  |  |  | 238.5 | 238.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72563 | 313 | 321, 1 |  | 06.05.05.02.17.00.00.00 |  | TAP-72563 | [TAP-72563] ¦ [V4.0][Cyber]PI10 New Communication Library Wrapper (Instrumentation) | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79110 | 314 | 1 |  | 06.05.05.02.18.00.00.00 |  | TAP-79110 | [TAP-79110] ¦ [V4.0] [Comms] [Cyber] New communication library update and migration (PI12) | Feature | Done |  |  |  |  | 499.5 | 499.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85853 | 315 | 1 |  | 06.05.05.02.19.00.00.00 |  | TAP-85853 | [TAP-85853] ¦ [Cyber][V4.0] ADV INST Complete migration of subsystem to new communication library | Feature | Done |  |  |  |  | 120 | 120 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58886 | 316 | 1, 321 |  | 06.05.05.02.20.00.00.00 |  | TAP-58886 | [TAP-58886] ¦ [Comms] [Cyber] Enable secure DDS communication | Feature | Done |  |  |  |  | 42 | 42 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58884 | 317 | 1, 321 |  | 06.05.05.02.21.00.00.00 |  | TAP-58884 | [TAP-58884] ¦ [Comms] [Cyber] Re-Design and Enable secure UDP communication | Feature | Done |  |  |  |  | 47 | 47 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95056 | 318 | 1 |  | 06.05.05.02.22.00.00.00 |  | TAP-95056 | [TAP-95056] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability and Performance Improvement | Feature | Done |  |  |  |  | 85 | 85 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-7888 | 319 | 3 |  | 06.05.05.02.23.00.00.00 |  | TAP-7888 | [TAP-7888] ¦ [Cyber] Communication Middleware Layer 3 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88364 | 320 | 5 |  | 06.05.05.02.24.00.00.00 |  | TAP-88364 | [TAP-88364] ¦ [Cyber] [V4.0 RC2] Upgrade RTI DDS to latest patch level Version 6.0.1.35 | Feature | Done |  |  |  |  | 60 | 60 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58672 | 321 | 13 | 313, 312, 297, 298, 299, 300, 301, 302, 303, 304, 305, 306, 307, 308, 309, 310, 311, 316, 317 | 06.05.05.02.25.00.00.00 |  | TAP-58672 | [TAP-58672] ¦ [Cyber] Micro-Penetration Test by 3rd Party for DDS/UDP | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103513 | 322 | 3 |  | 06.05.05.02.26.00.00.00 |  | TAP-103513 | [TAP-103513] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability fixes and performance improvement (PI13) | Feature | Done |  |  |  |  | 66.5 | 66.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105505 | 323 | 5 |  | 06.05.05.02.27.00.00.00 |  | TAP-105505 | [TAP-105505] ¦ [Cyber][Adv Instruments] Miscelleneous communication library update and integration | Feature | Done |  |  |  |  | 39.5 | 39.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103503 | 324 | 5 |  | 06.05.05.02.28.00.00.00 |  | TAP-103503 | [TAP-103503] ¦ [4.0] [Foundation] Miscellaneous communication library update and integration | Feature | Done |  |  |  |  | 112.5 | 112.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87345 | 325 | 5 |  | 06.05.05.02.29.00.00.00 |  | TAP-87345 | [TAP-87345] ¦ [Comms][V4.0][Cyber] Comms Libraries stability fixes and miscelleneous enhancements | Feature | Done |  |  |  |  | 56 | 56 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85431 | 326 | 5 |  | 06.05.05.02.30.00.00.00 |  | TAP-85431 | [TAP-85431] ¦ [V4.0][Cyber][CLASSY] Documentation update for new communication library | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106775 | 327 | 9 |  | 06.05.05.02.31.00.00.00 |  | TAP-106775 | [TAP-106775] ¦ [V4.0][Cyber][CLASY] Documentation update for new communication library (PI14) | Feature | Done |  |  |  |  | 49 | 49 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85792 | 328 | 5 |  | 06.05.05.02.32.00.00.00 |  | TAP-85792 | [TAP-85792] ¦ [V4.0][Cyber] Secure UDP Completion and V&V | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95824 | 329 | 7 |  | 06.05.05.02.33.00.00.00 |  | TAP-95824 | [TAP-95824] ¦ [Cyber][V4.0] Refactor communication data corruption related requirements and tests | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95456 | 330 | 7 |  | 06.05.05.02.34.00.00.00 |  | TAP-95456 | [TAP-95456] ¦ [Cyber][V4.0] Refactor communication data corruption related requirements and tests | Feature | Done |  |  |  |  | 42 | 42 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55467 | 331 | 1 |  | 06.05.05.03.01.00.00.00 |  | TAP-55467 | [TAP-55467] ¦ [Cyber] SPIKE Investigate the use on FTP on the Hugo system | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-109370 | 332 | 3 |  | 06.05.05.03.02.00.00.00 |  | TAP-109370 | [TAP-109370] ¦ [Cyber] Upgrade the wolfssh to 1.4.16 | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58613 | 333 | 1 |  | 06.05.05.04.01.00.00.00 |  | TAP-58613 | [TAP-58613] ¦ [Cyber] [SPIKE] Review acceptability of current password strategy for UPS and Network Switch Risk: R024 | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-6961 | 334 | 351, 1 |  | 06.05.06.01.00.00.00.00 |  | TAP-6961 | [TAP-6961] ¦ [Cyber] EMBSW - Instrument Authentication Infrastructure | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1306 | 335 | 351, 1 |  | 06.05.06.02.00.00.00.00 |  | TAP-1306 | [TAP-1306] ¦ [Cyber] EMBSW - Instrument Identification Refactor | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-34960 | 336 | 351, 1 |  | 06.05.06.03.00.00.00.00 |  | TAP-34960 | [TAP-34960] ¦ [Cyber] Instrument Authentication Prototype and De-risking | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-25616 | 337 | 351, 1 |  | 06.05.06.04.00.00.00.00 |  | TAP-25616 | [TAP-25616] ¦ [Cyber] Instrument Authentication Infrastructure Workshop | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-159 | 338 | 351, 1 |  | 06.05.06.05.00.00.00.00 |  | TAP-159 | [TAP-159] ¦ [Cyber] Instrument Hardware Authentication Implementation | Feature | Done |  |  |  |  | 37 | 37 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55120 | 339 | 351, 1 |  | 06.05.06.06.00.00.00.00 |  | TAP-55120 | [TAP-55120] ¦ [Cyber] Instrument Authentication Design Inputs | Feature | Done |  |  |  |  | 4.5 | 4.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-54936 | 340 | 351, 1 |  | 06.05.06.07.00.00.00.00 |  | TAP-54936 | [TAP-54936] ¦ [Cyber] Instrument Authentication Hash Computation | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55141 | 341 | 351, 1 |  | 06.05.06.08.00.00.00.00 |  | TAP-55141 | [TAP-55141] ¦ [Cyber] SPIKE Instrument Authentication Secret Storage and Build Integration | Feature | Done |  |  |  |  | 25 | 25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-28790 | 342 | 351, 1 |  | 06.05.06.09.00.00.00.00 |  | TAP-28790 | [TAP-28790] ¦ [Cyber] Instrument Memory Authentication Implementation | Feature | Done |  |  |  |  | 49.5 | 49.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58335 | 343 | 351, 1 |  | 06.05.06.10.00.00.00.00 |  | TAP-58335 | [TAP-58335] ¦ [Cyber] Instrument Authentication Error Handling (Data Validation) | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58439 | 344 | 1, 351 |  | 06.05.06.11.00.00.00.00 |  | TAP-58439 | [TAP-58439] ¦ [Cyber] Instrument Authentication SHA256 PL Acceleration | Feature | Done |  |  |  |  | 93 | 93 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71057 | 345 | 1, 351 |  | 06.05.06.12.00.00.00.00 |  | TAP-71057 | [TAP-71057] ¦ [Cyber] Merge staging/instrument-authentication into develop | Feature | Done |  |  |  |  | 14.5 | 14.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-69072 | 346 | 1, 351 |  | 06.05.06.13.00.00.00.00 |  | TAP-69072 | [TAP-69072] ¦ [Cyber] Instrument Authentication Failure System Response | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55121 | 347 | 1, 351 |  | 06.05.06.14.00.00.00.00 |  | TAP-55121 | [TAP-55121] ¦ [Cyber] Instrument Authentication Penetration Testing Readiness | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71054 | 348 | 1, 351 |  | 06.05.06.15.00.00.00.00 |  | TAP-71054 | [TAP-71054] ¦ [Cyber] Instrument Authentication Error Handling (Data Authentication) | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58349 | 349 | 1 |  | 06.05.06.16.00.00.00.00 |  | TAP-58349 | [TAP-58349] ¦ [Cyber] Instrument Authentication Legacy Device Support | Feature | Done |  |  |  |  | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82020 | 350 | 1 |  | 06.05.06.17.00.00.00.00 |  | TAP-82020 | [TAP-82020] ¦ [Cyber] Production Plan for Instrument Authentication | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58647 | 351 | 352, 1 | 334, 335, 336, 337, 338, 339, 340, 341, 342, 343, 344, 345, 346, 347, 348 | 06.05.06.18.00.00.00.00 |  | TAP-58647 | [TAP-58647] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Basic Instrument Authentication | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58656 | 352 | 3 | 351 | 06.05.06.19.00.00.00.00 |  | TAP-58656 | [TAP-58656] ¦ [Cyber][Sentinel][Inst Auth] Implement Fixes for Findings in Micro Penetration Testing | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58337 | 353 | 7 |  | 06.05.06.20.00.00.00.00 |  | TAP-58337 | [TAP-58337] ¦ [Cyber] Instrument Authentication V&V Testing | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58350 | 354 | 9 |  | 06.05.06.21.00.00.00.00 |  | TAP-58350 | [TAP-58350] ¦ [Cyber] Instrument Authentication Documents and Critical Design Review | Feature | Done |  |  |  |  | 7.5 | 7.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83346 | 355 | 13 |  | 06.05.06.22.00.00.00.00 |  | TAP-83346 | [TAP-83346] ¦ [Cyber] Switch to Production Key Secrets | Feature | Accepted |  |  |  |  | 6 | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-83346 | 356 | 355 |  | 06.05.07.00.00.00.00.00 |  | LOT-2071 | [TAP-83346] ¦ [Cyber] Switch to Production Key Secrets | FX | Closed |  |  |  |  | 9 | 0 | 9 | 10.8 | 9 | 0% | 0 | 0 | Story Points
TAP-1758 | 357 | 1 |  | 06.05.07.01.00.00.00.00 |  | TAP-1758 | [TAP-1758] ¦ [Cyber] Define and implement USB whitelisting policies across all nodes | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12356 | 358 | 3 |  | 06.05.07.02.00.00.00.00 |  | TAP-12356 | [TAP-12356] ¦ [Cyber] Update network switch configuration for cyber release | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113853 | 359 | 7 |  | 06.05.08.01.00.00.00.00 |  | TAP-113853 | [TAP-113853] ¦ [Cyber] Continued NPS work for Product Security Release (PI 14) | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70569 | 360 | 1 |  | 06.05.08.02.00.00.00.00 |  | TAP-70569 | [TAP-70569] ¦ [Cyber] Formalize use of WolfSSH in ESAT and Data Access | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-25610 | 361 | 1 |  | 06.05.08.03.00.00.00.00 |  | TAP-25610 | [TAP-25610] ¦ [Cyber] Prepare ESAT-2 for Cybersecurity Release | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104060 | 362 | 5 |  | 06.05.08.04.00.00.00.00 |  | TAP-104060 | [TAP-104060] ¦ [V2.1] [Cyber] Certificate Installation Usability Improvements For Contract Manufacturer | Feature | Done |  |  |  |  | 58 | 58 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104830 | 363 | 5 |  | 06.05.08.05.00.00.00.00 |  | TAP-104830 | [TAP-104830] ¦ [Cyber] ESAT v2 - Migrating from v1 to v2 | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104832 | 364 | 5 |  | 06.05.08.06.00.00.00.00 |  | TAP-104832 | [TAP-104832] ¦ [Cyber] ESAT v2 Continued Stabilization of ESAT v2 (PI13) | Feature | Done |  |  |  |  | 144 | 144 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83501 | 365 | 17 |  | 06.05.08.07.00.00.00.00 |  | TAP-83501 | [TAP-83501] ¦ [v4.0] [Cyber] Update ESAT scripts to work with product security release | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103080 | 366 | 13 |  | 06.05.08.08.00.00.00.00 |  | TAP-103080 | [TAP-103080] ¦ [Cyber] ESAT v2, Support Field Service Use of CyberArk | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94851 | 367 | 3 |  | 06.05.08.09.00.00.00.00 |  | TAP-94851 | [TAP-94851] ¦ [Cyber] Continued ESAT v2 support, PI 12 | Feature | Done |  |  |  |  | 100 | 100 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-42212 | 368 | 13 |  | 06.05.08.10.00.00.00.00 |  | TAP-42212 | [TAP-42212] ¦ [Cyber] Penetration test ESAT and its interfaces for the Cybersecurity Release | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-42213 | 369 | 13 |  | 06.05.08.11.00.00.00.00 |  | TAP-42213 | [TAP-42213] ¦ [Cyber] Patch vulnerabilities discovered in penetration test report for cybersecurity ESAT solution | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-42213 | 370 | 369 |  | 06.05.09.00.00.00.00.00 |  | LOT-2069 | [TAP-42213] ¦ [Cyber] Patch vulnerabilities discovered in penetration test report for cybersecurity ESAT solution | FX | In progress |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-943 | 371 | 1 |  | 06.05.09.01.01.00.00.00 |  | TAP-943 | [TAP-943] ¦ [Cyber] System Configuration Enforcement | Feature | Done |  |  |  |  | 85 | 85 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12344 | 372 | 1 |  | 06.05.09.01.02.00.00.00 |  | TAP-12344 | [TAP-12344] ¦ [KontronEOL] [Cyber] Finalize Configuration Enforcement on all nodes | Feature | Done |  |  |  |  | 90 | 90 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-14178 | 373 | 1 |  | 06.05.09.01.03.00.00.00 |  | TAP-14178 | [TAP-14178] ¦ [Cyber] Add non-clinical element to GUI software | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83682 | 374 | 1 |  | 06.05.09.01.04.00.00.00 |  | TAP-83682 | [TAP-83682] ¦ [Cyber][v4.0] Finalize the non-clinical overlay for the GUI | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12345 | 375 | 5 |  | 06.05.09.01.05.00.00.00 |  | TAP-12345 | [TAP-12345] ¦ [V4.0][Cyber] Implement User Notification when running non clinical software | Feature | Done |  |  |  |  | 63 | 63 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115130 | 376 | 9 |  | 06.05.09.02.01.00.00.00 |  | TAP-115130 | [TAP-115130] ¦ [V4.0] [BRR] [Cyber] Platformers Documentation Updates | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113289 | 377 | 5 |  | 06.05.09.02.02.00.00.00 |  | TAP-113289 | [TAP-113289] ¦ [V4.0][Cyber] Certificate Cleanup and Stability | Feature | Done |  |  |  |  | 57 | 57 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72510 | 378 | 1 |  | 06.05.09.02.03.00.00.00 |  | TAP-72510 | [TAP-72510] ¦ [Cyber][V4] Certificate manager design changes | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-17759 | 379 | 1 |  | 06.05.09.02.04.00.00.00 |  | TAP-17759 | [TAP-17759] ¦ [Cyber] Ethercat certificate manager | Feature | Done |  |  |  |  | 28 | 28 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12346 | 380 | 3 |  | 06.05.09.02.05.00.00.00 |  | TAP-12346 | [TAP-12346] ¦ [Cyber] Implement certificate expiration notifications | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-56916 | 381 | 3 |  | 06.05.09.02.06.00.00.00 |  | TAP-56916 | [TAP-56916] ¦ [V4] [Cyber] Support for unified Medtronic hugo_id certificate | Feature | Done |  |  |  |  | 76 | 76 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-168 | 382 | 1 |  | 06.05.09.03.01.00.00.00 |  | TAP-168 | [TAP-168] ¦ [Cyber] Deployment manager Interface Updates | Feature | Done |  |  |  |  | 78 | 78 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-8250 | 383 | 1 |  | 06.05.09.03.02.00.00.00 |  | TAP-8250 | [TAP-8250] ¦ [KontronEOL][Cyber][DM] Peripheral deployment support | Feature | Done |  |  |  |  | 184 | 184 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1753 | 384 | 1 |  | 06.05.09.03.03.00.00.00 |  | TAP-1753 | [TAP-1753] ¦ [Cyber] Define strategy and implement secure deployment of packages | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-8252 | 385 | 3 |  | 06.05.09.03.04.00.00.00 |  | TAP-8252 | [TAP-8252] ¦ [Cyber] Support for peripheral deployment | Feature | Done |  |  |  |  | 107 | 107 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-42170 | 386 | 3 |  | 06.05.09.03.05.00.00.00 |  | TAP-42170 | [TAP-42170] ¦ [V4.0][Cyber] Secure Deployment | Feature | Done |  |  |  |  | 111.5 | 111.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-59531 | 387 | 3 |  | 06.05.09.03.06.00.00.00 |  | TAP-59531 | [TAP-59531] ¦ [Cyber] Deployment Support for QNX arm | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-108253 | 388 | 5 |  | 06.05.09.03.07.00.00.00 |  | TAP-108253 | [TAP-108253] ¦ [Cyber] Release Build Testing with Engineering Keys | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-68 | 389 | 1 |  | 06.05.09.04.01.00.00.00 |  | TAP-68 | [TAP-68] ¦ [KontronEOL] [ICG] [Cyber] v2 / QNX 7.1 Build Environment Support - Part 2 | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2578 | 390 | 1 |  | 06.05.09.04.02.00.00.00 |  | TAP-2578 | [TAP-2578] ¦ [ICG] [Cyber] Signing system for Einstein Phase 1 | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-8581 | 391 | 1 |  | 06.05.09.04.03.00.00.00 |  | TAP-8581 | [TAP-8581] ¦ [ICG] [Cyber] Certificate Management (UEFI) and Secure Boot Detection | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-20257 | 392 | 1 |  | 06.05.09.04.04.00.00.00 |  | TAP-20257 | [TAP-20257] ¦ [Cyber] Security enhancement for binary production and CI infrastructure | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55053 | 393 | 1 |  | 06.05.09.04.05.00.00.00 |  | TAP-55053 | [TAP-55053] ¦ [Cyber] SPIKE Investigate and Detail the Product Security Impacts to Test and Resolutions Risk: R019 - Foundation | Feature | Done |  |  |  |  | 43 | 43 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71880 | 394 | 1 |  | 06.05.09.04.06.00.00.00 |  | TAP-71880 | [TAP-71880] ¦ [Cyber][SPIKE] Investigate and Detail the SSH update in SW V&V - Instrumentation | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-53454 | 395 | 1 |  | 06.05.09.04.07.00.00.00 |  | TAP-53454 | [TAP-53454] ¦ [Cyber] Centralize engineering key for Windows/Zynq | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-53456 | 396 | 3 |  | 06.05.09.04.08.00.00.00 |  | TAP-53456 | [TAP-53456] ¦ [Cyber] Production signing infrastructure setup | Feature | Done |  |  |  |  | 37 | 37 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96136 | 397 | 3 |  | 06.05.09.04.09.00.00.00 |  | TAP-96136 | [TAP-96136] ¦ [Cyber][IDP][V4.0] Build Infrastructure Signing | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-28462 | 398 | 5 |  | 06.05.09.04.10.00.00.00 |  | TAP-28462 | [TAP-28462] ¦ [Cyber] Provide Production Signing | Feature | Done |  |  |  |  | 80 | 80 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84668 | 399 | 13 |  | 06.05.09.04.11.00.00.00 |  | TAP-84668 | [TAP-84668] ¦ [Cyber] Support for Product variants for Project Sentinel | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83453 | 400 | 1 |  | 06.05.10.01.00.00.00.00 |  | TAP-83453 | [TAP-83453] ¦ [Cyber] Allow front port network connection in Operable state | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84353 | 401 | 1 |  | 06.05.10.02.00.00.00.00 |  | TAP-84353 | [TAP-84353] ¦ [Cyber] BSP armv7 updates to support Manufacturing/Field Service | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84354 | 402 | 3 |  | 06.05.10.03.00.00.00.00 |  | TAP-84354 | [TAP-84354] ¦ [Cyber] Windows BSP updates to support Manufacturing | Feature | Done |  |  |  |  | 16.1 | 16.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84352 | 403 | 3 |  | 06.05.10.04.00.00.00.00 |  | TAP-84352 | [TAP-84352] ¦ [Cyber] Certificate Bootstrap mode | Feature | Done |  |  |  |  | 43 | 43 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84351 | 404 | 3 |  | 06.05.10.05.00.00.00.00 |  | TAP-84351 | [TAP-84351] ¦ [Cyber] BSP x86 updates to support Manufacturing/Field Support | Feature | Done |  |  |  |  | 41 | 41 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84384 | 405 | 5 |  | 06.05.10.06.00.00.00.00 |  | TAP-84384 | [TAP-84384] ¦ [Cyber] FRU replacement application for updating ORTI switch and ups configuration | Feature | Done |  |  |  |  | 77.6 | 77.6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84357 | 406 | 13 |  | 06.05.10.07.00.00.00.00 |  | TAP-84357 | [TAP-84357] ¦ [Cyber] Tool for installing certificates on FRU/ HLA Programming | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Story Points
TAP-82906 | 407 | 13 |  | 06.05.10.08.00.00.00.00 |  | TAP-82906 | [TAP-82906] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 2 (Development and Testing) - PI13 | Feature | Done |  |  |  |  | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84376 | 408 | 13 | 3 | 06.05.10.09.00.00.00.00 |  | TAP-84376 | [TAP-84376] ¦ [Cyber] Dry Run of FRU replacements for US launch | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84366 | 409 | 13 |  | 06.05.10.10.00.00.00.00 |  | TAP-84366 | [TAP-84366] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 1(Initial Development and Investigation) | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103615 | 410 | 13 |  | 06.05.10.11.00.00.00.00 |  | TAP-103615 | [TAP-103615] ¦ [Cyber] Briefcase Method Prototyping | Feature | Done |  |  |  |  | 17 | 17 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105519 | 411 | 13 | 3 | 06.05.10.12.00.00.00.00 |  | TAP-105519 | [TAP-105519] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 2 (Development and Testing) - PI14 | Feature | Done |  |  |  |  | 56.5 | 56.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104008 | 412 | 19 |  | 06.05.10.13.00.00.00.00 |  | TAP-104008 | [TAP-104008] ¦ [Cyber] 4.0 IDU Manufacturing Updates | Feature | In progress |  |  |  |  | 6 | 2 | 1 hr | 1 hr | 4 | 33.33% | 0 | 0 | Story Points
TAP-85190 | 413 | 19 |  | 06.05.10.14.00.00.00.00 |  | TAP-85190 | [TAP-85190] ¦ [Cyber] Transfer of Misc. integration tools to PLXS | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Story Points
TAP-84497 | 414 | 19 |  | 06.05.10.15.00.00.00.00 |  | TAP-84497 | [TAP-84497] ¦ [Cyber] Manufacturing SRA BSP to support rasa and idu testers | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84358 | 415 | 19 |  | 06.05.10.16.00.00.00.00 |  | TAP-84358 | [TAP-84358] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 1 - PI12 (before validation) | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84360 | 416 | 19 |  | 06.05.10.17.00.00.00.00 |  | TAP-84360 | [TAP-84360] ¦ [Cyber] Base Programming Station OS updates | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84363 | 417 | 19 |  | 06.05.10.18.00.00.00.00 |  | TAP-84363 | [TAP-84363] ¦ [Cyber] SC/iSIM Programming Station Updates for Manufacturing | Feature | Accepted |  |  |  |  | 27 | 0 | 1 hr | 1 hr | 27 | 0% | 0 | 0 | Story Points
TAP-84361 | 418 | 19 |  | 06.05.10.19.00.00.00.00 |  | TAP-84361 | [TAP-84361] ¦ [Cyber] Tower Programming Station Updates for Manufacturing | Feature | In progress |  |  |  |  | 10.5 | 5 | 1 hr | 1 hr | 5.5 | 47.62% | 0 | 0 | Story Points
TAP-84362 | 419 | 19 |  | 06.05.10.20.00.00.00.00 |  | TAP-84362 | [TAP-84362] ¦ [Cyber] Cart Programming Station Updates for Manufacturing | Feature | Groomed |  |  |  |  | 15 | 0 | 1 hr | 1 hr | 15 | 0% | 0 | 0 | Story Points
TAP-84367 | 420 | 19 |  | 06.05.10.21.00.00.00.00 |  | TAP-84367 | [TAP-84367] ¦ [Cyber] Dry Run of SC Functional Tests at Manufacturing | Feature | Accepted |  |  |  |  | 6 | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-83129 | 421 | 19 |  | 06.05.10.22.00.00.00.00 |  | TAP-83129 | [TAP-83129] ¦ [Cyber] Investigate password programming functions | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81647 | 422 | 19 |  | 06.05.10.23.00.00.00.00 |  | TAP-81647 | [TAP-81647] ¦ [Cyber] Create Manufacturing BSP for cart/tpsc/fse to support FCT | Feature | Done |  |  |  |  | 61 | 61 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97718 | 423 | 19 |  | 06.05.10.24.00.00.00.00 |  | TAP-97718 | [TAP-97718] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - commanders - PI13 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88670 | 424 | 19 |  | 06.05.10.25.00.00.00.00 |  | TAP-88670 | [TAP-88670] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - SRA installation | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88672 | 425 | 19 |  | 06.05.10.26.00.00.00.00 |  | TAP-88672 | [TAP-88672] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - commanders - PI12 | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88676 | 426 | 19 |  | 06.05.10.27.00.00.00.00 |  | TAP-88676 | [TAP-88676] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Communication | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88673 | 427 | 19 |  | 06.05.10.28.00.00.00.00 |  | TAP-88673 | [TAP-88673] ¦ [Cyber] FCT35 Cage, Mech, FRU - deployment | Feature | In progress |  |  |  |  | 87.5 | 39 | 1 hr | 1 hr | 48.5 | 44.57% | 0 | 0 | Story Points
TAP-88679 | 428 | 19 |  | 06.05.10.29.00.00.00.00 |  | TAP-88679 | [TAP-88679] ¦ [Cyber] FCT35 Cage, Mech, FRU - LabView/Windows application | Feature | Accepted |  |  |  |  | 21 | 0 | 1 hr | 1 hr | 21 | 0% | 0 | 0 | Story Points
TAP-88681 | 429 | 19 |  | 06.05.10.30.00.00.00.00 |  | TAP-88681 | [TAP-88681] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Full Testing | Feature | Accepted |  |  |  |  | 50 | 0 | 1 hr | 1 hr | 50 | 0% | 0 | 0 | Story Points
TAP-83134 | 430 | 19 |  | 06.05.10.31.00.00.00.00 |  | TAP-83134 | [TAP-83134] ¦ [Cyber] Investigate feasiblity of CyberArk REST API Integration | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83144 | 431 | 19 |  | 06.05.10.32.00.00.00.00 |  | TAP-83144 | [TAP-83144] ¦ [Cyber] Investigate feasibility of CyberArk agent based Integration | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84364 | 432 | 19 |  | 06.05.10.33.00.00.00.00 |  | TAP-84364 | [TAP-84364] ¦ [Cyber] Tower FRU Programming Station Updates | Feature | Accepted |  |  |  |  | 17 | 0 | 1 hr | 1 hr | 17 | 0% | 0 | 0 | Story Points
TAP-84365 | 433 | 19 |  | 06.05.10.34.00.00.00.00 |  | TAP-84365 | [TAP-84365] ¦ [Cyber] SC FRU Programming Station Updates | Feature | Accepted |  |  |  |  | 2 | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0 | Story Points
TAP-97710 | 434 | 19 |  | 06.05.10.35.00.00.00.00 |  | TAP-97710 | [TAP-97710] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 1 - PI13 (before validation) | Feature | Done |  |  |  |  | 31.5 | 31.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-126486 | 435 | 19 |  | 06.05.10.36.00.00.00.00 |  | TAP-126486 | [TAP-126486] ¦ [Cyber] 4.0 IDU Manufacturing Deployment Updates PI16 | Feature | PROPOSED |  |  |  |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | 0 | 0 | Story Points
TAP-126416 | 436 | 19 |  | 06.05.10.37.00.00.00.00 |  | TAP-126416 | [TAP-126416] ¦ [Cyber] FCT35 Cage, Mech, FRU - LabView/Windows application (PI16) | Feature | PROPOSED |  |  |  |  | 17 | 0 | 1 hr | 1 hr | 17 | 0% | 0 | 0 | Story Points
TAP-88671 | 437 | 21 |  | 06.05.10.38.00.00.00.00 |  | TAP-88671 | [TAP-88671] ¦ [Cyber] Programming Computers Final Release and Validation | Feature | Accepted |  |  |  |  | 62 | 0 | 1 hr | 1 hr | 62 | 0% | 0 | 0 | Story Points
TAP-85233 | 438 | 21 |  | 06.05.10.39.00.00.00.00 |  | TAP-85233 | [TAP-85233] ¦ [Cyber] Manufacturing Integration of 4.0 | Feature | Accepted |  |  |  |  | 50 | 0 | 1 hr | 1 hr | 50 | 0% | 0 | 0 | Story Points
TAP-85206 | 439 | 21 |  | 06.05.10.40.00.00.00.00 |  | TAP-85206 | [TAP-85206] ¦ [Cyber] SW4.0 SW BOM Creation (for PLXS) | Feature | Accepted |  |  |  |  | 30 | 0 | 1 hr | 1 hr | 30 | 0% | 0 | 0 | Story Points
TAP-88682 | 440 | 21 |  | 06.05.10.41.00.00.00.00 |  | TAP-88682 | [TAP-88682] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Work Instructions and TRS updates | Feature | Accepted |  |  |  |  | 47 | 0 | 1 hr | 1 hr | 47 | 0% | 0 | 0 | Story Points
TAP-88684 | 441 | 21 |  | 06.05.10.42.00.00.00.00 |  | TAP-88684 | [TAP-88684] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Validation Support | Feature | Accepted |  |  |  |  | 70 | 0 | 1 hr | 1 hr | 70 | 0% | 0 | 0 | Story Points
TAP-84377 | 442 | 21 |  | 06.05.10.43.00.00.00.00 |  | TAP-84377 | [TAP-84377] ¦ [Cyber] IT infrastructure setup at Plexus to support certificate management | Feature | Accepted |  |  |  |  | 10 | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0 | Story Points
TAP-83152 | 443 | 21 |  | 06.05.10.44.00.00.00.00 |  | TAP-83152 | [TAP-83152] ¦ [Cyber] Manufacturing Integration of Unique Password Programming | Feature | Accepted |  |  |  |  | 25 | 0 | 1 hr | 1 hr | 25 | 0% | 0 | 0 | Story Points
TAP-125288 | 444 | 23 |  | 06.05.10.45.00.00.00.00 |  | TAP-125288 | [TAP-125288] ¦ [Cyber] Finalize US Launch Work Instructions | Feature | In progress |  |  |  |  | 27 | 6 | 1 hr | 1 hr | 21 | 22.22% | 0 | 0 | Story Points
TAP-85224 | 445 | 23 |  | 06.05.10.46.00.00.00.00 |  | TAP-85224 | [TAP-85224] ¦ [Cyber] Field Service Tools NPS Validation Support | Feature | In progress |  |  |  |  | 49 | 0 | 1 hr | 1 hr | 49 | 0% | 0 | 0 | Story Points
TAP-87779 | 446 | 23 |  | 06.05.10.47.00.00.00.00 |  | TAP-87779 | [TAP-87779] ¦ [Cyber] HLA Upgrade Support for Project Sentinel Phase 3(Implementation and Validation) | Feature | In progress |  |  |  |  | 61 | 11 | 1 hr | 1 hr | 50 | 18.03% | 0 | 0 | Story Points
TAP-118514 | 447 | 21 |  | 06.05.10.48.00.00.00.00 |  | TAP-118514 | [TAP-118514] ¦ [Cyber] Finalize and Validate service procedures for OUS cyber launch. | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-118512 | 448 | 21 |  | 06.05.10.49.00.00.00.00 |  | TAP-118512 | [TAP-118512] ¦ [Cyber] Developing Service Procedures for use after Plexus Transfer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-118513 | 449 | 21 |  | 06.05.10.50.00.00.00.00 |  | TAP-118513 | [TAP-118513] ¦ [Cyber] Developing HLA Field Upgrade Procedures for Service use | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-118513 | 450 | 449 |  | 06.05.11.00.00.00.00.00 |  | LOT-6123 | [TAP-118513] ¦ [Cyber] Developing HLA Field Upgrade Procedures for Service use | FX | In progress |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-105489 | 451 | 1 |  | 06.05.11.01.00.00.00.00 |  | TAP-105489 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Feature | Done |  |  |  |  | 37.7 | 37.7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96772 | 452 | 1 |  | 06.05.11.02.00.00.00.00 |  | TAP-96772 | [TAP-96772] ¦ Support collapse of staging/cyber to develop | Feature | Done |  |  |  |  | 114 | 114 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106940 | 453 | 3 |  | 06.05.11.03.00.00.00.00 |  | TAP-106940 | [TAP-106940] ¦ [Cyber] Miscellaneous EC2 Blockers | Feature | Done |  |  |  |  | 73.6 | 73.6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105164 | 454 | 3 |  | 06.05.11.04.00.00.00.00 |  | TAP-105164 | [TAP-105164] ¦ [Cyber] Daily integration stability Issue | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86114 | 455 | 5 |  | 06.05.11.05.00.00.00.00 |  | TAP-86114 | [TAP-86114] ¦ [Cyber] System Performance Analysis with cyber security features | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106957 | 456 | 5 |  | 06.05.11.06.00.00.00.00 |  | TAP-106957 | [TAP-106957] ¦ [Cyber] Miscellaneous EC3 Blockers | Feature | Done |  |  |  |  | 102.5 | 102.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106958 | 457 | 7 |  | 06.05.11.07.00.00.00.00 |  | TAP-106958 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Feature | Done |  |  |  |  | 218.4 | 218.4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-116625 | 458 | 13 |  | 06.05.11.08.00.00.00.00 |  | TAP-116625 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | Feature | Accepted |  |  |  |  | 31.5 | 6.5 | 1 hr | 1 hr | 25 | 20.63% | 0 | 0 | Story Points
TAP-116625 | 459 | 458 |  | 06.05.12.01.00.00.00.00 |  | RAS-6745 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | Defect | Investigation |  |  |  |  | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26% | 0 | 0 | Story Points
TAP-116625 | 460 | 458 |  | 06.06.00.00.00.00.00.00 |  | LOT-6029 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | SFX | Closed |  |  |  |  | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26% | 0 | 0 | Story Points
TAP-116625 | 461 | 458 |  | 06.06.01.00.00.00.00.00 |  | LOT-6030 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | FX | Closed |  |  |  |  | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26% | 0 | 0 | Story Points
TAP-87152 | 462 | 3 |  | 06.06.01.01.00.00.00.00 |  | TAP-87152 | [TAP-87152] ¦ [V4.0][CTF EOL] Cart LED Driver Updates | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87151 | 463 | 3 |  | 06.06.01.02.00.00.00.00 |  | TAP-87151 | [TAP-87151] ¦ [V4.0][CTF EOL] Requirements and Infrastructure | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87153 | 464 | 7 |  | 06.06.01.03.00.00.00.00 |  | TAP-87153 | [TAP-87153] ¦ [V4.0][CTF EOL] Integration and Solution Verification for CART | Feature | Done |  |  |  |  | 45 | 45 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82936 | 465 | 3 |  | 06.06.01.04.00.00.00.00 |  | TAP-82936 | [TAP-82936] ¦ [V4.0][CTF EOL] Reliability and maintainability improvements | Feature | Done |  |  |  |  | 17 | 17 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87184 | 466 | 7 |  | 06.06.01.05.00.00.00.00 |  | TAP-87184 | [TAP-87184] ¦ [V4.0][CTF EOL] Startup Changes and TPSC Application Upgrade for EOL | Feature | Done |  |  |  |  | 31.5 | 31.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-92586 | 467 | 3 |  | 06.06.01.06.00.00.00.00 |  | TAP-92586 | [TAP-92586] ¦ [V4.0][CTF EOL] Cart Application Upgrade for EOL | Feature | Done |  |  |  |  | 27 | 27 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-93993 | 468 | 5 |  | 06.06.01.07.00.00.00.00 |  | TAP-93993 | [TAP-93993] ¦ [V4.0][CTF EOL] FSE Application Upgrade for EOL | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85050 | 469 | 7 |  | 06.06.01.08.00.00.00.00 |  | TAP-85050 | [TAP-85050] ¦ [V4.0][CTF EOL] Finalize Documentation | Feature | Done |  |  |  |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82998 | 470 | 3 |  | 06.06.01.09.00.00.00.00 |  | TAP-82998 | [TAP-82998] ¦ [V4.0][CTF EOL][Cyber] PL updates to support Embedded EOL Project | Feature | Done |  |  |  |  | 56 | 56 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82937 | 471 | 3 |  | 06.06.01.10.00.00.00.00 |  | TAP-82937 | [TAP-82937] ¦ [V4.0][CTF EOL][Cyber] Manufacturing updates to support Embedded EOL Project | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82935 | 472 | 3 |  | 06.06.01.11.00.00.00.00 |  | TAP-82935 | [TAP-82935] ¦ [V4.0][CTF EOL][Cyber] OS Updates to support Embedded EOL project | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70407 | 473 | 3 |  | 06.06.01.12.00.00.00.00 |  | TAP-70407 | [TAP-70407] ¦ [V4.0][CTF EOL] Cart/TPSC/FSE continuing SW support for new boards spin off | Feature | Done |  |  |  |  | 160 | 160 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87411 | 474 | 3 |  | 06.06.01.13.00.00.00.00 |  | TAP-87411 | [TAP-87411] ¦ [V4.0][CTF EOL][Cyber] Prototype OS Updates to support Embedded EOL project | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97620 | 475 | 7 |  | 06.06.01.14.00.00.00.00 |  | TAP-97620 | [TAP-97620] ¦ [V4.0][CTF EOL] Integration and Solution Verification TPSC | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106789 | 476 | 7 |  | 06.06.01.15.00.00.00.00 |  | TAP-106789 | [TAP-106789] ¦ [V4.0][RC1][CTF EOL] Integration and Solution Verification FSE | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points

## Log
DataTimeStamp (?) | Event (?) | Data (?) | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
|  |  | TAP-106789 |  | TAP-95817
|  |  | TAP-106789 |  | TAP-94622
|  |  | TAP-106789 |  | TAP-94625
|  |  | TAP-106789 |  | TAP-96038
|  |  | TAP-106789 |  | TAP-113927
|  |  | TAP-106789 |  | TAP-114710
|  |  | TAP-106789 |  | TAP-113325
|  |  | TAP-106789 |  | TAP-114167
|  |  | TAP-106789 |  | TAP-114725
|  |  | TAP-106789 |  | TAP-113935
|  |  | TAP-106789 |  | TAP-113936
|  |  | TAP-106789 |  | TAP-112047
|  |  | TAP-106789 |  | TAP-125115
|  |  | TAP-106789 |  | TAP-125124
|  |  | TAP-106789 |  | TAP-125261
|  |  | TAP-106789 |  | TAP-125786
|  |  | TAP-106789 |  | TAP-125128
|  |  | TAP-106789 |  | TAP-113857
|  |  | TAP-106789 |  | TAP-88107
|  |  | TAP-106789 |  | TAP-88093

## Summary
Resource Names | Sum FDR
EDISON | 530
ATLAS | 592
PLATFORMERS | 741
TOOLSRULES | 407
FRED | 502
DRUSHTI | 145
BUILDERS | 923
ASTRANPSDEVELOPERS | 254
ASTRANPSVALIDATORS | 126
VISUAL | 431
ELECTRON | 5
PIXELPOETS | 302
HORIZON | 387
STORMCHASERS | 378
TRIPLETEA | 470
BOOSTERS | 334
CLASSY | 363
TEAMBD | 461
USERFLOWSW | 325
COREINSTRUMENTS | 67
PUPPETEERS | 79
FUSION | 245.75
I2E | 273.75
JACOBIANS | 275.75
COSSACKS | 343
POWERSTORMERS | 355
DOCUMENTOWNERS | 32
CASTLEBLACK | 6
ICONICS | 137
INFRAWARRIORS | 130.5
NEXUS | 157.5
STELLARS | 177
TECHTITANS | 179
Total FDR: | 35748.75