## Project
Text10 | Unique ID | Unique ID Successors | Unique ID Predecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Number10 | Number11 | Duration | Duration1 | Number12 | % Complete | Number13 | Number14 | Text24
TAP-79978 | 1 | 3, 2 | 295, 366, 145, 332, 341, 345, 356, 479, 216 | 03.02.00.00.00.00.00.00 |  | TAP-79978 | [TAP-79978] ¦ [Milestone][V4.0] (EC1) Engineering Candidate 1 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85787 | 2 |  | 1 | 03.03.00.00.00.00.00.00 |  | TAP-85787 | [TAP-85787] ¦ [Prochain][V4.0] (EC1) Engineering Candidate 1 Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79979 | 3 | 4, 5, 551, 554 | 515, 486, 526, 538, 480, 527, 525, 1, 547, 546, 545, 56, 539, 516, 150, 499, 445, 371, 606, 336, 601, 194, 458, 442, 634, 635, 637, 626, 627, 629, 631, 639, 636 | 03.04.00.00.00.00.00.00 |  | TAP-79979 | [TAP-79979] ¦ [Milestone][V4.0] (EC2) Engineering Candidate 2 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85788 | 4 |  | 3 | 03.05.00.00.00.00.00.00 |  | TAP-85788 | [TAP-85788] ¦ [Prochain][V4.0] (EC2) Engineering Candidate 2 Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79981 | 5 | 6, 9 | 540, 358, 348, 607, 451, 548, 450, 3, 383, 293, 392, 448, 608, 92, 495, 494, 492, 34, 141, 528, 191, 49, 28, 90, 446, 347, 382, 443, 453, 508, 512, 632, 77 | 03.06.00.00.00.00.00.00 |  | TAP-79981 | [TAP-79981] ¦ [Milestone][V4.0] (EC3) Engineering Candidate 3 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104120 | 6 |  | 5 | 03.07.00.00.00.00.00.00 |  | TAP-104120 | [TAP-104120] ¦ [Prochain][V4.0] (EC3) Engineering Candidate 3 Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104131 | 7 | 8, 9 | 218 | 03.08.00.00.00.00.00.00 |  | TAP-104131 | [TAP-104131] ¦ [Milestone][V4.0] (RC1) Release Candidate 1 Finalized Test Code and NPS | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104132 | 8 |  | 7 | 03.09.00.00.00.00.00.00 |  | TAP-104132 | [TAP-104132] ¦ [Prochain][V4.0] (RC1) Release Candidate 1 Finalized Test Code and NPS Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79982 | 9 | 11, 10 | 154, 452, 511 | 03.10.00.00.00.00.00.00 |  | TAP-79982 | [TAP-79982] ¦ [Milestone][V4.0] (BRR) Build Readiness Review | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104121 | 10 |  | 9 | 03.11.00.00.00.00.00.00 |  | TAP-104121 | [TAP-104121] ¦ [Prochain][V4.0] (BRR) Build Readiness Review Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79983 | 11 | 15, 12, 271, 272 |  | 03.12.00.00.00.00.00.00 |  | TAP-79983 | [TAP-79983] ¦ [Milestone][V4.0] (TRR) Test Readiness Review | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85789 | 12 |  | 11 | 03.13.00.00.00.00.00.00 |  | TAP-85789 | [TAP-85789] ¦ [Prochain][V4.0] (TRR) Test Readiness Review Prochain Buffer | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83580 | 13 | 14 | 131 | 03.14.00.00.00.00.00.00 |  | TAP-83580 | [TAP-83580] ¦ [Milestone][V4.0] (RC2) Release Candidate 2 USA Launch Service and Manufacturing Support | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104122 | 14 |  | 13 | 03.15.00.00.00.00.00.00 |  | TAP-104122 | [TAP-104122] ¦ [Prochain][V4.0] (RC2) Release Candidate 2 USA Launch Service and Manufacturing Support Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-79984 | 15 | 17, 16 | 277, 278, 305, 307, 315 | 03.16.00.00.00.00.00.00 |  | TAP-79984 | [TAP-79984] ¦ [Milestone][V4.0] V&V Complete | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104178 | 16 |  | 15 | 03.17.00.00.00.00.00.00 |  | TAP-104178 | [TAP-104178] ¦ [Prochain][V4.0] V&V Complete Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-79985 | 17 | 18 | 15, 497, 308, 309, 319, 312, 320, 317, 318, 310, 313, 314, 311, 284, 306 | 03.18.00.00.00.00.00.00 |  | TAP-79985 | [TAP-79985] ¦ [Milestone][V4.0] (DVR) Design Verification Review | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104179 | 18 |  | 17 | 03.19.00.00.00.00.00.00 |  | TAP-104179 | [TAP-104179] ¦ [Prochain][V4.0] (DVR) Design Verification Review Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104128 | 19 | 20 | 578, 579 | 03.20.00.00.00.00.00.00 |  | TAP-104128 | [TAP-104128] ¦ [Milestone][V4.0] (RC3-Manufacturing) Release Candidate 3 Full Plexus Transfer Code | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104173 | 20 |  | 19 | 03.21.00.00.00.00.00.00 |  | TAP-104173 | [TAP-104173] ¦ [Prochain][V4.0] (RC3-Manufacturing) Release Candidate 3 Full Plexus Transfer Code Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-87766 | 21 | 22 | 120, 582, 581, 580, 583, 584, 590, 591, 592 | 03.22.00.00.00.00.00.00 |  | TAP-87766 | [TAP-87766] ¦ [Milestone][V4.0] NPS Manufacturing SW Complete | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104180 | 22 |  | 21 | 03.23.00.00.00.00.00.00 |  | TAP-104180 | [TAP-104180] ¦ [Prochain][V4.0] NPS Manufacturing SW Complete Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-83590 | 23 | 24 | 587 | 03.24.00.00.00.00.00.00 |  | TAP-83590 | [TAP-83590] ¦ [Milestone][V4.0] NPS Service Software | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104181 | 24 |  | 23 | 03.25.00.00.00.00.00.00 |  | TAP-104181 | [TAP-104181] ¦ [Prochain][V4.0] NPS Service Software Prochain Buffer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-104181 | 25 | 24 |  | 04.01.00.00.00.00.00.00 |  | RAS-11338 | [TAP-104181] ¦ [Prochain][V4.0] NPS Service Software Prochain Buffer | Enhancement | Confirmed |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-86327 | 26 | 1 |  | 04.01.01.00.00.00.00.00 |  | TAP-86327 | [TAP-86327] ¦ (RAS-11338) Log Event and notify user when no LLM is detected on ACA | Feature | Done |  |  |  |  | 25 | 25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86327 | 27 | 26 |  | 04.02.00.00.00.00.00.00 |  | RAS-11933 | [TAP-86327] ¦ (RAS-11338) Log Event and notify user when no LLM is detected on ACA | Enhancement | Confirmed |  |  |  |  | 46 | 25 | 46 | 55.2 | 21 | 54.35% | 0 | 0 | Story Points
TAP-104062 | 28 | 5 |  | 04.02.01.00.00.00.00.00 |  | TAP-104062 | [TAP-104062] ¦ [v4.0] (RAS-11933) Add torque stable logging to IDU startup | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104062 | 29 | 28 |  | 04.03.00.00.00.00.00.00 |  | RAS-12231 | [TAP-104062] ¦ [v4.0] (RAS-11933) Add torque stable logging to IDU startup | Defect | Confirmed |  |  |  |  | 18 | 11 | 18 | 21.6 | 7 | 61.11% | 0 | 0 | Story Points
TAP-104062 | 30 | 28 |  | 04.04.00.00.00.00.00.00 |  | RAS-9806 | [TAP-104062] ¦ [v4.0] (RAS-11933) Add torque stable logging to IDU startup | Enhancement | Confirmed |  |  |  |  | 18 | 11 | 18 | 21.6 | 7 | 61.11% | 0 | 0 | Story Points
TAP-47497 | 31 | 1 |  | 04.06.01.00.00.00.00.00 |  | TAP-47497 | [TAP-47497] ¦ [MTBI] (Batch B) Allow setup joints to be manual controllable after ACA hot swap | Feature | Done |  |  |  |  | 23 | 23 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47497 | 32 | 31 |  | 04.07.00.00.00.00.00.00 |  | RAS-6750 | [TAP-47497] ¦ [MTBI] (Batch B) Allow setup joints to be manual controllable after ACA hot swap | Defect | Confirmed |  |  |  |  | 39 | 23 | 39 | 46.8 | 16 | 58.97% | 0 | 0 | Story Points
TAP-47497 | 33 | 31 |  | 04.08.00.00.00.00.00.00 |  | RAS-12678 | [TAP-47497] ¦ [MTBI] (Batch B) Allow setup joints to be manual controllable after ACA hot swap | Enhancement | Confirmed |  |  |  |  | 39 | 23 | 39 | 46.8 | 16 | 58.97% | 0 | 0 | Story Points
TAP-95751 | 34 | 5 |  | 04.08.01.00.00.00.00.00 |  | TAP-95751 | [TAP-95751] ¦ [RAS-12678][v4.0] Add instrument use life limit as a event | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95751 | 35 | 34 |  | 04.09.00.00.00.00.00.00 |  | RAS-12494 | [TAP-95751] ¦ [RAS-12678][v4.0] Add instrument use life limit as a event | Enhancement | Confirmed |  |  |  |  | 18 | 11 | 18 | 21.6 | 7 | 61.11% | 0 | 0 | Story Points
TAP-79084 | 36 | 1 |  | 04.10.01.00.00.00.00.00 |  | TAP-79084 | [TAP-79084] ¦ [iSim][v4.0] Add system deactivation functionality to the iSim + SC Configuration | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79084 | 37 | 36 |  | 04.11.00.00.00.00.00.00 |  | RAS-8531 | [TAP-79084] ¦ [iSim][v4.0] Add system deactivation functionality to the iSim + SC Configuration | Defect | Confirmed |  |  |  |  | 10 | 9 | 10 | 12 | 1 | 90% | 0 | 0 | Story Points
TAP-79084 | 38 | 36 |  | 04.11.01.00.00.00.00.00 |  | TAP-88130 | [TAP-79084] ¦ [iSim][v4.0] Add system deactivation functionality to the iSim + SC Configuration | Issue | Done | Foundation - Atlas | ATLAS |  |  | 10 | 9 | 10 | 12 | 1 | 100% | 0 | 0 | Story Points
TAP-86325 | 39 | 1 |  | 04.12.01.00.00.00.00.00 |  | TAP-86325 | [TAP-86325] ¦ (RAS-7054) Allow Wristed instrument fails calibration retries without detaching the instrument | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86325 | 40 | 39 |  | 04.13.00.00.00.00.00.00 |  | RAS-7239 | [TAP-86325] ¦ (RAS-7054) Allow Wristed instrument fails calibration retries without detaching the instrument | Enhancement | Confirmed |  |  |  |  | 44 | 26 | 44 | 52.8 | 18 | 59.09% | 0 | 0 | Story Points
TAP-86030 | 41 | 1 |  | 04.13.01.00.00.00.00.00 |  | TAP-86030 | [TAP-86030] ¦ (RAS-7239) Avoid flooding of UPS_manager tmp logs | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86030 | 42 | 41 |  | 04.14.00.00.00.00.00.00 |  | RAS-6778 | [TAP-86030] ¦ (RAS-7239) Avoid flooding of UPS_manager tmp logs | Defect | Confirmed |  |  |  |  | 5 | 5 | 5 | 6 | 0 | 100% | 0 | 0 | Story Points
TAP-86030 | 43 | 41 |  | 04.15.00.00.00.00.00.00 |  | RAS-11445 | [TAP-86030] ¦ (RAS-7239) Avoid flooding of UPS_manager tmp logs | Enhancement | Confirmed |  |  |  |  | 5 | 5 | 5 | 6 | 0 | 100% | 0 | 0 | Story Points
TAP-95635 | 44 | 1 |  | 04.15.01.00.00.00.00.00 |  | TAP-95635 | [TAP-95635] ¦ [RAS-11445] Add SMC Encode Initialization offsets to sqlite database | Feature | Done |  |  |  |  | 11.5 | 11.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95635 | 45 | 44 |  | 04.16.00.00.00.00.00.00 |  | RAS-13397 | [TAP-95635] ¦ [RAS-11445] Add SMC Encode Initialization offsets to sqlite database | Defect | Confirmed |  |  |  |  | 16.5 | 11.5 | 16.5 | 19.8 | 5 | 69.7% | 0 | 0 | Story Points
TAP-95635 | 46 | 44 |  | 04.17.00.00.00.00.00.00 |  | RAS-12483 | [TAP-95635] ¦ [RAS-11445] Add SMC Encode Initialization offsets to sqlite database | Enhancement | Confirmed |  |  |  |  | 16.5 | 11.5 | 16.5 | 19.8 | 5 | 69.7% | 0 | 0 | Story Points
TAP-84571 | 47 | 1 |  | 04.18.01.00.00.00.00.00 |  | TAP-84571 | [TAP-84571] ¦ (Close RAS-10913) Improve peripheral compat robustness by retrying after a wait period | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84571 | 48 | 47 |  | 04.19.00.00.00.00.00.00 |  | RAS-7795 | [TAP-84571] ¦ (Close RAS-10913) Improve peripheral compat robustness by retrying after a wait period | Defect | Confirmed |  |  |  |  | 12 | 8 | 12 | 14.4 | 4 | 66.67% | 0 | 0 | Story Points
TAP-97497 | 49 | 5 |  | 04.20.01.00.00.00.00.00 |  | TAP-97497 | [TAP-97497] ¦ [Drushti][RAS-1210] Change ACAD Error state color | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97497 | 50 | 49 |  | 04.21.00.00.00.00.00.00 |  | RAS-1818 | [TAP-97497] ¦ [Drushti][RAS-1210] Change ACAD Error state color | Enhancement | Confirmed |  |  |  |  | 21 | 13 | 21 | 25.2 | 8 | 61.9% | 0 | 0 | Story Points
TAP-6975 | 51 | 1 |  | 04.21.02.00.00.00.00.00 |  | TAP-6975 | [TAP-6975] ¦ [GUI](RAS-1818) Align behavior to match ergonomics when clutching and firing energy | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-6975 | 52 | 51 |  | 04.22.00.00.00.00.00.00 |  | RAS-12354 | [TAP-6975] ¦ [GUI](RAS-1818) Align behavior to match ergonomics when clutching and firing energy | Defect | Confirmed |  |  |  |  | 21 | 13 | 21 | 25.2 | 8 | 61.9% | 0 | 0 | Story Points
TAP-6975 | 53 | 51 |  | 04.24.01.00.00.00.00.00 |  | TAP-93494 | [TAP-6975] ¦ [GUI](RAS-1818) Align behavior to match ergonomics when clutching and firing energy | Issue | Done | Advanced Instruments - TeamBD | TEAMBD |  |  | 26 | 13 | 26 | 31.2 | 13 | 100% | 0 | 0 | Story Points
TAP-6975 | 54 | 51 |  | 04.25.01.00.00.00.00.00 |  | TAP-121806 | [TAP-6975] ¦ [GUI](RAS-1818) Align behavior to match ergonomics when clutching and firing energy | Issue | Done | Foundation - Classy 1 | CLASSY1 |  |  | 26 | 13 | 26 | 31.2 | 13 | 100% | 0 | 0 | Story Points
TAP-6975 | 55 | 51 |  | 04.27.00.00.00.00.00.00 |  | RAS-9223 | [TAP-6975] ¦ [GUI](RAS-1818) Align behavior to match ergonomics when clutching and firing energy | Enhancement | Confirmed |  |  |  |  | 26 | 13 | 26 | 31.2 | 13 | 50% | 0 | 0 | Story Points
TAP-71016 | 56 | 3 |  | 04.27.01.00.00.00.00.00 |  | TAP-71016 | [TAP-71016] ¦ [iSim][v4.0] Update Surgical Science Trainer build | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71016 | 57 | 56 |  | 04.27.01.01.00.00.00.00 | TAP-71016 | TAP-93805 | [TAP-71016] ¦ [iSim][v4.0] Update Surgical Science Trainer build | Issue | Done | Foundation - Atlas | ATLAS |  |  | 21 | 21 | 21 | 25.2 | 0 | 100% | 0 | 0 | Story Points
TAP-71016 | 58 | 56 |  | 04.28.00.00.00.00.00.00 |  | RAS-9897 | [TAP-71016] ¦ [iSim][v4.0] Update Surgical Science Trainer build | Defect | Confirmed |  |  |  |  | 37 | 21 | 37 | 44.4 | 16 | 56.76% | 0 | 0 | Story Points
TAP-71016 | 59 | 56 |  | 04.29.00.00.00.00.00.00 |  | RAS-11307 | [TAP-71016] ¦ [iSim][v4.0] Update Surgical Science Trainer build | Enhancement | Confirmed |  |  |  |  | 37 | 21 | 37 | 44.4 | 16 | 56.76% | 0 | 0 | Story Points
TAP-94703 | 60 | 1 |  | 04.29.01.00.00.00.00.00 |  | TAP-94703 | [TAP-94703] ¦ [RAS-11307] Indication of system deactivation from Tower startup failures | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94703 | 61 | 60 |  | 04.30.00.00.00.00.00.00 |  | RAS-4264 | [TAP-94703] ¦ [RAS-11307] Indication of system deactivation from Tower startup failures | Defect | Confirmed |  |  |  |  | 33 | 19 | 33 | 39.6 | 14 | 57.58% | 0 | 0 | Story Points
TAP-94703 | 62 | 60 |  | 04.30.01.00.00.00.00.00 |  | TAP-121691 | [TAP-94703] ¦ [RAS-11307] Indication of system deactivation from Tower startup failures | Issue | Done | Foundation - Atlas | ATLAS |  |  | 33 | 19 | 33 | 39.6 | 14 | 100% | 0 | 0 | Story Points
TAP-94703 | 63 | 60 |  | 04.31.00.00.00.00.00.00 |  | RAS-9030 | [TAP-94703] ¦ [RAS-11307] Indication of system deactivation from Tower startup failures | Enhancement | Confirmed |  |  |  |  | 33 | 19 | 33 | 39.6 | 14 | 57.58% | 0 | 0 | Story Points
TAP-58230 | 64 | 1 |  | 04.31.01.00.00.00.00.00 |  | TAP-58230 | [TAP-58230] ¦ [Tech Debt] Initial Build Variant Work | Feature | Done |  |  |  |  | 49 | 49 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-61982 | 65 | 1 |  | 04.31.02.00.00.00.00.00 |  | TAP-61982 | [TAP-61982] ¦ Merge gated derating infrastructure to develop | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-68699 | 66 | 1 |  | 04.31.04.00.00.00.00.00 |  | TAP-68699 | [TAP-68699] ¦ [Croc] Implement Twitch de-rating in iSim for user studies | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83329 | 67 | 1 |  | 04.31.08.00.00.00.00.00 |  | TAP-83329 | [TAP-83329] ¦ [Croc] [Tech Debt] Finalize Croc Variants Merge to Develop | Feature | Done |  |  |  |  | 43.75 | 43.75 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83329 | 68 | 67 |  | 04.31.08.05.00.00.00.00 | TAP-83329 | TAP-81639 | [TAP-83329] ¦ [Croc] [Tech Debt] Finalize Croc Variants Merge to Develop | Capability | Done |  |  |  |  | 45.75 | 43.75 | 45.75 | 54.9 | 2 | 100% | 0 | 0 | Story Points
TAP-6337 | 69 | 1 |  | 04.31.10.00.00.00.00.00 |  | TAP-6337 | [TAP-6337] ¦ [TechDebt] SPIKE - Consolidate instrument angle sign conventions across SRA and IDU | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-6337 | 70 | 69 |  | 04.31.11.00.00.00.00.00 |  | TAP-93546 | [TAP-6337] ¦ [TechDebt] SPIKE - Consolidate instrument angle sign conventions across SRA and IDU | Issue | Done | Outside ART - DocumentOwners | DOCUMENTOWNERS |  |  | 16 | 10 | 16 | 19.2 | 6 | 100% | 0 | 0 | Story Points
TAP-6337 | 71 | 69 |  | 04.32.00.00.00.00.00.00 |  | RAS-6239 | [TAP-6337] ¦ [TechDebt] SPIKE - Consolidate instrument angle sign conventions across SRA and IDU | Defect | Confirmed |  |  |  |  | 16 | 10 | 16 | 19.2 | 6 | 62.5% | 0 | 0 | Story Points
TAP-86333 | 72 | 1 |  | 04.32.01.00.00.00.00.00 |  | TAP-86333 | [TAP-86333] ¦ complete pending work for RAS-6750, RAS-6239 | Feature | Done |  |  |  |  | 10.75 | 10.75 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86333 | 73 | 72 |  | 04.33.00.00.00.00.00.00 |  | RAS-6961 | [TAP-86333] ¦ complete pending work for RAS-6750, RAS-6239 | Defect | Confirmed |  |  |  |  | 17.75 | 10.75 | 17.75 | 21.3 | 7 | 60.56% | 0 | 0 | Story Points
TAP-86312 | 74 | 1 |  | 04.33.01.00.00.00.00.00 |  | TAP-86312 | [TAP-86312] ¦ (RAS-6961)Retry ACA calibration in the instance when calibration times out during an arm hotswap | Feature | Done |  |  |  |  | 50 | 50 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86312 | 75 | 74 |  | 04.33.03.00.00.00.00.00 |  | RAS-15299 | [TAP-86312] ¦ (RAS-6961)Retry ACA calibration in the instance when calibration times out during an arm hotswap | Defect | Open |  |  |  |  | 87 | 50 | 87 | 104.4 | 37 | 57.47% | 0 | 0 | Story Points
TAP-86312 | 76 | 74 |  | 04.34.00.00.00.00.00.00 |  | RAS-15139 | [TAP-86312] ¦ (RAS-6961)Retry ACA calibration in the instance when calibration times out during an arm hotswap | Enhancement | Confirmed |  |  |  |  | 87 | 50 | 87 | 104.4 | 37 | 57.47% | 0 | 0 | Story Points
TAP-114212 | 77 | 5 |  | 04.39.01.00.00.00.00.00 |  | TAP-114212 | [TAP-114212] ¦ [V4.0][EC3][SC2] Fix RAS-13574 | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-114212 | 78 | 77 |  | 04.39.01.01.00.00.00.00 | TAP-114212 | TAP-96720 | [TAP-114212] ¦ [V4.0][EC3][SC2] Fix RAS-13574 | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 |  |  | 19 | 19 | 19 | 22.8 | 0 | 100% | 0 | 0 | Story Points
TAP-114212 | 79 | 77 |  | 04.40.00.00.00.00.00.00 |  | RAS-14745 | [TAP-114212] ¦ [V4.0][EC3][SC2] Fix RAS-13574 | Defect | Implemented |  |  |  |  | 29 | 19 | 29 | 34.8 | 10 | 65.52% | 0 | 0 | Story Points
TAP-114212 | 80 | 77 |  | 04.40.01.00.00.00.00.00 |  | TAP-122356 | [TAP-114212] ¦ [V4.0][EC3][SC2] Fix RAS-13574 | Issue | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 29 | 19 | 29 | 34.8 | 10 | 100% | 0 | 0 | Story Points
TAP-114212 | 81 | 77 |  | 04.44.00.00.00.00.00.00 |  | RAS-13173 | [TAP-114212] ¦ [V4.0][EC3][SC2] Fix RAS-13574 | Enhancement | Implemented |  |  |  |  | 36 | 19 | 36 | 43.2 | 17 | 52.78% | 0 | 0 | Story Points
TAP-84573 | 82 | 1 |  | 04.45.01.00.00.00.00.00 |  | TAP-84573 | [TAP-84573] ¦ [Drushti](RAS-9521) GUI Stuck Calibrate Arms Screen | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84573 | 83 | 82 |  | 04.46.00.00.00.00.00.00 |  | RAS-6611 | [TAP-84573] ¦ [Drushti](RAS-9521) GUI Stuck Calibrate Arms Screen | Defect | Implemented |  |  |  |  | 35 | 13 | 35 | 42 | 22 | 37.14% | 0 | 0 | Story Points
TAP-84573 | 84 | 82 |  | 04.49.00.00.00.00.00.00 |  | RAS-10917 | [TAP-84573] ¦ [Drushti](RAS-9521) GUI Stuck Calibrate Arms Screen | Enhancement | Closed |  |  |  |  | 35 | 13 | 35 | 42 | 22 | 37.14% | 0 | 0 | Story Points
TAP-81873 | 85 | 1 |  | 04.49.01.00.00.00.00.00 |  | TAP-81873 | [TAP-81873] ¦ [US URO] De-rating Prototype Jaw Opening & Closing Forces | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81874 | 86 | 1 |  | 04.49.02.00.00.00.00.00 |  | TAP-81874 | [TAP-81874] ¦ [US URO] De-rating Prototype Tracking Errors | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81924 | 87 | 1 |  | 04.49.03.00.00.00.00.00 |  | TAP-81924 | [TAP-81924] ¦ [US URO] De-rating Prototype Range Of Motion | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81925 | 88 | 1 |  | 04.49.04.00.00.00.00.00 |  | TAP-81925 | [TAP-81925] ¦ [US URO] De-rating Prototype Endoscope Directional Accuracy | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81926 | 89 | 1 |  | 04.49.05.00.00.00.00.00 |  | TAP-81926 | [TAP-81926] ¦ [US URO] De-rating Prototype Translation Distance in Time | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-91222 | 90 | 5 |  | 04.49.06.00.00.00.00.00 |  | TAP-91222 | [TAP-91222] ¦ [IRR][US URO] Set and Lock Out Articulation and Roll in De-Rating Tool | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96638 | 91 | 1 |  | 04.49.09.00.00.00.00.00 |  | TAP-96638 | [TAP-96638] ¦ [US URO] - Update URO Derating Tools to Address TMD Feedback | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104444 | 92 | 5 |  | 04.49.10.00.00.00.00.00 |  | TAP-104444 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104444 | 93 | 92 |  | 04.50.00.00.00.00.00.00 |  | RAS-15156 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Enhancement | Closed |  |  |  |  | 21 | 12 | 21 | 25.2 | 9 | 57.14% | 0 | 0 | Story Points
TAP-104444 | 94 | 92 |  | 04.51.00.00.00.00.00.00 |  | RAS-11303 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Defect | In progress |  |  |  |  | 21 | 12 | 21 | 25.2 | 9 | 57.14% | 0 | 0 | Story Points
TAP-104444 | 95 | 92 |  | 04.55.02.00.00.00.00.00 |  | TAP-122035 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Issue | In progress | Foundation - Classy | CLASSY |  |  | 24 | 12 | 24 | 28.8 | 12 | 50% | 0 | 0 | Story Points
TAP-104444 | 96 | 92 |  | 04.55.03.00.00.00.00.00 |  | TAP-112338 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Issue | Done | Foundation - Classy 1 | CLASSY1 |  |  | 24 | 12 | 24 | 28.8 | 12 | 100% | 0 | 0 | Story Points
TAP-104444 | 97 | 92 |  | 04.55.04.00.00.00.00.00 |  | TAP-117166 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Issue | Done | Foundation - Classy 2 | CLASSY2 |  |  | 24 | 12 | 24 | 28.8 | 12 | 100% | 0 | 0 | Story Points
TAP-113408 | 98 | 9 |  | 04.56.01.00.00.00.00.00 |  | TAP-113408 | [TAP-113408] ¦ [Foundation] Fix Design Documentation | Feature | Done |  |  |  |  | 50.8 | 50.8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113410 | 99 | 9 |  | 04.56.03.00.00.00.00.00 |  | TAP-113410 | [TAP-113410] ¦ [Core Instr] Fix Design Documentation | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113410 | 100 | 99 |  | 04.57.00.00.00.00.00.00 |  | RAS-15062 | [TAP-113410] ¦ [Core Instr] Fix Design Documentation | Enhancement | In progress |  |  |  |  | 21 | 13 | 21 | 25.2 | 8 | 61.9% | 0 | 0 | Story Points
TAP-125059 | 101 | 13 |  | 04.57.01.00.00.00.00.00 |  | TAP-125059 | [TAP-125059] ¦ [V4.0][Cyber] Upgrade from Staging GSO to Production GSO for build signing | Feature | Accepted |  |  |  |  | 24 | 2 | 1 hr | 1 hr | 22 | 8.333% | 0 | 0 | Story Points
TAP-125059 | 102 | 101 |  | 04.58.00.00.00.00.00.00 |  | RAS-15043 | [TAP-125059] ¦ [V4.0][Cyber] Upgrade from Staging GSO to Production GSO for build signing | Defect | In progress |  |  |  |  | 34.5 | 2 | 34.5 | 41.4 | 32.5 | 5.797% | 0 | 0 | Story Points
TAP-125059 | 103 | 101 |  | 04.59.00.00.00.00.00.00 |  | RAS-13563 | [TAP-125059] ¦ [V4.0][Cyber] Upgrade from Staging GSO to Production GSO for build signing | Enhancement | In progress |  |  |  |  | 37.5 | 2 | 37.5 | 45 | 35.5 | 5.333% | 0 | 0 | Story Points
TAP-93577 | 104 | 13 |  | 04.59.01.00.00.00.00.00 |  | TAP-93577 | [TAP-93577] ¦ {GUI}(v4.0) [Cyber] Package and send translation package to GDS | Feature | Done |  |  |  |  | 20 | 20 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96537 | 105 | 13 |  | 04.59.03.00.00.00.00.00 |  | TAP-96537 | [TAP-96537] ¦ {GUI} (RAS-7008) v3.0 Language Formals and Release | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-116321 | 106 | 13 |  | 04.59.08.00.00.00.00.00 |  | TAP-116321 | [TAP-116321] ¦ {GUI} (RAS-13563) v4.0 Language Formals and Release | Feature | Accepted |  |  |  |  | 18 | 0 | 1 hr | 1 hr | 18 | 0% | 0 | 0 | Story Points
TAP-116321 | 107 | 106 |  | 04.60.00.00.00.00.00.00 |  | RAS-15162 | [TAP-116321] ¦ {GUI} (RAS-13563) v4.0 Language Formals and Release | Defect | In progress |  |  |  |  | 35 | 0 | 35 | 42 | 35 | 0% | 0 | 0 | Story Points
TAP-126027 | 108 | 13 |  | 04.60.01.00.00.00.00.00 |  | TAP-126027 | [TAP-126027] ¦ [V4.0][RC1][Cyber] Implement penetration testing findings for WolfSSH 1.4.17 | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-126027 | 109 | 108 |  | 04.61.00.00.00.00.00.00 |  | RAS-15161 | [TAP-126027] ¦ [V4.0][RC1][Cyber] Implement penetration testing findings for WolfSSH 1.4.17 | Defect | In progress |  |  |  |  | 3 | 3 | 3 | 3.6 | 0 | 100% | 0 | 0 | Story Points
TAP-58674 | 110 | 13 |  | 04.61.01.00.00.00.00.00 |  | TAP-58674 | [TAP-58674] ¦ [Cyber] Implement Fixes for Findings in Micro Penetration Testing for DDS/UDP | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58674 | 111 | 110 |  | 04.62.00.00.00.00.00.00 |  | RAS-5764 | [TAP-58674] ¦ [Cyber] Implement Fixes for Findings in Micro Penetration Testing for DDS/UDP | Defect | In progress | Foundation - Atlas | ATLAS |  |  | 5 | 5 | 5 | 6 | 0 | 100% | 0 | 0 | Story Points
TAP-58674 | 112 | 110 |  | 04.63.00.00.00.00.00.00 |  | RAS-15045 | [TAP-58674] ¦ [Cyber] Implement Fixes for Findings in Micro Penetration Testing for DDS/UDP | Enhancement | In progress |  |  |  |  | 5 | 5 | 5 | 6 | 0 | 100% | 0 | 0 | Story Points
TAP-109870 | 113 | 13 |  | 04.63.01.00.00.00.00.00 |  | TAP-109870 | [TAP-109870] ¦ [Cyber] ESAT v2, Support Field Service Use of CyberArk P2 | Feature | Accepted |  |  |  |  | 121 | 85 | 1 hr | 1 hr | 36 | 70.25% | 0 | 0 | Story Points
TAP-122714 | 114 | 13 |  | 04.63.02.00.00.00.00.00 |  | TAP-122714 | [TAP-122714] ¦ [V4.0][RC2] ESAT v2: Additional ESAT and NPS content for V4 RC2 | Feature | Accepted |  |  |  |  | 130 | 59 | 1 hr | 1 hr | 71 | 45.38% | 0 | 0 | Story Points
TAP-122714 | 115 | 114 |  | 04.63.02.08.00.00.00.00 | TAP-122714 | TAP-81292 | [TAP-122714] ¦ [V4.0][RC2] ESAT v2: Additional ESAT and NPS content for V4 RC2 | Issue | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 155 | 59 | 155 | 186 | 96 | 100% | 0 | 0 | Story Points
TAP-122714 | 116 | 114 |  | 04.63.02.13.01.00.00.00 | TAP-122714 | TAP-126254 | [TAP-122714] ¦ [V4.0][RC2] ESAT v2: Additional ESAT and NPS content for V4 RC2 | Sub Task | In progress |  |  |  |  | 176 | 59 | 176 | 211.2 | 117 | 33.52% | 0 | 0 | Story Points
TAP-102220 | 117 | 13 |  | 04.63.02.16.00.00.00.00 | TAP-122714 | TAP-102220 | [TAP-102220] ¦ [V4] [Cyber] ESAT Laptop certificate installation | Feature | Done |  |  |  |  | 38 | 38 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-102220 | 118 | 117 |  | 04.64.00.00.00.00.00.00 |  | RAS-14944 | [TAP-102220] ¦ [V4] [Cyber] ESAT Laptop certificate installation | Enhancement | In progress |  |  |  |  | 77 | 38 | 77 | 92.4 | 39 | 49.35% | 0 | 0 | Story Points
TAP-84375 | 119 | 13 |  | 04.64.01.00.00.00.00.00 |  | TAP-84375 | [TAP-84375] ¦ [Cyber] US FRU Replacement Script/Procedure Updates | Feature | Done |  |  |  |  | 78 | 78 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87778 | 120 | 21 |  | 04.64.02.00.00.00.00.00 |  | TAP-87778 | [TAP-87778] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 2 (validation) | Feature | In progress |  |  |  |  | 42 | 0 | 1 hr | 1 hr | 42 | 0% | 0 | 0 | Story Points
TAP-115441 | 121 | 13 |  | 04.64.05.00.00.00.00.00 |  | TAP-115441 | [TAP-115441] ¦ [Cyber] Ubuntu BSP To support Plexus Programming | Feature | Accepted |  |  |  |  | 48.5 | 20 | 1 hr | 1 hr | 28.5 | 41.24% | 0 | 0 | Story Points
TAP-115441 | 122 | 121 |  | 04.65.00.00.00.00.00.00 |  | RAS-15282 | [TAP-115441] ¦ [Cyber] Ubuntu BSP To support Plexus Programming | Enhancement | In progress |  |  |  |  | 85 | 20 | 85 | 102 | 65 | 23.53% | 0 | 0 | Story Points
TAP-86043 | 123 | 13 |  | 04.65.01.00.00.00.00.00 |  | TAP-86043 | [TAP-86043] ¦ [Cyber] Enable ARM production security features | Feature | Accepted |  |  |  |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | 0 | 0 | Story Points
TAP-86043 | 124 | 123 |  | 04.66.00.00.00.00.00.00 |  | RAS-15141 | [TAP-86043] ¦ [Cyber] Enable ARM production security features | Enhancement | In progress |  |  |  |  | 3 | 0 | 3 | 3.6 | 3 | 0% | 0 | 0 | Story Points
TAP-111218 | 125 | 13 |  | 04.66.01.00.00.00.00.00 |  | TAP-111218 | [TAP-111218] ¦ [Cyber] Non Production Boot Deployment | Feature | In progress |  |  |  |  | 64 | 59 | 1 hr | 1 hr | 5 | 92.19% | 0 | 0 | Story Points
TAP-111218 | 126 | 125 |  | 04.67.00.00.00.00.00.00 |  | RAS-15154 | [TAP-111218] ¦ [Cyber] Non Production Boot Deployment | Defect | In progress |  |  |  |  | 122 | 59 | 122 | 146.4 | 63 | 48.36% | 0 | 0 | Story Points
TAP-125598 | 127 | 13 |  | 04.67.01.00.00.00.00.00 |  | TAP-125598 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Feature | Accepted |  |  |  |  | 12.5 | 0 | 1 hr | 1 hr | 12.5 | 0% | 0 | 0 | Story Points
TAP-125598 | 128 | 127 |  | 04.68.00.00.00.00.00.00 |  | RAS-15284 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Defect | In progress |  |  |  |  | 22 | 0 | 22 | 26.4 | 22 | 0% | 0 | 0 | Story Points
TAP-125598 | 129 | 127 |  | 04.68.01.00.00.00.00.00 |  | TAP-124550 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Issue | Open | Released Product Engineering - Drushti | DRUSHTI |  |  | 22 | 0 | 22 | 26.4 | 22 | 0% | 0 | 0 | Story Points
TAP-125598 | 130 | 127 |  | 04.70.00.00.00.00.00.00 |  | RAS-15286 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Enhancement | In progress |  |  |  |  | 22 | 0 | 22 | 26.4 | 22 | 0% | 0 | 0 | Story Points
TAP-128136 | 131 | 13 |  | 04.71.02.00.00.00.00.00 |  | TAP-128136 | [TAP-128136] ¦ {v4 RC2} RAS-15283 - Radio Button Misalignment in Visualization Screen for Non-English Languages | Feature | PROPOSED |  |  |  |  | 5 | 0 | 1 hr | 1 hr | 5 | 0% | 0 | 0 | Story Points
TAP-128136 | 132 | 131 |  | 04.72.00.00.00.00.00.00 |  | RAS-10734 | [TAP-128136] ¦ {v4 RC2} RAS-15283 - Radio Button Misalignment in Visualization Screen for Non-English Languages | Enhancement | In progress |  |  |  |  | 5 | 0 | 5 | 6 | 5 | 0% | 0 | 0 | Story Points
TAP-94626 | 133 | 1 |  | 04.72.04.00.00.00.00.00 |  | TAP-94626 | [TAP-94626] ¦ Reduce SW Verification dependency on test setup and tools - implementation | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94626 | 134 | 133 |  | 04.72.06.00.00.00.00.00 |  | TAP-122649 | [TAP-94626] ¦ Reduce SW Verification dependency on test setup and tools - implementation | Issue | Done | Foundation - Horizon | HORIZON |  |  | 51.5 | 31 | 51.5 | 61.8 | 20.5 | 100% | 0 | 0 | Story Points
TAP-115657 | 135 | 11 |  | 04.72.08.00.00.00.00.00 |  | TAP-115657 | [TAP-115657] ¦ [Cyber] Tracking Documentation For Design Outputs - EIN V4.0 Testability Detailed Designs | Feature | Done |  |  |  |  | 18.5 | 18.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-125101 | 136 | 13 |  | 04.72.12.00.00.00.00.00 |  | TAP-125101 | [TAP-125101] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - Foundation | Feature | Accepted |  |  |  |  | 79 | 17 | 1 hr | 1 hr | 62 | 21.52% | 0 | 0 | Story Points
TAP-125113 | 137 | 13 |  | 04.72.13.00.00.00.00.00 |  | TAP-125113 | [TAP-125113] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - AdvancedInstr | Feature | Accepted |  |  |  |  | 8.25 | 0 | 1 hr | 1 hr | 8.25 | 0% | 0 | 0 | Story Points
TAP-125114 | 138 | 13 |  | 04.72.14.00.00.00.00.00 |  | TAP-125114 | [TAP-125114] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - CoreInstr | Feature | Accepted |  |  |  |  | 6 | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-125114 | 139 | 138 |  | 04.72.16.00.00.00.00.00 |  | TAP-127952 | [TAP-125114] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - CoreInstr | Issue | In progress | Foundation - Storm Chasers | STORMCHASERS |  |  | 6 | 0 | 6 | 7.2 | 6 | 0% | 0 | 0 | Story Points
TAP-95509 | 140 | 1 |  | 05.01.00.00.00.00.00.00 |  | TAP-95509 | [TAP-95509] ¦ [IDP] Generate Doxygen documentation for every mainline. | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103380 | 141 | 5 |  | 05.02.00.00.00.00.00.00 |  | TAP-103380 | [TAP-103380] ¦ [IDP][Enabler] CMake clean-up | Feature | Done |  |  |  |  | 18.5 | 18.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103380 | 142 | 141 |  | 05.02.11.00.00.00.00.00 | TAP-103380 | TAP-108521 | [TAP-103380] ¦ [IDP][Enabler] CMake clean-up | Issue | Done | Shared Services - Seamless | SEAMLESS |  |  | 30.5 | 18.5 | 30.5 | 36.6 | 12 | 100% | 0 | 0 | Story Points
TAP-102422 | 143 | 9 |  | 05.03.00.00.00.00.00.00 |  | TAP-102422 | [TAP-102422] ¦ [IDP][Foundation] Support integration of the design documents into the code repository | Feature | Done |  |  |  |  | 17.2 | 17.2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95500 | 144 | 1 |  | 05.04.00.00.00.00.00.00 |  | TAP-95500 | [TAP-95500] ¦ [IDP] Use Code Change Impact Analysis Tool in Production | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95095 | 145 | 1 |  | 05.05.00.00.00.00.00.00 |  | TAP-95095 | [TAP-95095] ¦ [Tech Debt] PI12 - Improve Unit Tests (Foundation) | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95095 | 146 | 145 |  | 05.05.01.00.00.00.00.00 | TAP-95095 | TAP-94518 | [TAP-95095] ¦ [Tech Debt] PI12 - Improve Unit Tests (Foundation) | Issue | Done | Foundation - Classy 2 | CLASSY2 |  |  | 30 | 30 | 30 | 36 | 0 | 100% | 0 | 0 | Story Points
TAP-95095 | 147 | 145 |  | 05.05.02.00.00.00.00.00 | TAP-95095 | TAP-93137 | [TAP-95095] ¦ [Tech Debt] PI12 - Improve Unit Tests (Foundation) | Issue | Done | Foundation - Atlas | ATLAS |  |  | 30 | 30 | 30 | 36 | 0 | 100% | 0 | 0 | Story Points
TAP-95095 | 148 | 145 |  | 05.05.05.00.00.00.00.00 | TAP-95095 | TAP-93361 | [TAP-95095] ¦ [Tech Debt] PI12 - Improve Unit Tests (Foundation) | Issue | Done | Foundation - Fred | FRED |  |  | 32 | 30 | 32 | 38.4 | 2 | 100% | 0 | 0 | Story Points
TAP-95095 | 149 | 145 |  | 05.05.09.00.00.00.00.00 | TAP-95095 | TAP-92787 | [TAP-95095] ¦ [Tech Debt] PI12 - Improve Unit Tests (Foundation) | Issue | Done | Foundation - Classy 1 | CLASSY1 |  |  | 32 | 30 | 32 | 38.4 | 2 | 100% | 0 | 0 | Story Points
TAP-73233 | 150 | 3 |  | 05.06.00.00.00.00.00.00 |  | TAP-73233 | [TAP-73233] ¦ [Architecture][Infrastructure] Improve KPI collection and processing software | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87661 | 151 | 1 |  | 05.07.00.00.00.00.00.00 |  | TAP-87661 | [TAP-87661] ¦ [V&V Enabler] SW Verification - Improvements Batch2 - Foundation | Feature | Done |  |  |  |  | 9.5 | 9.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55705 | 152 | 1 |  | 05.08.00.00.00.00.00.00 |  | TAP-55705 | [TAP-55705] ¦ Refactor logging library | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55471 | 153 | 1 |  | 05.09.00.00.00.00.00.00 |  | TAP-55471 | [TAP-55471] ¦ [V4.0] Keep alarms, errors, safety, communication SW verification tests up to date | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-117503 | 154 | 9 |  | 05.10.00.00.00.00.00.00 |  | TAP-117503 | [TAP-117503] ¦ [Shared Services] [v4.0] sFMEA update and review | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83615 | 155 | 1 |  | 05.11.00.00.00.00.00.00 |  | TAP-83615 | [TAP-83615] ¦ [Architecture][Enabler] GECAT for Instruments Data Transportation - Foundation Support | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82932 | 156 | 1 |  | 05.12.00.00.00.00.00.00 |  | TAP-82932 | [TAP-82932] ¦ [V4.0] Stability issue investigation and resolution - PI11 | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82932 | 157 | 156 |  | 05.12.01.00.00.00.00.00 | TAP-82932 | TAP-59958 | [TAP-82932] ¦ [V4.0] Stability issue investigation and resolution - PI11 | Issue | Done | Foundation - Fred | FRED |  |  | 11 | 11 | 11 | 13.2 | 0 | 100% | 0 | 0 | Story Points
TAP-82932 | 158 | 156 |  | 05.12.03.00.00.00.00.00 | TAP-82932 | TAP-77873 | [TAP-82932] ¦ [V4.0] Stability issue investigation and resolution - PI11 | Issue | Done | Foundation - Boosters | BOOSTERS |  |  | 14 | 11 | 14 | 16.8 | 3 | 100% | 0 | 0 | Story Points
TAP-93110 | 159 | 1 |  | 05.13.00.00.00.00.00.00 |  | TAP-93110 | [TAP-93110] ¦ [V4.0][Architecture] Improve SW Virtualization Platform | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86330 | 160 | 1 |  | 05.14.00.00.00.00.00.00 |  | TAP-86330 | [TAP-86330] ¦ [v4.0](TAP-66316) Add SMC data recorder bfbs schema file to SMC Application package | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86330 | 161 | 160 |  | 05.14.01.00.00.00.00.00 | TAP-86330 | TAP-66316 | [TAP-86330] ¦ [v4.0](TAP-66316) Add SMC data recorder bfbs schema file to SMC Application package | Issue | Done | Released Product Engineering - Iconics | ICONICS |  |  | 5 | 5 | 5 | 6 | 0 | 100% | 0 | 0 | Story Points
TAP-83225 | 162 | 1 |  | 05.15.00.00.00.00.00.00 |  | TAP-83225 | [TAP-83225] ¦ [v4.0] Expanding ENDOSW tests to perform integration testing with GUI | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70472 | 163 | 1 |  | 05.16.00.00.00.00.00.00 |  | TAP-70472 | [TAP-70472] ¦ [V4.0] Implement EDID based detection of S3D and use Intel UHD graphics driver for SCDC Windows installation | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-16423 | 164 | 1 |  | 05.17.00.00.00.00.00.00 |  | TAP-16423 | [TAP-16423] ¦ [Infra] SW Integration Framework Prototype | Feature | Done |  |  |  |  | 139 | 139 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2693 | 165 | 1 |  | 05.18.00.00.00.00.00.00 |  | TAP-2693 | [TAP-2693] ¦ [Tech Debt][platformers][V&V] test infrastructure improvements Batch 1 | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-6886 | 166 | 1 |  | 05.19.00.00.00.00.00.00 |  | TAP-6886 | [TAP-6886] ¦ [Compliance] Establish Controlled Process for log data specification in JAMA | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115484 | 167 | 7 |  | 05.20.00.00.00.00.00.00 |  | TAP-115484 | [TAP-115484] ¦ QNX 7.1 BSP for FSE test fixture | Feature | Done |  |  |  |  | 4.1 | 4.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-64261 | 168 | 7 |  | 05.21.00.00.00.00.00.00 |  | TAP-64261 | [TAP-64261] ¦ [v4.0 SW][Arch][Enabler] Improve Unit Tests (Foundation) | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76479 | 169 | 1 |  | 05.22.00.00.00.00.00.00 |  | TAP-76479 | [TAP-76479] ¦ [Architecture][Spike] Future Software Item Breakdown - Align SWI, Repository, and Requirements - PI12 | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-48935 | 170 | 1 |  | 05.23.00.00.00.00.00.00 |  | TAP-48935 | [TAP-48935] ¦ [TechDebt]Refactor EtherCAT communication | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47057 | 171 | 1 |  | 05.24.00.00.00.00.00.00 |  | TAP-47057 | [TAP-47057] ¦ [Tech Debt] Integrate log_clock into product | Feature | Done |  |  |  |  | 49 | 49 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83342 | 172 | 1 |  | 05.25.00.00.00.00.00.00 |  | TAP-83342 | [TAP-83342] ¦ ESAT v2 Stability and Usability Enhancements | Feature | Done |  |  |  |  | 130 | 130 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83342 | 173 | 172 |  | 05.25.40.00.00.00.00.00 | TAP-83342 | TAP-99844 | [TAP-83342] ¦ ESAT v2 Stability and Usability Enhancements | Issue | Done | Foundation - Atlas | ATLAS |  |  | 257 | 130 | 257 | 308.4 | 127 | 100% | 0 | 0 | Story Points
TAP-71137 | 174 | 1 |  | 05.26.00.00.00.00.00.00 |  | TAP-71137 | [TAP-71137] ¦ [v4.0] GUI codebase cleanup | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-99176 | 175 | 7 |  | 05.27.00.00.00.00.00.00 |  | TAP-99176 | [TAP-99176] ¦ Update Failing Tests and Static Analysis | Feature | Done |  |  |  |  | 95 | 95 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95508 | 176 | 7 |  | 05.28.00.00.00.00.00.00 |  | TAP-95508 | [TAP-95508] ¦ [IDP] Improve build system - Batch 1 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95505 | 177 | 1 |  | 05.29.00.00.00.00.00.00 |  | TAP-95505 | [TAP-95505] ¦ [IDP] Support Unit Verification Process Improvement - Batch 1 | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72843 | 178 | 1 |  | 05.30.00.00.00.00.00.00 |  | TAP-72843 | [TAP-72843] ¦ Support collapse of develop-next back to develop | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70775 | 179 | 1 |  | 05.31.00.00.00.00.00.00 |  | TAP-70775 | [TAP-70775] ¦ [Infrastructure] Setup Minimal Simulink Projects for Impact Analysis Verification | Feature | Done |  |  |  |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-54303 | 180 | 1 |  | 05.32.00.00.00.00.00.00 |  | TAP-54303 | [TAP-54303] ¦ [Architecture][Spike] Future Software Item Breakdown - Align SWI, Repository, and Requirements | Feature | Done |  |  |  |  | 57.9 | 57.9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85444 | 181 | 1 |  | 05.33.00.00.00.00.00.00 |  | TAP-85444 | [TAP-85444] ¦ [V4.0][Visual] Tests and development process improvements after the new codebase merge | Feature | Done |  |  |  |  | 23.5 | 23.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81827 | 182 | 1 |  | 05.34.00.00.00.00.00.00 |  | TAP-81827 | [TAP-81827] ¦ [Infrastructure] Reduce Simulink Verification Runtime | Feature | Done |  |  |  |  | 53.5 | 53.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-66620 | 183 | 1 |  | 05.35.00.00.00.00.00.00 |  | TAP-66620 | [TAP-66620] ¦ [Tech Debt] Remove Testability Branch for Simulink Tools | Feature | Done |  |  |  |  | 53 | 53 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97622 | 184 | 7 |  | 05.36.00.00.00.00.00.00 |  | TAP-97622 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Feature | Done |  |  |  |  | 72 | 72 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97622 | 185 | 184 |  | 05.36.01.00.00.00.00.00 | TAP-97622 | TAP-97666 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Issue | Done | Foundation - Fred | FRED |  |  | 72 | 72 | 72 | 86.4 | 0 | 100% | 0 | 0 | Story Points
TAP-97622 | 186 | 184 |  | 05.36.02.00.00.00.00.00 | TAP-97622 | TAP-90298 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Issue | Done | Foundation - Atlas | ATLAS |  |  | 72 | 72 | 72 | 86.4 | 0 | 100% | 0 | 0 | Story Points
TAP-97622 | 187 | 184 |  | 05.36.10.00.00.00.00.00 | TAP-97622 | TAP-94003 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Issue | Done | Foundation - Platformers | PLATFORMERS |  |  | 89 | 72 | 89 | 106.8 | 17 | 100% | 0 | 0 | Story Points
TAP-97622 | 188 | 184 |  | 05.36.12.00.00.00.00.00 | TAP-97622 | TAP-101952 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Issue | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 |  |  | 94 | 72 | 94 | 112.8 | 22 | 100% | 0 | 0 | Story Points
TAP-97622 | 189 | 184 |  | 05.36.14.00.00.00.00.00 | TAP-97622 | TAP-101957 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Issue | Done | Foundation - Visual | VISUAL |  |  | 96 | 72 | 96 | 115.2 | 24 | 100% | 0 | 0 | Story Points
TAP-97622 | 190 | 184 |  | 05.36.24.00.00.00.00.00 | TAP-97622 | TAP-93125 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Issue | Done | Foundation - Classy 2 | CLASSY2 |  |  | 104.5 | 72 | 104.5 | 125.4 | 32.5 | 100% | 0 | 0 | Story Points
TAP-104009 | 191 | 5 |  | 05.37.00.00.00.00.00.00 |  | TAP-104009 | [TAP-104009] ¦ [V2.2] Field Script Readiness Evaluation | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-49649 | 192 | 1 |  | 05.38.00.00.00.00.00.00 |  | TAP-49649 | [TAP-49649] ¦ [Tech Debt] Complete ACS Rework | Feature | Done |  |  |  |  | 47 | 47 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113409 | 193 | 285, 9 |  | 05.39.00.00.00.00.00.00 |  | TAP-113409 | [TAP-113409] ¦ [V4][Adv Instr] Fix Design Documentation | Feature | Done |  |  |  |  | 28.5 | 28.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-68411 | 194 | 3 |  | 05.40.00.00.00.00.00.00 |  | TAP-68411 | [TAP-68411] ¦ [TechDebt] [v4.0] Remove sphlib | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76424 | 195 | 1 |  | 05.41.00.00.00.00.00.00 |  | TAP-76424 | [TAP-76424] ¦ [Tech Debt] Improve Unit Tests (Foundation) | Feature | Done |  |  |  |  | 28 | 28 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76424 | 196 | 195 |  | 05.41.01.00.00.00.00.00 | TAP-76424 | TAP-82163 | [TAP-76424] ¦ [Tech Debt] Improve Unit Tests (Foundation) | Issue | Done | Foundation - Atlas | ATLAS |  |  | 28 | 28 | 28 | 33.6 | 0 | 100% | 0 | 0 | Story Points
TAP-76424 | 197 | 195 |  | 05.41.02.00.00.00.00.00 | TAP-76424 | TAP-83056 | [TAP-76424] ¦ [Tech Debt] Improve Unit Tests (Foundation) | Issue | Done | Foundation - Fred | FRED |  |  | 28 | 28 | 28 | 33.6 | 0 | 100% | 0 | 0 | Story Points
TAP-76424 | 198 | 195 |  | 05.41.09.00.00.00.00.00 | TAP-76424 | TAP-82172 | [TAP-76424] ¦ [Tech Debt] Improve Unit Tests (Foundation) | Issue | Done | Foundation - Platformers | PLATFORMERS |  |  | 36 | 28 | 36 | 43.2 | 8 | 100% | 0 | 0 | Story Points
TAP-76424 | 199 | 195 |  | 05.41.12.00.00.00.00.00 | TAP-76424 | TAP-88763 | [TAP-76424] ¦ [Tech Debt] Improve Unit Tests (Foundation) | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 |  |  | 37 | 28 | 37 | 44.4 | 9 | 100% | 0 | 0 | Story Points
TAP-69437 | 200 | 1 |  | 05.42.00.00.00.00.00.00 |  | TAP-69437 | [TAP-69437] ¦ [Architecture] Improve alarm code generator workflow | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72858 | 201 | 1 |  | 05.43.00.00.00.00.00.00 |  | TAP-72858 | [TAP-72858] ¦ [V4.0][Inogeni][TechDebt] Post-release support and software refactoring | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72858 | 202 | 201 |  | 05.43.01.00.00.00.00.00 | TAP-72858 | TAP-74081 | [TAP-72858] ¦ [V4.0][Inogeni][TechDebt] Post-release support and software refactoring | Capability | Done |  |  |  |  | 31 | 31 | 31 | 37.2 | 0 | 100% | 0 | 0 | Story Points
TAP-72842 | 203 | 1 |  | 05.44.00.00.00.00.00.00 |  | TAP-72842 | [TAP-72842] ¦ Support collapse of develop-next back to develop | Feature | Done |  |  |  |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-61255 | 204 | 1 |  | 05.45.00.00.00.00.00.00 |  | TAP-61255 | [TAP-61255] ¦ [V4.0] Improve performance of Data Access software to allow support of more logs collection | Feature | Done |  |  |  |  | 79 | 79 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-53969 | 205 | 1 |  | 05.46.00.00.00.00.00.00 |  | TAP-53969 | [TAP-53969] ¦ [v4.0 SW][Tech Debt] Migrate C++ Unit Tests to new process/framework | Feature | Done |  |  |  |  | 72 | 72 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-53969 | 206 | 205 |  | 05.46.01.00.00.00.00.00 | TAP-53969 | TAP-54365 | [TAP-53969] ¦ [v4.0 SW][Tech Debt] Migrate C++ Unit Tests to new process/framework | Issue | Done | Foundation - Platformers | PLATFORMERS |  |  | 72 | 72 | 72 | 86.4 | 0 | 100% | 0 | 0 | Story Points
TAP-53969 | 207 | 205 |  | 05.46.04.00.00.00.00.00 | TAP-53969 | TAP-55017 | [TAP-53969] ¦ [v4.0 SW][Tech Debt] Migrate C++ Unit Tests to new process/framework | Issue | Done | Foundation - Marvel | MARVEL |  |  | 72 | 72 | 72 | 86.4 | 0 | 100% | 0 | 0 | Story Points
TAP-84311 | 208 | 1 |  | 05.47.00.00.00.00.00.00 |  | TAP-84311 | [TAP-84311] ¦ [Architecture][Infrastructure] Use Code Change Impact Analysis Tool to run only affected unit-tests | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-37832 | 209 | 1 |  | 05.48.00.00.00.00.00.00 |  | TAP-37832 | [TAP-37832] ¦ [v4.0 SW][techDebt] Fix remaining coverity findings for v4.0 software (PI7 Platform) | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-36556 | 210 | 1 |  | 05.49.00.00.00.00.00.00 |  | TAP-36556 | [TAP-36556] ¦ [Arch]Cleanup EtherCAT communication | Feature | Done |  |  |  |  | 40.25 | 40.25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47543 | 211 | 1 |  | 05.50.00.00.00.00.00.00 |  | TAP-47543 | [TAP-47543] ¦ [Arch][Enabler] Rework ACS Core | Feature | Done |  |  |  |  | 100.5 | 100.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-63938 | 212 | 1 |  | 05.51.00.00.00.00.00.00 |  | TAP-63938 | [TAP-63938] ¦ [V4.0][DFS] Logging update to better connect events with procedures - implementation | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-60608 | 213 | 1 |  | 05.52.00.00.00.00.00.00 |  | TAP-60608 | [TAP-60608] ¦ Replace Ripdraw SOUP library with in-house implementation | Feature | Done |  |  |  |  | 165 | 165 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-47915 | 214 | 1 |  | 05.53.00.00.00.00.00.00 |  | TAP-47915 | [TAP-47915] ¦ [Arch][Enabler] Refine RASA Applications | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-69540 | 215 | 1 |  | 05.54.00.00.00.00.00.00 |  | TAP-69540 | [TAP-69540] ¦ [Tech Debt][Simulink] Update unit tests to be compatible with Simulink SIL/PIL Testing | Feature | Done |  |  |  |  | 53.5 | 53.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71958 | 216 | 1 |  | 05.55.00.00.00.00.00.00 |  | TAP-71958 | [TAP-71958] ¦ [v3.0][Enabler] IDU Standalones Automation Enhancements - Part 1 | Feature | Done |  |  |  |  | 32.25 | 32.25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113411 | 217 | 9 |  | 05.56.00.00.00.00.00.00 |  | TAP-113411 | [TAP-113411] ¦ [RPE] Fix Design Documentation | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-122378 | 218 | 7 |  | 05.57.00.00.00.00.00.00 |  | TAP-122378 | [TAP-122378] ¦ [V4][RC1] Update Setup Arm Latency test duration as per new requirement | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113539 | 219 | 7 |  | 05.58.00.00.00.00.00.00 |  | TAP-113539 | [TAP-113539] ¦ ESAT v2 - Continued Improvement ESAT v2 (PI14) - Product Security | Feature | Done |  |  |  |  | 101 | 101 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113539 | 220 | 219 |  | 05.58.05.00.00.00.00.00 | TAP-113539 | TAP-113805 | [TAP-113539] ¦ ESAT v2 - Continued Improvement ESAT v2 (PI14) - Product Security | Issue | Done | Foundation - Tools Rules | TOOLSRULES |  |  | 122 | 101 | 122 | 146.4 | 21 | 100% | 0 | 0 | Story Points
TAP-114202 | 221 | 7 |  | 05.59.00.00.00.00.00.00 |  | TAP-114202 | [TAP-114202] ¦ [IDP][Enabler] Infrastructure maintenance PI14 | Feature | Done |  |  |  |  | 66.5 | 66.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106648 | 222 | 7 |  | 05.60.00.00.00.00.00.00 |  | TAP-106648 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Feature | Done |  |  |  |  | 64.1 | 64.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106648 | 223 | 222 |  | 05.60.01.00.00.00.00.00 | TAP-106648 | TAP-99185 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Issue | Done | Foundation - Classy 2 | CLASSY2 |  |  | 64.1 | 64.1 | 64.1 | 76.92 | 0 | 100% | 0 | 0 | Story Points
TAP-106648 | 224 | 222 |  | 05.60.06.00.00.00.00.00 | TAP-106648 | TAP-96973 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Issue | Done | Foundation - Fred | FRED |  |  | 68.1 | 64.1 | 68.1 | 81.72 | 4 | 100% | 0 | 0 | Story Points
TAP-106648 | 225 | 222 |  | 05.60.07.00.00.00.00.00 | TAP-106648 | TAP-84396 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Issue | Done | Foundation - Boosters | BOOSTERS |  |  | 68.1 | 64.1 | 68.1 | 81.72 | 4 | 100% | 0 | 0 | Story Points
TAP-106648 | 226 | 222 |  | 05.60.17.00.00.00.00.00 | TAP-106648 | TAP-107499 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Issue | Done | Foundation - Classy 1 | CLASSY1 |  |  | 85.2 | 64.1 | 85.2 | 102.24 | 21.1 | 100% | 0 | 0 | Story Points
TAP-106648 | 227 | 222 |  | 05.60.21.00.00.00.00.00 | TAP-106648 | TAP-114444 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Issue | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 |  |  | 91.2 | 64.1 | 91.2 | 109.44 | 27.1 | 100% | 0 | 0 | Story Points
TAP-106648 | 228 | 222 |  | 05.60.23.00.00.00.00.00 | TAP-106648 | TAP-107108 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 |  |  | 96.2 | 64.1 | 96.2 | 115.44 | 32.1 | 100% | 0 | 0 | Story Points
TAP-106648 | 229 | 222 |  | 05.60.25.00.00.00.00.00 | TAP-106648 | TAP-114194 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Issue | Done | Foundation - Horizon | HORIZON |  |  | 97.7 | 64.1 | 97.7 | 117.24 | 33.6 | 100% | 0 | 0 | Story Points
TAP-95494 | 230 | 7 |  | 05.61.00.00.00.00.00.00 |  | TAP-95494 | [TAP-95494] ¦ [IDP][V4.0] SW Integration QNX_x86_64 Ecosystem into Production | Feature | Done |  |  |  |  | 230 | 230 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95494 | 231 | 230 |  | 06.00.00.00.00.00.00.00 |  | LOT-1403 | [TAP-95494] ¦ [IDP][V4.0] SW Integration QNX_x86_64 Ecosystem into Production | Initiative | In progress |  |  |  |  | 455 | 230 | 455 | 546 | 225 | 50.55% | 0 | 0 | Story Points
TAP-95494 | 232 | 230 |  | 06.01.00.00.00.00.00.00 |  | LOT-6165 | [TAP-95494] ¦ [IDP][V4.0] SW Integration QNX_x86_64 Ecosystem into Production | FX | Open |  |  |  |  | 455 | 230 | 455 | 546 | 225 | 50.55% | 0 | 0 | Story Points
TAP-111461 | 233 | 7 |  | 06.01.01.00.00.00.00.00 |  | TAP-111461 | [TAP-111461] ¦ [V4.0] [Cyber] Peripheral deployment cleanup | Feature | Done |  |  |  |  | 47.5 | 47.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105342 | 234 | 7 |  | 06.01.02.00.00.00.00.00 |  | TAP-105342 | [TAP-105342] ¦ [Cyber][V4.0] Define and Create Test Build to support formal SW VV | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-111460 | 235 | 7 |  | 06.01.03.00.00.00.00.00 |  | TAP-111460 | [TAP-111460] ¦ [V4.0][V&V] Test User Notification when running non clinical software | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87417 | 236 | 7 |  | 06.01.04.00.00.00.00.00 |  | TAP-87417 | [TAP-87417] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun Batch2 and Test Fix - Foundation | Feature | Done |  |  |  |  | 207.5 | 207.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87417 | 237 | 236 |  | 06.01.04.01.00.00.00.00 | TAP-87417 | TAP-95032 | [TAP-87417] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun Batch2 and Test Fix - Foundation | Issue | Done | Foundation - Atlas | ATLAS |  |  | 207.5 | 207.5 | 207.5 | 249 | 0 | 100% | 0 | 0 | Story Points
TAP-87417 | 238 | 236 |  | 06.01.04.10.00.00.00.00 | TAP-87417 | TAP-76503 | [TAP-87417] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun Batch2 and Test Fix - Foundation | Capability | Done |  |  |  |  | 219.5 | 207.5 | 219.5 | 263.4 | 12 | 100% | 0 | 0 | Story Points
TAP-84549 | 239 | 7 |  | 06.01.05.00.00.00.00.00 |  | TAP-84549 | [TAP-84549] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun and Test Fix - AdvancedInstruments | Feature | Done |  |  |  |  | 140.125 | 140.125 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84549 | 240 | 239 |  | 06.01.05.79.00.00.00.00 | TAP-84549 | TAP-94636 | [TAP-84549] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun and Test Fix - AdvancedInstruments | Capability | Done |  |  |  |  | 253.75 | 140.125 | 253.75 | 304.5 | 113.625 | 100% | 0 | 0 | Story Points
TAP-83547 | 241 | 7 |  | 06.01.06.00.00.00.00.00 |  | TAP-83547 | [TAP-83547] ¦ [Cyber][V4.0][V&V] pre-EC1 Dryrun - Foundation | Feature | Done |  |  |  |  | 52 | 52 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83547 | 242 | 241 |  | 06.01.06.14.00.00.00.00 | TAP-83547 | TAP-63682 | [TAP-83547] ¦ [Cyber][V4.0][V&V] pre-EC1 Dryrun - Foundation | Capability | Done |  |  |  |  | 77 | 52 | 77 | 92.4 | 25 | 100% | 0 | 0 | Story Points
TAP-85483 | 243 | 7 |  | 06.01.07.00.00.00.00.00 |  | TAP-85483 | [TAP-85483] ¦ [Cyber][V4.0][Advanced Instruments] SW Verification - Improvements | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85483 | 244 | 243 |  | 06.01.07.03.00.00.00.00 | TAP-85483 | TAP-84553 | [TAP-85483] ¦ [Cyber][V4.0][Advanced Instruments] SW Verification - Improvements | Capability | Done |  |  |  |  | 29 | 29 | 29 | 34.8 | 0 | 100% | 0 | 0 | Story Points
TAP-57120 | 245 | 7 |  | 06.01.08.00.00.00.00.00 |  | TAP-57120 | [TAP-57120] ¦ [Cyber][V4.0][V&V] Investigation of DDS Secure and UDP Secure Impact on SW Testing - Foundation | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84563 | 246 | 7 |  | 06.01.09.00.00.00.00.00 |  | TAP-84563 | [TAP-84563] ¦ [Cyber][V4.0][V&V] Investigation of DDS Secure and UDP Secure Impact on SW Testing - AdvancedInstruments | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85482 | 247 | 7 |  | 06.01.10.00.00.00.00.00 |  | TAP-85482 | [TAP-85482] ¦ [V4.0][Foundation][Cyber] SW Verification - Improvements | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85482 | 248 | 247 |  | 06.01.10.03.00.00.00.00 | TAP-85482 | TAP-76524 | [TAP-85482] ¦ [V4.0][Foundation][Cyber] SW Verification - Improvements | Capability | Done |  |  |  |  | 71 | 71 | 71 | 85.2 | 0 | 100% | 0 | 0 | Story Points
TAP-85484 | 249 | 7 |  | 06.01.11.00.00.00.00.00 |  | TAP-85484 | [TAP-85484] ¦ [V4.0][V&V][Cyber][Core Instruments] SW Verification - Improvements | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94634 | 250 | 7 |  | 06.01.12.00.00.00.00.00 |  | TAP-94634 | [TAP-94634] ¦ [Cyber][V4.0][V&V] Test TOOLS and Test Environment Update | Feature | Done |  |  |  |  | 113.5 | 113.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-67835 | 251 | 7 |  | 06.01.13.00.00.00.00.00 |  | TAP-67835 | [TAP-67835] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - CoreInstruments | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-67834 | 252 | 7 |  | 06.01.14.00.00.00.00.00 |  | TAP-67834 | [TAP-67834] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - Foundation | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84546 | 253 | 7 |  | 06.01.15.00.00.00.00.00 |  | TAP-84546 | [TAP-84546] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - AdvancedInstruments | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105122 | 254 | 11 |  | 06.01.16.00.00.00.00.00 |  | TAP-105122 | [TAP-105122] ¦ [V4][RC1][V&V][Cyber] Test TOOLS and Test Environment Update Preparing for Formal V&V | Feature | Done |  |  |  |  | 103 | 103 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105122 | 255 | 254 |  | 06.01.16.31.00.00.00.00 | TAP-105122 | TAP-114766 | [TAP-105122] ¦ [V4][RC1][V&V][Cyber] Test TOOLS and Test Environment Update Preparing for Formal V&V | Issue | Done | Shared Services - Triple Tea | TRIPLETEA |  |  | 165 | 103 | 165 | 198 | 62 | 100% | 0 | 0 | Story Points
TAP-88236 | 256 | 7 |  | 06.01.17.00.00.00.00.00 |  | TAP-88236 | [TAP-88236] ¦ [Cyber][V4.0][V&V] Engineering Candidate EC1 SW Test Dryrun and Test Failure Fix - Foundation | Feature | Done |  |  |  |  | 322.5 | 322.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-111448 | 257 | 7 |  | 06.01.18.00.00.00.00.00 |  | TAP-111448 | [TAP-111448] ¦ [Cyber][V4.0][V&V] Secure Deployment V&V | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88387 | 258 | 7 |  | 06.01.19.00.00.00.00.00 |  | TAP-88387 | [TAP-88387] ¦ [Cyber][V4.0][V&V] Engineering Candidate EC1 SW Test Dryrun and Test Failure Fix - AdvancedInstruments | Feature | Done |  |  |  |  | 277.55 | 277.55 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87440 | 259 | 7 |  | 06.01.20.00.00.00.00.00 |  | TAP-87440 | [TAP-87440] ¦ [Cyber][V4.0][V&V] Update Test Items to Support Authenticated Communication - Foundation | Feature | Done |  |  |  |  | 96 | 96 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86973 | 260 | 7 |  | 06.01.21.00.00.00.00.00 |  | TAP-86973 | [TAP-86973] ¦ [Cyber][V4.0][V&V] Update Test Items to Support Authenticated Communication - AdvancedInstruments | Feature | Done |  |  |  |  | 57.5 | 57.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106162 | 261 | 7 |  | 06.01.22.00.00.00.00.00 |  | TAP-106162 | [TAP-106162] ¦ [Cyber][V&V] Test certificate expiration notifications | Feature | Done |  |  |  |  | 59 | 59 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88231 | 262 | 7 |  | 06.01.23.00.00.00.00.00 |  | TAP-88231 | [TAP-88231] ¦ [V4][RC1][V&V] [Cyber] Post-EC1 SW Test Dryrun and Test Failure Fix on Test Build - Foundation | Feature | Done |  |  |  |  | 398 | 398 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88386 | 263 | 7 |  | 06.01.24.00.00.00.00.00 |  | TAP-88386 | [TAP-88386] ¦ [V4][RC1][V&V] [Cyber] Post-EC1 SW Test Dryrun and Test Failure Fix on Test Build - AdvancedInstruments | Feature | Done |  |  |  |  | 156.45 | 156.45 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105883 | 264 | 7 |  | 06.01.25.00.00.00.00.00 |  | TAP-105883 | [TAP-105883] ¦ [Cyber][V4.0][V&V] Test Automation of Controls Nominal Behavior SSRs | Feature | Done |  |  |  |  | 88.25 | 88.25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88384 | 265 | 11 |  | 06.01.26.00.00.00.00.00 |  | TAP-88384 | [TAP-88384] ¦ [Cyber][V4.0][V&V] TRR Deliverables Preparation - AdvancedInstruments | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87425 | 266 | 11 |  | 06.01.27.00.00.00.00.00 |  | TAP-87425 | [TAP-87425] ¦ [Cyber][V4.0][V&V] TRR Deliverables Preparation - Foundation | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87425 | 267 | 266 |  | 06.01.27.04.00.00.00.00 | TAP-87425 | TAP-87418 | [TAP-87425] ¦ [Cyber][V4.0][V&V] TRR Deliverables Preparation - Foundation | Capability | Done |  |  |  |  | 12 | 8 | 12 | 14.4 | 4 | 100% | 0 | 0 | Story Points
TAP-105169 | 268 | 7 |  | 06.01.28.00.00.00.00.00 |  | TAP-105169 | [TAP-105169] ¦ [Cyber][Platformers][V&V] V&V for Ethercat CM and expiration notifications | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-108089 | 269 | 11 |  | 06.01.29.00.00.00.00.00 |  | TAP-108089 | [TAP-108089] ¦ [V4][RC1][V&V] TRR Project Wide Documents Release | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87421 | 270 | 11 |  | 06.01.30.00.00.00.00.00 |  | TAP-87421 | [TAP-87421] ¦ [V4][RC1][V&V] [Cyber] TRR Deliverables Release - Foundation | Feature | Done |  |  |  |  | 201 | 201 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88385 | 271 | 15 | 11 | 06.01.31.00.00.00.00.00 |  | TAP-88385 | [TAP-88385] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - AdvancedInstruments | Feature | Groomed |  |  |  |  | 245.75 | 1.5 | 1 hr | 1 hr | 244.25 | 0.6104% | 0 | 0 | Story Points
TAP-87426 | 272 | 15 | 11 | 06.01.32.00.00.00.00.00 |  | TAP-87426 | [TAP-87426] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - Foundation | Feature | Groomed |  |  |  |  | 202 | 19 | 1 hr | 1 hr | 183 | 9.406% | 0 | 0 | Story Points
TAP-113928 | 273 | 15 |  | 06.01.33.00.00.00.00.00 |  | TAP-113928 | [TAP-113928] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - CoreInstruments | Feature | Groomed |  |  |  |  | 61 | 1 | 1 hr | 1 hr | 60 | 1.639% | 0 | 0 | Story Points
TAP-88621 | 274 | 11 |  | 06.01.34.00.00.00.00.00 |  | TAP-88621 | [TAP-88621] ¦ [V4][RC1][V&V] [Cyber] TRR Deliverables Release - AdvancedInstruments | Feature | Done |  |  |  |  | 152 | 152 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-125121 | 275 | 13 |  | 06.01.35.00.00.00.00.00 |  | TAP-125121 | [TAP-125121] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - AdvancedInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125126 | 276 | 15 |  | 06.01.36.00.00.00.00.00 |  | TAP-125126 | [TAP-125126] ¦ [V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - AdvancedInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125127 | 277 | 15 |  | 06.01.38.00.00.00.00.00 |  | TAP-125127 | [TAP-125127] ¦ [V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - CoreInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125125 | 278 | 15 |  | 06.01.39.00.00.00.00.00 |  | TAP-125125 | [TAP-125125] ¦ 🚩[V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - Foundation | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125120 | 279 | 13 |  | 06.01.41.00.00.00.00.00 |  | TAP-125120 | [TAP-125120] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - Foundation | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125122 | 280 | 13 |  | 06.01.42.00.00.00.00.00 |  | TAP-125122 | [TAP-125122] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - CoreInstr | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-125122 | 281 | 280 |  | 06.02.00.00.00.00.00.00 |  | LOT-6109 | [TAP-125122] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - CoreInstr | FX | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-115485 | 282 | 9 |  | 06.02.01.01.00.00.00.00 |  | TAP-115485 | [TAP-115485] ¦ [Cyber] Tracking Documentation For Design Planning | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-115498 | 283 | 9 |  | 06.02.01.02.00.00.00.00 |  | TAP-115498 | [TAP-115498] ¦ [Cyber] Tracking Documentation For Design Inputs | Feature | PROPOSED |  |  |  |  | 4.5 | 4.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115511 | 284 | 17 |  | 06.02.01.03.00.00.00.00 |  | TAP-115511 | [TAP-115511] ¦ [V4.0][RC1][Cyber][Project Wide V&V Reports] Tracking Documentation For Design Verification | Feature | Accepted |  |  |  |  | 28 | 3 | 1 hr | 1 hr | 25 | 10.71% | 0 | 0 | Story Points
TAP-115768 | 285 | 9 | 193 | 06.02.01.04.00.00.00.00 |  | TAP-115768 | [TAP-115768] ¦ [V4][RC1] BRR Deliverables Release - AdvancedInstruments | Feature | Done |  |  |  |  | 45 | 45 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115637 | 286 | 9 |  | 06.02.01.05.00.00.00.00 |  | TAP-115637 | [TAP-115637] ¦ [Cyber] Tracking Documentation For Design Outputs | Feature | PROPOSED |  |  |  |  | 2 | 1 | 1 hr | 1 hr | 1 | 50% | 0 | 0 | Story Points
TAP-115695 | 287 | 11 |  | 06.02.01.06.00.00.00.00 |  | TAP-115695 | [TAP-115695] ¦ [Cyber] Tracking Documentation For Design Outputs - EIN V4.0 Unit Verification Checklists | Feature | Done |  |  |  |  | 37 | 37 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115718 | 288 | 11 |  | 06.02.01.07.00.00.00.00 |  | TAP-115718 | [TAP-115718] ¦ [Cyber] Tracking Documentation For EIN V4.0 Readiness Reviews BOM | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115722 | 289 | 9 |  | 06.02.01.08.00.00.00.00 |  | TAP-115722 | [TAP-115722] ¦ [Cyber] Tracking Documentation For EIN V4.0 SW Design Reviews | Feature | Done |  |  |  |  | 41 | 41 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-115735 | 290 | 9 |  | 06.02.01.09.00.00.00.00 |  | TAP-115735 | [TAP-115735] ¦ [Cyber] Tracking Documentation For EIN V4.0 Product Risk Management | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-115742 | 291 | 9 |  | 06.02.01.10.00.00.00.00 |  | TAP-115742 | [TAP-115742] ¦ [Cyber] Tracking Documentation For Design Transfer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-115742 | 292 | 291 |  | 06.02.02.00.00.00.00.00 |  | LOT-6179 | [TAP-115742] ¦ [Cyber] Tracking Documentation For Design Transfer | FX | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-105163 | 293 | 5 |  | 06.02.02.01.00.00.00.00 |  | TAP-105163 | [TAP-105163] ¦ [v4.0][Cyber] NPS development for Advanced Instruments scrum teams in PI13 | Feature | Done |  |  |  |  | 40 | 40 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105163 | 294 | 293 |  | 06.02.02.01.03.00.00.00 | TAP-105163 | TAP-83349 | [TAP-105163] ¦ [v4.0][Cyber] NPS development for Advanced Instruments scrum teams in PI13 | Capability | Done |  |  |  |  | 41 | 40 | 41 | 49.2 | 1 | 100% | 0 | 0 | Story Points
TAP-96204 | 295 | 1 |  | 06.02.02.02.00.00.00.00 |  | TAP-96204 | [TAP-96204] ¦ [v4.0][Cyber] NPS development for I2E, Jacobians, Scrumbledores, TeamBD, Pixel Poets - PI12 | Feature | Done |  |  |  |  | 27 | 27 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83444 | 296 | 7 |  | 06.02.02.03.00.00.00.00 |  | TAP-83444 | [TAP-83444] ¦ [v4.0] [Cyber] NPS Validation for BRR/TRR - PI11 | Feature | Done |  |  |  |  | 1 | 1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105160 | 297 | 7 |  | 06.02.02.04.00.00.00.00 |  | TAP-105160 | [TAP-105160] ¦ [Cyber][V4.0] NPS development for Triple tea - PI13 | Feature | Done |  |  |  |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96051 | 298 | 7 |  | 06.02.02.05.00.00.00.00 |  | TAP-96051 | [TAP-96051] ¦ [Cyber][V4.0] NPS development for Inbetweeners - PI12 | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105534 | 299 | 7 |  | 06.02.02.06.00.00.00.00 |  | TAP-105534 | [TAP-105534] ¦ [Cyber][V4.0] NPS development for FRED team | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94624 | 300 | 1 |  | 06.02.02.07.00.00.00.00 |  | TAP-94624 | [TAP-94624] ¦ [Cyber][V4.0] NPS development for CLASSY team - PI12 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105053 | 301 | 7 |  | 06.02.02.08.00.00.00.00 |  | TAP-105053 | [TAP-105053] ¦ [Cyber][V4.0] NPS development for Inbetweeners - PI13 | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-90275 | 302 | 11 |  | 06.02.02.09.00.00.00.00 |  | TAP-90275 | [TAP-90275] ¦ [v4.0] NPS validation for BRR/TRR - RC1 | Feature | Done |  |  |  |  | 361 | 361 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96135 | 303 | 7 |  | 06.02.02.10.00.00.00.00 |  | TAP-96135 | [TAP-96135] ¦ [Cyber][V4.0] NPS development for Tools Rules team - PI12 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96135 | 304 | 303 |  | 06.02.03.00.00.00.00.00 |  | LOT-6108 | [TAP-96135] ¦ [Cyber][V4.0] NPS development for Tools Rules team - PI12 | FX | Open |  |  |  |  | 5 | 5 | 5 | 6 | 0 | 100% | 0 | 0 | Story Points
TAP-116341 | 305 | 15 |  | 06.02.03.01.00.00.00.00 |  | TAP-116341 | [TAP-116341] ¦ [SOUP][v4.0][Cyber] [IW] SOUP SQR Agile Release | Feature | Accepted |  |  |  |  | 100 | 0 | 1 hr | 1 hr | 100 | 0% | 0 | 0 | Story Points
TAP-123260 | 306 | 17 |  | 06.02.03.02.00.00.00.00 |  | TAP-123260 | [TAP-123260] ¦ [SOUP][V4.0][DVR] SOUP Verification activities | Feature | Accepted |  |  |  |  | 13 | 0 | 1 hr | 1 hr | 13 | 0% | 0 | 0 | Story Points
TAP-116345 | 307 | 15 |  | 06.02.03.03.00.00.00.00 |  | TAP-116345 | [TAP-116345] ¦ [V4.0][PI15] SOUP complete analysis - Foundation ART | Feature | Accepted |  |  |  |  | 23 | 3 | 1 hr | 1 hr | 20 | 13.04% | 0 | 0 | Story Points
TAP-96719 | 308 | 17 |  | 06.02.03.04.00.00.00.00 |  | TAP-96719 | [TAP-96719] ¦ [v4.0][Cyber][PI13] SOUP Initial analysis | Feature | Done |  |  |  |  | 140 | 140 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96675 | 309 | 17 |  | 06.02.03.05.00.00.00.00 |  | TAP-96675 | [TAP-96675] ¦ [v4.0][Cyber][PI13] SOUP complete analysis - Foundation ART | Feature | Done |  |  |  |  | 46 | 46 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83010 | 310 | 17 |  | 06.02.03.06.00.00.00.00 |  | TAP-83010 | [TAP-83010] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - Advanced Instruments ART | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95434 | 311 | 17 |  | 06.02.03.07.00.00.00.00 |  | TAP-95434 | [TAP-95434] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - Foundation ART | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106670 | 312 | 17 |  | 06.02.03.08.00.00.00.00 |  | TAP-106670 | [TAP-106670] ¦ [v4.0][Cyber][PI14] SOUP complete analysis - Foundation ART | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95432 | 313 | 17 |  | 06.02.03.09.00.00.00.00 |  | TAP-95432 | [TAP-95432] ¦ [v4.0][Cyber][PI12] SOUP Initial analysis | Feature | Done |  |  |  |  | 101 | 101 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72332 | 314 | 17 |  | 06.02.03.10.00.00.00.00 |  | TAP-72332 | [TAP-72332] ¦ [V4.0][Cyber][PI13] SOUP V&V Tasks | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113388 | 315 | 15 |  | 06.02.03.11.00.00.00.00 |  | TAP-113388 | [TAP-113388] ¦ [V4.0][Cyber][PI14] SOUP V&V Tasks [BRR/TRR] | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113388 | 316 | 315 |  | 06.02.03.12.01.00.00.00 |  | LOT-6294 | [TAP-113388] ¦ [V4.0][Cyber][PI14] SOUP V&V Tasks [BRR/TRR] | Task | Blocked |  |  |  |  | 40 | 21 | 40 | 48 | 19 | 52.5% | 0 | 0 | Story Points
TAP-103997 | 317 | 17 |  | 06.02.03.13.00.00.00.00 |  | TAP-103997 | [TAP-103997] ¦ [v4.0][Cyber][PI13] SOUP complete analysis - Advanced Instruments ART | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97857 | 318 | 17 |  | 06.02.03.14.00.00.00.00 |  | TAP-97857 | [TAP-97857] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - RPE ART | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95435 | 319 | 17 |  | 06.02.03.15.00.00.00.00 |  | TAP-95435 | [TAP-95435] ¦ [v4.0][Cyber][PI13] SOUP SQR Agile Release | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106240 | 320 | 17 |  | 06.02.03.16.00.00.00.00 |  | TAP-106240 | [TAP-106240] ¦ [v4.0][Cyber][PI14] SOUP SQR Agile Release | Feature | Done |  |  |  |  | 65.5 | 65.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106240 | 321 | 320 |  | 06.04.00.00.00.00.00.00 |  | RAS-8678 | [TAP-106240] ¦ [v4.0][Cyber][PI14] SOUP SQR Agile Release | Enhancement | Investigation |  |  |  |  | 129 | 65.5 | 129 | 154.8 | 63.5 | 50.78% | 0 | 0 | Story Points
TAP-106240 | 322 | 320 |  | 06.05.00.00.00.00.00.00 |  | LOT-2066 | [TAP-106240] ¦ [v4.0][Cyber][PI14] SOUP SQR Agile Release | SFX | In progress |  |  |  |  | 129 | 65.5 | 129 | 154.8 | 63.5 | 50.78% | 0 | 0 | Story Points
TAP-106240 | 323 | 320 |  | 06.05.01.00.00.00.00.00 |  | LOT-4751 | [TAP-106240] ¦ [v4.0][Cyber][PI14] SOUP SQR Agile Release | Task | Open | Foundation - Atlas | ATLAS |  |  | 129 | 65.5 | 129 | 154.8 | 63.5 | 50.78% | 0 | 0 | Story Points
TAP-106240 | 324 | 320 |  | 06.05.02.00.00.00.00.00 |  | LOT-5776 | [TAP-106240] ¦ [v4.0][Cyber][PI14] SOUP SQR Agile Release | FX | Closed |  |  |  |  | 129 | 65.5 | 129 | 154.8 | 63.5 | 50.78% | 0 | 0 | Story Points
TAP-2133 | 325 | 332, 1 |  | 06.05.02.01.01.00.00.00 |  | TAP-2133 | [TAP-2133] ¦ [Cyber] Prototype Chain of Trust boot up for QNX x86 platform on 7.1 OS | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12357 | 326 | 332, 1 |  | 06.05.02.01.02.00.00.00 |  | TAP-12357 | [TAP-12357] ¦ [Cyber] Implement chain of trust on QNX x86 platform | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-17155 | 327 | 332, 1 |  | 06.05.02.01.03.00.00.00 |  | TAP-17155 | [TAP-17155] ¦ [Cyber] SPIKE Investigate needs for Unique/Non-Unique BIOS passwords on each system | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12358 | 328 | 332, 1 |  | 06.05.02.01.04.00.00.00 |  | TAP-12358 | [TAP-12358] ¦ [Cyber] Implement fallback mechanism for verification failures for QNX x86 | Feature | Done |  |  |  |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12361 | 329 | 332, 1 |  | 06.05.02.01.05.00.00.00 |  | TAP-12361 | [TAP-12361] ¦ [Cyber] Investigate Hard coded secrets in QNX x86 platforms | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2135 | 330 | 332, 1 |  | 06.05.02.01.06.00.00.00 |  | TAP-2135 | [TAP-2135] ¦ [Cyber] Hardware failure handling enhancement for QNX 7.1 x86 OS | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12360 | 331 | 332, 1 |  | 06.05.02.01.07.00.00.00 |  | TAP-12360 | [TAP-12360] ¦ [Cyber] Implement TPM usage in QNX x86 | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58662 | 332 | 333, 1 | 325, 326, 327, 328, 329, 330, 331 | 06.05.02.01.08.00.00.00 |  | TAP-58662 | [TAP-58662] ¦ [Cyber] Micro-Penetration Test by 3rd Party for QNX x86 Secure Boot | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13749 | 333 | 1 | 332 | 06.05.02.01.09.00.00.00 |  | TAP-13749 | [TAP-13749] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 - chain of trust | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13749 | 334 | 333 |  | 06.05.02.01.10.00.00.00 |  | LOT-5320 | [TAP-13749] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 - chain of trust | Task | Done |  |  |  |  | 13 | 8 | 13 | 15.6 | 5 | 100% | 0 | 0 | Story Points
TAP-70864 | 335 | 1 |  | 06.05.02.01.11.00.00.00 |  | TAP-70864 | [TAP-70864] ¦ [Cyber] Operations and Service support planning for bsp changes | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72558 | 336 | 3 |  | 06.05.02.01.12.00.00.00 |  | TAP-72558 | [TAP-72558] ¦ [Boosters][Cyber] Integrate WolfSSH in Data Access and miscellaneous logging improvement | Feature | Done |  |  |  |  | 59 | 59 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13750 | 337 | 9 |  | 06.05.02.01.13.00.00.00 |  | TAP-13750 | [TAP-13750] ¦ [Cyber] Finish the QA, V&V tasks related to QNX x86 OS for Cyber release | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13750 | 338 | 337 |  | 06.05.02.02.00.00.00.00 |  | LOT-5425 | [TAP-13750] ¦ [Cyber] Finish the QA, V&V tasks related to QNX x86 OS for Cyber release | FX | Closed |  |  |  |  | 10 | 7 | 10 | 12 | 3 | 70% | 0 | 0 | Story Points
TAP-2134 | 339 | 341, 1 |  | 06.05.02.02.01.00.00.00 |  | TAP-2134 | [TAP-2134] ¦ [Cyber] Implement secure storage for QNX x86 7.1 OS platform | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2134 | 340 | 339 |  | 06.05.02.02.01.01.00.00 | TAP-2134 | TAP-34122 | [TAP-2134] ¦ [Cyber] Implement secure storage for QNX x86 7.1 OS platform | Issue | Done | Foundation - Atlas | ATLAS |  |  | 32 | 32 | 32 | 38.4 | 0 | 100% | 0 | 0 | Story Points
TAP-58909 | 341 | 342, 1 | 339 | 06.05.02.02.02.00.00.00 |  | TAP-58909 | [TAP-58909] ¦ [Cyber] Micro-Penetration Test by 3rd Party for QNX x86 Data Protection | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58919 | 342 | 1 | 341 | 06.05.02.02.03.00.00.00 |  | TAP-58919 | [TAP-58919] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 Data Protections | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58919 | 343 | 342 |  | 06.05.02.03.00.00.00.00 |  | LOT-5779 | [TAP-58919] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 Data Protections | FX | Closed |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-4982 | 344 | 1 |  | 06.05.02.03.01.00.00.00 |  | TAP-4982 | [TAP-4982] ¦ [Cyber] Least privilege mechanism on QNX x86 node | Feature | Done |  |  |  |  | 194 | 194 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58840 | 345 | 346, 1 |  | 06.05.02.03.02.00.00.00 |  | TAP-58840 | [TAP-58840] ¦ [Cyber] QNX x86: WolfSSH Integration | Feature | Done |  |  |  |  | 73 | 73 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12359 | 346 | 1 | 345 | 06.05.02.03.03.00.00.00 |  | TAP-12359 | [TAP-12359] ¦ [Cyber] Implement OS Hardening of QNX x86 nodes (SSH, SFTP, USB, etc) | Feature | Done |  |  |  |  | 137.5 | 137.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70489 | 347 | 348, 5 |  | 06.05.02.03.04.00.00.00 |  | TAP-70489 | [TAP-70489] ¦ [Cyber] Micro-Penetration Test Readiness and Support by 3rd Party for QNX x86 OS Hardening | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70490 | 348 | 5 | 347 | 06.05.02.03.05.00.00.00 |  | TAP-70490 | [TAP-70490] ¦ 🚩[Cyber] Implement Fixes for Findings in Micro Penetration Testing for QNX x86 OS Hardening | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70490 | 349 | 348 |  | 06.05.03.00.00.00.00.00 |  | LOT-5778 | [TAP-70490] ¦ 🚩[Cyber] Implement Fixes for Findings in Micro Penetration Testing for QNX x86 OS Hardening | FX | Closed |  |  |  |  | 4 | 4 | 4 | 4.8 | 0 | 100% | 0 | 0 | Story Points
TAP-1005 | 350 | 356, 1 |  | 06.05.03.01.01.00.00.00 |  | TAP-1005 | [TAP-1005] ¦ [Cyber] Create obfuscated secret key during run time | Feature | Done |  |  |  |  | 90 | 90 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1182 | 351 | 356, 1 |  | 06.05.03.01.02.00.00.00 |  | TAP-1182 | [TAP-1182] ¦ [Cyber] [Enabler] Define road map for Zynq Authenticated boot | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-7423 | 352 | 356, 1 |  | 06.05.03.01.03.00.00.00 |  | TAP-7423 | [TAP-7423] ¦ [Cyber] Establish Chain of trust on zynq platform | Feature | Done |  |  |  |  | 167.5 | 167.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12362 | 353 | 356, 1 |  | 06.05.03.01.04.00.00.00 |  | TAP-12362 | [TAP-12362] ¦ [Cyber] Implement fallback for qnx armv7 nodes | Feature | Done |  |  |  |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83759 | 354 | 1, 356 |  | 06.05.03.01.05.00.00.00 |  | TAP-83759 | [TAP-83759] ¦ [Critical][Cyber][V4.0] Investigate and Fix Backup OS | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83759 | 355 | 354 |  | 06.05.03.01.05.01.00.00 | TAP-83759 | TAP-88550 | [TAP-83759] ¦ [Critical][Cyber][V4.0] Investigate and Fix Backup OS | Issue | Done | Foundation - Atlas | ATLAS |  |  | 8 | 8 | 8 | 9.6 | 0 | 100% | 0 | 0 | Story Points
TAP-58663 | 356 | 358, 1 | 350, 351, 352, 353, 362, 354 | 06.05.03.01.06.00.00.00 |  | TAP-58663 | [TAP-58663] ¦ [Cyber] Micro-Penetration Readiness and Test by 3rd Party for QNX Zynq | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58663 | 357 | 356 |  | 06.05.03.01.06.01.00.00 | TAP-58663 | TAP-101748 | [TAP-58663] ¦ [Cyber] Micro-Penetration Readiness and Test by 3rd Party for QNX Zynq | Issue | Done | Foundation - Atlas | ATLAS |  |  | 9 | 9 | 9 | 10.8 | 0 | 100% | 0 | 0 | Story Points
TAP-13752 | 358 | 5 | 356 | 06.05.03.01.07.00.00.00 |  | TAP-13752 | [TAP-13752] ¦ [Cyber] Implementation penetration testing finding for QNX armv7 nodes | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13752 | 359 | 358 |  | 06.05.03.01.07.01.00.00 | TAP-13752 | TAP-105375 | [TAP-13752] ¦ [Cyber] Implementation penetration testing finding for QNX armv7 nodes | Issue | Done | Foundation - Atlas | ATLAS |  |  | 11 | 11 | 11 | 13.2 | 0 | 100% | 0 | 0 | Story Points
TAP-13753 | 360 | 9 |  | 06.05.03.01.08.00.00.00 |  | TAP-13753 | [TAP-13753] ¦ [Cyber] Finish cyber analysis, V&V, and QA related tasks for QNX Armv7 OS | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13753 | 361 | 360 |  | 06.05.03.02.00.00.00.00 |  | LOT-5426 | [TAP-13753] ¦ [Cyber] Finish cyber analysis, V&V, and QA related tasks for QNX Armv7 OS | FX | Closed |  |  |  |  | 2 | 2 | 2 | 2.4 | 0 | 100% | 0 | 0 | Story Points
TAP-13751 | 362 | 356, 1 |  | 06.05.03.02.01.00.00.00 |  | TAP-13751 | [TAP-13751] ¦ [Cyber] Implement secure key storage for QNX armv7 | Feature | Done |  |  |  |  | 82 | 82 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13751 | 363 | 362 |  | 06.05.03.02.01.14.00.00 | TAP-13751 | TAP-55174 | [TAP-13751] ¦ [Cyber] Implement secure key storage for QNX armv7 | Issue | Done | Foundation - Bart | BART |  |  | 155 | 82 | 155 | 186 | 73 | 100% | 0 | 0 | Story Points
TAP-13751 | 364 | 362 |  | 06.05.03.03.00.00.00.00 |  | LOT-5780 | [TAP-13751] ¦ [Cyber] Implement secure key storage for QNX armv7 | FX | Closed |  |  |  |  | 158 | 82 | 158 | 189.6 | 76 | 51.9% | 0 | 0 | Story Points
TAP-84498 | 365 | 1 |  | 06.05.03.03.01.00.00.00 |  | TAP-84498 | [TAP-84498] ¦ [Cyber]User Separation for Zynq nodes | Feature | Done |  |  |  |  | 33.5 | 33.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105165 | 366 | 1 |  | 06.05.03.03.02.00.00.00 |  | TAP-105165 | [TAP-105165] ¦ Improvements for Finalizing Cyber Development | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-76492 | 367 | 1 |  | 06.05.03.03.03.00.00.00 |  | TAP-76492 | [TAP-76492] ¦ [Cyber] Increase Security of Key exchange | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-7424 | 368 | 1 |  | 06.05.03.03.04.00.00.00 |  | TAP-7424 | [TAP-7424] ¦ [Cyber] QNX7 Arm OS hardening | Feature | Done |  |  |  |  | 133.5 | 133.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-7424 | 369 | 368 |  | 06.05.03.03.04.45.00.00 | TAP-7424 | TAP-35633 | [TAP-7424] ¦ [Cyber] QNX7 Arm OS hardening | Issue | Done | Foundation - Fred | FRED |  |  | 259 | 133.5 | 259 | 310.8 | 125.5 | 100% | 0 | 0 | Story Points
TAP-58839 | 370 | 1 |  | 06.05.03.03.05.00.00.00 |  | TAP-58839 | [TAP-58839] ¦ [Cyber] QNX Zynq: WolfSSH Integration | Feature | Done |  |  |  |  | 25.5 | 25.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-73977 | 371 | 3 |  | 06.05.03.03.06.00.00.00 |  | TAP-73977 | [TAP-73977] ¦ [Cyber] PL key obfuscation and storage hardening | Feature | Done |  |  |  |  | 89.5 | 89.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-73977 | 372 | 371 |  | 06.05.04.00.00.00.00.00 |  | LOT-5777 | [TAP-73977] ¦ [Cyber] PL key obfuscation and storage hardening | FX | Closed |  |  |  |  | 176 | 89.5 | 176 | 211.2 | 86.5 | 50.85% | 0 | 0 | Story Points
TAP-1743 | 373 | 382, 1 |  | 06.05.04.01.01.00.00.00 |  | TAP-1743 | [TAP-1743] ¦ [Cyber] Certificate(s) to install as PK onWindows systems | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1744 | 374 | 382, 1 |  | 06.05.04.01.02.00.00.00 |  | TAP-1744 | [TAP-1744] ¦ [Cyber] 3 versions of UEFI firmware for testing Windows secure boot | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2423 | 375 | 382, 1 |  | 06.05.04.01.03.00.00.00 |  | TAP-2423 | [TAP-2423] ¦ [Cyber] Update 3rd party libraries and components on Windows Bamboo agents for v2.0 | Feature | Done |  |  |  |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2423 | 376 | 375 |  | 06.05.04.01.03.06.00.00 | TAP-2423 | EIN-14365 | [TAP-2423] ¦ [Cyber] Update 3rd party libraries and components on Windows Bamboo agents for v2.0 | Development Task | Closed |  |  |  |  | 5 | 3 | 5 | 6 | 2 | 60% | 0 | 0 | Story Points
TAP-1745 | 377 | 382, 1 |  | 06.05.04.01.04.00.00.00 |  | TAP-1745 | [TAP-1745] ¦ [Cyber] Kontron specific instructions on updating the TPM certificate stores | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1742 | 378 | 382, 1 |  | 06.05.04.01.05.00.00.00 |  | TAP-1742 | [TAP-1742] ¦ [Cyber] Define Strategy and Architecture for Windows Cyber Security | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12365 | 379 | 382, 1 |  | 06.05.04.01.06.00.00.00 |  | TAP-12365 | [TAP-12365] ¦ [Cyber] Implement chain of trust on the Windows Platform | Feature | Done |  |  |  |  | 52.5 | 52.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-63713 | 380 | 1, 382 |  | 06.05.04.01.07.00.00.00 |  | TAP-63713 | [TAP-63713] ¦ [Cyber] Implement Authentic Code Execution on the Windows Platform | Feature | Done |  |  |  |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-63713 | 381 | 380 |  | 06.05.04.01.07.01.00.00 | TAP-63713 | TAP-91613 | [TAP-63713] ¦ [Cyber] Implement Authentic Code Execution on the Windows Platform | Issue | Done | Foundation - Atlas | ATLAS |  |  | 35 | 35 | 35 | 42 | 0 | 100% | 0 | 0 | Story Points
TAP-58664 | 382 | 383, 5 | 373, 374, 375, 377, 378, 379, 380 | 06.05.04.01.08.00.00.00 |  | TAP-58664 | [TAP-58664] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Windows x86 | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13756 | 383 | 5 | 382 | 06.05.04.01.09.00.00.00 |  | TAP-13756 | [TAP-13756] ¦ [Cyber] Implement penetration testing findings for Windows OS | Feature | Done |  |  |  |  | 52.5 | 52.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13758 | 384 | 9 |  | 06.05.04.01.10.00.00.00 |  | TAP-13758 | [TAP-13758] ¦ [Cyber] Finish the QA tasks related to Windows for Cyber release | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-13758 | 385 | 384 |  | 06.05.04.02.00.00.00.00 |  | LOT-5427 | [TAP-13758] ¦ [Cyber] Finish the QA tasks related to Windows for Cyber release | FX | Closed |  |  |  |  | 2 | 2 | 2 | 2.4 | 0 | 100% | 0 | 0 | Story Points
TAP-12370 | 386 | 1 |  | 06.05.04.02.01.00.00.00 |  | TAP-12370 | [TAP-12370] ¦ [Cyber] Implement secure storage on windows platform | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12370 | 387 | 386 |  | 06.05.04.03.00.00.00.00 |  | LOT-5781 | [TAP-12370] ¦ [Cyber] Implement secure storage on windows platform | FX | Closed |  |  |  |  | 68 | 36 | 68 | 81.6 | 32 | 52.94% | 0 | 0 | Story Points
TAP-12367 | 388 | 1 |  | 06.05.04.03.01.00.00.00 |  | TAP-12367 | [TAP-12367] ¦ [Cyber] Implement least privilege strategy for the windows platform | Feature | Done |  |  |  |  | 83 | 83 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12368 | 389 | 1 |  | 06.05.04.03.02.00.00.00 |  | TAP-12368 | [TAP-12368] ¦ [Cyber] Windows OS Interface Hardening | Feature | Done |  |  |  |  | 110 | 110 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12369 | 390 | 1 |  | 06.05.04.03.03.00.00.00 |  | TAP-12369 | [TAP-12369] ¦ [Cyber] Investigate hard coded secrets on Windows Platform | Feature | Done |  |  |  |  | 1 | 1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58837 | 391 | 1 |  | 06.05.04.03.04.00.00.00 |  | TAP-58837 | [TAP-58837] ¦ [Cyber] Windows: WolfSSH Integration | Feature | Done |  |  |  |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104858 | 392 | 5 |  | 06.05.04.03.05.00.00.00 |  | TAP-104858 | [TAP-104858] ¦ [Cyber] WinOS Data and network protection | Feature | Done |  |  |  |  | 14.1 | 14.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104858 | 393 | 392 |  | 06.05.05.00.00.00.00.00 |  | LOT-2073 | [TAP-104858] ¦ [Cyber] WinOS Data and network protection | FX | In progress |  |  |  |  | 27.2 | 14.1 | 27.2 | 32.64 | 13.1 | 51.84% | 0 | 0 | Story Points
TAP-76410 | 394 | 404, 1 |  | 06.05.05.01.01.00.00.00 |  | TAP-76410 | [TAP-76410] ¦ [Cyber] Integrate secure EtherCAT into system | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58458 | 395 | 404, 1 |  | 06.05.05.01.02.00.00.00 |  | TAP-58458 | [TAP-58458] ¦ [Cyber] Update Secure Communication Library | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-177 | 396 | 404, 1 |  | 06.05.05.01.03.00.00.00 |  | TAP-177 | [TAP-177] ¦ [Cyber] Design Secure EtherCAT Communication | Feature | Done |  |  |  |  | 66 | 66 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-4936 | 397 | 404, 1 |  | 06.05.05.01.04.00.00.00 |  | TAP-4936 | [TAP-4936] ¦ [Cyber] Implement Secure EtherCAT cyclic communication and cybersecurity framework | Feature | Done |  |  |  |  | 46 | 46 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55077 | 398 | 404, 1 |  | 06.05.05.01.05.00.00.00 |  | TAP-55077 | [TAP-55077] ¦ [Cyber] SPIKE Investigate and Architect the Solution to Authenticate File Over Ethercat Communications Risk: R021 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71075 | 399 | 404, 1 |  | 06.05.05.01.06.00.00.00 |  | TAP-71075 | [TAP-71075] ¦ [Cyber] Implement Authenticated File Over Ethercat Communications | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71074 | 400 | 404, 1 |  | 06.05.05.01.07.00.00.00 |  | TAP-71074 | [TAP-71074] ¦ [v4.0][Cyber] Implement EtherCAT security for the acyclic communication path | Feature | Done |  |  |  |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83828 | 401 | 1 |  | 06.05.05.01.08.00.00.00 |  | TAP-83828 | [TAP-83828] ¦ [Cyber] Ethercat Master updates to support RASA Testers and Manufacturing | Feature | Done |  |  |  |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83633 | 402 | 7 |  | 06.05.05.01.09.00.00.00 |  | TAP-83633 | [TAP-83633] ¦ [V4.0][Cyber][Tech Debt] Complete Test Infrastructure for Secure EtherCAT | Feature | Done |  |  |  |  | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95486 | 403 | 7 |  | 06.05.05.01.10.00.00.00 |  | TAP-95486 | [TAP-95486] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Authentication Tests for FoE and Cyclic | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58669 | 404 | 405, 13 | 397, 399, 396, 398, 400, 395, 394 | 06.05.05.01.11.00.00.00 |  | TAP-58669 | [TAP-58669] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Ethercat/SSL | Feature | Done |  |  |  |  | 5.5 | 5.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58670 | 405 | 13 | 404 | 06.05.05.01.12.00.00.00 |  | TAP-58670 | [TAP-58670] ¦ [Cyber] Correct penetration testing findings for Ethercat/SSL | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106190 | 406 | 7 |  | 06.05.05.01.13.00.00.00 |  | TAP-106190 | [TAP-106190] ¦ 🚩[v4.0][Cyber] EtherCAT SSC<->Master Anti-Replay Tests for Ayclic | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106193 | 407 | 7 |  | 06.05.05.01.14.00.00.00 |  | TAP-106193 | [TAP-106193] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Anti-Replay Tests for FoE | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97725 | 408 | 7 |  | 06.05.05.01.15.00.00.00 |  | TAP-97725 | [TAP-97725] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Authentication Tests for Ayclic | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95051 | 409 | 7 |  | 06.05.05.01.16.00.00.00 |  | TAP-95051 | [TAP-95051] ¦ [v4.0][Sentinel][Cyber] EtherCAT Stability Improvements + Test Fixes | Feature | Done |  |  |  |  | 85 | 85 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95051 | 410 | 409 |  | 06.05.05.02.00.00.00.00 |  | LOT-5345 | [TAP-95051] ¦ [v4.0][Sentinel][Cyber] EtherCAT Stability Improvements + Test Fixes | FX | In progress |  |  |  |  | 157 | 85 | 157 | 188.4 | 72 | 54.14% | 0 | 0 | Story Points
TAP-149 | 411 | 444, 1 |  | 06.05.05.02.01.00.00.00 |  | TAP-149 | [TAP-149] ¦ [Cyber] Secure UDP | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-141 | 412 | 444, 1 |  | 06.05.05.02.02.00.00.00 |  | TAP-141 | [TAP-141] ¦ [Cyber] UDP library new features | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-158 | 413 | 444, 1 |  | 06.05.05.02.03.00.00.00 |  | TAP-158 | [TAP-158] ¦ [Cyber] Secure Communication Library | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-193 | 414 | 444, 1 |  | 06.05.05.02.04.00.00.00 |  | TAP-193 | [TAP-193] ¦ [Cyber] Investigate DDS Domains | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-178 | 415 | 444, 1 |  | 06.05.05.02.05.00.00.00 |  | TAP-178 | [TAP-178] ¦ [Cyber] Communication Library New Interface Phase 1 | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-178 | 416 | 415 |  | 06.05.05.02.05.02.00.00 | TAP-178 | TAP-725 | [TAP-178] ¦ [Cyber] Communication Library New Interface Phase 1 | Sub Task | Done |  |  |  |  | 8 | 8 | 8 | 9.6 | 0 | 100% | 0 | 0 | Story Points
TAP-115 | 417 | 444, 1 |  | 06.05.05.02.06.00.00.00 |  | TAP-115 | [TAP-115] ¦ [Cyber] Communication Middleware Layer Phase 2 | Feature | Done |  |  |  |  | 57 | 57 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-133 | 418 | 444, 1 |  | 06.05.05.02.07.00.00.00 |  | TAP-133 | [TAP-133] ¦ [Cyber] [Spike] DDS Secure Feasibility | Feature | Done |  |  |  |  | 23 | 23 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-125 | 419 | 444, 1 |  | 06.05.05.02.08.00.00.00 |  | TAP-125 | [TAP-125] ¦ [Cyber] Integrate Communication Library Interface in Alarms | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1010 | 420 | 444, 1 |  | 06.05.05.02.09.00.00.00 |  | TAP-1010 | [TAP-1010] ¦ [Cyber] Cleanup usage of DDS Domains | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-25137 | 421 | 444, 1 |  | 06.05.05.02.10.00.00.00 |  | TAP-25137 | [TAP-25137] ¦ [Cyber][Arch]Improve Testability of New Communication Libraries (UDP) | Feature | Done |  |  |  |  | 89 | 89 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55466 | 422 | 444, 1 |  | 06.05.05.02.11.00.00.00 |  | TAP-55466 | [TAP-55466] ¦ [Cyber][Arch]Improve Testability of New Communication Libraries (DDS) (Phase 1) | Feature | Done |  |  |  |  | 43 | 43 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55473 | 423 | 444, 1 |  | 06.05.05.02.12.00.00.00 |  | TAP-55473 | [TAP-55473] ¦ [Cyber] [Arch] [Enabler] [Storm Chasers] Communication library update: head tracking | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55557 | 424 | 444, 1 |  | 06.05.05.02.13.00.00.00 |  | TAP-55557 | [TAP-55557] ¦ [Cyber] [Arch] [Enabler] Supporting integration of new communication library | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55463 | 425 | 444, 1 |  | 06.05.05.02.14.00.00.00 |  | TAP-55463 | [TAP-55463] ¦ [Cyber] [Arch] [Enabler][Fred] Integrate new communication library into ACS communication | Feature | Done |  |  |  |  | 9 | 9 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55464 | 426 | 444, 1 |  | 06.05.05.02.15.00.00.00 |  | TAP-55464 | [TAP-55464] ¦ [Cyber] [Arch] [Enabler] [Boosters] Communication library update: configuration | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71118 | 427 | 444, 1 |  | 06.05.05.02.16.00.00.00 |  | TAP-71118 | [TAP-71118] ¦ [V4.0][Cyber] PI10 New Communication Library Wrapper (Foundation) | Feature | Done |  |  |  |  | 238.5 | 238.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71118 | 428 | 427 |  | 06.05.05.02.16.04.00.00 | TAP-71118 | TAP-74854 | [TAP-71118] ¦ [V4.0][Cyber] PI10 New Communication Library Wrapper (Foundation) | Capability | Done |  |  |  |  | 239.5 | 238.5 | 239.5 | 287.4 | 1 | 100% | 0 | 0 | Story Points
TAP-72563 | 429 | 444, 1 |  | 06.05.05.02.17.00.00.00 |  | TAP-72563 | [TAP-72563] ¦ [V4.0][Cyber]PI10 New Communication Library Wrapper (Instrumentation) | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72563 | 430 | 429 |  | 06.05.05.02.17.04.00.00 | TAP-72563 | TAP-55533 | [TAP-72563] ¦ [V4.0][Cyber]PI10 New Communication Library Wrapper (Instrumentation) | Capability | Done |  |  |  |  | 17 | 16 | 17 | 20.4 | 1 | 100% | 0 | 0 | Story Points
TAP-79110 | 431 | 1 |  | 06.05.05.02.18.00.00.00 |  | TAP-79110 | [TAP-79110] ¦ [V4.0] [Comms] [Cyber] New communication library update and migration (PI12) | Feature | Done |  |  |  |  | 499.5 | 499.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-79110 | 432 | 431 |  | 06.05.05.02.18.16.00.00 | TAP-79110 | TAP-88839 | [TAP-79110] ¦ [V4.0] [Comms] [Cyber] New communication library update and migration (PI12) | Capability | Done |  |  |  |  | 532.5 | 499.5 | 532.5 | 639 | 33 | 100% | 0 | 0 | Story Points
TAP-85853 | 433 | 1 |  | 06.05.05.02.19.00.00.00 |  | TAP-85853 | [TAP-85853] ¦ [Cyber][V4.0] ADV INST Complete migration of subsystem to new communication library | Feature | Done |  |  |  |  | 120 | 120 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85853 | 434 | 433 |  | 06.05.05.02.19.06.00.00 | TAP-85853 | TAP-55475 | [TAP-85853] ¦ [Cyber][V4.0] ADV INST Complete migration of subsystem to new communication library | Capability | Done |  |  |  |  | 125 | 120 | 125 | 150 | 5 | 100% | 0 | 0 | Story Points
TAP-58886 | 435 | 1, 444 |  | 06.05.05.02.20.00.00.00 |  | TAP-58886 | [TAP-58886] ¦ [Comms] [Cyber] Enable secure DDS communication | Feature | Done |  |  |  |  | 42 | 42 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58886 | 436 | 435 |  | 06.05.05.02.20.07.00.00 | TAP-58886 | TAP-86764 | [TAP-58886] ¦ [Comms] [Cyber] Enable secure DDS communication | Issue | Done | Shared Services - Edison | EDISON |  |  | 61 | 42 | 61 | 73.2 | 19 | 100% | 0 | 0 | Story Points
TAP-58886 | 437 | 435 |  | 06.05.05.02.20.08.00.00 | TAP-58886 | TAP-85264 | [TAP-58886] ¦ [Comms] [Cyber] Enable secure DDS communication | Capability | Done |  |  |  |  | 61 | 42 | 61 | 73.2 | 19 | 100% | 0 | 0 | Story Points
TAP-58884 | 438 | 1, 444 |  | 06.05.05.02.21.00.00.00 |  | TAP-58884 | [TAP-58884] ¦ [Comms] [Cyber] Re-Design and Enable secure UDP communication | Feature | Done |  |  |  |  | 47 | 47 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95056 | 439 | 1 |  | 06.05.05.02.22.00.00.00 |  | TAP-95056 | [TAP-95056] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability and Performance Improvement | Feature | Done |  |  |  |  | 85 | 85 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95056 | 440 | 439 |  | 06.05.05.02.22.18.00.00 | TAP-95056 | TAP-103917 | [TAP-95056] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability and Performance Improvement | Issue | Done | Foundation - Horizon | HORIZON |  |  | 159 | 85 | 159 | 190.8 | 74 | 100% | 0 | 0 | Story Points
TAP-95056 | 441 | 439 |  | 06.05.05.02.22.19.00.00 | TAP-95056 | TAP-101885 | [TAP-95056] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability and Performance Improvement | Issue | Done | Shared Services - Power Stormers | POWERSTORMERS |  |  | 159 | 85 | 159 | 190.8 | 74 | 100% | 0 | 0 | Story Points
TAP-7888 | 442 | 3 |  | 06.05.05.02.23.00.00.00 |  | TAP-7888 | [TAP-7888] ¦ [Cyber] Communication Middleware Layer 3 | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88364 | 443 | 5 |  | 06.05.05.02.24.00.00.00 |  | TAP-88364 | [TAP-88364] ¦ [Cyber] [V4.0 RC2] Upgrade RTI DDS to latest patch level Version 6.0.1.35 | Feature | Done |  |  |  |  | 60 | 60 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58672 | 444 | 13 | 429, 427, 411, 412, 413, 414, 415, 417, 418, 419, 420, 421, 422, 423, 424, 425, 426, 435, 438 | 06.05.05.02.25.00.00.00 |  | TAP-58672 | [TAP-58672] ¦ [Cyber] Micro-Penetration Test by 3rd Party for DDS/UDP | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103513 | 445 | 3 |  | 06.05.05.02.26.00.00.00 |  | TAP-103513 | [TAP-103513] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability fixes and performance improvement (PI13) | Feature | Done |  |  |  |  | 66.5 | 66.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105505 | 446 | 5 |  | 06.05.05.02.27.00.00.00 |  | TAP-105505 | [TAP-105505] ¦ [Cyber][Adv Instruments] Miscelleneous communication library update and integration | Feature | Done |  |  |  |  | 39.5 | 39.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105505 | 447 | 446 |  | 06.05.05.02.27.18.00.00 | TAP-105505 | TAP-76374 | [TAP-105505] ¦ [Cyber][Adv Instruments] Miscelleneous communication library update and integration | Capability | Done |  |  |  |  | 73 | 39.5 | 73 | 87.6 | 33.5 | 100% | 0 | 0 | Story Points
TAP-103503 | 448 | 5 |  | 06.05.05.02.28.00.00.00 |  | TAP-103503 | [TAP-103503] ¦ [4.0] [Foundation] Miscellaneous communication library update and integration | Feature | Done |  |  |  |  | 112.5 | 112.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103503 | 449 | 448 |  | 06.05.05.02.28.16.00.00 | TAP-103503 | TAP-108906 | [TAP-103503] ¦ [4.0] [Foundation] Miscellaneous communication library update and integration | Issue | Done | Foundation - Classy 2 | CLASSY2 |  |  | 162.5 | 112.5 | 162.5 | 195 | 50 | 100% | 0 | 0 | Story Points
TAP-87345 | 450 | 5 |  | 06.05.05.02.29.00.00.00 |  | TAP-87345 | [TAP-87345] ¦ [Comms][V4.0][Cyber] Comms Libraries stability fixes and miscelleneous enhancements | Feature | Done |  |  |  |  | 56 | 56 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85431 | 451 | 5 |  | 06.05.05.02.30.00.00.00 |  | TAP-85431 | [TAP-85431] ¦ [V4.0][Cyber][CLASSY] Documentation update for new communication library | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106775 | 452 | 9 |  | 06.05.05.02.31.00.00.00 |  | TAP-106775 | [TAP-106775] ¦ [V4.0][Cyber][CLASY] Documentation update for new communication library (PI14) | Feature | Done |  |  |  |  | 49 | 49 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85792 | 453 | 5 |  | 06.05.05.02.32.00.00.00 |  | TAP-85792 | [TAP-85792] ¦ [V4.0][Cyber] Secure UDP Completion and V&V | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95824 | 454 | 7 |  | 06.05.05.02.33.00.00.00 |  | TAP-95824 | [TAP-95824] ¦ [Cyber][V4.0] Refactor communication data corruption related requirements and tests | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95456 | 455 | 7 |  | 06.05.05.02.34.00.00.00 |  | TAP-95456 | [TAP-95456] ¦ [Cyber][V4.0] Refactor communication data corruption related requirements and tests | Feature | Done |  |  |  |  | 42 | 42 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-95456 | 456 | 455 |  | 06.05.05.03.00.00.00.00 |  | LOT-5355 | [TAP-95456] ¦ [Cyber][V4.0] Refactor communication data corruption related requirements and tests | FX | Closed |  |  |  |  | 70 | 42 | 70 | 84 | 28 | 60% | 0 | 0 | Story Points
TAP-55467 | 457 | 1 |  | 06.05.05.03.01.00.00.00 |  | TAP-55467 | [TAP-55467] ¦ [Cyber] SPIKE Investigate the use on FTP on the Hugo system | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-109370 | 458 | 3 |  | 06.05.05.03.02.00.00.00 |  | TAP-109370 | [TAP-109370] ¦ [Cyber] Upgrade the wolfssh to 1.4.16 | Feature | Done |  |  |  |  | 14 | 14 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-109370 | 459 | 458 |  | 06.05.05.04.00.00.00.00 |  | LOT-5354 | [TAP-109370] ¦ [Cyber] Upgrade the wolfssh to 1.4.16 | FX | Closed |  |  |  |  | 22 | 14 | 22 | 26.4 | 8 | 63.64% | 0 | 0 | Story Points
TAP-58613 | 460 | 1 |  | 06.05.05.04.01.00.00.00 |  | TAP-58613 | [TAP-58613] ¦ [Cyber] [SPIKE] Review acceptability of current password strategy for UPS and Network Switch Risk: R024 | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58613 | 461 | 460 |  | 06.05.06.00.00.00.00.00 |  | LOT-2077 | [TAP-58613] ¦ [Cyber] [SPIKE] Review acceptability of current password strategy for UPS and Network Switch Risk: R024 | FX | In progress |  |  |  |  | 10 | 10 | 10 | 12 | 0 | 100% | 0 | 0 | Story Points
TAP-6961 | 462 | 479, 1 |  | 06.05.06.01.00.00.00.00 |  | TAP-6961 | [TAP-6961] ¦ [Cyber] EMBSW - Instrument Authentication Infrastructure | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-1306 | 463 | 479, 1 |  | 06.05.06.02.00.00.00.00 |  | TAP-1306 | [TAP-1306] ¦ [Cyber] EMBSW - Instrument Identification Refactor | Feature | Done |  |  |  |  | 36 | 36 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-34960 | 464 | 479, 1 |  | 06.05.06.03.00.00.00.00 |  | TAP-34960 | [TAP-34960] ¦ [Cyber] Instrument Authentication Prototype and De-risking | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-25616 | 465 | 479, 1 |  | 06.05.06.04.00.00.00.00 |  | TAP-25616 | [TAP-25616] ¦ [Cyber] Instrument Authentication Infrastructure Workshop | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-159 | 466 | 479, 1 |  | 06.05.06.05.00.00.00.00 |  | TAP-159 | [TAP-159] ¦ [Cyber] Instrument Hardware Authentication Implementation | Feature | Done |  |  |  |  | 37 | 37 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55120 | 467 | 479, 1 |  | 06.05.06.06.00.00.00.00 |  | TAP-55120 | [TAP-55120] ¦ [Cyber] Instrument Authentication Design Inputs | Feature | Done |  |  |  |  | 4.5 | 4.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-54936 | 468 | 479, 1 |  | 06.05.06.07.00.00.00.00 |  | TAP-54936 | [TAP-54936] ¦ [Cyber] Instrument Authentication Hash Computation | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55141 | 469 | 479, 1 |  | 06.05.06.08.00.00.00.00 |  | TAP-55141 | [TAP-55141] ¦ [Cyber] SPIKE Instrument Authentication Secret Storage and Build Integration | Feature | Done |  |  |  |  | 25 | 25 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-28790 | 470 | 479, 1 |  | 06.05.06.09.00.00.00.00 |  | TAP-28790 | [TAP-28790] ¦ [Cyber] Instrument Memory Authentication Implementation | Feature | Done |  |  |  |  | 49.5 | 49.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58335 | 471 | 479, 1 |  | 06.05.06.10.00.00.00.00 |  | TAP-58335 | [TAP-58335] ¦ [Cyber] Instrument Authentication Error Handling (Data Validation) | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58439 | 472 | 1, 479 |  | 06.05.06.11.00.00.00.00 |  | TAP-58439 | [TAP-58439] ¦ [Cyber] Instrument Authentication SHA256 PL Acceleration | Feature | Done |  |  |  |  | 93 | 93 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71057 | 473 | 1, 479 |  | 06.05.06.12.00.00.00.00 |  | TAP-71057 | [TAP-71057] ¦ [Cyber] Merge staging/instrument-authentication into develop | Feature | Done |  |  |  |  | 14.5 | 14.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-69072 | 474 | 1, 479 |  | 06.05.06.13.00.00.00.00 |  | TAP-69072 | [TAP-69072] ¦ [Cyber] Instrument Authentication Failure System Response | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55121 | 475 | 1, 479 |  | 06.05.06.14.00.00.00.00 |  | TAP-55121 | [TAP-55121] ¦ [Cyber] Instrument Authentication Penetration Testing Readiness | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71054 | 476 | 1, 479 |  | 06.05.06.15.00.00.00.00 |  | TAP-71054 | [TAP-71054] ¦ [Cyber] Instrument Authentication Error Handling (Data Authentication) | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58349 | 477 | 1 |  | 06.05.06.16.00.00.00.00 |  | TAP-58349 | [TAP-58349] ¦ [Cyber] Instrument Authentication Legacy Device Support | Feature | Done |  |  |  |  | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82020 | 478 | 1 |  | 06.05.06.17.00.00.00.00 |  | TAP-82020 | [TAP-82020] ¦ [Cyber] Production Plan for Instrument Authentication | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58647 | 479 | 480, 1 | 462, 463, 464, 465, 466, 467, 468, 469, 470, 471, 472, 473, 474, 475, 476 | 06.05.06.18.00.00.00.00 |  | TAP-58647 | [TAP-58647] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Basic Instrument Authentication | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58656 | 480 | 3 | 479 | 06.05.06.19.00.00.00.00 |  | TAP-58656 | [TAP-58656] ¦ [Cyber][Sentinel][Inst Auth] Implement Fixes for Findings in Micro Penetration Testing | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58337 | 481 | 7 |  | 06.05.06.20.00.00.00.00 |  | TAP-58337 | [TAP-58337] ¦ [Cyber] Instrument Authentication V&V Testing | Feature | Done |  |  |  |  | 11 | 11 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-58350 | 482 | 9 |  | 06.05.06.21.00.00.00.00 |  | TAP-58350 | [TAP-58350] ¦ [Cyber] Instrument Authentication Documents and Critical Design Review | Feature | Done |  |  |  |  | 7.5 | 7.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83346 | 483 | 13 |  | 06.05.06.22.00.00.00.00 |  | TAP-83346 | [TAP-83346] ¦ [Cyber] Switch to Production Key Secrets | Feature | Accepted |  |  |  |  | 6 | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-83346 | 484 | 483 |  | 06.05.07.00.00.00.00.00 |  | LOT-2071 | [TAP-83346] ¦ [Cyber] Switch to Production Key Secrets | FX | Closed |  |  |  |  | 9 | 0 | 9 | 10.8 | 9 | 0% | 0 | 0 | Story Points
TAP-1758 | 485 | 1 |  | 06.05.07.01.00.00.00.00 |  | TAP-1758 | [TAP-1758] ¦ [Cyber] Define and implement USB whitelisting policies across all nodes | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12356 | 486 | 3 |  | 06.05.07.02.00.00.00.00 |  | TAP-12356 | [TAP-12356] ¦ [Cyber] Update network switch configuration for cyber release | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12356 | 487 | 486 |  | 06.05.08.00.00.00.00.00 |  | LOT-2070 | [TAP-12356] ¦ [Cyber] Update network switch configuration for cyber release | FX | In progress |  |  |  |  | 18 | 12 | 18 | 21.6 | 6 | 66.67% | 0 | 0 | Story Points
TAP-113853 | 488 | 7 |  | 06.05.08.01.00.00.00.00 |  | TAP-113853 | [TAP-113853] ¦ [Cyber] Continued NPS work for Product Security Release (PI 14) | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70569 | 489 | 1 |  | 06.05.08.02.00.00.00.00 |  | TAP-70569 | [TAP-70569] ¦ [Cyber] Formalize use of WolfSSH in ESAT and Data Access | Feature | Done |  |  |  |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70569 | 490 | 489 |  | 06.05.08.02.05.00.00.00 | TAP-70569 | TAP-96476 | [TAP-70569] ¦ [Cyber] Formalize use of WolfSSH in ESAT and Data Access | Issue | Done | Foundation - Boosters | BOOSTERS |  |  | 39 | 32 | 39 | 46.8 | 7 | 100% | 0 | 0 | Story Points
TAP-25610 | 491 | 1 |  | 06.05.08.03.00.00.00.00 |  | TAP-25610 | [TAP-25610] ¦ [Cyber] Prepare ESAT-2 for Cybersecurity Release | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104060 | 492 | 5 |  | 06.05.08.04.00.00.00.00 |  | TAP-104060 | [TAP-104060] ¦ [V2.1] [Cyber] Certificate Installation Usability Improvements For Contract Manufacturer | Feature | Done |  |  |  |  | 58 | 58 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104060 | 493 | 492 |  | 06.05.08.04.01.00.00.00 | TAP-104060 | TAP-104888 | [TAP-104060] ¦ [V2.1] [Cyber] Certificate Installation Usability Improvements For Contract Manufacturer | Issue | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS |  |  | 58 | 58 | 58 | 69.6 | 0 | 100% | 0 | 0 | Story Points
TAP-104830 | 494 | 5 |  | 06.05.08.05.00.00.00.00 |  | TAP-104830 | [TAP-104830] ¦ [Cyber] ESAT v2 - Migrating from v1 to v2 | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104832 | 495 | 5 |  | 06.05.08.06.00.00.00.00 |  | TAP-104832 | [TAP-104832] ¦ [Cyber] ESAT v2 Continued Stabilization of ESAT v2 (PI13) | Feature | Done |  |  |  |  | 144 | 144 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104832 | 496 | 495 |  | 06.05.08.06.10.00.00.00 | TAP-104832 | TAP-108907 | [TAP-104832] ¦ [Cyber] ESAT v2 Continued Stabilization of ESAT v2 (PI13) | Issue | Done | Foundation - Atlas | ATLAS |  |  | 183 | 144 | 183 | 219.6 | 39 | 100% | 0 | 0 | Story Points
TAP-83501 | 497 | 17 |  | 06.05.08.07.00.00.00.00 |  | TAP-83501 | [TAP-83501] ¦ [v4.0] [Cyber] Update ESAT scripts to work with product security release | Feature | Done |  |  |  |  | 71 | 71 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103080 | 498 | 13 |  | 06.05.08.08.00.00.00.00 |  | TAP-103080 | [TAP-103080] ¦ [Cyber] ESAT v2, Support Field Service Use of CyberArk | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94851 | 499 | 3 |  | 06.05.08.09.00.00.00.00 |  | TAP-94851 | [TAP-94851] ¦ [Cyber] Continued ESAT v2 support, PI 12 | Feature | Done |  |  |  |  | 100 | 100 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-94851 | 500 | 499 |  | 06.05.08.09.34.00.00.00 | TAP-94851 | TAP-83403 | [TAP-94851] ¦ [Cyber] Continued ESAT v2 support, PI 12 | Sub Task | Done |  |  |  |  | 194 | 100 | 194 | 232.8 | 94 | 100% | 0 | 0 | Story Points
TAP-42212 | 501 | 13 |  | 06.05.08.10.00.00.00.00 |  | TAP-42212 | [TAP-42212] ¦ [Cyber] Penetration test ESAT and its interfaces for the Cybersecurity Release | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-42213 | 502 | 13 |  | 06.05.08.11.00.00.00.00 |  | TAP-42213 | [TAP-42213] ¦ [Cyber] Patch vulnerabilities discovered in penetration test report for cybersecurity ESAT solution | Feature | Accepted |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-42213 | 503 | 502 |  | 06.05.09.00.00.00.00.00 |  | LOT-2069 | [TAP-42213] ¦ [Cyber] Patch vulnerabilities discovered in penetration test report for cybersecurity ESAT solution | FX | In progress |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-943 | 504 | 1 |  | 06.05.09.01.01.00.00.00 |  | TAP-943 | [TAP-943] ¦ [Cyber] System Configuration Enforcement | Feature | Done |  |  |  |  | 85 | 85 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12344 | 505 | 1 |  | 06.05.09.01.02.00.00.00 |  | TAP-12344 | [TAP-12344] ¦ [KontronEOL] [Cyber] Finalize Configuration Enforcement on all nodes | Feature | Done |  |  |  |  | 90 | 90 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-14178 | 506 | 1 |  | 06.05.09.01.03.00.00.00 |  | TAP-14178 | [TAP-14178] ¦ [Cyber] Add non-clinical element to GUI software | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83682 | 507 | 1 |  | 06.05.09.01.04.00.00.00 |  | TAP-83682 | [TAP-83682] ¦ [Cyber][v4.0] Finalize the non-clinical overlay for the GUI | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12345 | 508 | 5 |  | 06.05.09.01.05.00.00.00 |  | TAP-12345 | [TAP-12345] ¦ [V4.0][Cyber] Implement User Notification when running non clinical software | Feature | Done |  |  |  |  | 63 | 63 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12345 | 509 | 508 |  | 06.05.09.01.05.02.00.00 | TAP-12345 | TAP-104815 | [TAP-12345] ¦ [V4.0][Cyber] Implement User Notification when running non clinical software | Issue | Done | Foundation - Classy 2 | CLASSY2 |  |  | 63 | 63 | 63 | 75.6 | 0 | 100% | 0 | 0 | Story Points
TAP-12345 | 510 | 508 |  | 06.05.09.02.00.00.00.00 |  | LOT-5348 | [TAP-12345] ¦ [V4.0][Cyber] Implement User Notification when running non clinical software | FX | Closed |  |  |  |  | 115 | 63 | 115 | 138 | 52 | 54.78% | 0 | 0 | Story Points
TAP-115130 | 511 | 9 |  | 06.05.09.02.01.00.00.00 |  | TAP-115130 | [TAP-115130] ¦ [V4.0] [BRR] [Cyber] Platformers Documentation Updates | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-113289 | 512 | 5 |  | 06.05.09.02.02.00.00.00 |  | TAP-113289 | [TAP-113289] ¦ [V4.0][Cyber] Certificate Cleanup and Stability | Feature | Done |  |  |  |  | 57 | 57 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-72510 | 513 | 1 |  | 06.05.09.02.03.00.00.00 |  | TAP-72510 | [TAP-72510] ¦ [Cyber][V4] Certificate manager design changes | Feature | Done |  |  |  |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-17759 | 514 | 1 |  | 06.05.09.02.04.00.00.00 |  | TAP-17759 | [TAP-17759] ¦ [Cyber] Ethercat certificate manager | Feature | Done |  |  |  |  | 28 | 28 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-12346 | 515 | 3 |  | 06.05.09.02.05.00.00.00 |  | TAP-12346 | [TAP-12346] ¦ [Cyber] Implement certificate expiration notifications | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-56916 | 516 | 3 |  | 06.05.09.02.06.00.00.00 |  | TAP-56916 | [TAP-56916] ¦ [V4] [Cyber] Support for unified Medtronic hugo_id certificate | Feature | Done |  |  |  |  | 76 | 76 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-56916 | 517 | 516 |  | 06.05.09.03.00.00.00.00 |  | LOT-5349 | [TAP-56916] ¦ [V4] [Cyber] Support for unified Medtronic hugo_id certificate | FX | In progress |  |  |  |  | 130 | 76 | 130 | 156 | 54 | 58.46% | 0 | 0 | Story Points
TAP-168 | 518 | 1 |  | 06.05.09.03.01.00.00.00 |  | TAP-168 | [TAP-168] ¦ [Cyber] Deployment manager Interface Updates | Feature | Done |  |  |  |  | 78 | 78 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-168 | 519 | 518 |  | 06.05.09.03.01.06.00.00 | TAP-168 | TAP-3064 | [TAP-168] ¦ [Cyber] Deployment manager Interface Updates | Sub Task | Done |  |  |  |  | 83 | 78 | 83 | 99.6 | 5 | 100% | 0 | 0 | Story Points
TAP-168 | 520 | 518 |  | 06.05.09.03.01.13.00.00 | TAP-168 | TAP-1651 | [TAP-168] ¦ [Cyber] Deployment manager Interface Updates | Capability | Done |  |  |  |  | 83 | 78 | 83 | 99.6 | 5 | 100% | 0 | 0 | Story Points
TAP-168 | 521 | 518 |  | 06.05.09.03.01.14.00.00 | TAP-168 | EIN-20944 | [TAP-168] ¦ [Cyber] Deployment manager Interface Updates | Enhancement | Closed |  |  |  |  | 83 | 78 | 83 | 99.6 | 5 | 93.98% | 0 | 0 | Story Points
TAP-8250 | 522 | 1 |  | 06.05.09.03.02.00.00.00 |  | TAP-8250 | [TAP-8250] ¦ [KontronEOL][Cyber][DM] Peripheral deployment support | Feature | Done |  |  |  |  | 184 | 184 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-8250 | 523 | 522 |  | 06.05.09.03.02.52.00.00 | TAP-8250 | TAP-16776 | [TAP-8250] ¦ [KontronEOL][Cyber][DM] Peripheral deployment support | Sub Task | Done |  |  |  |  | 368 | 184 | 368 | 441.6 | 184 | 100% | 0 | 0 | Story Points
TAP-1753 | 524 | 1 |  | 06.05.09.03.03.00.00.00 |  | TAP-1753 | [TAP-1753] ¦ [Cyber] Define strategy and implement secure deployment of packages | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-8252 | 525 | 3 |  | 06.05.09.03.04.00.00.00 |  | TAP-8252 | [TAP-8252] ¦ [Cyber] Support for peripheral deployment | Feature | Done |  |  |  |  | 107 | 107 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-42170 | 526 | 3 |  | 06.05.09.03.05.00.00.00 |  | TAP-42170 | [TAP-42170] ¦ [V4.0][Cyber] Secure Deployment | Feature | Done |  |  |  |  | 111.5 | 111.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-59531 | 527 | 3 |  | 06.05.09.03.06.00.00.00 |  | TAP-59531 | [TAP-59531] ¦ [Cyber] Deployment Support for QNX arm | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-108253 | 528 | 5 |  | 06.05.09.03.07.00.00.00 |  | TAP-108253 | [TAP-108253] ¦ [Cyber] Release Build Testing with Engineering Keys | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-108253 | 529 | 528 |  | 06.05.09.04.00.00.00.00 |  | LOT-5350 | [TAP-108253] ¦ [Cyber] Release Build Testing with Engineering Keys | FX | In progress |  |  |  |  | 40 | 21 | 40 | 48 | 19 | 52.5% | 0 | 0 | Story Points
TAP-68 | 530 | 1 |  | 06.05.09.04.01.00.00.00 |  | TAP-68 | [TAP-68] ¦ [KontronEOL] [ICG] [Cyber] v2 / QNX 7.1 Build Environment Support - Part 2 | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2578 | 531 | 1 |  | 06.05.09.04.02.00.00.00 |  | TAP-2578 | [TAP-2578] ¦ [ICG] [Cyber] Signing system for Einstein Phase 1 | Feature | Done |  |  |  |  | 6 | 6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-2578 | 532 | 531 |  | 06.05.09.04.02.01.00.00 | TAP-2578 | TAP-2831 | [TAP-2578] ¦ [ICG] [Cyber] Signing system for Einstein Phase 1 | Sub Task | Done |  |  |  |  | 6 | 6 | 6 | 7.2 | 0 | 100% | 0 | 0 | Story Points
TAP-8581 | 533 | 1 |  | 06.05.09.04.03.00.00.00 |  | TAP-8581 | [TAP-8581] ¦ [ICG] [Cyber] Certificate Management (UEFI) and Secure Boot Detection | Feature | Done |  |  |  |  | 31 | 31 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-20257 | 534 | 1 |  | 06.05.09.04.04.00.00.00 |  | TAP-20257 | [TAP-20257] ¦ [Cyber] Security enhancement for binary production and CI infrastructure | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-55053 | 535 | 1 |  | 06.05.09.04.05.00.00.00 |  | TAP-55053 | [TAP-55053] ¦ [Cyber] SPIKE Investigate and Detail the Product Security Impacts to Test and Resolutions Risk: R019 - Foundation | Feature | Done |  |  |  |  | 43 | 43 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-71880 | 536 | 1 |  | 06.05.09.04.06.00.00.00 |  | TAP-71880 | [TAP-71880] ¦ [Cyber][SPIKE] Investigate and Detail the SSH update in SW V&V - Instrumentation | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-53454 | 537 | 1 |  | 06.05.09.04.07.00.00.00 |  | TAP-53454 | [TAP-53454] ¦ [Cyber] Centralize engineering key for Windows/Zynq | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-53456 | 538 | 3 |  | 06.05.09.04.08.00.00.00 |  | TAP-53456 | [TAP-53456] ¦ [Cyber] Production signing infrastructure setup | Feature | Done |  |  |  |  | 37 | 37 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-96136 | 539 | 3 |  | 06.05.09.04.09.00.00.00 |  | TAP-96136 | [TAP-96136] ¦ [Cyber][IDP][V4.0] Build Infrastructure Signing | Feature | Done |  |  |  |  | 22 | 22 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-28462 | 540 | 5 |  | 06.05.09.04.10.00.00.00 |  | TAP-28462 | [TAP-28462] ¦ [Cyber] Provide Production Signing | Feature | Done |  |  |  |  | 80 | 80 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84668 | 541 | 13 |  | 06.05.09.04.11.00.00.00 |  | TAP-84668 | [TAP-84668] ¦ [Cyber] Support for Product variants for Project Sentinel | Feature | Done |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84668 | 542 | 541 |  | 06.05.10.00.00.00.00.00 |  | LOT-6033 | [TAP-84668] ¦ [Cyber] Support for Product variants for Project Sentinel | FX | In progress |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-83453 | 543 | 1 |  | 06.05.10.01.00.00.00.00 |  | TAP-83453 | [TAP-83453] ¦ [Cyber] Allow front port network connection in Operable state | Feature | Done |  |  |  |  | 21 | 21 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84353 | 544 | 1 |  | 06.05.10.02.00.00.00.00 |  | TAP-84353 | [TAP-84353] ¦ [Cyber] BSP armv7 updates to support Manufacturing/Field Service | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84354 | 545 | 3 |  | 06.05.10.03.00.00.00.00 |  | TAP-84354 | [TAP-84354] ¦ [Cyber] Windows BSP updates to support Manufacturing | Feature | Done |  |  |  |  | 16.1 | 16.1 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84352 | 546 | 3 |  | 06.05.10.04.00.00.00.00 |  | TAP-84352 | [TAP-84352] ¦ [Cyber] Certificate Bootstrap mode | Feature | Done |  |  |  |  | 43 | 43 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84351 | 547 | 3 |  | 06.05.10.05.00.00.00.00 |  | TAP-84351 | [TAP-84351] ¦ [Cyber] BSP x86 updates to support Manufacturing/Field Support | Feature | Done |  |  |  |  | 41 | 41 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84384 | 548 | 5 |  | 06.05.10.06.00.00.00.00 |  | TAP-84384 | [TAP-84384] ¦ [Cyber] FRU replacement application for updating ORTI switch and ups configuration | Feature | Done |  |  |  |  | 77.6 | 77.6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84357 | 549 | 13 |  | 06.05.10.07.00.00.00.00 |  | TAP-84357 | [TAP-84357] ¦ [Cyber] Tool for installing certificates on FRU/ HLA Programming | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Story Points
TAP-82906 | 550 | 13 |  | 06.05.10.08.00.00.00.00 |  | TAP-82906 | [TAP-82906] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 2 (Development and Testing) - PI13 | Feature | Done |  |  |  |  | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84376 | 551 | 13 | 3 | 06.05.10.09.00.00.00.00 |  | TAP-84376 | [TAP-84376] ¦ [Cyber] Dry Run of FRU replacements for US launch | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84366 | 552 | 13 |  | 06.05.10.10.00.00.00.00 |  | TAP-84366 | [TAP-84366] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 1(Initial Development and Investigation) | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-103615 | 553 | 13 |  | 06.05.10.11.00.00.00.00 |  | TAP-103615 | [TAP-103615] ¦ [Cyber] Briefcase Method Prototyping | Feature | Done |  |  |  |  | 17 | 17 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105519 | 554 | 13 | 3 | 06.05.10.12.00.00.00.00 |  | TAP-105519 | [TAP-105519] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 2 (Development and Testing) - PI14 | Feature | Done |  |  |  |  | 56.5 | 56.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-104008 | 555 | 19 |  | 06.05.10.13.00.00.00.00 |  | TAP-104008 | [TAP-104008] ¦ [Cyber] 4.0 IDU Manufacturing Updates | Feature | In progress |  |  |  |  | 6 | 2 | 1 hr | 1 hr | 4 | 33.33% | 0 | 0 | Story Points
TAP-85190 | 556 | 19 |  | 06.05.10.14.00.00.00.00 |  | TAP-85190 | [TAP-85190] ¦ [Cyber] Transfer of Misc. integration tools to PLXS | Feature | Accepted |  |  |  |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | 0 | 0 | Story Points
TAP-84497 | 557 | 19 |  | 06.05.10.15.00.00.00.00 |  | TAP-84497 | [TAP-84497] ¦ [Cyber] Manufacturing SRA BSP to support rasa and idu testers | Feature | Done |  |  |  |  | 33 | 33 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84358 | 558 | 19 |  | 06.05.10.16.00.00.00.00 |  | TAP-84358 | [TAP-84358] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 1 - PI12 (before validation) | Feature | Done |  |  |  |  | 19 | 19 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84360 | 559 | 19 |  | 06.05.10.17.00.00.00.00 |  | TAP-84360 | [TAP-84360] ¦ [Cyber] Base Programming Station OS updates | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84363 | 560 | 19 |  | 06.05.10.18.00.00.00.00 |  | TAP-84363 | [TAP-84363] ¦ [Cyber] SC/iSIM Programming Station Updates for Manufacturing | Feature | Accepted |  |  |  |  | 27 | 0 | 1 hr | 1 hr | 27 | 0% | 0 | 0 | Story Points
TAP-84361 | 561 | 19 |  | 06.05.10.19.00.00.00.00 |  | TAP-84361 | [TAP-84361] ¦ [Cyber] Tower Programming Station Updates for Manufacturing | Feature | In progress |  |  |  |  | 10.5 | 5 | 1 hr | 1 hr | 5.5 | 47.62% | 0 | 0 | Story Points
TAP-84362 | 562 | 19 |  | 06.05.10.20.00.00.00.00 |  | TAP-84362 | [TAP-84362] ¦ [Cyber] Cart Programming Station Updates for Manufacturing | Feature | Groomed |  |  |  |  | 15 | 0 | 1 hr | 1 hr | 15 | 0% | 0 | 0 | Story Points
TAP-84367 | 563 | 19 |  | 06.05.10.21.00.00.00.00 |  | TAP-84367 | [TAP-84367] ¦ [Cyber] Dry Run of SC Functional Tests at Manufacturing | Feature | Accepted |  |  |  |  | 6 | 0 | 1 hr | 1 hr | 6 | 0% | 0 | 0 | Story Points
TAP-83129 | 564 | 19 |  | 06.05.10.22.00.00.00.00 |  | TAP-83129 | [TAP-83129] ¦ [Cyber] Investigate password programming functions | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-81647 | 565 | 19 |  | 06.05.10.23.00.00.00.00 |  | TAP-81647 | [TAP-81647] ¦ [Cyber] Create Manufacturing BSP for cart/tpsc/fse to support FCT | Feature | Done |  |  |  |  | 61 | 61 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97718 | 566 | 19 |  | 06.05.10.24.00.00.00.00 |  | TAP-97718 | [TAP-97718] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - commanders - PI13 | Feature | Done |  |  |  |  | 5 | 5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88670 | 567 | 19 |  | 06.05.10.25.00.00.00.00 |  | TAP-88670 | [TAP-88670] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - SRA installation | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88672 | 568 | 19 |  | 06.05.10.26.00.00.00.00 |  | TAP-88672 | [TAP-88672] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - commanders - PI12 | Feature | Done |  |  |  |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88676 | 569 | 19 |  | 06.05.10.27.00.00.00.00 |  | TAP-88676 | [TAP-88676] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Communication | Feature | Done |  |  |  |  | 2 | 2 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-88673 | 570 | 19 |  | 06.05.10.28.00.00.00.00 |  | TAP-88673 | [TAP-88673] ¦ [Cyber] FCT35 Cage, Mech, FRU - deployment | Feature | In progress |  |  |  |  | 87.5 | 39 | 1 hr | 1 hr | 48.5 | 44.57% | 0 | 0 | Story Points
TAP-88679 | 571 | 19 |  | 06.05.10.29.00.00.00.00 |  | TAP-88679 | [TAP-88679] ¦ [Cyber] FCT35 Cage, Mech, FRU - LabView/Windows application | Feature | Accepted |  |  |  |  | 21 | 0 | 1 hr | 1 hr | 21 | 0% | 0 | 0 | Story Points
TAP-88681 | 572 | 19 |  | 06.05.10.30.00.00.00.00 |  | TAP-88681 | [TAP-88681] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Full Testing | Feature | Accepted |  |  |  |  | 50 | 0 | 1 hr | 1 hr | 50 | 0% | 0 | 0 | Story Points
TAP-83134 | 573 | 19 |  | 06.05.10.31.00.00.00.00 |  | TAP-83134 | [TAP-83134] ¦ [Cyber] Investigate feasiblity of CyberArk REST API Integration | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-83144 | 574 | 19 |  | 06.05.10.32.00.00.00.00 |  | TAP-83144 | [TAP-83144] ¦ [Cyber] Investigate feasibility of CyberArk agent based Integration | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-84364 | 575 | 19 |  | 06.05.10.33.00.00.00.00 |  | TAP-84364 | [TAP-84364] ¦ [Cyber] Tower FRU Programming Station Updates | Feature | Accepted |  |  |  |  | 17 | 0 | 1 hr | 1 hr | 17 | 0% | 0 | 0 | Story Points
TAP-84365 | 576 | 19 |  | 06.05.10.34.00.00.00.00 |  | TAP-84365 | [TAP-84365] ¦ [Cyber] SC FRU Programming Station Updates | Feature | Accepted |  |  |  |  | 2 | 0 | 1 hr | 1 hr | 2 | 0% | 0 | 0 | Story Points
TAP-97710 | 577 | 19 |  | 06.05.10.35.00.00.00.00 |  | TAP-97710 | [TAP-97710] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 1 - PI13 (before validation) | Feature | Done |  |  |  |  | 31.5 | 31.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-126486 | 578 | 19 |  | 06.05.10.36.00.00.00.00 |  | TAP-126486 | [TAP-126486] ¦ [Cyber] 4.0 IDU Manufacturing Deployment Updates PI16 | Feature | PROPOSED |  |  |  |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | 0 | 0 | Story Points
TAP-126416 | 579 | 19 |  | 06.05.10.37.00.00.00.00 |  | TAP-126416 | [TAP-126416] ¦ [Cyber] FCT35 Cage, Mech, FRU - LabView/Windows application (PI16) | Feature | PROPOSED |  |  |  |  | 17 | 0 | 1 hr | 1 hr | 17 | 0% | 0 | 0 | Story Points
TAP-88671 | 580 | 21 |  | 06.05.10.38.00.00.00.00 |  | TAP-88671 | [TAP-88671] ¦ [Cyber] Programming Computers Final Release and Validation | Feature | Accepted |  |  |  |  | 62 | 0 | 1 hr | 1 hr | 62 | 0% | 0 | 0 | Story Points
TAP-85233 | 581 | 21 |  | 06.05.10.39.00.00.00.00 |  | TAP-85233 | [TAP-85233] ¦ [Cyber] Manufacturing Integration of 4.0 | Feature | Accepted |  |  |  |  | 50 | 0 | 1 hr | 1 hr | 50 | 0% | 0 | 0 | Story Points
TAP-85206 | 582 | 21 |  | 06.05.10.40.00.00.00.00 |  | TAP-85206 | [TAP-85206] ¦ [Cyber] SW4.0 SW BOM Creation (for PLXS) | Feature | Accepted |  |  |  |  | 30 | 0 | 1 hr | 1 hr | 30 | 0% | 0 | 0 | Story Points
TAP-88682 | 583 | 21 |  | 06.05.10.41.00.00.00.00 |  | TAP-88682 | [TAP-88682] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Work Instructions and TRS updates | Feature | Accepted |  |  |  |  | 47 | 0 | 1 hr | 1 hr | 47 | 0% | 0 | 0 | Story Points
TAP-88684 | 584 | 21 |  | 06.05.10.42.00.00.00.00 |  | TAP-88684 | [TAP-88684] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Validation Support | Feature | Accepted |  |  |  |  | 70 | 0 | 1 hr | 1 hr | 70 | 0% | 0 | 0 | Story Points
TAP-84377 | 585 | 21 |  | 06.05.10.43.00.00.00.00 |  | TAP-84377 | [TAP-84377] ¦ [Cyber] IT infrastructure setup at Plexus to support certificate management | Feature | Accepted |  |  |  |  | 10 | 0 | 1 hr | 1 hr | 10 | 0% | 0 | 0 | Story Points
TAP-83152 | 586 | 21 |  | 06.05.10.44.00.00.00.00 |  | TAP-83152 | [TAP-83152] ¦ [Cyber] Manufacturing Integration of Unique Password Programming | Feature | Accepted |  |  |  |  | 25 | 0 | 1 hr | 1 hr | 25 | 0% | 0 | 0 | Story Points
TAP-125288 | 587 | 23 |  | 06.05.10.45.00.00.00.00 |  | TAP-125288 | [TAP-125288] ¦ [Cyber] Finalize US Launch Work Instructions | Feature | In progress |  |  |  |  | 27 | 6 | 1 hr | 1 hr | 21 | 22.22% | 0 | 0 | Story Points
TAP-85224 | 588 | 23 |  | 06.05.10.46.00.00.00.00 |  | TAP-85224 | [TAP-85224] ¦ [Cyber] Field Service Tools NPS Validation Support | Feature | In progress |  |  |  |  | 49 | 0 | 1 hr | 1 hr | 49 | 0% | 0 | 0 | Story Points
TAP-87779 | 589 | 23 |  | 06.05.10.47.00.00.00.00 |  | TAP-87779 | [TAP-87779] ¦ [Cyber] HLA Upgrade Support for Project Sentinel Phase 3(Implementation and Validation) | Feature | In progress |  |  |  |  | 61 | 11 | 1 hr | 1 hr | 50 | 18.03% | 0 | 0 | Story Points
TAP-118514 | 590 | 21 |  | 06.05.10.48.00.00.00.00 |  | TAP-118514 | [TAP-118514] ¦ [Cyber] Finalize and Validate service procedures for OUS cyber launch. | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-118512 | 591 | 21 |  | 06.05.10.49.00.00.00.00 |  | TAP-118512 | [TAP-118512] ¦ [Cyber] Developing Service Procedures for use after Plexus Transfer | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-118513 | 592 | 21 |  | 06.05.10.50.00.00.00.00 |  | TAP-118513 | [TAP-118513] ¦ [Cyber] Developing HLA Field Upgrade Procedures for Service use | Feature | PROPOSED |  |  |  |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | 0 | 0 | Story Points
TAP-118513 | 593 | 592 |  | 06.05.11.00.00.00.00.00 |  | LOT-6123 | [TAP-118513] ¦ [Cyber] Developing HLA Field Upgrade Procedures for Service use | FX | In progress |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | Story Points
TAP-105489 | 594 | 1 |  | 06.05.11.01.00.00.00.00 |  | TAP-105489 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Feature | Done |  |  |  |  | 37.7 | 37.7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-105489 | 595 | 594 |  | 06.05.11.01.01.00.00.00 | TAP-105489 | TAP-101285 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Issue | Done | Advanced Instruments - TeamBD | TEAMBD |  |  | 37.7 | 37.7 | 37.7 | 45.24 | 0 | 100% | 0 | 0 | Story Points
TAP-105489 | 596 | 594 |  | 06.05.11.01.02.00.00.00 | TAP-105489 | TAP-107992 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Issue | Done | Foundation | FOUNDATION |  |  | 37.7 | 37.7 | 37.7 | 45.24 | 0 | 100% | 0 | 0 | Story Points
TAP-105489 | 597 | 594 |  | 06.05.11.01.14.00.00.00 | TAP-105489 | TAP-102482 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Issue | Done | Foundation - Classy 1 | CLASSY1 |  |  | 49.4 | 37.7 | 49.4 | 59.28 | 11.7 | 100% | 0 | 0 | Story Points
TAP-105489 | 598 | 594 |  | 06.05.11.01.17.00.00.00 | TAP-105489 | TAP-107837 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Issue | Done | Shared Services | SHAREDSERVICES |  |  | 57.4 | 37.7 | 57.4 | 68.88 | 19.7 | 100% | 0 | 0 | Story Points
TAP-105489 | 599 | 594 |  | 06.05.11.01.18.00.00.00 | TAP-105489 | TAP-107010 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Issue | Done | Shared Services - Seamless | SEAMLESS |  |  | 57.4 | 37.7 | 57.4 | 68.88 | 19.7 | 100% | 0 | 0 | Story Points
TAP-96772 | 600 | 1 |  | 06.05.11.02.00.00.00.00 |  | TAP-96772 | [TAP-96772] ¦ Support collapse of staging/cyber to develop | Feature | Done |  |  |  |  | 114 | 114 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106940 | 601 | 3 |  | 06.05.11.03.00.00.00.00 |  | TAP-106940 | [TAP-106940] ¦ [Cyber] Miscellaneous EC2 Blockers | Feature | Done |  |  |  |  | 73.6 | 73.6 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106940 | 602 | 601 |  | 06.05.11.03.04.00.00.00 | TAP-106940 | TAP-108003 | [TAP-106940] ¦ [Cyber] Miscellaneous EC2 Blockers | Issue | Done | Foundation - Atlas | ATLAS |  |  | 79.6 | 73.6 | 79.6 | 95.52 | 6 | 100% | 0 | 0 | Story Points
TAP-106940 | 603 | 601 |  | 06.05.11.03.14.00.00.00 | TAP-106940 | TAP-107144 | [TAP-106940] ¦ [Cyber] Miscellaneous EC2 Blockers | Issue | Done | Foundation - Classy 2 | CLASSY2 |  |  | 97.6 | 73.6 | 97.6 | 117.12 | 24 | 100% | 0 | 0 | Story Points
TAP-106940 | 604 | 601 |  | 06.05.11.03.16.00.00.00 | TAP-106940 | TAP-104939 | [TAP-106940] ¦ [Cyber] Miscellaneous EC2 Blockers | Issue | Done | Foundation - Fred | FRED |  |  | 105.6 | 73.6 | 105.6 | 126.72 | 32 | 100% | 0 | 0 | Story Points
TAP-106940 | 605 | 601 |  | 06.05.11.03.32.00.00.00 | TAP-106940 | TAP-110498 | [TAP-106940] ¦ [Cyber] Miscellaneous EC2 Blockers | Issue | Done | Released Product Engineering - Drushti | DRUSHTI |  |  | 124.6 | 73.6 | 124.6 | 149.52 | 51 | 100% | 0 | 0 | Story Points
TAP-105164 | 606 | 3 |  | 06.05.11.04.00.00.00.00 |  | TAP-105164 | [TAP-105164] ¦ [Cyber] Daily integration stability Issue | Feature | Done |  |  |  |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-86114 | 607 | 5 |  | 06.05.11.05.00.00.00.00 |  | TAP-86114 | [TAP-86114] ¦ [Cyber] System Performance Analysis with cyber security features | Feature | Done |  |  |  |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106957 | 608 | 5 |  | 06.05.11.06.00.00.00.00 |  | TAP-106957 | [TAP-106957] ¦ [Cyber] Miscellaneous EC3 Blockers | Feature | Done |  |  |  |  | 102.5 | 102.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106957 | 609 | 608 |  | 06.05.11.06.01.00.00.00 | TAP-106957 | TAP-113363 | [TAP-106957] ¦ [Cyber] Miscellaneous EC3 Blockers | Issue | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES |  |  | 102.5 | 102.5 | 102.5 | 123 | 0 | 100% | 0 | 0 | Story Points
TAP-106957 | 610 | 608 |  | 06.05.11.06.31.00.00.00 | TAP-106957 | TAP-117571 | [TAP-106957] ¦ [Cyber] Miscellaneous EC3 Blockers | Issue | Done | Foundation - Platformers | PLATFORMERS |  |  | 154 | 102.5 | 154 | 184.8 | 51.5 | 100% | 0 | 0 | Story Points
TAP-106957 | 611 | 608 |  | 06.05.11.06.33.00.00.00 | TAP-106957 | TAP-115012 | [TAP-106957] ¦ [Cyber] Miscellaneous EC3 Blockers | Issue | Done | Foundation - Visual | VISUAL |  |  | 154 | 102.5 | 154 | 184.8 | 51.5 | 100% | 0 | 0 | Story Points
TAP-106958 | 612 | 7 |  | 06.05.11.07.00.00.00.00 |  | TAP-106958 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Feature | Done |  |  |  |  | 218.4 | 218.4 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106958 | 613 | 612 |  | 06.05.11.07.02.00.00.00 | TAP-106958 | TAP-110506 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Advanced Instruments - Machete | MACHETE |  |  | 218.4 | 218.4 | 218.4 | 262.08 | 0 | 100% | 0 | 0 | Story Points
TAP-106958 | 614 | 612 |  | 06.05.11.07.05.00.00.00 | TAP-106958 | TAP-104890 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Advanced Instruments - Pixel Poets | PIXELPOETS |  |  | 222.4 | 218.4 | 222.4 | 266.88 | 4 | 100% | 0 | 0 | Story Points
TAP-106958 | 615 | 612 |  | 06.05.11.07.08.00.00.00 | TAP-106958 | TAP-105370 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Core Instruments | COREINSTRUMENTS |  |  | 225.4 | 218.4 | 225.4 | 270.48 | 7 | 100% | 0 | 0 | Story Points
TAP-106958 | 616 | 612 |  | 06.05.11.07.55.00.00.00 | TAP-106958 | TAP-107899 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Foundation - Fred | FRED |  |  | 342.8 | 218.4 | 342.8 | 411.36 | 124.4 | 100% | 0 | 0 | Story Points
TAP-106958 | 617 | 612 |  | 06.05.11.07.60.00.00.00 | TAP-106958 | TAP-52296 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Foundation - Horizon | HORIZON |  |  | 357.8 | 218.4 | 357.8 | 429.36 | 139.4 | 100% | 0 | 0 | Story Points
TAP-106958 | 618 | 612 |  | 06.05.11.07.74.00.00.00 | TAP-106958 | TAP-119434 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 |  |  | 386.8 | 218.4 | 386.8 | 464.16 | 168.4 | 100% | 0 | 0 | Story Points
TAP-106958 | 619 | 612 |  | 06.05.11.07.81.00.00.00 | TAP-106958 | TAP-118588 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Shared Services - Edison | EDISON |  |  | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100% | 0 | 0 | Story Points
TAP-106958 | 620 | 612 |  | 06.05.11.07.82.00.00.00 | TAP-106958 | TAP-118612 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Shared Services - Seamless | SEAMLESS |  |  | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100% | 0 | 0 | Story Points
TAP-106958 | 621 | 612 |  | 06.05.11.07.83.00.00.00 | TAP-106958 | TAP-113464 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Issue | Done | Outside ART | OUTSIDEART |  |  | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100% | 0 | 0 | Story Points
TAP-116625 | 622 | 13 |  | 06.05.11.08.00.00.00.00 |  | TAP-116625 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | Feature | Accepted |  |  |  |  | 31.5 | 6.5 | 1 hr | 1 hr | 25 | 20.63% | 0 | 0 | Story Points
TAP-116625 | 623 | 622 |  | 06.05.12.01.00.00.00.00 |  | RAS-6745 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | Defect | Investigation |  |  |  |  | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26% | 0 | 0 | Story Points
TAP-116625 | 624 | 622 |  | 06.06.00.00.00.00.00.00 |  | LOT-6029 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | SFX | Closed |  |  |  |  | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26% | 0 | 0 | Story Points
TAP-116625 | 625 | 622 |  | 06.06.01.00.00.00.00.00 |  | LOT-6030 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | FX | Closed |  |  |  |  | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26% | 0 | 0 | Story Points
TAP-87152 | 626 | 3 |  | 06.06.01.01.00.00.00.00 |  | TAP-87152 | [TAP-87152] ¦ [V4.0][CTF EOL] Cart LED Driver Updates | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87151 | 627 | 3 |  | 06.06.01.02.00.00.00.00 |  | TAP-87151 | [TAP-87151] ¦ [V4.0][CTF EOL] Requirements and Infrastructure | Feature | Done |  |  |  |  | 29 | 29 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87153 | 628 | 7 |  | 06.06.01.03.00.00.00.00 |  | TAP-87153 | [TAP-87153] ¦ [V4.0][CTF EOL] Integration and Solution Verification for CART | Feature | Done |  |  |  |  | 45 | 45 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82936 | 629 | 3 |  | 06.06.01.04.00.00.00.00 |  | TAP-82936 | [TAP-82936] ¦ [V4.0][CTF EOL] Reliability and maintainability improvements | Feature | Done |  |  |  |  | 17 | 17 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-87184 | 630 | 7 |  | 06.06.01.05.00.00.00.00 |  | TAP-87184 | [TAP-87184] ¦ [V4.0][CTF EOL] Startup Changes and TPSC Application Upgrade for EOL | Feature | Done |  |  |  |  | 31.5 | 31.5 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-92586 | 631 | 3 |  | 06.06.01.06.00.00.00.00 |  | TAP-92586 | [TAP-92586] ¦ [V4.0][CTF EOL] Cart Application Upgrade for EOL | Feature | Done |  |  |  |  | 27 | 27 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-93993 | 632 | 5 |  | 06.06.01.07.00.00.00.00 |  | TAP-93993 | [TAP-93993] ¦ [V4.0][CTF EOL] FSE Application Upgrade for EOL | Feature | Done |  |  |  |  | 12 | 12 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-85050 | 633 | 7 |  | 06.06.01.08.00.00.00.00 |  | TAP-85050 | [TAP-85050] ¦ [V4.0][CTF EOL] Finalize Documentation | Feature | Done |  |  |  |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82998 | 634 | 3 |  | 06.06.01.09.00.00.00.00 |  | TAP-82998 | [TAP-82998] ¦ [V4.0][CTF EOL][Cyber] PL updates to support Embedded EOL Project | Feature | Done |  |  |  |  | 56 | 56 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82937 | 635 | 3 |  | 06.06.01.10.00.00.00.00 |  | TAP-82937 | [TAP-82937] ¦ [V4.0][CTF EOL][Cyber] Manufacturing updates to support Embedded EOL Project | Feature | Done |  |  |  |  | 30 | 30 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-82935 | 636 | 3 |  | 06.06.01.11.00.00.00.00 |  | TAP-82935 | [TAP-82935] ¦ [V4.0][CTF EOL][Cyber] OS Updates to support Embedded EOL project | Feature | Done |  |  |  |  | 7 | 7 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70407 | 637 | 3 |  | 06.06.01.12.00.00.00.00 |  | TAP-70407 | [TAP-70407] ¦ [V4.0][CTF EOL] Cart/TPSC/FSE continuing SW support for new boards spin off | Feature | Done |  |  |  |  | 160 | 160 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-70407 | 638 | 637 |  | 06.06.01.12.01.00.00.00 | TAP-70407 | TAP-71063 | [TAP-70407] ¦ [V4.0][CTF EOL] Cart/TPSC/FSE continuing SW support for new boards spin off | Capability | Done |  |  |  |  | 160 | 160 | 160 | 192 | 0 | 100% | 0 | 0 | Story Points
TAP-87411 | 639 | 3 |  | 06.06.01.13.00.00.00.00 |  | TAP-87411 | [TAP-87411] ¦ [V4.0][CTF EOL][Cyber] Prototype OS Updates to support Embedded EOL project | Feature | Done |  |  |  |  | 26 | 26 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-97620 | 640 | 7 |  | 06.06.01.14.00.00.00.00 |  | TAP-97620 | [TAP-97620] ¦ [V4.0][CTF EOL] Integration and Solution Verification TPSC | Feature | Done |  |  |  |  | 13 | 13 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points
TAP-106789 | 641 | 7 |  | 06.06.01.15.00.00.00.00 |  | TAP-106789 | [TAP-106789] ¦ [V4.0][RC1][CTF EOL] Integration and Solution Verification FSE | Feature | Done |  |  |  |  | 10 | 10 | 1 hr | 1 hr | 0 | 100% | 0 | 0 | Story Points

## Log
DataTimeStamp (?) | Event (?) | Data (?) | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
|  |  | TAP-106789 |  | TAP-95817
|  |  | TAP-106789 |  | TAP-94622
|  |  | TAP-106789 |  | TAP-94625
|  |  | TAP-106789 |  | TAP-96038
|  |  | TAP-106789 |  | TAP-113927
|  |  | TAP-106789 |  | TAP-114710
|  |  | TAP-106789 |  | TAP-113325
|  |  | TAP-106789 |  | TAP-114167
|  |  | TAP-106789 |  | TAP-114725
|  |  | TAP-106789 |  | TAP-113935
|  |  | TAP-106789 |  | TAP-113936
|  |  | TAP-106789 |  | TAP-112047
|  |  | TAP-106789 |  | TAP-125115
|  |  | TAP-106789 |  | TAP-125124
|  |  | TAP-106789 |  | TAP-125261
|  |  | TAP-106789 |  | TAP-125786
|  |  | TAP-106789 |  | TAP-125128
|  |  | TAP-106789 |  | TAP-113857
|  |  | TAP-106789 |  | TAP-88107
|  |  | TAP-106789 |  | TAP-88093
|  |  | TAP-106789 | TAP-84495
|  |  | TAP-106789 |  | TAP-84495

## Summary
Resource Names | Sum FDR
ICONICS | 310
CLASSY2 | 4467
SEAMLESS | 710
CLASSY1 | 4425
STELLARS | 364
PIXELPOETS | 3009
BOOSTERS | 4192
MARVEL | 425
SCRUMBLEDORES | 2165
USERFLOWSW | 1296
JACOBIANS | 1942
ATLAS | 7394
ELECTRON | 35
STORMCHASERS2 | 4045
PLATFORMERS | 6620
DRUSHTI | 1034
MIRAGE | 21
TEAMBD | 3027
HORIZON | 6426
SOUPERTROOPERS | 1091
EDISON | 5146
COREINSTRUMENTS | 1291
I2E | 1893
SUNRISERS | 1297
ASTRANPSVALIDATORS | 528
CROCNROLL | 859
BUGHUNTERS | 535
DOCUMENTOWNERS | 157
ANGLERS | 0
FRED | 6753
CLASSY | 463
STORMCHASERS1 | 3217
PUPPETEERS | 139
REFRACT | 144
TOOLSRULES | 3219
BUILDERS | 1367
ASTRANPSDEVELOPERS | 1016
VISUAL | 4724
STORMCHASERS | 425
TRIPLETEA | 943
BART | 1745
SLEEPWALKERS | 378
CASTLEBLACK | 2078
COSSACKS | 3520
REFLECT | 106
INBETWEENERS | 491
KTBR | 24
SWIFT | 72
FLOWRIDERS | 56.5
HAPPYJAWS | 56.5
NEXUS | 178
INFRAWARRIORS | 189
FUSION | 553
MACHETE | 613
POWERSTORMERS | 514
TECHTITANS | 179
GPT1 | 60
PROBABLYSTILLEMBED | 70
FOUNDATION | 37.7
SHAREDSERVICES | 57.4
OUTSIDEART | 394.8
Total FDR: | 2025391.55