## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete
TAP-79978 | 1 | *3,2 | *758,897,271,841,852,858,885,1165,464 | 03.02.00.00.00.00.00.00 |  | TAP-79978 | [TAP-79978] ¦ [Milestone][V4.0] (EC1) Engineering Candidate 1 | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-85787 | 2 |  | *1 | 03.03.00.00.00.00.00.00 |  | TAP-85787 | [TAP-85787] ¦ [Prochain][V4.0] (EC1) Engineering Candidate 1 Prochain Buffer | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-79979 | 3 | *4,5,1318,1325 | *1235,1179,1257,1287,1166,1262,1253,1,1309,1305,1303,67,1290,1237,281,1207,1070,909,1428,846,1418,396,1111,1061,1492,1495,1499,1469,1471,1478,1483,1506,1497 | 03.04.00.00.00.00.00.00 |  | TAP-79979 | [TAP-79979] ¦ [Milestone][V4.0] (EC2) Engineering Candidate 2 | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-85788 | 4 |  | *3 | 03.05.00.00.00.00.00.00 |  | TAP-85788 | [TAP-85788] ¦ [Prochain][V4.0] (EC2) Engineering Candidate 2 Prochain Buffer | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-79981 | 5 | *6,9 | *1293,887,869,1431,1091,1311,1086,3,926,753,941,1078,1434,133,1197,1195,1191,38,255,1263,384,58,30,128,1074,867,924,1062,1099,1220,1226,1486,110 | 03.06.00.00.00.00.00.00 |  | TAP-79981 | [TAP-79981] ¦ [Milestone][V4.0] (EC3) Engineering Candidate 3 | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-104120 | 6 |  | *5 | 03.07.00.00.00.00.00.00 |  | TAP-104120 | [TAP-104120] ¦ [Prochain][V4.0] (EC3) Engineering Candidate 3 Prochain Buffer | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-104131 | 7 | *8,9 | *473 | 03.08.00.00.00.00.00.00 |  | TAP-104131 | [TAP-104131] ¦ [Milestone][V4.0] (RC1) Release Candidate 1 Finalized Test Code and NPS | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-104132 | 8 |  | *7 | 03.09.00.00.00.00.00.00 |  | TAP-104132 | [TAP-104132] ¦ [Prochain][V4.0] (RC1) Release Candidate 1 Finalized Test Code and NPS Prochain Buffer | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-79982 | 9 | *11,10 | *290,1095,1224 | 03.10.00.00.00.00.00.00 |  | TAP-79982 | [TAP-79982] ¦ [Milestone][V4.0] (BRR) Build Readiness Review | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-104121 | 10 |  | *9 | 03.11.00.00.00.00.00.00 |  | TAP-104121 | [TAP-104121] ¦ [Prochain][V4.0] (BRR) Build Readiness Review Prochain Buffer | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-79983 | 11 | *15,12,668,676 |  | 03.12.00.00.00.00.00.00 |  | TAP-79983 | [TAP-79983] ¦ [Milestone][V4.0] (TRR) Test Readiness Review | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-85789 | 12 |  | *11 | 03.13.00.00.00.00.00.00 |  | TAP-85789 | [TAP-85789] ¦ [Prochain][V4.0] (TRR) Test Readiness Review Prochain Buffer | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-83580 | 13 | *14 | *213 | 03.14.00.00.00.00.00.00 |  | TAP-83580 | [TAP-83580] ¦ [Milestone][V4.0] (RC2) Release Candidate 2 USA Launch Service and Manufacturing Support | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104122 | 14 |  | *13 | 03.15.00.00.00.00.00.00 |  | TAP-104122 | [TAP-104122] ¦ [Prochain][V4.0] (RC2) Release Candidate 2 USA Launch Service and Manufacturing Support Prochain Buffer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-79984 | 15 | *17,16 | *702,703,782,791,817 | 03.16.00.00.00.00.00.00 |  | TAP-79984 | [TAP-79984] ¦ [Milestone][V4.0] V&V Complete | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104178 | 16 |  | *15 | 03.17.00.00.00.00.00.00 |  | TAP-104178 | [TAP-104178] ¦ [Prochain][V4.0] V&V Complete Prochain Buffer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-79985 | 17 | *18 | *15,1201,794,796,823,810,825,819,821,804,813,815,806,715,789 | 03.18.00.00.00.00.00.00 |  | TAP-79985 | [TAP-79985] ¦ [Milestone][V4.0] (DVR) Design Verification Review | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104179 | 18 |  | *17 | 03.19.00.00.00.00.00.00 |  | TAP-104179 | [TAP-104179] ¦ [Prochain][V4.0] (DVR) Design Verification Review Prochain Buffer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104128 | 19 | *20 | *1379,1381 | 03.20.00.00.00.00.00.00 |  | TAP-104128 | [TAP-104128] ¦ [Milestone][V4.0] (RC3-Manufacturing) Release Candidate 3 Full Plexus Transfer Code | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104173 | 20 |  | *19 | 03.21.00.00.00.00.00.00 |  | TAP-104173 | [TAP-104173] ¦ [Prochain][V4.0] (RC3-Manufacturing) Release Candidate 3 Full Plexus Transfer Code Prochain Buffer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-87766 | 21 | *22 | *198,1387,1385,1383,1389,1391,1404,1405,1406 | 03.22.00.00.00.00.00.00 |  | TAP-87766 | [TAP-87766] ¦ [Milestone][V4.0] NPS Manufacturing SW Complete | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104180 | 22 |  | *21 | 03.23.00.00.00.00.00.00 |  | TAP-104180 | [TAP-104180] ¦ [Prochain][V4.0] NPS Manufacturing SW Complete Prochain Buffer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-83590 | 23 | *24 | *1397 | 03.24.00.00.00.00.00.00 |  | TAP-83590 | [TAP-83590] ¦ [Milestone][V4.0] NPS Service Software | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104181 | 24 |  | *23 | 03.25.00.00.00.00.00.00 |  | TAP-104181 | [TAP-104181] ¦ [Prochain][V4.0] NPS Service Software Prochain Buffer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-86327 | 25 | *1 |  | 04.01.01.00.00.00.00.00 |  | TAP-86327 | [TAP-86327] ¦ (RAS-11338) Log Event and notify user when no LLM is detected on ACA | Feature | Done |  |  | Parent Task | User Stories | 25 | 25 | 1 hr | 1 hr | 0 | 100%
TAP-86327_ICONICS | 26 | *25 |  | 04.01.01.01.00.00.00.00 | TAP-86327 | TAP-67832 | [TAP-86327_ICONICS] ¦ [RAS-8541] Add sqlite message when no LLM detected | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 25 | 25 | 25 | 30 | 0 | 100%
TAP-86327_CLASSY2 | 27 | *25 |  | 04.01.01.07.00.00.00.00 | TAP-86327 | TAP-86844 | [TAP-86327_CLASSY2] ¦ PI11 S1 KT on Jama Pull to KTBR team from Classy | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 36 | 25 | 36 | 43.2 | 11 | 100%
TAP-86327_SEAMLESS | 28 | *25 |  | 04.01.01.08.00.00.00.00 | TAP-86327 | TAP-87798 | [TAP-86327_SEAMLESS] ¦ [RAS-8541] Support to Unplug LLM from SA_J4 stack | User Story | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 36 | 25 | 36 | 43.2 | 11 | 100%
TAP-86327_CLASSY1 | 29 | *25 |  | 04.01.01.10.00.00.00.00 | TAP-86327 | TAP-93381 | [TAP-86327_CLASSY1] ¦ Automated JAMA Alarms/Log pull for develop | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 44 | 25 | 44 | 52.8 | 19 | 100%
TAP-104062 | 30 | *5 |  | 04.02.01.00.00.00.00.00 |  | TAP-104062 | [TAP-104062] ¦ [v4.0] (RAS-11933) Add torque stable logging to IDU startup | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-104062_STELLARS | 31 | *30 |  | 04.02.01.01.00.00.00.00 | TAP-104062 | TAP-105887 | [TAP-104062_STELLARS] ¦ [Spike] [Stellars] [RAS-11933] Understand current implementation and propose solutions | User Story | Done | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-104062_PIXELPOETS | 32 | *30 |  | 04.03.01.00.00.00.00.00 |  | TAP-101881 | [TAP-104062_PIXELPOETS] ¦ Set width in OrtLargeChronologicalNotificationsElement to fix string cutoff | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 18 | 11 | 18 | 21.6 | 7 | 100%
TAP-104062_BOOSTERS | 33 | *30 |  | 04.04.01.00.00.00.00.00 |  | TAP-73857 | [TAP-104062_BOOSTERS] ¦ Update archives manager | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 18 | 11 | 18 | 21.6 | 7 | 100%
TAP-104062_MARVEL | 34 | *30 |  | 04.05.01.00.00.00.00.00 |  | TAP-44976 | [TAP-104062_MARVEL] ¦ Remove interrupt-based checking from EPO check in subsystem_fse | User Story | Done | Foundation - Marvel | MARVEL | Child Task | User Stories | 18 | 11 | 18 | 21.6 | 7 | 100%
TAP-47497 | 35 | *1 |  | 04.06.01.00.00.00.00.00 |  | TAP-47497 | [TAP-47497] ¦ [MTBI] (Batch B) Allow setup joints to be manual controllable after ACA hot swap | Feature | Done |  |  | Parent Task | User Stories | 23 | 23 | 1 hr | 1 hr | 0 | 100%
TAP-47497_SCRUMBLEDORES | 36 | *35 |  | 04.06.01.01.00.00.00.00 | TAP-47497 | TAP-48064 | [TAP-47497_SCRUMBLEDORES] ¦ [Scrumbledores] Prototype code to Allow setup joints to be manual controllable after ACA hot swap | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 23 | 23 | 23 | 27.6 | 0 | 100%
TAP-47497_ORGANELLES | 37 | *35 |  | 04.06.01.03.00.00.00.00 | TAP-47497 | TAP-48863 | [TAP-47497_ORGANELLES] ¦ Spike: FlowRiders investigation for TAP-48069 | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 27 | 23 | 27 | 32.4 | 4 | 100%
TAP-95751 | 38 | *5 |  | 04.08.01.00.00.00.00.00 |  | TAP-95751 | [TAP-95751] ¦ [RAS-12678][v4.0] Add instrument use life limit as a event | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-95751_STELLARS | 39 | *38 |  | 04.08.01.01.00.00.00.00 | TAP-95751 | TAP-106163 | [TAP-95751_STELLARS] ¦ [Stellars] [RAS-12678] [Spike] Understand current implementation and propose solutions | User Story | Done | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-95751_ICONICS | 40 | *38 |  | 04.09.01.00.00.00.00.00 |  | TAP-105387 | [TAP-95751_ICONICS] ¦ Implement Changes to log Calibration Offsets of Control Device to sqlite as non debug event | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 18 | 11 | 18 | 21.6 | 7 | 100%
TAP-79084 | 41 | *1 |  | 04.10.01.00.00.00.00.00 |  | TAP-79084 | [TAP-79084] ¦ [iSim][v4.0] Add system deactivation functionality to the iSim + SC Configuration | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-79084_ORGANELLES | 42 | *41 |  | 04.10.01.01.00.00.00.00 | TAP-79084 | TAP-71147 | [TAP-79084_ORGANELLES] ¦ [iSim][TechDebt] Implement system deactivation in the simulator | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-79084_JACOBIANS | 43 | *41 |  | 04.10.01.02.00.00.00.00 | TAP-79084 | TAP-83543 | [TAP-79084_JACOBIANS] ¦ [iSim][TechDebt] Implement system deactivation on sc+sim configuration continued | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-79084_ATLAS | 44 | *41 |  | 04.11.01.00.00.00.00.00 |  | TAP-88130 | [TAP-79084_ATLAS] ¦ [DEFECT] RAS-8531 Volume setting failure in SCDC install FFU | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 10 | 9 | 10 | 12 | 1 | 100%
TAP-86325 | 45 | *1 |  | 04.12.01.00.00.00.00.00 |  | TAP-86325 | [TAP-86325] ¦ (RAS-7054) Allow Wristed instrument fails calibration retries without detaching the instrument | Feature | Done |  |  | Parent Task | User Stories | 26 | 26 | 1 hr | 1 hr | 0 | 100%
TAP-86325_ICONICS | 46 | *45 |  | 04.12.01.01.00.00.00.00 | TAP-86325 | TAP-86142 | [TAP-86325_ICONICS] ¦ [KTBR] [RAS-7054] Investigate and understand the implementation | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 26 | 26 | 26 | 31.2 | 0 | 100%
TAP-86325_SEAMLESS | 47 | *45 |  | 04.12.01.07.00.00.00.00 | TAP-86325 | TAP-87467 | [TAP-86325_SEAMLESS] ¦ [KTBR] [RAS-7054] Perform Dry runs | User Story | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 38 | 26 | 38 | 45.6 | 12 | 100%
TAP-86030 | 48 | *1 |  | 04.13.01.00.00.00.00.00 |  | TAP-86030 | [TAP-86030] ¦ (RAS-7239) Avoid flooding of UPS_manager tmp logs | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-86030_ICONICS | 49 | *48 |  | 04.13.01.01.00.00.00.00 | TAP-86030 | TAP-75111 | [TAP-86030_ICONICS] ¦ [RAS-7239] ups_manager logger improvement | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-86030_ELECTRON | 50 | *48 |  | 04.14.01.00.00.00.00.00 |  | TAP-51975 | [TAP-86030_ELECTRON] ¦ investigate and fix eliding of text in S3D PriorityMessages panel | User Story | Done | Advanced Instruments - Electron | ELECTRON | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-95635 | 51 | *1 |  | 04.15.01.00.00.00.00.00 |  | TAP-95635 | [TAP-95635] ¦ [RAS-11445] Add SMC Encode Initialization offsets to sqlite database | Feature | Done |  |  | Parent Task | User Stories | 11.5 | 11.5 | 1 hr | 1 hr | 0 | 100%
TAP-95635_ICONICS | 52 | *51 |  | 04.15.01.01.00.00.00.00 | TAP-95635 | TAP-96538 | [TAP-95635_ICONICS] ¦ [Spike] Investigation on logging calibration offsets to sqlite for RAS-11445 | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 11.5 | 11.5 | 11.5 | 13.8 | 0 | 100%
TAP-95635_STORMCHASERS2 | 53 | *51 |  | 04.15.01.03.00.00.00.00 | TAP-95635 | TAP-97279 | [TAP-95635_STORMCHASERS2] ¦ [RAS-11445] Storm chasers indepedent review support | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 14.5 | 11.5 | 14.5 | 17.4 | 3 | 100%
TAP-95635_SCRUMBLEDORES | 54 | *51 |  | 04.17.01.00.00.00.00.00 |  | TAP-83502 | [TAP-95635_SCRUMBLEDORES] ¦ Remove unconnected lines in library | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 16.5 | 11.5 | 16.5 | 19.8 | 5 | 100%
TAP-84571 | 55 | *1 |  | 04.18.01.00.00.00.00.00 |  | TAP-84571 | [TAP-84571] ¦ (Close RAS-10913) Improve peripheral compat robustness by retrying after a wait period | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-84571_ICONICS | 56 | *55 |  | 04.18.01.01.00.00.00.00 | TAP-84571 | TAP-83264 | [TAP-84571_ICONICS] ¦ [RAS-10913] Sleep in between peripheral config retries | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-84571_PLATFORMERS | 57 | *55 |  | 04.18.01.03.00.00.00.00 | TAP-84571 | TAP-86632 | [TAP-84571_PLATFORMERS] ¦ [RAS-10913] [Improve peripheral compat check robustness] Platformers review support | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 11 | 8 | 11 | 13.2 | 3 | 100%
TAP-97497 | 58 | *5 |  | 04.20.01.00.00.00.00.00 |  | TAP-97497 | [TAP-97497] ¦ [Drushti][RAS-1210] Change ACAD Error state color | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-97497_DRUSHTI | 59 | *58 |  | 04.20.01.01.00.00.00.00 | TAP-97497 | TAP-97498 | [TAP-97497_DRUSHTI] ¦ [Drushti][Spike] Change error state from Navy Blue to Grey | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-97497_MIRAGE | 60 | *58 |  | 04.21.01.00.00.00.00.00 |  | TAP-219 | [TAP-97497_MIRAGE] ¦ [RAS-1818] disable ergonomic adjustments from SID during clutch | User Story | Done | Advanced Instruments - Mirage | MIRAGE | Child Task | User Stories | 21 | 13 | 21 | 25.2 | 8 | 100%
TAP-6975 | 61 | *1 |  | 04.21.02.00.00.00.00.00 |  | TAP-6975 | [TAP-6975] ¦ [GUI](RAS-1818) Align behavior to match ergonomics when clutching and firing energy | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-6975_DRUSHTI | 62 | *61 |  | 04.21.02.01.00.00.00.00 | TAP-6975 | TAP-85747 | [TAP-6975_DRUSHTI] ¦ [Drushti][Spike] Ergonomic adjustments can be made on SID while clutch is enabled | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-6975_PIXELPOETS | 63 | *61 |  | 04.22.01.00.00.00.00.00 |  | TAP-103630 | [TAP-6975_PIXELPOETS] ¦ Fix Notcode-60 when transitioning to surgery screen | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 21 | 13 | 21 | 25.2 | 8 | 100%
TAP-6975_TEAMBD | 64 | *61 |  | 04.24.01.00.00.00.00.00 |  | TAP-93494 | [TAP-6975_TEAMBD] ¦ Part 2 - Deactivation causes core dump - [v4] shutdown slow | Issue | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 26 | 13 | 26 | 31.2 | 13 | 100%
TAP-6975_CLASSY1 | 65 | *61 |  | 04.25.01.00.00.00.00.00 |  | TAP-121806 | [TAP-6975_CLASSY1] ¦ TPSC-ACS Comm Loss happened during arm startup | Issue | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 26 | 13 | 26 | 31.2 | 13 | 100%
TAP-6975_HORIZON | 66 | *61 |  | 04.26.01.00.00.00.00.00 |  | TAP-124118 | [TAP-6975_HORIZON] ¦ Disable ESU when FSE detects low temp | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 26 | 13 | 26 | 31.2 | 13 | 100%
TAP-71016 | 67 | *3 |  | 04.27.01.00.00.00.00.00 |  | TAP-71016 | [TAP-71016] ¦ [iSim][v4.0] Update Surgical Science Trainer build | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-71016_ATLAS | 68 | *67 |  | 04.27.01.01.00.00.00.00 | TAP-71016 | TAP-93805 | [TAP-71016_ATLAS] ¦ [BUG] Debug Simbionix install failure | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-71016_SOUPERTROOPERS | 69 | *67 |  | 04.27.01.07.00.00.00.00 | TAP-71016 | TAP-109193 | [TAP-71016_SOUPERTROOPERS] ¦ [SPIKE] SOUP: Surgical Science version update | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 29 | 21 | 29 | 34.8 | 8 | 100%
TAP-71016_EDISON | 70 | *67 |  | 04.27.01.09.00.00.00.00 | TAP-71016 | TAP-110437 | [TAP-71016_EDISON] ¦ Update Surgical Science build plan to add signature file to ESAT deployment package | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 33 | 21 | 33 | 39.6 | 12 | 100%
TAP-94703 | 71 | *1 |  | 04.29.01.00.00.00.00.00 |  | TAP-94703 | [TAP-94703] ¦ [RAS-11307] Indication of system deactivation from Tower startup failures | Feature | Done |  |  | Parent Task | User Stories | 19 | 19 | 1 hr | 1 hr | 0 | 100%
TAP-94703_DRUSHTI | 72 | *71 |  | 04.29.01.01.00.00.00.00 | TAP-94703 | TAP-95481 | [TAP-94703_DRUSHTI] ¦ [Drushti][Spike][RAS-11307] Indication of system deactivation from Tower startup failures | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 19 | 19 | 19 | 22.8 | 0 | 100%
TAP-94703_ATLAS | 73 | *71 |  | 04.30.01.00.00.00.00.00 |  | TAP-121691 | [TAP-94703_ATLAS] ¦ Caching on windows cause empty files | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 33 | 19 | 33 | 39.6 | 14 | 100%
TAP-58230 | 74 | *1 |  | 04.31.01.00.00.00.00.00 |  | TAP-58230 | [TAP-58230] ¦ [Tech Debt] Initial Build Variant Work | Feature | Done |  |  | Parent Task | User Stories | 49 | 49 | 1 hr | 1 hr | 0 | 100%
TAP-58230_TEAMBD | 75 | *74 |  | 04.31.01.01.00.00.00.00 | TAP-58230 | TAP-67529 | [TAP-58230_TEAMBD] ¦ [Croc] Initial Develop to staging/advanced-instruments File Diff | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 49 | 49 | 49 | 58.8 | 0 | 100%
TAP-58230_SIRIUS | 76 | *74 |  | 04.31.01.02.00.00.00.00 | TAP-58230 | TAP-72410 | [TAP-58230_SIRIUS] ¦ Remove clip applier, monopolar, WRS, GoNext, and straight instrument controller | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 49 | 49 | 49 | 58.8 | 0 | 100%
TAP-58230_ORGANELLES | 77 | *74 |  | 04.31.01.04.00.00.00.00 | TAP-58230 | TAP-75291 | [TAP-58230_ORGANELLES] ¦ [Reflect] Add Croc and Newton iSim functionality to develop | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 51 | 49 | 51 | 61.2 | 2 | 100%
TAP-58230_PIXELPOETS | 78 | *74 |  | 04.31.01.05.00.00.00.00 | TAP-58230 | TAP-75434 | [TAP-58230_PIXELPOETS] ¦ [Spike] [Positron] Investigate use of idu_dev flag in GUI | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 51 | 49 | 51 | 61.2 | 2 | 100%
TAP-58230_I2E | 79 | *74 |  | 04.31.01.06.00.00.00.00 | TAP-58230 | TAP-75497 | [TAP-58230_I2E] ¦ [Enabler] [Croc] Prepare develop branch merge to i2e-croc | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 51 | 49 | 51 | 61.2 | 2 | 100%
TAP-58230_SUNRISERS | 80 | *74 |  | 04.31.01.10.00.00.00.00 | TAP-58230 | TAP-74565 | [TAP-58230_SUNRISERS] ¦ [Croc][TechDebt][FF] Initial Build Variant Work - Implementation | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 66 | 49 | 66 | 79.2 | 17 | 100%
TAP-61982 | 81 | *1 |  | 04.31.02.00.00.00.00.00 |  | TAP-61982 | [TAP-61982] ¦ Merge gated derating infrastructure to develop | Feature | Done |  |  | Parent Task | User Stories | 32 | 32 | 1 hr | 1 hr | 0 | 100%
TAP-61982_SIRIUS | 82 | *81 |  | 04.31.02.01.00.00.00.00 | TAP-61982 | TAP-65280 | [TAP-61982_SIRIUS] ¦ [Sirius] Port derating tool to develop and Implement Unit Tests | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 32 | 32 | 32 | 38.4 | 0 | 100%
TAP-61982_ORGANELLES | 83 | *81 |  | 04.31.02.02.00.00.00.00 | TAP-61982 | TAP-65359 | [TAP-61982_ORGANELLES] ¦ Add Selected MSC Derating Parameters from staging/advanced-instruments | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 32 | 32 | 32 | 38.4 | 0 | 100%
TAP-61982_ASTRANPSVALIDATORS | 84 | *81 |  | 04.31.02.07.00.00.00.00 | TAP-61982 | TAP-80165 | [TAP-61982_ASTRANPSVALIDATORS] ¦ [v2.1] Validate Derating Tools | User Story | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task | User Stories | 40.5 | 32 | 40.5 | 48.6 | 8.5 | 100%
TAP-61982_TEAMBD | 85 | *81 |  | 04.31.03.00.00.00.00.00 |  | TAP-72283 | [TAP-61982_TEAMBD] ¦ [Newton] Restore Newton build after updating Ligasure Error bus for Marystein | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 46 | 32 | 46 | 55.2 | 14 | 100%
TAP-68699 | 86 | *1 |  | 04.31.04.00.00.00.00.00 |  | TAP-68699 | [TAP-68699] ¦ [Croc] Implement Twitch de-rating in iSim for user studies | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-68699_SIRIUS | 87 | *86 |  | 04.31.04.01.00.00.00.00 | TAP-68699 | TAP-75639 | [TAP-68699_SIRIUS] ¦ [Croc][Sirius] Update Twitch derating Trajectory | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-83329 | 88 | *1 |  | 04.31.08.00.00.00.00.00 |  | TAP-83329 | [TAP-83329] ¦ [Croc] [Tech Debt] Finalize Croc Variants Merge to Develop | Feature | Done |  |  | Parent Task | User Stories | 43.75 | 43.75 | 1 hr | 1 hr | 0 | 100%
TAP-83329_CROCNROLL | 89 | *88 |  | 04.31.08.01.00.00.00.00 | TAP-83329 | TAP-81811 | [TAP-83329_CROCNROLL] ¦ [Sirius/CrocNRoll] Merge staging/RAS-9030 to Develop | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 43.75 | 43.75 | 43.75 | 52.5 | 0 | 100%
TAP-83329_SCRUMBLEDORES | 90 | *88 |  | 04.31.08.02.00.00.00.00 | TAP-83329 | TAP-83344 | [TAP-83329_SCRUMBLEDORES] ¦ [Croc][Scrumbledores] Simplify UNIT_IxStmExchangeModeStapler unit | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 43.75 | 43.75 | 43.75 | 52.5 | 0 | 100%
TAP-83329_EDISON | 91 | *88 |  | 04.31.08.04.00.00.00.00 | TAP-83329 | TAP-71738 | [TAP-83329_EDISON] ¦ Enable idu_dev in engineering builds | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 45.75 | 43.75 | 45.75 | 54.9 | 2 | 100%
TAP-83329_SIRIUS | 92 | *88 |  | 04.31.08.05.01.00.00.00 | TAP-83329 | TAP-75157 | [TAP-83329_SIRIUS] ¦ [Croc][SPIKE] [Sirius] Investigate existing endstop detection algorithm [Part 1] | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 45.75 | 43.75 | 45.75 | 54.9 | 2 | 100%
TAP-83329_I2E | 93 | *88 |  | 04.31.08.05.04.00.00.00 | TAP-83329 | TAP-79773 | [TAP-83329_I2E] ¦ [Croc] [IDU CMD] Extend tool functionality to include croc reload and instrument exchange | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 54.25 | 43.75 | 54.25 | 65.1 | 10.5 | 100%
TAP-83329_SUNRISERS | 94 | *88 |  | 04.31.08.06.00.00.00.00 | TAP-83329 | TAP-83258 | [TAP-83329_SUNRISERS] ¦ [croc][sunrisers]Merge SRO changes from staging/adv-inst to staging/RAS-9030 | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 62.25 | 43.75 | 62.25 | 74.7 | 18.5 | 100%
TAP-83329_JACOBIANS | 95 | *88 |  | 04.31.09.00.00.00.00.00 |  | TAP-86829 | [TAP-83329_JACOBIANS] ¦ [Newton][Jacobian] Investigate and Update Z-offset | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 69.25 | 43.75 | 69.25 | 83.1 | 25.5 | 100%
TAP-6337 | 96 | *1 |  | 04.31.10.00.00.00.00.00 |  | TAP-6337 | [TAP-6337] ¦ [TechDebt] SPIKE - Consolidate instrument angle sign conventions across SRA and IDU | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-6337_TEAMBD | 97 | *96 |  | 04.31.10.01.00.00.00.00 | TAP-6337 | TAP-26714 | [TAP-6337_TEAMBD] ¦ [TechDebt][Newton] Remove gain from sra_controller update_idu_joints_d | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 10 | 10 | 10 | 12 | 0 | 100%
TAP-6337_I2E | 98 | *96 |  | 04.31.10.03.00.00.00.00 | TAP-6337 | TAP-36689 | [TAP-6337_I2E] ¦ [SPIKE][Newton] Investigate IDU tools impact with sign convention change | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 11 | 10 | 11 | 13.2 | 1 | 100%
TAP-6337_BUGHUNTERS | 99 | *96 |  | 04.31.10.05.00.00.00.00 | TAP-6337 | TAP-36942 | [TAP-6337_BUGHUNTERS] ¦ [BugHunters] Ensure IDU MIL Test are passing after sign convention update | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 14 | 10 | 14 | 16.8 | 4 | 100%
TAP-6337_DOCUMENTOWNERS | 100 | *96 |  | 04.31.11.00.00.00.00.00 |  | TAP-93546 | [TAP-6337_DOCUMENTOWNERS] ¦ Instruments not opening for extraction with --idu_dev flag on | Issue | Done | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 16 | 10 | 16 | 19.2 | 6 | 100%
TAP-86333 | 101 | *1 |  | 04.32.01.00.00.00.00.00 |  | TAP-86333 | [TAP-86333] ¦ complete pending work for RAS-6750, RAS-6239 | Feature | Done |  |  | Parent Task | User Stories | 10.75 | 10.75 | 1 hr | 1 hr | 0 | 100%
TAP-86333_JACOBIANS | 102 | *101 |  | 04.32.01.01.00.00.00.00 | TAP-86333 | TAP-80273 | [TAP-86333_JACOBIANS] ¦ [RAS-6239] EIN-SWI-69 FM's analysis | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 10.75 | 10.75 | 10.75 | 12.9 | 0 | 100%
TAP-86333_SCRUMBLEDORES | 103 | *101 |  | 04.32.01.02.00.00.00.00 | TAP-86333 | TAP-80385 | [TAP-86333_SCRUMBLEDORES] ¦ [Scrumbledores] Analyze impact to FM's in cFMEA and sFMEA based on changes to requirement in RAS-6750 | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 10.75 | 10.75 | 10.75 | 12.9 | 0 | 100%
TAP-86333_ICONICS | 104 | *101 |  | 04.32.01.03.00.00.00.00 | TAP-86333 | TAP-75115 | [TAP-86333_ICONICS] ¦ [RAS-6239] Implement, Test, Rework & Review Closure | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 10.75 | 10.75 | 10.75 | 12.9 | 0 | 100%
TAP-86312 | 105 | *1 |  | 04.33.01.00.00.00.00.00 |  | TAP-86312 | [TAP-86312] ¦ (RAS-6961)Retry ACA calibration in the instance when calibration times out during an arm hotswap | Feature | Done |  |  | Parent Task | User Stories | 50 | 50 | 1 hr | 1 hr | 0 | 100%
TAP-86312_ICONICS | 106 | *105 |  | 04.33.01.01.00.00.00.00 | TAP-86312 | TAP-86169 | [TAP-86312_ICONICS] ¦ [KTBR] [RAS-6961] Investigate and understand the implementation | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 50 | 50 | 50 | 60 | 0 | 100%
TAP-86312_DRUSHTI | 107 | *105 |  | 04.33.01.08.00.00.00.00 | TAP-86312 | TAP-87093 | [TAP-86312_DRUSHTI] ¦ [Spike][Drushti] Support RAS-6961 to KTBR | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 65 | 50 | 65 | 78 | 15 | 100%
TAP-86312_CLASSY2 | 108 | *105 |  | 04.33.01.16.00.00.00.00 | TAP-86312 | TAP-94627 | [TAP-86312_CLASSY2] ¦ Update Alarms Pull Scripts to Resolve Bugs Discovered w/ProdSec Artifact Definitions | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 87 | 50 | 87 | 104.4 | 37 | 100%
TAP-86312_PIXELPOETS | 109 | *105 |  | 04.33.02.00.00.00.00.00 |  | TAP-109588 | [TAP-86312_PIXELPOETS] ¦ [v4.0][Pixel Poets][SPIKE] Check EIN-SSR_GUI-301 coverage | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 87 | 50 | 87 | 104.4 | 37 | 100%
TAP-114212 | 110 | *5 |  | 04.39.01.00.00.00.00.00 |  | TAP-114212 | [TAP-114212] ¦ [V4.0][EC3][SC2] Fix RAS-13574 | Feature | Done |  |  | Parent Task | User Stories | 19 | 19 | 1 hr | 1 hr | 0 | 100%
TAP-114212_STORMCHASERS2 | 111 | *110 |  | 04.39.01.01.00.00.00.00 | TAP-114212 | TAP-96720 | [TAP-114212_STORMCHASERS2] ¦ [SC2] Fix the issue SWI-56 code does not correspond to EIN-SSR_SCSW-694 | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 19 | 19 | 19 | 22.8 | 0 | 100%
TAP-114212_PIXELPOETS | 112 | *110 |  | 04.40.01.00.00.00.00.00 |  | TAP-122356 | [TAP-114212_PIXELPOETS] ¦ Notecode message is displayed truncated on the S3D screen | Issue | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 29 | 19 | 29 | 34.8 | 10 | 100%
TAP-114212_DRUSHTI | 113 | *110 |  | 04.40.01.01.00.00.00.00 |  | TAP-122701 | [TAP-114212_DRUSHTI] ¦ Testing all the notecodes with and without deviation using armsim | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 29 | 19 | 29 | 34.8 | 10 | 100%
TAP-84573 | 114 | *1 |  | 04.45.01.00.00.00.00.00 |  | TAP-84573 | [TAP-84573] ¦ [Drushti](RAS-9521) GUI Stuck Calibrate Arms Screen | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-84573_DRUSHTI | 115 | *114 |  | 04.45.01.01.00.00.00.00 | TAP-84573 | TAP-71883 | [TAP-84573_DRUSHTI] ¦ [Drushti] GUI Stuck Calibrate Arms Screen | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-84573_PIXELPOETS | 116 | *114 |  | 04.47.01.00.00.00.00.00 |  | TAP-110594 | [TAP-84573_PIXELPOETS] ¦ Generate .ts files for V4 | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 35 | 13 | 35 | 42 | 22 | 100%
TAP-81873 | 117 | *1 |  | 04.49.01.00.00.00.00.00 |  | TAP-81873 | [TAP-81873] ¦ [US URO] De-rating Prototype Jaw Opening & Closing Forces | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-81873_ORGANELLES | 118 | *117 |  | 04.49.01.01.00.00.00.00 | TAP-81873 | TAP-86602 | [TAP-81873_ORGANELLES] ¦ [US URO][Organelles] Implement jaw opening/closing force derating | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-81874 | 119 | *1 |  | 04.49.02.00.00.00.00.00 |  | TAP-81874 | [TAP-81874] ¦ [US URO] De-rating Prototype Tracking Errors | Feature | Done |  |  | Parent Task | User Stories | 14 | 14 | 1 hr | 1 hr | 0 | 100%
TAP-81874_ORGANELLES | 120 | *119 |  | 04.49.02.01.00.00.00.00 | TAP-81874 | TAP-86614 | [TAP-81874_ORGANELLES] ¦ [US URO] Develop filter for derating tracking error | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 14 | 14 | 14 | 16.8 | 0 | 100%
TAP-81924 | 121 | *1 |  | 04.49.03.00.00.00.00.00 |  | TAP-81924 | [TAP-81924] ¦ [US URO] De-rating Prototype Range Of Motion | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-81924_ORGANELLES | 122 | *121 |  | 04.49.03.01.00.00.00.00 | TAP-81924 | TAP-86617 | [TAP-81924_ORGANELLES] ¦ [US URO][Organelles] Develop derating software to support: EIN-SR-617 - Dexterity: Articulating Instruments Range of Motion | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-81925 | 123 | *1 |  | 04.49.04.00.00.00.00.00 |  | TAP-81925 | [TAP-81925] ¦ [US URO] De-rating Prototype Endoscope Directional Accuracy | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-81925_ORGANELLES | 124 | *123 |  | 04.49.04.01.00.00.00.00 | TAP-81925 | TAP-86625 | [TAP-81925_ORGANELLES] ¦ [US URO][Organelles] Develop derating software to support: EIN-SR-1290 - Endoscope Control: Directional Accuracy | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-81925_JACOBIANS | 125 | *123 |  | 04.49.04.03.00.00.00.00 | TAP-81925 | TAP-87195 | [TAP-81925_JACOBIANS] ¦ [US URO][Jacobians] Support Organelles on Camera Control Updates | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 10 | 9 | 10 | 12 | 1 | 100%
TAP-81926 | 126 | *1 |  | 04.49.05.00.00.00.00.00 |  | TAP-81926 | [TAP-81926] ¦ [US URO] De-rating Prototype Translation Distance in Time | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-81926_ORGANELLES | 127 | *126 |  | 04.49.05.01.00.00.00.00 | TAP-81926 | TAP-86611 | [TAP-81926_ORGANELLES] ¦ [US URO] Derating translation velocity | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-91222 | 128 | *5 |  | 04.49.06.00.00.00.00.00 |  | TAP-91222 | [TAP-91222] ¦ [IRR][US URO] Set and Lock Out Articulation and Roll in De-Rating Tool | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-91222_ANGLERS | 129 | *128 |  | 04.49.06.01.00.00.00.00 | TAP-91222 | TAP-105300 | [TAP-91222_ANGLERS] ¦ Generate pre-defined trajectories for use in the IDU controller binary | User Story | Done | Core Instruments - Anglers | ANGLERS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-91222_ORGANELLES | 130 | *128 |  | 04.49.07.00.00.00.00.00 |  | TAP-92684 | [TAP-91222_ORGANELLES] ¦ Merge staging-RAS-10917 to develop | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-96638 | 131 | *1 |  | 04.49.09.00.00.00.00.00 |  | TAP-96638 | [TAP-96638] ¦ [US URO] - Update URO Derating Tools to Address TMD Feedback | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-96638_ORGANELLES | 132 | *131 |  | 04.49.09.01.00.00.00.00 | TAP-96638 | TAP-96528 | [TAP-96638_ORGANELLES] ¦ Update Endoscope tool to also derate in z-direction | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-104444 | 133 | *5 |  | 04.49.10.00.00.00.00.00 |  | TAP-104444 | [TAP-104444] ¦ [US URO] - PI13 URO Derating Tool Updates to Address Feedback | Feature | Done |  |  | Parent Task | User Stories | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-104444_ORGANELLES | 134 | *133 |  | 04.49.10.01.00.00.00.00 | TAP-104444 | TAP-102023 | [TAP-104444_ORGANELLES] ¦ Merge derating logging updates to develop | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-104444_I2E | 135 | *133 |  | 04.49.11.00.00.00.00.00 |  | TAP-99022 | [TAP-104444_I2E] ¦ [v3.1][IRR][IDU CMD][I2E] Add Shears functionality to M-IRR's tool within Discrete Control Command | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 21 | 12 | 21 | 25.2 | 9 | 100%
TAP-104444_PLATFORMERS | 136 | *133 |  | 04.52.01.00.00.00.00.00 |  | TAP-122350 | [TAP-104444_PLATFORMERS] ¦ [V4][Platformers] Uncaught exception in thread in TeneoBridge | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 21 | 12 | 21 | 25.2 | 9 | 100%
TAP-104444_EDISON | 137 | *133 |  | 04.54.01.00.00.00.00.00 |  | TAP-124592 | [TAP-104444_EDISON] ¦ Update zynq bsp build plan to include a release test build variant | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 24 | 12 | 24 | 28.8 | 12 | 100%
TAP-104444_FRED | 138 | *133 |  | 04.55.01.00.00.00.00.00 |  | TAP-115706 | [TAP-104444_FRED] ¦ [Fred] Update Software Unit(s) Verification Checklists based on new Verification Plan | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 24 | 12 | 24 | 28.8 | 12 | 100%
TAP-104444_CLASSY | 139 | *133 |  | 04.55.02.00.00.00.00.00 |  | TAP-122035 | [TAP-104444_CLASSY] ¦ Automated Unit Test Failure Report: test_error_bridge failed | Issue | In progress | Foundation - Classy | CLASSY | Child Task | User Stories | 24 | 12 | 24 | 28.8 | 12 | 50%
TAP-104444_CLASSY1 | 140 | *133 |  | 04.55.03.00.00.00.00.00 |  | TAP-112338 | [TAP-104444_CLASSY1] ¦ Automated Unit Test Failure Report: test_internal_error_client failed | Issue | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 24 | 12 | 24 | 28.8 | 12 | 100%
TAP-104444_CLASSY2 | 141 | *133 |  | 04.55.04.00.00.00.00.00 |  | TAP-117166 | [TAP-104444_CLASSY2] ¦ Automated Unit Test Failure Report: test_gui_indicator_interface failed | Issue | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 24 | 12 | 24 | 28.8 | 12 | 100%
TAP-104444_BOOSTERS | 142 | *133 |  | 04.55.07.00.00.00.00.00 |  | TAP-63861 | [TAP-104444_BOOSTERS] ¦ Generate KPI report with number on bar plots | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 29.5 | 12 | 29.5 | 35.4 | 17.5 | 100%
TAP-113408 | 143 | *9 |  | 04.56.01.00.00.00.00.00 |  | TAP-113408 | [TAP-113408] ¦ [Foundation] Fix Design Documentation | Feature | Done |  |  | Parent Task | User Stories | 50.8 | 50.8 | 1 hr | 1 hr | 0 | 100%
TAP-113408_HORIZON | 144 | *143 |  | 04.56.01.01.00.00.00.00 | TAP-113408 | TAP-113832 | [TAP-113408_HORIZON] ¦ [Horizon] Add CTF EOL content to Markdown SDDs | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 50.8 | 50.8 | 50.8 | 60.96 | 0 | 100%
TAP-113408_FRED | 145 | *143 |  | 04.56.01.02.00.00.00.00 | TAP-113408 | TAP-106356 | [TAP-113408_FRED] ¦ [Fred] Review design documents in EIN_NG repository | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 50.8 | 50.8 | 50.8 | 60.96 | 0 | 100%
TAP-113408_CLASSY2 | 146 | *143 |  | 04.56.01.03.00.00.00.00 | TAP-113408 | TAP-114259 | [TAP-113408_CLASSY2] ¦ [Classy]Update EIN-SWI-500,386 Error Bridge, Client Interface Software Design Document after migration to md format | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 50.8 | 50.8 | 50.8 | 60.96 | 0 | 100%
TAP-113408_STORMCHASERS1 | 147 | *143 |  | 04.56.01.12.00.00.00.00 | TAP-113408 | TAP-114367 | [TAP-113408_STORMCHASERS1] ¦ [V4.0][SC1] Review/fix design documents and merge to code repository | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 65.8 | 50.8 | 65.8 | 78.96 | 15 | 100%
TAP-113408_ATLAS | 148 | *143 |  | 04.56.01.13.00.00.00.00 | TAP-113408 | TAP-106633 | [TAP-113408_ATLAS] ¦ [enabler] Review design document after markdown conversion | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 65.8 | 50.8 | 65.8 | 78.96 | 15 | 100%
TAP-113408_STORMCHASERS2 | 149 | *143 |  | 04.56.01.14.00.00.00.00 | TAP-113408 | TAP-114508 | [TAP-113408_STORMCHASERS2] ¦ [V4.0][SC2] Fix Design Documentation | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 65.8 | 50.8 | 65.8 | 78.96 | 15 | 100%
TAP-113408_BOOSTERS | 150 | *143 |  | 04.56.01.15.00.00.00.00 | TAP-113408 | TAP-114809 | [TAP-113408_BOOSTERS] ¦ [Boosters] Fix issues for EIN-SWI-323,577 Data Access Software Design Document | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 65.8 | 50.8 | 65.8 | 78.96 | 15 | 100%
TAP-113408_EDISON | 151 | *143 |  | 04.56.01.22.00.00.00.00 | TAP-113408 | TAP-116191 | [TAP-113408_EDISON] ¦ Fix references and equations | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 72.8 | 50.8 | 72.8 | 87.36 | 22 | 100%
TAP-113408_DOCUMENTOWNERS | 152 | *143 |  | 04.56.01.26.00.00.00.00 | TAP-113408 | TAP-123494 | [TAP-113408_DOCUMENTOWNERS] ¦ Documentation: Update references.md files | User Story | Done | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 75.8 | 50.8 | 75.8 | 90.96 | 25 | 100%
TAP-113408_CLASSY | 153 | *143 |  | 04.56.01.28.00.00.00.00 | TAP-113408 | TAP-124024 | [TAP-113408_CLASSY] ¦ [CDR Action Item] Update secure communication design document | User Story | Done | Foundation - Classy | CLASSY | Child Task | User Stories | 76 | 50.8 | 76 | 91.2 | 25.2 | 100%
TAP-113408_PLATFORMERS | 154 | *143 |  | 04.56.02.00.00.00.00.00 |  | TAP-121844 | [TAP-113408_PLATFORMERS] ¦ [V4][Platformers] Certificate Manager design document update | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 76 | 50.8 | 76 | 91.2 | 25.2 | 100%
TAP-113410 | 155 | *9 |  | 04.56.03.00.00.00.00.00 |  | TAP-113410 | [TAP-113410] ¦ [Core Instr] Fix Design Documentation | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-113410_SIRIUS | 156 | *155 |  | 04.56.03.01.00.00.00.00 | TAP-113410 | TAP-116594 | [TAP-113410_SIRIUS] ¦ [v4.0][Sirius] Fix EIN-SWI-380, 381, 382, 604 Markdown DD Content | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-113410_HAPPYJAWS | 157 | *155 |  | 04.56.03.04.00.00.00.00 | TAP-113410 | TAP-116597 | [TAP-113410_HAPPYJAWS] ¦ [v4.0][Sirius] Fix EIN-SWI-383 Markdown DD Content | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 17 | 13 | 17 | 20.4 | 4 | 100%
TAP-113410_PUPPETEERS | 158 | *155 |  | 04.56.03.06.00.00.00.00 | TAP-113410 | TAP-117362 | [TAP-113410_PUPPETEERS] ¦ [Puppeteers] fix design docs for kinematics SWIs | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 19 | 13 | 19 | 22.8 | 6 | 100%
TAP-113410_FRED | 159 | *155 |  | 04.56.04.00.00.00.00.00 |  | TAP-123436 | [TAP-113410_FRED] ¦ [Fred] Correct SWI tags for Joint Secondary Updater files | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 19 | 13 | 19 | 22.8 | 6 | 100%
TAP-113410_REFRACT | 160 | *155 |  | 04.56.05.00.00.00.00.00 |  | TAP-123735 | [TAP-113410_REFRACT] ¦ Fix iSim SimPC Design Doc | User Story | Done | Shared Services - Refract | REFRACT | Child Task | User Stories | 19 | 13 | 19 | 22.8 | 6 | 100%
TAP-125059 | 161 | *13 |  | 04.57.01.00.00.00.00.00 |  | TAP-125059 | [TAP-125059] ¦ [V4.0][Cyber] Upgrade from Staging GSO to Production GSO for build signing | Feature | Accepted |  |  | Parent Task | User Stories | 24 | 2 | 1 hr | 1 hr | 22 | 8.333%
TAP-125059_EDISON | 162 | *161 |  | 04.57.01.01.00.00.00.00 | TAP-125059 | TAP-125061 | [TAP-125059_EDISON] ¦ WIndows Signing VM should point to Production GSO | User Story | Groomed | Shared Services - Edison | EDISON | Child Task | User Stories | 24 | 2 | 24 | 28.8 | 22 | 8.333%
TAP-125059_ATLAS | 163 | *161 |  | 04.57.01.03.00.00.00.00 | TAP-125059 | TAP-125065 | [TAP-125059_ATLAS] ¦ Update Keys and Certs in BSP x86 Repo | User Story | In progress | Foundation - Atlas | ATLAS | Child Task | User Stories | 25.5 | 2 | 25.5 | 30.6 | 23.5 | 7.843%
TAP-125059_PLATFORMERS | 164 | *161 |  | 04.57.01.08.00.00.00.00 | TAP-125059 | TAP-114070 | [TAP-125059_PLATFORMERS] ¦ [V4][Platformers] Update the production keys in ein_ng repo and clean up | User Story | In progress | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 34.5 | 2 | 34.5 | 41.4 | 32.5 | 5.797%
TAP-125059_TOOLSRULES | 165 | *161 |  | 04.57.01.09.00.00.00.00 | TAP-125059 | TAP-126353 | [TAP-125059_TOOLSRULES] ¦ ESAT v2: Ensure ESAT points at Staging GSO to Production GSO for build signing | User Story | Open | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 34.5 | 2 | 34.5 | 41.4 | 32.5 | 5.797%
TAP-125059_FRED | 166 | *161 |  | 04.58.02.00.00.00.00.00 |  | TAP-125256 | [TAP-125059_FRED] ¦ Closing non-open semaphore in BinarySemaphore | User Story | Open | Foundation - Fred | FRED | Child Task | User Stories | 37.5 | 2 | 37.5 | 45 | 35.5 | 5.333%
TAP-93577 | 167 | *13 |  | 04.59.01.00.00.00.00.00 |  | TAP-93577 | [TAP-93577] ¦ {GUI}(v4.0) [Cyber] Package and send translation package to GDS | Feature | Done |  |  | Parent Task | User Stories | 20 | 20 | 1 hr | 1 hr | 0 | 100%
TAP-93577_DRUSHTI | 168 | *167 |  | 04.59.01.01.00.00.00.00 | TAP-93577 | TAP-74766 | [TAP-93577_DRUSHTI] ¦ [Drushti][V4.0] Create package to Transperfect | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 20 | 20 | 20 | 24 | 0 | 100%
TAP-93577_ATLAS | 169 | *167 |  | 04.59.02.00.00.00.00.00 |  | TAP-111716 | [TAP-93577_ATLAS] ¦ Fix language package installation issue | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 38 | 20 | 38 | 45.6 | 18 | 100%
TAP-96537 | 170 | *13 |  | 04.59.03.00.00.00.00.00 |  | TAP-96537 | [TAP-96537] ¦ {GUI} (RAS-7008) v3.0 Language Formals and Release | Feature | Done |  |  | Parent Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-96537_DRUSHTI | 171 | *170 |  | 04.59.03.01.00.00.00.00 | TAP-96537 | TAP-74762 | [TAP-96537_DRUSHTI] ¦ [Drushti][V3.0] Language Package Formal Execution Part-4 {6} | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 31 | 31 | 31 | 37.2 | 0 | 100%
TAP-96537_EDISON | 172 | *170 |  | 04.59.03.10.00.00.00.00 | TAP-96537 | TAP-116066 | [TAP-96537_EDISON] ¦ [V3] Language Pack formal build/bundle/sign | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 56 | 31 | 56 | 67.2 | 25 | 100%
TAP-116321 | 173 | *13 |  | 04.59.08.00.00.00.00.00 |  | TAP-116321 | [TAP-116321] ¦ {GUI} (RAS-13563) v4.0 Language Formals and Release | Feature | Accepted |  |  | Parent Task | User Stories | 18 | 0 | 1 hr | 1 hr | 18 | 0%
TAP-116321_DRUSHTI | 174 | *173 |  | 04.59.08.01.00.00.00.00 | TAP-116321 | TAP-123781 | [TAP-116321_DRUSHTI] ¦ [Drushti] [v4.0] prep for v4 language formals | User Story | In progress | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 18 | 0 | 18 | 21.6 | 18 | 0%
TAP-116321_EDISON | 175 | *173 |  | 04.59.08.07.00.00.00.00 | TAP-116321 | TAP-116219 | [TAP-116321_EDISON] ¦ [V4] Language Pack formal build/bundle/sign | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 35 | 0 | 35 | 42 | 35 | 100%
TAP-126027 | 176 | *13 |  | 04.60.01.00.00.00.00.00 |  | TAP-126027 | [TAP-126027] ¦ [V4.0][RC1][Cyber] Implement penetration testing findings for WolfSSH 1.4.17 | Feature | Done |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-126027_EDISON | 177 | *176 |  | 04.60.01.01.00.00.00.00 | TAP-126027 | TAP-126046 | [TAP-126027_EDISON] ¦ [Defcon] Update WolfSSH 1.4.17 with nmap patch | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-126027_ATLAS | 178 | *176 |  | 04.60.01.02.00.00.00.00 | TAP-126027 | TAP-126054 | [TAP-126027_ATLAS] ¦ Integration test on the RC1 with wolfssh patch | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-58674 | 179 | *13 |  | 04.61.01.00.00.00.00.00 |  | TAP-58674 | [TAP-58674] ¦ [Cyber] Implement Fixes for Findings in Micro Penetration Testing for DDS/UDP | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-58674_FRED | 180 | *179 |  | 04.61.01.05.00.00.00.00 | TAP-58674 | TAP-123394 | [TAP-58674_FRED] ¦ UDP Pentesting Fixes | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-109870 | 181 | *13 |  | 04.63.01.00.00.00.00.00 |  | TAP-109870 | [TAP-109870] ¦ [Cyber] ESAT v2, Support Field Service Use of CyberArk P2 | Feature | Accepted |  |  | Parent Task | User Stories | 121 | 85 | 1 hr | 1 hr | 36 | 70.25%
TAP-109870_TOOLSRULES | 182 | *181 |  | 04.63.01.01.00.00.00.00 | TAP-109870 | TAP-109434 | [TAP-109870_TOOLSRULES] ¦ ESAT v2 CyberArk: create tab for importing json | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 121 | 85 | 121 | 145.2 | 36 | 100%
TAP-109870_BUILDERS | 183 | *181 |  | 04.63.01.09.00.00.00.00 | TAP-109870 | TAP-116109 | [TAP-109870_BUILDERS] ¦ Finalize schema for subsystem table in CyberArk | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 162 | 85 | 162 | 194.4 | 77 | 100%
TAP-122714 | 184 | *13 |  | 04.63.02.00.00.00.00.00 |  | TAP-122714 | [TAP-122714] ¦ [V4.0][RC2] ESAT v2: Additional ESAT and NPS content for V4 RC2 | Feature | Accepted |  |  | Parent Task | User Stories | 130 | 59 | 1 hr | 1 hr | 71 | 45.38%
TAP-122714_EDISON | 185 | *184 |  | 04.63.02.01.00.00.00.00 | TAP-122714 | TAP-90356 | [TAP-122714_EDISON] ¦ Release Deployment Testing using esat-v2 | User Story | Groomed | Shared Services - Edison | EDISON | Child Task | User Stories | 130 | 59 | 130 | 156 | 71 | 45.38%
TAP-122714_ASTRANPSDEVELOPERS | 186 | *184 |  | 04.63.02.04.00.00.00.00 | TAP-122714 | TAP-121830 | [TAP-122714_ASTRANPSDEVELOPERS] ¦ ESAT v2 - Convert ssh commands to wolfssh in grablog scripts | User Story | In progress | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 139 | 59 | 139 | 166.8 | 80 | 42.45%
TAP-122714_TOOLSRULES | 187 | *184 |  | 04.63.02.08.00.00.00.00 | TAP-122714 | TAP-81292 | [TAP-122714_TOOLSRULES] ¦ Currently, the user has to wait for a response from the esat_worker when the validate button is pressed. This may take longer than expected (v2) | Issue | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 155 | 59 | 155 | 186 | 96 | 100%
TAP-122714_PLATFORMERS | 188 | *184 |  | 04.63.02.11.00.00.00.00 | TAP-122714 | TAP-125462 | [TAP-122714_PLATFORMERS] ¦ [V4.0][Platformers] Investigate ESAT-DM DDS drops | User Story | Open | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 165 | 59 | 165 | 198 | 106 | 35.76%
TAP-102220 | 189 | *13 |  | 04.63.02.16.00.00.00.00 | TAP-122714 | TAP-102220 | [TAP-102220] ¦ [V4] [Cyber] ESAT Laptop certificate installation | Feature | Done |  |  | Parent Task | User Stories | 38 | 38 | 1 hr | 1 hr | 0 | 100%
TAP-102220_TOOLSRULES | 190 | *189 |  | 04.63.02.16.01.00.00.00 | TAP-102220 | TAP-114733 | [TAP-102220_TOOLSRULES] ¦ [V4.0] [ToolsRules] ESAT can handle no certificates | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 38 | 38 | 38 | 45.6 | 0 | 100%
TAP-102220_ASTRANPSDEVELOPERS | 191 | *189 |  | 04.63.02.17.00.00.00.00 | TAP-122714 | TAP-124853 | [TAP-102220_ASTRANPSDEVELOPERS] ¦ ESAT v2: only install peripherals if ORTI OS version is >= 4.0.3 | User Story | In progress | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 61 | 38 | 61 | 73.2 | 23 | 62.3%
TAP-102220_EDISON | 192 | *189 |  | 04.63.02.18.00.00.00.00 | TAP-122714 | TAP-126345 | [TAP-102220_EDISON] ¦ ESAT v2: Prod ESAT Build for v4.0/RC2 | User Story | Open | Shared Services - Edison | EDISON | Child Task | User Stories | 61 | 38 | 61 | 73.2 | 23 | 62.3%
TAP-84375 | 193 | *13 |  | 04.64.01.00.00.00.00.00 |  | TAP-84375 | [TAP-84375] ¦ [Cyber] US FRU Replacement Script/Procedure Updates | Feature | Done |  |  | Parent Task | User Stories | 78 | 78 | 1 hr | 1 hr | 0 | 100%
TAP-84375_BUILDERS | 194 | *193 |  | 04.64.01.01.00.00.00.00 | TAP-84375 | TAP-84681 | [TAP-84375_BUILDERS] ¦ Updates to SC Input Arm Programming scripts in field | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 78 | 78 | 78 | 93.6 | 0 | 100%
TAP-84375_ATLAS | 195 | *193 |  | 04.64.01.19.00.00.00.00 | TAP-84375 | TAP-115760 | [TAP-84375_ATLAS] ¦ [Spike] Investigate feasibility of combining USB packages for US launch. | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 130 | 78 | 130 | 156 | 52 | 100%
TAP-84375_EDISON | 196 | *193 |  | 04.64.01.28.00.00.00.00 | TAP-84375 | TAP-118467 | [TAP-84375_EDISON] ¦ Fix service scripts after function changes in BSP | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 142 | 78 | 142 | 170.4 | 64 | 100%
TAP-84375_PLATFORMERS | 197 | *193 |  | 04.64.01.30.00.00.00.00 | TAP-84375 | TAP-121619 | [TAP-84375_PLATFORMERS] ¦ ethercat_master_bootstrap crashes on SRA without RASA attached | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 145 | 78 | 145 | 174 | 67 | 100%
TAP-87778 | 198 | *21 |  | 04.64.02.00.00.00.00.00 |  | TAP-87778 | [TAP-87778] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 2 (validation) | Feature | In progress |  |  | Parent Task | User Stories | 42 | 0 | 1 hr | 1 hr | 42 | 0%
TAP-87778_BUILDERS | 199 | *198 |  | 04.64.02.01.00.00.00.00 | TAP-87778 | TAP-86863 | [TAP-87778_BUILDERS] ¦ Transfer of manufacturing BSP to EE team | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 42 | 0 | 42 | 50.4 | 42 | 0%
TAP-87778_ATLAS | 200 | *198 |  | 04.64.02.15.00.00.00.00 | TAP-87778 | TAP-125254 | [TAP-87778_ATLAS] ¦ Build Finalized 4.0 Manufacturing BSP | User Story | Groomed | Foundation - Atlas | ATLAS | Child Task | User Stories | 77 | 0 | 77 | 92.4 | 77 | 0%
TAP-115441 | 201 | *13 |  | 04.64.05.00.00.00.00.00 |  | TAP-115441 | [TAP-115441] ¦ [Cyber] Ubuntu BSP To support Plexus Programming | Feature | Accepted |  |  | Parent Task | User Stories | 48.5 | 20 | 1 hr | 1 hr | 28.5 | 41.24%
TAP-115441_ATLAS | 202 | *201 |  | 04.64.05.02.00.00.00.00 | TAP-115441 | TAP-116103 | [TAP-115441_ATLAS] ¦ [Spike] Determine the current use cases of the Ubuntu Programing Computer. | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 48.5 | 20 | 48.5 | 58.2 | 28.5 | 100%
TAP-115441_PLATFORMERS | 203 | *201 |  | 04.64.05.18.00.00.00.00 | TAP-115441 | TAP-123976 | [TAP-115441_PLATFORMERS] ¦ [V4][Platformers] ESAT certificate manager runs on Linux | User Story | Open | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 82 | 20 | 82 | 98.4 | 62 | 24.39%
TAP-115441_ASTRANPSVALIDATORS | 204 | *201 |  | 04.64.05.19.00.00.00.00 | TAP-115441 | TAP-123977 | [TAP-115441_ASTRANPSVALIDATORS] ¦ [Enabler][Astra] Validate Linux ESAT V2 for certificate installation to itself | User Story | Groomed | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task | User Stories | 82 | 20 | 82 | 98.4 | 62 | 24.39%
TAP-86043 | 205 | *13 |  | 04.65.01.00.00.00.00.00 |  | TAP-86043 | [TAP-86043] ¦ [Cyber] Enable ARM production security features | Feature | Accepted |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-86043_ATLAS | 206 | *205 |  | 04.65.01.01.00.00.00.00 | TAP-86043 | TAP-86044 | [TAP-86043_ATLAS] ¦ Enable jtag and efuse writing on QNX ARM Boards | User Story | Open | Foundation - Atlas | ATLAS | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-111218 | 207 | *13 |  | 04.66.01.00.00.00.00.00 |  | TAP-111218 | [TAP-111218] ¦ [Cyber] Non Production Boot Deployment | Feature | In progress |  |  | Parent Task | User Stories | 64 | 59 | 1 hr | 1 hr | 5 | 92.19%
TAP-111218_EDISON | 208 | *207 |  | 04.66.01.01.00.00.00.00 | TAP-111218 | TAP-111220 | [TAP-111218_EDISON] ¦ Create a skeleton bamboo plan for non production boot token | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 64 | 59 | 64 | 76.8 | 5 | 100%
TAP-111218_ATLAS | 209 | *207 |  | 04.66.01.02.00.00.00.00 | TAP-111218 | TAP-111228 | [TAP-111218_ATLAS] ¦ Create an application that leverages logging infrastructure and logs the UUID of the flash | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 64 | 59 | 64 | 76.8 | 5 | 100%
TAP-125598 | 210 | *13 |  | 04.67.01.00.00.00.00.00 |  | TAP-125598 | [TAP-125598] ¦ [v4.0][RC2][Visual] Endo software fails to set the S3D to S2D | Feature | Accepted |  |  | Parent Task | User Stories | 12.5 | 0 | 1 hr | 1 hr | 12.5 | 0%
TAP-125598_VISUAL | 211 | *210 |  | 04.67.01.01.00.00.00.00 | TAP-125598 | TAP-125369 | [TAP-125598_VISUAL] ¦ [v4.0][Visual] Fix the 2D/3D switching issue | User Story | In progress | Foundation - Visual | VISUAL | Child Task | User Stories | 12.5 | 0 | 12.5 | 15 | 12.5 | 0%
TAP-125598_DRUSHTI | 212 | *210 |  | 04.68.01.00.00.00.00.00 |  | TAP-124550 | [TAP-125598_DRUSHTI] ¦ Incorrect Scrollbar and Missing Left Graphic Line in ICG Visualization Menu on ORTI Side Panel | Issue | Open | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 22 | 0 | 22 | 26.4 | 22 | 0%
TAP-128136 | 213 | *13 |  | 04.71.02.00.00.00.00.00 |  | TAP-128136 | [TAP-128136] ¦ {v4 RC2} RAS-15283 - Radio Button Misalignment in Visualization Screen for Non-English Languages | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-128136_DRUSHTI | 214 | *213 |  | 04.71.02.01.00.00.00.00 | TAP-128136 | TAP-128138 | [TAP-128136_DRUSHTI] ¦ [RAS-15283] [v4 RC2] Fix Implementation | User Story | Open | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 5 | 0 | 5 | 6 | 5 | 0%
TAP-128136_ELECTRON | 215 | *213 |  | 04.72.01.00.00.00.00.00 |  | TAP-81556 | [TAP-128136_ELECTRON] ¦ Improve armsim: Add an Ergonomic Tab | User Story | Done | Advanced Instruments - Electron | ELECTRON | Child Task | User Stories | 5 | 0 | 5 | 6 | 5 | 100%
TAP-128136_PIXELPOETS | 216 | *213 |  | 04.72.03.00.00.00.00.00 |  | TAP-83020 | [TAP-128136_PIXELPOETS] ¦ Running ATF should run SSR only by default | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 8 | 0 | 8 | 9.6 | 8 | 100%
TAP-94626 | 217 | *1 |  | 04.72.04.00.00.00.00.00 |  | TAP-94626 | [TAP-94626] ¦ Reduce SW Verification dependency on test setup and tools - implementation | Feature | Done |  |  | Parent Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-94626_CROCNROLL | 218 | *217 |  | 04.72.04.01.00.00.00.00 | TAP-94626 | TAP-96595 | [TAP-94626_CROCNROLL] ¦ [CrocNRoll] [Spike] Identify tests that use specialized tools | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 31 | 31 | 31 | 37.2 | 0 | 100%
TAP-94626_TEAMBD | 219 | *217 |  | 04.72.04.02.00.00.00.00 | TAP-94626 | TAP-96730 | [TAP-94626_TEAMBD] ¦ [v4.0][TeamBD] Revisit testing strategy for MARYSTEIN_CLOSED_LOOP_SYSTEM Requirements | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 31 | 31 | 31 | 37.2 | 0 | 100%
TAP-94626_JACOBIANS | 220 | *217 |  | 04.72.04.04.00.00.00.00 | TAP-94626 | TAP-91861 | [TAP-94626_JACOBIANS] ¦ Create MIL test for Surgeon Engagement: Head Tracking (2/2): Implement Test | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 34 | 31 | 34 | 40.8 | 3 | 100%
TAP-94626_SCRUMBLEDORES | 221 | *217 |  | 04.72.04.08.00.00.00.00 | TAP-94626 | TAP-97643 | [TAP-94626_SCRUMBLEDORES] ¦ [v4.0][Scrumbledores][SPIKE] Identify tests that use specialized tools | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 46 | 31 | 46 | 55.2 | 15 | 100%
TAP-94626_BUGHUNTERS | 222 | *217 |  | 04.72.04.09.00.00.00.00 | TAP-94626 | TAP-99216 | [TAP-94626_BUGHUNTERS] ¦ [BH] MIL test for EIN-SSR_MSC-196 - peer review | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 46 | 31 | 46 | 55.2 | 15 | 100%
TAP-94626_HORIZON | 223 | *217 |  | 04.72.06.00.00.00.00.00 |  | TAP-122649 | [TAP-94626_HORIZON] ¦ [V&V][v4.0][Cyber][Horizon] FSE - Improve time measurement in TCs | Issue | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 51.5 | 31 | 51.5 | 61.8 | 20.5 | 100%
TAP-115657 | 224 | *11 |  | 04.72.08.00.00.00.00.00 |  | TAP-115657 | [TAP-115657] ¦ [Cyber] Tracking Documentation For Design Outputs - EIN V4.0 Testability Detailed Designs | Feature | Done |  |  | Parent Task | User Stories | 18.5 | 18.5 | 1 hr | 1 hr | 0 | 100%
TAP-115657_FRED | 225 | *224 |  | 04.72.08.01.00.00.00.00 | TAP-115657 | TAP-115658 | [TAP-115657_FRED] ¦ EIN-TESTSWI-6, 28, 29, 30, 31 RASA Joint Bridge Software Testability Design Document | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 18.5 | 18.5 | 18.5 | 22.2 | 0 | 100%
TAP-115657_VISUAL | 226 | *224 |  | 04.72.08.07.00.00.00.00 | TAP-115657 | TAP-115676 | [TAP-115657_VISUAL] ¦ [V4.0][Visual][V&V] EIN-TESTSWI-76 ENDO Software Testability Design Document | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 23.5 | 18.5 | 23.5 | 28.2 | 5 | 100%
TAP-115657_CLASSY1 | 227 | *224 |  | 04.72.08.08.00.00.00.00 | TAP-115657 | TAP-115680 | [TAP-115657_CLASSY1] ¦ [CLASSY] Review EIN-TESTSWI-68,69,70,71,72,73,74,75; EIN-TEST SWI-14,18,15; EIN-TESTSWI-19, 92 After port to the repo | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 23.5 | 18.5 | 23.5 | 28.2 | 5 | 100%
TAP-115657_BOOSTERS | 228 | *224 |  | 04.72.08.09.00.00.00.00 | TAP-115657 | TAP-115681 | [TAP-115657_BOOSTERS] ¦ [Boosters] EIN-TESTSWI-12 Logging Software Testability Design Document | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 23.5 | 18.5 | 23.5 | 28.2 | 5 | 100%
TAP-115657_STORMCHASERS1 | 229 | *224 |  | 04.72.08.10.00.00.00.00 | TAP-115657 | TAP-115682 | [TAP-115657_STORMCHASERS1] ¦ Release the SC EIN-TESTSWI-63, 20, 65, 64, 102, 62, 93 - EIN V4.0 to agile | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 23.5 | 18.5 | 23.5 | 28.2 | 5 | 100%
TAP-115657_ATLAS | 230 | *224 |  | 04.72.08.11.00.00.00.00 | TAP-115657 | TAP-115685 | [TAP-115657_ATLAS] ¦ EIN-TESTSWI-91 Disabling Windows10 Kiosk Mode Testability Design Document | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 23.5 | 18.5 | 23.5 | 28.2 | 5 | 100%
TAP-115657_PLATFORMERS | 231 | *224 |  | 04.72.08.12.00.00.00.00 | TAP-115657 | TAP-115691 | [TAP-115657_PLATFORMERS] ¦ EIN-TESTSWI-11, 103 UPS Manager SW Testability Design Document | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 23.5 | 18.5 | 23.5 | 28.2 | 5 | 100%
TAP-115657_HORIZON | 232 | *224 |  | 04.72.10.00.00.00.00.00 |  | TAP-102254 | [TAP-115657_HORIZON] ¦ [V4.0][V&V][Horizon] TRR Documents Ready for Release | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 29.5 | 18.5 | 29.5 | 35.4 | 11 | 100%
TAP-125101 | 233 | *13 |  | 04.72.12.00.00.00.00.00 |  | TAP-125101 | [TAP-125101] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - Foundation | Feature | Accepted |  |  | Parent Task | User Stories | 79 | 17 | 1 hr | 1 hr | 62 | 21.52%
TAP-125101_PLATFORMERS | 234 | *233 |  | 04.72.12.02.00.00.00.00 | TAP-125101 | TAP-125230 | [TAP-125101_PLATFORMERS] ¦ [Cyber][V4][RC2] (Placeholder) DM HIL Pre-RC2 Test Dryrun/Failure Fix | User Story | Open | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 79 | 17 | 79 | 94.8 | 62 | 21.52%
TAP-125101_VISUAL | 235 | *233 |  | 04.72.12.06.00.00.00.00 | TAP-125101 | TAP-125264 | [TAP-125101_VISUAL] ¦ [V4.0][RC2][Visual][V&V] Pre RC2 build -Dry runs | User Story | Open | Foundation - Visual | VISUAL | Child Task | User Stories | 82 | 17 | 82 | 98.4 | 65 | 20.73%
TAP-125101_FRED | 236 | *233 |  | 04.72.12.12.00.00.00.00 | TAP-125101 | TAP-123183 | [TAP-125101_FRED] ¦ [Cyber][TRR][Fred][VnV] Improve RASA TC Stability | User Story | In progress | Foundation - Fred | FRED | Child Task | User Stories | 88.5 | 17 | 88.5 | 106.2 | 71.5 | 19.21%
TAP-125101_HORIZON | 237 | *233 |  | 04.72.12.13.00.00.00.00 | TAP-125101 | TAP-123104 | [TAP-125101_HORIZON] ¦ [v4.0][Cyber][Horizon][VnV] Test Stability Improvements CTF | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 88.5 | 17 | 88.5 | 106.2 | 71.5 | 100%
TAP-125101_STORMCHASERS | 238 | *233 |  | 04.72.12.19.00.00.00.00 | TAP-125101 | TAP-125345 | [TAP-125101_STORMCHASERS] ¦ [V4][RC2][SC] pre-RC2 Final Dry Run | User Story | Open | Foundation - Storm Chasers | STORMCHASERS | Child Task | User Stories | 95.5 | 17 | 95.5 | 114.6 | 78.5 | 17.8%
TAP-125101_ATLAS | 239 | *233 |  | 04.72.12.20.00.00.00.00 | TAP-125101 | TAP-125346 | [TAP-125101_ATLAS] ¦ [V4][RC2][Atlas]pre-RC2 Dryrun and Failure Fix | User Story | Open | Foundation - Atlas | ATLAS | Child Task | User Stories | 95.5 | 17 | 95.5 | 114.6 | 78.5 | 17.8%
TAP-125101_EDISON | 240 | *233 |  | 04.72.12.23.00.00.00.00 | TAP-125101 | TAP-124900 | [TAP-125101_EDISON] ¦ [V4][RC2][TestBuild] Establish a build plan to save a copy of released test build at Artifactory folder of hugo-released-einstein-local | User Story | Open | Shared Services - Edison | EDISON | Child Task | User Stories | 105.5 | 17 | 105.5 | 126.6 | 88.5 | 16.11%
TAP-125101_ASTRANPSDEVELOPERS | 241 | *233 |  | 04.72.12.26.00.00.00.00 | TAP-125101 | TAP-125461 | [TAP-125101_ASTRANPSDEVELOPERS] ¦ [V4][RC2][TOOL] GenerateVersionTable v4.x.x fix | User Story | In progress | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 115.5 | 17 | 115.5 | 138.6 | 98.5 | 14.72%
TAP-125101_TRIPLETEA | 242 | *233 |  | 04.72.12.27.00.00.00.00 | TAP-125101 | TAP-122754 | [TAP-125101_TRIPLETEA] ¦ [TM] replace old Jira url with new JIra url | User Story | In progress | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 115.5 | 17 | 115.5 | 138.6 | 98.5 | 14.72%
TAP-125101_BOOSTERS | 243 | *233 |  | 04.72.12.29.00.00.00.00 | TAP-125101 | TAP-126036 | [TAP-125101_BOOSTERS] ¦ [Boosters] Reserve capacity | User Story | Open | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 116.5 | 17 | 116.5 | 139.8 | 99.5 | 14.59%
TAP-125101_CLASSY | 244 | *233 |  | 04.72.12.31.00.00.00.00 | TAP-125101 | TAP-126051 | [TAP-125101_CLASSY] ¦ [Classy] Re-run UDP VnV for micro-penetration fix branch | User Story | Open | Foundation - Classy | CLASSY | Child Task | User Stories | 117.5 | 17 | 117.5 | 141 | 100.5 | 14.47%
TAP-125113 | 245 | *13 |  | 04.72.13.00.00.00.00.00 |  | TAP-125113 | [TAP-125113] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - AdvancedInstr | Feature | Accepted |  |  | Parent Task | User Stories | 8.25 | 0 | 1 hr | 1 hr | 8.25 | 0%
TAP-125113_TEAMBD | 246 | *245 |  | 04.72.13.01.00.00.00.00 | TAP-125113 | TAP-125449 | [TAP-125113_TEAMBD] ¦ [V4.0][RC2][V&V][TeamBD] Placeholder for Pre-RC2 Activities | User Story | Open | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 8.25 | 0 | 8.25 | 9.9 | 8.25 | 0%
TAP-125113_ROMULUS | 247 | *245 |  | 04.72.13.02.00.00.00.00 | TAP-125113 | TAP-126000 | [TAP-125113_ROMULUS] ¦ [V4.0][RC2][V&V][Romulus] Placeholder for Pre-RC2 Activities | User Story | Open | Advanced Instruments - Romulus | ROMULUS | Child Task | User Stories | 8.25 | 0 | 8.25 | 9.9 | 8.25 | 0%
TAP-125113_REMUS | 248 | *245 |  | 04.72.13.03.00.00.00.00 | TAP-125113 | TAP-126001 | [TAP-125113_REMUS] ¦ [V4.0][RC2][V&V][Remus] Placeholder for Pre-RC2 Activities | User Story | Open | Advanced Instruments - Remus | REMUS | Child Task | User Stories | 8.25 | 0 | 8.25 | 9.9 | 8.25 | 0%
TAP-125114 | 249 | *13 |  | 04.72.14.00.00.00.00.00 |  | TAP-125114 | [TAP-125114] ¦ [V4.0][RC2][Cyber][V&V] Pre-RC2 Test Dryrun/Failure Fix and Test Environment Preparation - CoreInstr | Feature | Accepted |  |  | Parent Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 0%
TAP-125114_SIRIUS | 250 | *249 |  | 04.72.14.01.00.00.00.00 | TAP-125114 | TAP-126150 | [TAP-125114_SIRIUS] ¦ [v4.0 RC2][Sirius] PLACEHOLDER Update EIN-TC_SW-XXXX | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-125114_PUPPETEERS | 251 | *249 |  | 04.72.14.02.00.00.00.00 | TAP-125114 | TAP-126305 | [TAP-125114_PUPPETEERS] ¦ [v4.0 RC2][Puppeteers] PLACEHOLDER Update EIN-TC_SW-XXXX | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-125114_STORMCHASERS | 252 | *249 |  | 04.72.16.00.00.00.00.00 |  | TAP-127952 | [TAP-125114_STORMCHASERS] ¦ [V4][RC1 Formal] Connection issues for several SC BPs | Issue | In progress | Foundation - Storm Chasers | STORMCHASERS | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-95509 | 253 | *1 |  | 05.01.00.00.00.00.00.00 |  | TAP-95509 | [TAP-95509] ¦ [IDP] Generate Doxygen documentation for every mainline. | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-95509_EDISON | 254 | *253 |  | 05.01.01.00.00.00.00.00 | TAP-95509 | TAP-96142 | [TAP-95509_EDISON] ¦ [IDP] Generate Doxygen documentation for every mainline. | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-103380 | 255 | *5 |  | 05.02.00.00.00.00.00.00 |  | TAP-103380 | [TAP-103380] ¦ [IDP][Enabler] CMake clean-up | Feature | Done |  |  | Parent Task | User Stories | 18.5 | 18.5 | 1 hr | 1 hr | 0 | 100%
TAP-103380_EDISON | 256 | *255 |  | 05.02.01.00.00.00.00.00 | TAP-103380 | TAP-97795 | [TAP-103380_EDISON] ¦ Reformat CMake files | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 18.5 | 18.5 | 18.5 | 22.2 | 0 | 100%
TAP-103380_SEAMLESS | 257 | *255 |  | 05.02.11.00.00.00.00.00 | TAP-103380 | TAP-108521 | [TAP-103380_SEAMLESS] ¦ IDU Fixture packaging | Issue | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 30.5 | 18.5 | 30.5 | 36.6 | 12 | 100%
TAP-102422 | 258 | *9 |  | 05.03.00.00.00.00.00.00 |  | TAP-102422 | [TAP-102422] ¦ [IDP][Foundation] Support integration of the design documents into the code repository | Feature | Done |  |  | Parent Task | User Stories | 17.2 | 17.2 | 1 hr | 1 hr | 0 | 100%
TAP-102422_FRED | 259 | *258 |  | 05.03.01.00.00.00.00.00 | TAP-102422 | TAP-106337 | [TAP-102422_FRED] ¦ Copy design documents to code repository | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_CLASSY1 | 260 | *258 |  | 05.03.02.00.00.00.00.00 | TAP-102422 | TAP-106536 | [TAP-102422_CLASSY1] ¦ [CLASSY1] Copy design documents to sharepoint repository | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_BART | 261 | *258 |  | 05.03.03.00.00.00.00.00 | TAP-102422 | TAP-106525 | [TAP-102422_BART] ¦ [v4.0][Cyber] Update PS-PL Interface document for RASA/IDU | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_STORMCHASERS2 | 262 | *258 |  | 05.03.04.00.00.00.00.00 | TAP-102422 | TAP-106598 | [TAP-102422_STORMCHASERS2] ¦ [SC2] Support integration of the design documents into the code repository | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_STORMCHASERS1 | 263 | *258 |  | 05.03.05.00.00.00.00.00 | TAP-102422 | TAP-106750 | [TAP-102422_STORMCHASERS1] ¦ [SC1] Support integration of the design documents into the code repository | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_EDISON | 264 | *258 |  | 05.03.06.00.00.00.00.00 | TAP-102422 | TAP-106787 | [TAP-102422_EDISON] ¦ Test md format | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_HORIZON | 265 | *258 |  | 05.03.07.00.00.00.00.00 | TAP-102422 | TAP-106897 | [TAP-102422_HORIZON] ¦ Copy design documents to code repository | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_CLASSY2 | 266 | *258 |  | 05.03.08.00.00.00.00.00 | TAP-102422 | TAP-106911 | [TAP-102422_CLASSY2] ¦ [CLASSY2] Copy design documents to sharepoint repository | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_BOOSTERS | 267 | *258 |  | 05.03.09.00.00.00.00.00 | TAP-102422 | TAP-106932 | [TAP-102422_BOOSTERS] ¦ [Boosters] Copy design document to shared are | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-102422_VISUAL | 268 | *258 |  | 05.03.10.00.00.00.00.00 | TAP-102422 | TAP-106935 | [TAP-102422_VISUAL] ¦ [v4.0][visual] Copy design documents to sharepoint repository | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 17.2 | 17.2 | 17.2 | 20.64 | 0 | 100%
TAP-95500 | 269 | *1 |  | 05.04.00.00.00.00.00.00 |  | TAP-95500 | [TAP-95500] ¦ [IDP] Use Code Change Impact Analysis Tool in Production | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-95500_EDISON | 270 | *269 |  | 05.04.01.00.00.00.00.00 | TAP-95500 | TAP-96143 | [TAP-95500_EDISON] ¦ Add impacted SWIs to the PR Merge Advisor | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-95095 | 271 | *1 |  | 05.05.00.00.00.00.00.00 |  | TAP-95095 | [TAP-95095] ¦ [Tech Debt] PI12 - Improve Unit Tests (Foundation) | Feature | Done |  |  | Parent Task | User Stories | 30 | 30 | 1 hr | 1 hr | 0 | 100%
TAP-95095_CLASSY2 | 272 | *271 |  | 05.05.01.00.00.00.00.00 | TAP-95095 | TAP-94518 | [TAP-95095_CLASSY2] ¦ Automated Unit Test Failure Report: test_error_bridge failed | Issue | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 30 | 30 | 30 | 36 | 0 | 100%
TAP-95095_ATLAS | 273 | *271 |  | 05.05.02.00.00.00.00.00 | TAP-95095 | TAP-93137 | [TAP-95095_ATLAS] ¦ Automated Unit Test Failure Report: test_library_os_wrapper_ipc failed | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 30 | 30 | 30 | 36 | 0 | 100%
TAP-95095_FRED | 274 | *271 |  | 05.05.05.00.00.00.00.00 | TAP-95095 | TAP-93361 | [TAP-95095_FRED] ¦ Automated Unit Test Failure Report: test_library_zynq_SensorUnitTest failed: Disable | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 32 | 30 | 32 | 38.4 | 2 | 100%
TAP-95095_PLATFORMERS | 275 | *271 |  | 05.05.07.00.00.00.00.00 | TAP-95095 | TAP-97700 | [TAP-95095_PLATFORMERS] ¦ [V4][Platformers] Disable intermittent unit tests | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 32 | 30 | 32 | 38.4 | 2 | 100%
TAP-95095_STORMCHASERS2 | 276 | *271 |  | 05.05.08.00.00.00.00.00 | TAP-95095 | TAP-97781 | [TAP-95095_STORMCHASERS2] ¦ [V4.0][SC2] Investigate and disable (if possible) bad SC unit tests | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 32 | 30 | 32 | 38.4 | 2 | 100%
TAP-95095_CLASSY1 | 277 | *271 |  | 05.05.09.00.00.00.00.00 | TAP-95095 | TAP-92787 | [TAP-95095_CLASSY1] ¦ Automated Unit Test Failure Report: test_dds_communication failed | Issue | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 32 | 30 | 32 | 38.4 | 2 | 100%
TAP-95095_BOOSTERS | 278 | *271 |  | 05.05.11.00.00.00.00.00 | TAP-95095 | TAP-97913 | [TAP-95095_BOOSTERS] ¦ [Boosters] Disable test_library_log_process_RelayStorageUnitTest unit test | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 32.5 | 30 | 32.5 | 39 | 2.5 | 100%
TAP-95095_VISUAL | 279 | *271 |  | 05.05.12.00.00.00.00.00 | TAP-95095 | TAP-101927 | [TAP-95095_VISUAL] ¦ [v4.0] [Visual] Extend ks-hive-client functionality | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 32.5 | 30 | 32.5 | 39 | 2.5 | 100%
TAP-95095_SCRUMBLEDORES | 280 | *271 |  | 05.05.16.00.00.00.00.00 | TAP-95095 | TAP-101612 | [TAP-95095_SCRUMBLEDORES] ¦ [Scrumbledores][Tech Debt] Ring Buffer Unit Test Update | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 40 | 30 | 40 | 48 | 10 | 100%
TAP-73233 | 281 | *3 |  | 05.06.00.00.00.00.00.00 |  | TAP-73233 | [TAP-73233] ¦ [Architecture][Infrastructure] Improve KPI collection and processing software | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-73233_BOOSTERS | 282 | *281 |  | 05.06.01.00.00.00.00.00 | TAP-73233 | TAP-48215 | [TAP-73233_BOOSTERS] ¦ System state in KPI report | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-87661 | 283 | *1 |  | 05.07.00.00.00.00.00.00 |  | TAP-87661 | [TAP-87661] ¦ [V&V Enabler] SW Verification - Improvements Batch2 - Foundation | Feature | Done |  |  | Parent Task | User Stories | 9.5 | 9.5 | 1 hr | 1 hr | 0 | 100%
TAP-87661_VISUAL | 284 | *283 |  | 05.07.01.00.00.00.00.00 | TAP-87661 | TAP-94525 | [TAP-87661_VISUAL] ¦ [v2.2] [Visual] Migration of v2.2 TDs from Jama to git | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 9.5 | 9.5 | 9.5 | 11.4 | 0 | 100%
TAP-55705 | 285 | *1 |  | 05.08.00.00.00.00.00.00 |  | TAP-55705 | [TAP-55705] ¦ Refactor logging library | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-55705_HORIZON | 286 | *285 |  | 05.08.01.00.00.00.00.00 | TAP-55705 | TAP-46624 | [TAP-55705_HORIZON] ¦ Refactor einsting::log::process::LogProcessBase | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-55705_BOOSTERS | 287 | *285 |  | 05.08.02.00.00.00.00.00 | TAP-55705 | TAP-47255 | [TAP-55705_BOOSTERS] ¦ [Boosters] Investigate effect of detaching thread in Event Logging Client | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-55471 | 288 | *1 |  | 05.09.00.00.00.00.00.00 |  | TAP-55471 | [TAP-55471] ¦ [V4.0] Keep alarms, errors, safety, communication SW verification tests up to date | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-55471_CLASSY1 | 289 | *288 |  | 05.09.01.00.00.00.00.00 | TAP-55471 | TAP-55573 | [TAP-55471_CLASSY1] ¦ Merge the staging branch into the 4.0 tests master (develop-next) | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-117503 | 290 | *9 |  | 05.10.00.00.00.00.00.00 |  | TAP-117503 | [TAP-117503] ¦ [Shared Services] [v4.0] sFMEA update and review | Feature | Done |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-117503_REFRACT | 291 | *290 |  | 05.10.01.00.00.00.00.00 | TAP-117503 | TAP-115792 | [TAP-117503_REFRACT] ¦ [V4.0][Refract] Review all FMs for ISIM Subsystem | User Story | Done | Shared Services - Refract | REFRACT | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-83615 | 292 | *1 |  | 05.11.00.00.00.00.00.00 |  | TAP-83615 | [TAP-83615] ¦ [Architecture][Enabler] GECAT for Instruments Data Transportation - Foundation Support | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-83615_FRED | 293 | *292 |  | 05.11.01.00.00.00.00.00 | TAP-83615 | TAP-85763 | [TAP-83615_FRED] ¦ Add 50 extra bytes to IDU cyclic dictionaries | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-82932 | 294 | *1 |  | 05.12.00.00.00.00.00.00 |  | TAP-82932 | [TAP-82932] ¦ [V4.0] Stability issue investigation and resolution - PI11 | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-82932_FRED | 295 | *294 |  | 05.12.01.00.00.00.00.00 | TAP-82932 | TAP-59958 | [TAP-82932_FRED] ¦ [v4] TPSC subsystem process dies after 1 hour. | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-82932_BOOSTERS | 296 | *294 |  | 05.12.03.00.00.00.00.00 | TAP-82932 | TAP-77873 | [TAP-82932_BOOSTERS] ¦ [Tools] High CPU during KPI collection | Issue | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 14 | 11 | 14 | 16.8 | 3 | 100%
TAP-93110 | 297 | *1 |  | 05.13.00.00.00.00.00.00 |  | TAP-93110 | [TAP-93110] ¦ [V4.0][Architecture] Improve SW Virtualization Platform | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-93110_SLEEPWALKERS | 298 | *297 |  | 05.13.01.00.00.00.00.00 | TAP-93110 | TAP-87025 | [TAP-93110_SLEEPWALKERS] ¦ [VMs]Writing python script to download vm images [Einstein Replicator] artifacts from artifactory | User Story | Done | Shared Services - Sleepwalkers | SLEEPWALKERS | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-86330 | 299 | *1 |  | 05.14.00.00.00.00.00.00 |  | TAP-86330 | [TAP-86330] ¦ [v4.0](TAP-66316) Add SMC data recorder bfbs schema file to SMC Application package | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-86330_ICONICS | 300 | *299 |  | 05.14.01.00.00.00.00.00 | TAP-86330 | TAP-66316 | [TAP-86330_ICONICS] ¦ SMC data recorder bfbs not packaged | Issue | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-83225 | 301 | *1 |  | 05.15.00.00.00.00.00.00 |  | TAP-83225 | [TAP-83225] ¦ [v4.0] Expanding ENDOSW tests to perform integration testing with GUI | Feature | Done |  |  | Parent Task | User Stories | 19 | 19 | 1 hr | 1 hr | 0 | 100%
TAP-83225_VISUAL | 302 | *301 |  | 05.15.01.00.00.00.00.00 | TAP-83225 | TAP-84608 | [TAP-83225_VISUAL] ¦ [Visual] [Spike] Identify interactions with GUI to create additional test designs | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 19 | 19 | 19 | 22.8 | 0 | 100%
TAP-70472 | 303 | *1 |  | 05.16.00.00.00.00.00.00 |  | TAP-70472 | [TAP-70472] ¦ [V4.0] Implement EDID based detection of S3D and use Intel UHD graphics driver for SCDC Windows installation | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-70472_ATLAS | 304 | *303 |  | 05.16.01.00.00.00.00.00 | TAP-70472 | TAP-87645 | [TAP-70472_ATLAS] ¦ Update Documentation to Add Intel 6th generation graphics driver | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-70472_SOUPERTROOPERS | 305 | *303 |  | 05.16.03.00.00.00.00.00 | TAP-70472 | TAP-74887 | [TAP-70472_SOUPERTROOPERS] ¦ Windows display driver SOUP | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 10 | 7 | 10 | 12 | 3 | 100%
TAP-16423 | 306 | *1 |  | 05.17.00.00.00.00.00.00 |  | TAP-16423 | [TAP-16423] ¦ [Infra] SW Integration Framework Prototype | Feature | Done |  |  | Parent Task | User Stories | 139 | 139 | 1 hr | 1 hr | 0 | 100%
TAP-16423_SLEEPWALKERS | 307 | *306 |  | 05.17.01.00.00.00.00.00 | TAP-16423 | TAP-19180 | [TAP-16423_SLEEPWALKERS] ¦ [Spike] Investigate possibilities to scale up CAH - Storz test case | User Story | Done | Shared Services - Sleepwalkers | SLEEPWALKERS | Child Task | User Stories | 139 | 139 | 139 | 166.8 | 0 | 100%
TAP-2693 | 308 | *1 |  | 05.18.00.00.00.00.00.00 |  | TAP-2693 | [TAP-2693] ¦ [Tech Debt][platformers][V&V] test infrastructure improvements Batch 1 | Feature | Done |  |  | Parent Task | User Stories | 26 | 26 | 1 hr | 1 hr | 0 | 100%
TAP-2693_PLATFORMERS | 309 | *308 |  | 05.18.01.00.00.00.00.00 | TAP-2693 | TAP-46130 | [TAP-2693_PLATFORMERS] ¦ [Arch][Enabler][Platformers][V&V] Investigate the ability to run test cases in debug mode on CI | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 26 | 26 | 26 | 31.2 | 0 | 100%
TAP-6886 | 310 | *1 |  | 05.19.00.00.00.00.00.00 |  | TAP-6886 | [TAP-6886] ¦ [Compliance] Establish Controlled Process for log data specification in JAMA | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-6886_CASTLEBLACK | 311 | *310 |  | 05.19.01.00.00.00.00.00 | TAP-6886 | TAP-47406 | [TAP-6886_CASTLEBLACK] ¦ [Spike] Draft Process for log data specification | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-6886_BOOSTERS | 312 | *310 |  | 05.19.03.00.00.00.00.00 | TAP-6886 | TAP-57042 | [TAP-6886_BOOSTERS] ¦ [Boosters] Tool for Event Log localization | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 9 | 8 | 9 | 10.8 | 1 | 100%
TAP-115484 | 313 | *7 |  | 05.20.00.00.00.00.00.00 |  | TAP-115484 | [TAP-115484] ¦ QNX 7.1 BSP for FSE test fixture | Feature | Done |  |  | Parent Task | User Stories | 4.1 | 4.1 | 1 hr | 1 hr | 0 | 100%
TAP-115484_BUILDERS | 314 | *313 |  | 05.20.01.00.00.00.00.00 | TAP-115484 | TAP-115516 | [TAP-115484_BUILDERS] ¦ [Spike] Determine need for new BSP support for test fixture. | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 4.1 | 4.1 | 4.1 | 4.92 | 0 | 100%
TAP-64261 | 315 | *7 |  | 05.21.00.00.00.00.00.00 |  | TAP-64261 | [TAP-64261] ¦ [v4.0 SW][Arch][Enabler] Improve Unit Tests (Foundation) | Feature | Done |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-64261_CLASSY1 | 316 | *315 |  | 05.21.01.00.00.00.00.00 | TAP-64261 | TAP-55803 | [TAP-64261_CLASSY1] ¦ [Spike] Analyze coverage and identify unit test improvements | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-76479 | 317 | *1 |  | 05.22.00.00.00.00.00.00 |  | TAP-76479 | [TAP-76479] ¦ [Architecture][Spike] Future Software Item Breakdown - Align SWI, Repository, and Requirements - PI12 | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-76479_BOOSTERS | 318 | *317 |  | 05.22.01.00.00.00.00.00 | TAP-76479 | TAP-74576 | [TAP-76479_BOOSTERS] ¦ [Boosters] Merge directory restructuring staging branch into develop | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-76479_VISUAL | 319 | *317 |  | 05.22.02.00.00.00.00.00 | TAP-76479 | TAP-56997 | [TAP-76479_VISUAL] ¦ [Visual] [v4.0] Refactor ENDOSW Software items | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-76479_FRED | 320 | *317 |  | 05.22.05.00.00.00.00.00 | TAP-76479 | TAP-87037 | [TAP-76479_FRED] ¦ Revise EtherCAT requirements in Product Security JAMA project | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 19 | 15 | 19 | 22.8 | 4 | 100%
TAP-48935 | 321 | *1 |  | 05.23.00.00.00.00.00.00 |  | TAP-48935 | [TAP-48935] ¦ [TechDebt]Refactor EtherCAT communication | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-48935_FRED | 322 | *321 |  | 05.23.01.00.00.00.00.00 | TAP-48935 | TAP-37274 | [TAP-48935_FRED] ¦ Automate EtherCAT ENI file creation | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-48935_EDISON | 323 | *321 |  | 05.23.03.00.00.00.00.00 | TAP-48935 | TAP-51370 | [TAP-48935_EDISON] ¦ Update Acontis EC Master to 3.1.4.05 for v4 | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 21 | 16 | 21 | 25.2 | 5 | 100%
TAP-47057 | 324 | *1 |  | 05.24.00.00.00.00.00.00 |  | TAP-47057 | [TAP-47057] ¦ [Tech Debt] Integrate log_clock into product | Feature | Done |  |  | Parent Task | User Stories | 49 | 49 | 1 hr | 1 hr | 0 | 100%
TAP-47057_BOOSTERS | 325 | *324 |  | 05.24.01.00.00.00.00.00 | TAP-47057 | TAP-47471 | [TAP-47057_BOOSTERS] ¦ [Boosters] Integrate log_clock process into the logging subsystem | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 49 | 49 | 49 | 58.8 | 0 | 100%
TAP-47057_COSSACKS | 326 | *324 |  | 05.24.13.00.00.00.00.00 | TAP-47057 | TAP-49439 | [TAP-47057_COSSACKS] ¦ [CI] Create Log Clock build plan | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 89 | 49 | 89 | 106.8 | 40 | 100%
TAP-83342 | 327 | *1 |  | 05.25.00.00.00.00.00.00 |  | TAP-83342 | [TAP-83342] ¦ ESAT v2 Stability and Usability Enhancements | Feature | Done |  |  | Parent Task | User Stories | 130 | 130 | 1 hr | 1 hr | 0 | 100%
TAP-83342_TOOLSRULES | 328 | *327 |  | 05.25.01.00.00.00.00.00 | TAP-83342 | TAP-83330 | [TAP-83342_TOOLSRULES] ¦ Periodic messages in AOP logger should be reduced in esat worker v2, when using npm run start | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 130 | 130 | 130 | 156 | 0 | 100%
TAP-83342_ASTRANPSDEVELOPERS | 329 | *327 |  | 05.25.02.00.00.00.00.00 | TAP-83342 | TAP-83261 | [TAP-83342_ASTRANPSDEVELOPERS] ¦ Replace all console logs with logger statements, or remove them if moot (ESAT V2 JS worker) | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 130 | 130 | 130 | 156 | 0 | 100%
TAP-83342_ATLAS | 330 | *327 |  | 05.25.40.00.00.00.00.00 | TAP-83342 | TAP-99844 | [TAP-83342_ATLAS] ¦ Investigate ESAT v2 Windows DLLs loaded | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 257 | 130 | 257 | 308.4 | 127 | 100%
TAP-71137 | 331 | *1 |  | 05.26.00.00.00.00.00.00 |  | TAP-71137 | [TAP-71137] ¦ [v4.0] GUI codebase cleanup | Feature | Done |  |  | Parent Task | User Stories | 14 | 14 | 1 hr | 1 hr | 0 | 100%
TAP-71137_DRUSHTI | 332 | *331 |  | 05.26.01.00.00.00.00.00 | TAP-71137 | TAP-55405 | [TAP-71137_DRUSHTI] ¦ Remove unused GUI related library files | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 14 | 14 | 14 | 16.8 | 0 | 100%
TAP-71137_ELECTRON | 333 | *331 |  | 05.26.02.00.00.00.00.00 | TAP-71137 | TAP-76045 | [TAP-71137_ELECTRON] ¦ GUI codebase cleanup -qml errors | User Story | Done | Advanced Instruments - Electron | ELECTRON | Child Task | User Stories | 14 | 14 | 14 | 16.8 | 0 | 100%
TAP-71137_EDISON | 334 | *331 |  | 05.26.03.00.00.00.00.00 | TAP-71137 | TAP-87054 | [TAP-71137_EDISON] ¦ Need support for rebuilding Qt 5.15 libraries | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 14 | 14 | 14 | 16.8 | 0 | 100%
TAP-99176 | 335 | *7 |  | 05.27.00.00.00.00.00.00 |  | TAP-99176 | [TAP-99176] ¦ Update Failing Tests and Static Analysis | Feature | Done |  |  | Parent Task | User Stories | 95 | 95 | 1 hr | 1 hr | 0 | 100%
TAP-99176_JACOBIANS | 336 | *335 |  | 05.27.01.00.00.00.00.00 | TAP-99176 | TAP-105052 | [TAP-99176_JACOBIANS] ¦ [Jacobians] Review Static Analysis - Camera Control | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 95 | 95 | 95 | 114 | 0 | 100%
TAP-99176_ORGANELLES | 337 | *335 |  | 05.27.02.00.00.00.00.00 | TAP-99176 | TAP-105311 | [TAP-99176_ORGANELLES] ¦ Automatically add MSO only Framework job to Simulink PRs | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 95 | 95 | 95 | 114 | 0 | 100%
TAP-99176_SCRUMBLEDORES | 338 | *335 |  | 05.27.04.00.00.00.00.00 | TAP-99176 | TAP-105050 | [TAP-99176_SCRUMBLEDORES] ¦ [Scrumbledores][MIL] Fix EIN-TC_SW-3568 MIL test | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 97 | 95 | 97 | 116.4 | 2 | 100%
TAP-99176_TEAMBD | 339 | *335 |  | 05.27.07.00.00.00.00.00 | TAP-99176 | TAP-105504 | [TAP-99176_TEAMBD] ¦ [v4.0][TeamBD] Fix UNIT_MrystnCalibrateHardstopJaw unit test | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 104 | 95 | 104 | 124.8 | 9 | 100%
TAP-99176_BUGHUNTERS | 340 | *335 |  | 05.27.16.00.00.00.00.00 | TAP-99176 | TAP-105152 | [TAP-99176_BUGHUNTERS] ¦ [BH] Implement - failure response and other MIL tests execution in parallel mode | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 108.5 | 95 | 108.5 | 130.2 | 13.5 | 100%
TAP-99176_CROCNROLL | 341 | *335 |  | 05.27.17.00.00.00.00.00 | TAP-99176 | TAP-106062 | [TAP-99176_CROCNROLL] ¦ [v4.0][CrocNRoll] Update MIL test EIN-TC_SW_2538 failing on Simulink Test Framework | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 108.5 | 95 | 108.5 | 130.2 | 13.5 | 100%
TAP-99176_SIRIUS | 342 | *335 |  | 05.27.18.00.00.00.00.00 | TAP-99176 | TAP-106063 | [TAP-99176_SIRIUS] ¦ [v4.0][Sirius] Update MIL test EIN-TC_SW_3730 failing on Simulink Test Framework | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 108.5 | 95 | 108.5 | 130.2 | 13.5 | 100%
TAP-99176_I2E | 343 | *335 |  | 05.27.19.00.00.00.00.00 | TAP-99176 | TAP-106107 | [TAP-99176_I2E] ¦ [v4.0][I2E] Fix coverity static analysis errors for EIN-SWI-168 | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 108.5 | 95 | 108.5 | 130.2 | 13.5 | 100%
TAP-99176_PIXELPOETS | 344 | *335 |  | 05.27.21.00.00.00.00.00 | TAP-99176 | TAP-106112 | [TAP-99176_PIXELPOETS] ¦ [V3.0][PixelPoets] Review Static Analysis | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 111.5 | 95 | 111.5 | 133.8 | 16.5 | 100%
TAP-99176_SUNRISERS | 345 | *335 |  | 05.27.36.00.00.00.00.00 | TAP-99176 | TAP-110520 | [TAP-99176_SUNRISERS] ¦ [V4.0][Sunrisers] Support BH - Simulink test framework change review during parallel mode [RASA unit tests] | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 152.5 | 95 | 152.5 | 183 | 57.5 | 100%
TAP-95508 | 346 | *7 |  | 05.28.00.00.00.00.00.00 |  | TAP-95508 | [TAP-95508] ¦ [IDP] Improve build system - Batch 1 | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-95508_EDISON | 347 | *346 |  | 05.28.01.00.00.00.00.00 | TAP-95508 | TAP-100854 | [TAP-95508_EDISON] ¦ Cleanup Simulink plan create rules and update instance types | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-95505 | 348 | *1 |  | 05.29.00.00.00.00.00.00 |  | TAP-95505 | [TAP-95505] ¦ [IDP] Support Unit Verification Process Improvement - Batch 1 | Feature | Done |  |  | Parent Task | User Stories | 19 | 19 | 1 hr | 1 hr | 0 | 100%
TAP-95505_EDISON | 349 | *348 |  | 05.29.01.00.00.00.00.00 | TAP-95505 | TAP-96428 | [TAP-95505_EDISON] ¦ CompilerFlags: Export compiler flags | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 19 | 19 | 19 | 22.8 | 0 | 100%
TAP-95505_ASTRANPSDEVELOPERS | 350 | *348 |  | 05.29.04.00.00.00.00.00 | TAP-95505 | TAP-96820 | [TAP-95505_ASTRANPSDEVELOPERS] ¦ Automate the Manual activities performed to Generate code review report artifacts | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 22 | 19 | 22 | 26.4 | 3 | 100%
TAP-72843 | 351 | *1 |  | 05.30.00.00.00.00.00.00 |  | TAP-72843 | [TAP-72843] ¦ Support collapse of develop-next back to develop | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-72843_SIRIUS | 352 | *351 |  | 05.30.01.00.00.00.00.00 | TAP-72843 | TAP-73803 | [TAP-72843_SIRIUS] ¦ [v4.0] [Sirius] Support Develop/Develop Next Code Merge | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-72843_I2E | 353 | *351 |  | 05.30.02.00.00.00.00.00 | TAP-72843 | TAP-74139 | [TAP-72843_I2E] ¦ [v4.0][I2E] Support Develop/Develop-next collapse | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-72843_ELECTRON | 354 | *351 |  | 05.30.03.00.00.00.00.00 | TAP-72843 | TAP-74426 | [TAP-72843_ELECTRON] ¦ [4.0] GUI support for develop becoming 4.0 | User Story | Done | Advanced Instruments - Electron | ELECTRON | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-70775 | 355 | *1 |  | 05.31.00.00.00.00.00.00 |  | TAP-70775 | [TAP-70775] ¦ [Infrastructure] Setup Minimal Simulink Projects for Impact Analysis Verification | Feature | Done |  |  | Parent Task | User Stories | 24 | 24 | 1 hr | 1 hr | 0 | 100%
TAP-70775_ORGANELLES | 356 | *355 |  | 05.31.01.00.00.00.00.00 | TAP-70775 | TAP-87102 | [TAP-70775_ORGANELLES] ¦ [Infrastructure] Create Simulink Project template using sim_controller | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-54303 | 357 | *1 |  | 05.32.00.00.00.00.00.00 |  | TAP-54303 | [TAP-54303] ¦ [Architecture][Spike] Future Software Item Breakdown - Align SWI, Repository, and Requirements | Feature | Done |  |  | Parent Task | User Stories | 57.9 | 57.9 | 1 hr | 1 hr | 0 | 100%
TAP-54303_BOOSTERS | 358 | *357 |  | 05.32.01.00.00.00.00.00 | TAP-54303 | TAP-55294 | [TAP-54303_BOOSTERS] ¦ [Boosters] Review and refactor Logging, KPI, Data Access and Data Recorder Software items | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 57.9 | 57.9 | 57.9 | 69.48 | 0 | 100%
TAP-54303_FRED | 359 | *357 |  | 05.32.05.00.00.00.00.00 | TAP-54303 | TAP-55874 | [TAP-54303_FRED] ¦ Review software item breakdown and requirements for Freds software items | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 71.9 | 57.9 | 71.9 | 86.28 | 14 | 100%
TAP-54303_STORMCHASERS2 | 360 | *357 |  | 05.32.06.00.00.00.00.00 | TAP-54303 | TAP-56357 | [TAP-54303_STORMCHASERS2] ¦ [StormChasers2] Future Software Item Breakdown - Investigate current SWI structure and create plan | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 71.9 | 57.9 | 71.9 | 86.28 | 14 | 100%
TAP-54303_CASTLEBLACK | 361 | *357 |  | 05.32.07.00.00.00.00.00 | TAP-54303 | TAP-56202 | [TAP-54303_CASTLEBLACK] ¦ [Compliance] Update Repository Structure Guideline | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 71.9 | 57.9 | 71.9 | 86.28 | 14 | 100%
TAP-54303_ATLAS | 362 | *357 |  | 05.32.09.00.00.00.00.00 | TAP-54303 | TAP-56774 | [TAP-54303_ATLAS] ¦ [Enabler] Discussion of current Atlas SWIs and Possible change to software items | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 81.9 | 57.9 | 81.9 | 98.28 | 24 | 100%
TAP-54303_VISUAL | 363 | *357 |  | 05.32.10.00.00.00.00.00 | TAP-54303 | TAP-56998 | [TAP-54303_VISUAL] ¦ [Visual][Spike] Investigate refactoring ENDOSW directory structure | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 81.9 | 57.9 | 81.9 | 98.28 | 24 | 100%
TAP-54303_HORIZON | 364 | *357 |  | 05.32.11.00.00.00.00.00 | TAP-54303 | TAP-57556 | [TAP-54303_HORIZON] ¦ [Architecture][Spike] Future Software Item Breakdown: Review SW Item proposal | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 81.9 | 57.9 | 81.9 | 98.28 | 24 | 100%
TAP-85444 | 365 | *1 |  | 05.33.00.00.00.00.00.00 |  | TAP-85444 | [TAP-85444] ¦ [V4.0][Visual] Tests and development process improvements after the new codebase merge | Feature | Done |  |  | Parent Task | User Stories | 23.5 | 23.5 | 1 hr | 1 hr | 0 | 100%
TAP-85444_VISUAL | 366 | *365 |  | 05.33.01.00.00.00.00.00 | TAP-85444 | TAP-85417 | [TAP-85444_VISUAL] ¦ [Visual] [v4.0] EndoLogger functionality extension | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 23.5 | 23.5 | 23.5 | 28.2 | 0 | 100%
TAP-81827 | 367 | *1 |  | 05.34.00.00.00.00.00.00 |  | TAP-81827 | [TAP-81827] ¦ [Infrastructure] Reduce Simulink Verification Runtime | Feature | Done |  |  | Parent Task | User Stories | 53.5 | 53.5 | 1 hr | 1 hr | 0 | 100%
TAP-81827_ORGANELLES | 368 | *367 |  | 05.34.01.00.00.00.00.00 | TAP-81827 | TAP-44795 | [TAP-81827_ORGANELLES] ¦ [Organelles][Infrastructure] Generate subsystem build metric report as part of test framework | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 53.5 | 53.5 | 53.5 | 64.2 | 0 | 100%
TAP-81827_SIRIUS | 369 | *367 |  | 05.34.03.00.00.00.00.00 | TAP-81827 | TAP-85202 | [TAP-81827_SIRIUS] ¦ [Infrastructure][Sirius] Reduce runtime for IDU controller tests | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 55.5 | 53.5 | 55.5 | 66.6 | 2 | 100%
TAP-81827_JACOBIANS | 370 | *367 |  | 05.34.08.00.00.00.00.00 | TAP-81827 | TAP-90284 | [TAP-81827_JACOBIANS] ¦ [Jacobians] Add Assessments to UNIT_SingleHandleFiltering Tests | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 70.5 | 53.5 | 70.5 | 84.6 | 17 | 100%
TAP-66620 | 371 | *1 |  | 05.35.00.00.00.00.00.00 |  | TAP-66620 | [TAP-66620] ¦ [Tech Debt] Remove Testability Branch for Simulink Tools | Feature | Done |  |  | Parent Task | User Stories | 53 | 53 | 1 hr | 1 hr | 0 | 100%
TAP-66620_REFLECT | 372 | *371 |  | 05.35.01.00.00.00.00.00 | TAP-66620 | TAP-68125 | [TAP-66620_REFLECT] ¦ Integrate Idu Error Injector Into IDU Controller | User Story | Done | Advanced Instruments - Reflect | REFLECT | Child Task | User Stories | 53 | 53 | 53 | 63.6 | 0 | 100%
TAP-66620_INBETWEENERS | 373 | *371 |  | 05.35.09.00.00.00.00.00 | TAP-66620 | TAP-68133 | [TAP-66620_INBETWEENERS] ¦ Unit Verification for New Error Injector SWIs | User Story | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 69 | 53 | 69 | 82.8 | 16 | 100%
TAP-97622 | 374 | *7 |  | 05.36.00.00.00.00.00.00 |  | TAP-97622 | [TAP-97622] ¦ [V4.0][Tech Debt] Fix Unit Verification (Foundation) | Feature | Done |  |  | Parent Task | User Stories | 72 | 72 | 1 hr | 1 hr | 0 | 100%
TAP-97622_FRED | 375 | *374 |  | 05.36.01.00.00.00.00.00 | TAP-97622 | TAP-97666 | [TAP-97622_FRED] ¦ Fix unit test: Automated Unit Test Failure Report: test_library_zynq_SensorUnitTest failed | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 72 | 72 | 72 | 86.4 | 0 | 100%
TAP-97622_ATLAS | 376 | *374 |  | 05.36.02.00.00.00.00.00 | TAP-97622 | TAP-90298 | [TAP-97622_ATLAS] ¦ Automated Unit Test Failure Report: test_library_common_communication failed | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 72 | 72 | 72 | 86.4 | 0 | 100%
TAP-97622_CLASSY1 | 377 | *374 |  | 05.36.09.00.00.00.00.00 | TAP-97622 | TAP-94661 | [TAP-97622_CLASSY1] ¦ SslWrapper Unit Tests are failing on Windows | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 89 | 72 | 89 | 106.8 | 17 | 100%
TAP-97622_PLATFORMERS | 378 | *374 |  | 05.36.10.00.00.00.00.00 | TAP-97622 | TAP-94003 | [TAP-97622_PLATFORMERS] ¦ Automated Unit Test Failure Report: test_system_monitor_shutdown_sequence failed | Issue | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 89 | 72 | 89 | 106.8 | 17 | 100%
TAP-97622_STORMCHASERS1 | 379 | *374 |  | 05.36.12.00.00.00.00.00 | TAP-97622 | TAP-101952 | [TAP-97622_STORMCHASERS1] ¦ Automated Unit Test Failure Report: test_ups_dds_communication_interface failed | Issue | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 94 | 72 | 94 | 112.8 | 22 | 100%
TAP-97622_VISUAL | 380 | *374 |  | 05.36.14.00.00.00.00.00 | TAP-97622 | TAP-101957 | [TAP-97622_VISUAL] ¦ [Visual]Automated Unit Test Failure Report: test_storz_dds_interface failed | Issue | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 96 | 72 | 96 | 115.2 | 24 | 100%
TAP-97622_BOOSTERS | 381 | *374 |  | 05.36.17.00.00.00.00.00 | TAP-97622 | TAP-105663 | [TAP-97622_BOOSTERS] ¦ [Boosters] Fix static analysis error for Boosters subsystems | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 97.5 | 72 | 97.5 | 117 | 25.5 | 100%
TAP-97622_HORIZON | 382 | *374 |  | 05.36.19.00.00.00.00.00 | TAP-97622 | TAP-103254 | [TAP-97622_HORIZON] ¦ [Spike] Address ACS static analysis errors | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 100.5 | 72 | 100.5 | 120.6 | 28.5 | 100%
TAP-97622_CLASSY2 | 383 | *374 |  | 05.36.24.00.00.00.00.00 | TAP-97622 | TAP-93125 | [TAP-97622_CLASSY2] ¦ Automated Unit Test Failure Report: test_safety_monitor failed | Issue | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 104.5 | 72 | 104.5 | 125.4 | 32.5 | 100%
TAP-104009 | 384 | *5 |  | 05.37.00.00.00.00.00.00 |  | TAP-104009 | [TAP-104009] ¦ [V2.2] Field Script Readiness Evaluation | Feature | Done |  |  | Parent Task | User Stories | 34 | 34 | 1 hr | 1 hr | 0 | 100%
TAP-104009_BUILDERS | 385 | *384 |  | 05.37.01.00.00.00.00.00 | TAP-104009 | TAP-101937 | [TAP-104009_BUILDERS] ¦ Equivalency Memo | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 34 | 34 | 34 | 40.8 | 0 | 100%
TAP-49649 | 386 | *1 |  | 05.38.00.00.00.00.00.00 |  | TAP-49649 | [TAP-49649] ¦ [Tech Debt] Complete ACS Rework | Feature | Done |  |  | Parent Task | User Stories | 47 | 47 | 1 hr | 1 hr | 0 | 100%
TAP-49649_MARVEL | 387 | *386 |  | 05.38.01.00.00.00.00.00 | TAP-49649 | TAP-48147 | [TAP-49649_MARVEL] ¦ [ACS Arch] Functional Isolation Monitor arch rework | User Story | Done | Foundation - Marvel | MARVEL | Child Task | User Stories | 47 | 47 | 47 | 56.4 | 0 | 100%
TAP-113409 | 388 | *721,9 |  | 05.39.00.00.00.00.00.00 |  | TAP-113409 | [TAP-113409] ¦ [V4][Adv Instr] Fix Design Documentation | Feature | Done |  |  | Parent Task | User Stories | 28.5 | 28.5 | 1 hr | 1 hr | 0 | 100%
TAP-113409_PIXELPOETS | 389 | *388 |  | 05.39.01.00.00.00.00.00 | TAP-113409 | TAP-106910 | [TAP-113409_PIXELPOETS] ¦ [IDP][Pixel Poets] Review Design documents in the source code | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 28.5 | 28.5 | 28.5 | 34.2 | 0 | 100%
TAP-113409_REFRACT | 390 | *388 |  | 05.39.02.00.00.00.00.00 | TAP-113409 | TAP-113811 | [TAP-113409_REFRACT] ¦ [iSim] Support Integration of Design Documents into Repo - Corrections | User Story | Done | Shared Services - Refract | REFRACT | Child Task | User Stories | 28.5 | 28.5 | 28.5 | 34.2 | 0 | 100%
TAP-113409_CROCNROLL | 391 | *388 |  | 05.39.03.00.00.00.00.00 | TAP-113409 | TAP-113862 | [TAP-113409_CROCNROLL] ¦ [CrocNRoll] Support Integration of Design Documents into Repo - Revise | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 28.5 | 28.5 | 28.5 | 34.2 | 0 | 100%
TAP-113409_I2E | 392 | *388 |  | 05.39.04.00.00.00.00.00 | TAP-113409 | TAP-113990 | [TAP-113409_I2E] ¦ [v4.0][IDP][I2E] Review and Fix EIN-SWI-285's MD DD | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 28.5 | 28.5 | 28.5 | 34.2 | 0 | 100%
TAP-113409_TEAMBD | 393 | *388 |  | 05.39.11.00.00.00.00.00 | TAP-113409 | TAP-114095 | [TAP-113409_TEAMBD] ¦ [v4.0][IDP] Fix EIN-SWI-178 Markdown DD Content | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 38.5 | 28.5 | 38.5 | 46.2 | 10 | 100%
TAP-113409_SCRUMBLEDORES | 394 | *388 |  | 05.39.13.00.00.00.00.00 | TAP-113409 | TAP-114324 | [TAP-113409_SCRUMBLEDORES] ¦ [v4.0][IDP][Scrumbledores] Review and Fix EIN-SWI-295 MD DD | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 39 | 28.5 | 39 | 46.8 | 10.5 | 100%
TAP-113409_PUPPETEERS | 395 | *388 |  | 05.39.14.00.00.00.00.00 | TAP-113409 | TAP-115641 | [TAP-113409_PUPPETEERS] ¦ [Puppeteers] Support Integration of Design Documents into Repo - Corrections | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 39 | 28.5 | 39 | 46.8 | 10.5 | 100%
TAP-68411 | 396 | *3 |  | 05.40.00.00.00.00.00.00 |  | TAP-68411 | [TAP-68411] ¦ [TechDebt] [v4.0] Remove sphlib | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-68411_EDISON | 397 | *396 |  | 05.40.01.00.00.00.00.00 | TAP-68411 | TAP-85519 | [TAP-68411_EDISON] ¦ Update the build system to remove sphlib dependencies and include wolfcrypt library | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-68411_ICONICS | 398 | *396 |  | 05.40.02.00.00.00.00.00 | TAP-68411 | TAP-85517 | [TAP-68411_ICONICS] ¦ Update all the effected SWI's in the Software architecture, Design documents and Test protocols | User Story | Done | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-68411_CASTLEBLACK | 399 | *396 |  | 05.40.05.00.00.00.00.00 | TAP-68411 | TAP-87300 | [TAP-68411_CASTLEBLACK] ¦ [Architecture] Remove sphlib SWI from 4.0 Architecture | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 22 | 15 | 22 | 26.4 | 7 | 100%
TAP-76424 | 400 | *1 |  | 05.41.00.00.00.00.00.00 |  | TAP-76424 | [TAP-76424] ¦ [Tech Debt] Improve Unit Tests (Foundation) | Feature | Done |  |  | Parent Task | User Stories | 28 | 28 | 1 hr | 1 hr | 0 | 100%
TAP-76424_ATLAS | 401 | *400 |  | 05.41.01.00.00.00.00.00 | TAP-76424 | TAP-82163 | [TAP-76424_ATLAS] ¦ Automated Unit Test Failure Report: test_library_os_wrapper_thread failed | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 28 | 28 | 28 | 33.6 | 0 | 100%
TAP-76424_FRED | 402 | *400 |  | 05.41.02.00.00.00.00.00 | TAP-76424 | TAP-83056 | [TAP-76424_FRED] ¦ Automated Unit Test Failure Report: test_ethercat_ssc_sscwrapper failed | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 28 | 28 | 28 | 33.6 | 0 | 100%
TAP-76424_CLASSY2 | 403 | *400 |  | 05.41.03.00.00.00.00.00 | TAP-76424 | TAP-86233 | [TAP-76424_CLASSY2] ¦ [CLASSY] Fix TestSafetyEnableInterface.TestReadWrite | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 28 | 28 | 28 | 33.6 | 0 | 100%
TAP-76424_BOOSTERS | 404 | *400 |  | 05.41.05.00.00.00.00.00 | TAP-76424 | TAP-87840 | [TAP-76424_BOOSTERS] ¦ Remove logging registration thread to reduce test execution time. | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 29 | 28 | 29 | 34.8 | 1 | 100%
TAP-76424_CLASSY1 | 405 | *400 |  | 05.41.07.00.00.00.00.00 | TAP-76424 | TAP-90609 | [TAP-76424_CLASSY1] ¦ Windows Unit Tests for Log Archival fail with exit code 0xc0000135 | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 34 | 28 | 34 | 40.8 | 6 | 100%
TAP-76424_PLATFORMERS | 406 | *400 |  | 05.41.09.00.00.00.00.00 | TAP-76424 | TAP-82172 | [TAP-76424_PLATFORMERS] ¦ Automated Unit Test Failure Report: test_teneobridge failed | Issue | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 36 | 28 | 36 | 43.2 | 8 | 100%
TAP-76424_STORMCHASERS2 | 407 | *400 |  | 05.41.12.00.00.00.00.00 | TAP-76424 | TAP-88763 | [TAP-76424_STORMCHASERS2] ¦ Automated Unit Test Failure Report: test_library_smc_ergonomics_ergonomics failed | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 37 | 28 | 37 | 44.4 | 9 | 100%
TAP-69437 | 408 | *1 |  | 05.42.00.00.00.00.00.00 |  | TAP-69437 | [TAP-69437] ¦ [Architecture] Improve alarm code generator workflow | Feature | Done |  |  | Parent Task | User Stories | 33 | 33 | 1 hr | 1 hr | 0 | 100%
TAP-69437_CLASSY1 | 409 | 408 |  | 05.42.01.00.00.00.00.00 | TAP-69437 | TAP-68202 | [TAP-69437_CLASSY1] ¦ [CLASSY] Implement Alarms Code Generator Tool Versioning | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 33 | 33 | 33 | 39.6 | 0 | 100%
TAP-69437_EDISON | 410 | *408 |  | 05.42.03.00.00.00.00.00 | TAP-69437 | TAP-71864 | [TAP-69437_EDISON] ¦ [Edison] Create Jama service account to run export | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 41 | 33 | 41 | 49.2 | 8 | 100%
TAP-69437_CASTLEBLACK | 411 | *408 |  | 05.42.07.00.00.00.00.00 | TAP-69437 | TAP-73897 | [TAP-69437_CASTLEBLACK] ¦ Present new log data process to teams | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 54 | 33 | 54 | 64.8 | 21 | 100%
TAP-69437_CLASSY2 | 412 | *408 |  | 05.42.11.00.00.00.00.00 | TAP-69437 | TAP-87637 | [TAP-69437_CLASSY2] ¦ Implement Support for Output Json File in Alarm Pulls with List of the Users to Latest Jama Updates | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 58 | 33 | 58 | 69.6 | 25 | 100%
TAP-72858 | 413 | *1 |  | 05.43.00.00.00.00.00.00 |  | TAP-72858 | [TAP-72858] ¦ [V4.0][Inogeni][TechDebt] Post-release support and software refactoring | Feature | Done |  |  | Parent Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-72858_HORIZON | 414 | *413 |  | 05.43.01.01.00.00.00.00 | TAP-72858 | TAP-74653 | [TAP-72858_HORIZON] ¦ [Inogeni] Inogeni system startup discussion | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 31 | 31 | 31 | 37.2 | 0 | 100%
TAP-72842 | 415 | *1 |  | 05.44.00.00.00.00.00.00 |  | TAP-72842 | [TAP-72842] ¦ Support collapse of develop-next back to develop | Feature | Done |  |  | Parent Task | User Stories | 24 | 24 | 1 hr | 1 hr | 0 | 100%
TAP-72842_BOOSTERS | 416 | *415 |  | 05.44.01.00.00.00.00.00 | TAP-72842 | TAP-74212 | [TAP-72842_BOOSTERS] ¦ [Boosters] Support transition of develop-next back to develop | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_PLATFORMERS | 417 | *415 |  | 05.44.02.00.00.00.00.00 | TAP-72842 | TAP-74856 | [TAP-72842_PLATFORMERS] ¦ [Platformers] Support develop-next merge | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_COSSACKS | 418 | *415 |  | 05.44.03.00.00.00.00.00 | TAP-72842 | TAP-74863 | [TAP-72842_COSSACKS] ¦ [CI] Support V&V automated tests execution with merge develop-next back to develop | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_FRED | 419 | *415 |  | 05.44.04.00.00.00.00.00 | TAP-72842 | TAP-75429 | [TAP-72842_FRED] ¦ Support merge of develop-next to develop | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_VISUAL | 420 | *415 |  | 05.44.05.00.00.00.00.00 | TAP-72842 | TAP-76092 | [TAP-72842_VISUAL] ¦ [Visual] Reserve capacity to support develop/develop-next collapse | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_BART | 421 | *415 |  | 05.44.06.00.00.00.00.00 | TAP-72842 | TAP-76181 | [TAP-72842_BART] ¦ [PL] Support collapse of develop next | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_KTBR | 422 | *415 |  | 05.44.07.00.00.00.00.00 | TAP-72842 | TAP-76280 | [TAP-72842_KTBR] ¦ [KTBR] Support transition of develop-next back to develop | User Story | Done | Foundation - KTBR | KTBR | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_STORMCHASERS1 | 423 | *415 |  | 05.44.08.00.00.00.00.00 | TAP-72842 | TAP-76313 | [TAP-72842_STORMCHASERS1] ¦ [SC1][PLACEHOLDER] Support develop-next transition to develop | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-72842_HORIZON | 424 | *415 |  | 05.44.10.00.00.00.00.00 | TAP-72842 | TAP-76449 | [TAP-72842_HORIZON] ¦ [Horizon] Support collapse of develop next | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 27 | 24 | 27 | 32.4 | 3 | 100%
TAP-61255 | 425 | *1 |  | 05.45.00.00.00.00.00.00 |  | TAP-61255 | [TAP-61255] ¦ [V4.0] Improve performance of Data Access software to allow support of more logs collection | Feature | Done |  |  | Parent Task | User Stories | 79 | 79 | 1 hr | 1 hr | 0 | 100%
TAP-61255_BOOSTERS | 426 | *425 |  | 05.45.01.00.00.00.00.00 | TAP-61255 | TAP-59716 | [TAP-61255_BOOSTERS] ¦ Data Access collector process should handle large backlog of data records | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 79 | 79 | 79 | 94.8 | 0 | 100%
TAP-53969 | 427 | *1 |  | 05.46.00.00.00.00.00.00 |  | TAP-53969 | [TAP-53969] ¦ [v4.0 SW][Tech Debt] Migrate C++ Unit Tests to new process/framework | Feature | Done |  |  | Parent Task | User Stories | 72 | 72 | 1 hr | 1 hr | 0 | 100%
TAP-53969_PLATFORMERS | 428 | *427 |  | 05.46.01.00.00.00.00.00 | TAP-53969 | TAP-54365 | [TAP-53969_PLATFORMERS] ¦ Unit Test library_deployment_test_linux failing | Issue | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 72 | 72 | 72 | 86.4 | 0 | 100%
TAP-53969_FRED | 429 | *427 |  | 05.46.02.00.00.00.00.00 | TAP-53969 | TAP-47541 | [TAP-53969_FRED] ¦ [swift]EIN-SWI-105 sra_ethercat_ssc_wrapper_unit tests | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 72 | 72 | 72 | 86.4 | 0 | 100%
TAP-53969_SWIFT | 430 | *427 |  | 05.46.03.00.00.00.00.00 | TAP-53969 | TAP-48184 | [TAP-53969_SWIFT] ¦ [swift-EIN-SWI-462]Write GTests for library/smc_configuration | User Story | Done | Foundation - Swift | SWIFT | Child Task | User Stories | 72 | 72 | 72 | 86.4 | 0 | 100%
TAP-53969_MARVEL | 431 | *427 |  | 05.46.04.00.00.00.00.00 | TAP-53969 | TAP-55017 | [TAP-53969_MARVEL] ¦ UnitTest test_library_sra_slave_applications intermittently failing | Issue | Done | Foundation - Marvel | MARVEL | Child Task | User Stories | 72 | 72 | 72 | 86.4 | 0 | 100%
TAP-53969_HORIZON | 432 | *427 |  | 05.46.11.00.00.00.00.00 | TAP-53969 | TAP-57527 | [TAP-53969_HORIZON] ¦ [Horizon] Investigate status of TPSC, FSE, ACA Unit test | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 92 | 72 | 92 | 110.4 | 20 | 100%
TAP-53969_CLASSY1 | 433 | *427 |  | 05.46.20.00.00.00.00.00 | TAP-53969 | TAP-51212 | [TAP-53969_CLASSY1] ¦ [classy] Improve unit test coverage for alarms subsystem | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 120.5 | 72 | 120.5 | 144.6 | 48.5 | 100%
TAP-84311 | 434 | *1 |  | 05.47.00.00.00.00.00.00 |  | TAP-84311 | [TAP-84311] ¦ [Architecture][Infrastructure] Use Code Change Impact Analysis Tool to run only affected unit-tests | Feature | Done |  |  | Parent Task | User Stories | 19 | 19 | 1 hr | 1 hr | 0 | 100%
TAP-84311_FRED | 435 | *434 |  | 05.47.01.00.00.00.00.00 | TAP-84311 | TAP-84320 | [TAP-84311_FRED] ¦ Local build of impacted unit tests | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 19 | 19 | 19 | 22.8 | 0 | 100%
TAP-37832 | 436 | *1 |  | 05.48.00.00.00.00.00.00 |  | TAP-37832 | [TAP-37832] ¦ [v4.0 SW][techDebt] Fix remaining coverity findings for v4.0 software (PI7 Platform) | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-37832_PLATFORMERS | 437 | *436 |  | 05.48.01.00.00.00.00.00 | TAP-37832 | TAP-47993 | [TAP-37832_PLATFORMERS] ¦ [Platformers] Fix low risk coverity findings | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-37832_BOOSTERS | 438 | *436 |  | 05.48.02.00.00.00.00.00 | TAP-37832 | TAP-48100 | [TAP-37832_BOOSTERS] ¦ [Boosters] Fix remaining coverity findings in Logging subsystem | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-37832_ATLAS | 439 | *436 |  | 05.48.03.00.00.00.00.00 | TAP-37832 | TAP-48845 | [TAP-37832_ATLAS] ¦ Atlas coverty review | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-37832_HORIZON | 440 | *436 |  | 05.48.04.00.00.00.00.00 | TAP-37832 | TAP-46813 | [TAP-37832_HORIZON] ¦ [TechDebt] Run Coverity report of Joe SWIs | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-36556 | 441 | *1 |  | 05.49.00.00.00.00.00.00 |  | TAP-36556 | [TAP-36556] ¦ [Arch]Cleanup EtherCAT communication | Feature | Done |  |  | Parent Task | User Stories | 40.25 | 40.25 | 1 hr | 1 hr | 0 | 100%
TAP-36556_HORIZON | 442 | *441 |  | 05.49.01.00.00.00.00.00 | TAP-36556 | TAP-27934 | [TAP-36556_HORIZON] ¦ [Spike] Investigate if ssc_wrapper still needs specific interfaces | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 40.25 | 40.25 | 40.25 | 48.3 | 0 | 100%
TAP-36556_SOUPERTROOPERS | 443 | *441 |  | 05.49.16.00.00.00.00.00 | TAP-36556 | TAP-79942 | [TAP-36556_SOUPERTROOPERS] ¦ SOUP: Update EtherCAT SSC to version 5.13 for version 4.0 | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 76.25 | 40.25 | 76.25 | 91.5 | 36 | 100%
TAP-47543 | 444 | *1 |  | 05.50.00.00.00.00.00.00 |  | TAP-47543 | [TAP-47543] ¦ [Arch][Enabler] Rework ACS Core | Feature | Done |  |  | Parent Task | User Stories | 100.5 | 100.5 | 1 hr | 1 hr | 0 | 100%
TAP-47543_MARVEL | 445 | *444 |  | 05.50.01.00.00.00.00.00 | TAP-47543 | TAP-48102 | [TAP-47543_MARVEL] ¦ [ACS Arch] SWI Definition | User Story | Done | Foundation - Marvel | MARVEL | Child Task | User Stories | 100.5 | 100.5 | 100.5 | 120.6 | 0 | 100%
TAP-63938 | 446 | *1 |  | 05.51.00.00.00.00.00.00 |  | TAP-63938 | [TAP-63938] ¦ [V4.0][DFS] Logging update to better connect events with procedures - implementation | Feature | Done |  |  | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-63938_BOOSTERS | 447 | *446 |  | 05.51.01.00.00.00.00.00 | TAP-63938 | TAP-71764 | [TAP-63938_BOOSTERS] ¦ [Boosters] Log procedure ID on x86 nodes | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 29 | 29 | 29 | 34.8 | 0 | 100%
TAP-60608 | 448 | *1 |  | 05.52.00.00.00.00.00.00 |  | TAP-60608 | [TAP-60608] ¦ Replace Ripdraw SOUP library with in-house implementation | Feature | Done |  |  | Parent Task | User Stories | 165 | 165 | 1 hr | 1 hr | 0 | 100%
TAP-60608_STELLARS | 449 | *448 |  | 05.52.01.00.00.00.00.00 | TAP-60608 | TAP-73984 | [TAP-60608_STELLARS] ¦ Implement the Unit Tests for the Serial communication (SPI) functionality | User Story | Done | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 165 | 165 | 165 | 198 | 0 | 100%
TAP-60608_FRED | 450 | *448 |  | 05.52.25.00.00.00.00.00 | TAP-60608 | TAP-75427 | [TAP-60608_FRED] ¦ Support RipDraw Work | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 298 | 165 | 298 | 357.6 | 133 | 100%
TAP-47915 | 451 | *1 |  | 05.53.00.00.00.00.00.00 |  | TAP-47915 | [TAP-47915] ¦ [Arch][Enabler] Refine RASA Applications | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-47915_HORIZON | 452 | *451 |  | 05.53.01.00.00.00.00.00 | TAP-47915 | TAP-44975 | [TAP-47915_HORIZON] ¦ Enable testing RASA integration tests on VM | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-69540 | 453 | *1 |  | 05.54.00.00.00.00.00.00 |  | TAP-69540 | [TAP-69540] ¦ [Tech Debt][Simulink] Update unit tests to be compatible with Simulink SIL/PIL Testing | Feature | Done |  |  | Parent Task | User Stories | 53.5 | 53.5 | 1 hr | 1 hr | 0 | 100%
TAP-69540_SUNRISERS | 454 | *453 |  | 05.54.01.00.00.00.00.00 | TAP-69540 | TAP-73317 | [TAP-69540_SUNRISERS] ¦ [Tech Debt][Simulink][FF] Update unit tests to be compatible with Simulink SIL/PIL Testing - [Review only from FF] | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 53.5 | 53.5 | 53.5 | 64.2 | 0 | 100%
TAP-69540_ORGANELLES | 455 | *453 |  | 05.54.02.00.00.00.00.00 | TAP-69540 | TAP-74049 | [TAP-69540_ORGANELLES] ¦ [Simulink] Update Unit tests for SIL/PIL compatibility for msc/mso tests | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 53.5 | 53.5 | 53.5 | 64.2 | 0 | 100%
TAP-69540_BUGHUNTERS | 456 | *453 |  | 05.54.03.00.00.00.00.00 | TAP-69540 | TAP-72580 | [TAP-69540_BUGHUNTERS] ¦ [Enabler][BugHunters] Simulink Harness Management - part 1 | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 53.5 | 53.5 | 53.5 | 64.2 | 0 | 100%
TAP-69540_TEAMBD | 457 | *453 |  | 05.54.04.00.00.00.00.00 | TAP-69540 | TAP-74809 | [TAP-69540_TEAMBD] ¦ [Simulink][TeamBD] Update Unit tests for SIL/PIL compatibility | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 53.5 | 53.5 | 53.5 | 64.2 | 0 | 100%
TAP-69540_REFLECT | 458 | *453 |  | 05.54.05.00.00.00.00.00 | TAP-69540 | TAP-74894 | [TAP-69540_REFLECT] ¦ [Simulink][Reflect] Update sim_controller unit_tests for SIL/PIL compatibility | User Story | Done | Advanced Instruments - Reflect | REFLECT | Child Task | User Stories | 53.5 | 53.5 | 53.5 | 64.2 | 0 | 100%
TAP-69540_SIRIUS | 459 | *453 |  | 05.54.07.00.00.00.00.00 | TAP-69540 | TAP-75034 | [TAP-69540_SIRIUS] ¦ [Simulink] [Sirius] Update Unit tests for SIL/PIL compatibility | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 54.5 | 53.5 | 54.5 | 65.4 | 1 | 100%
TAP-69540_FLOWRIDERS | 460 | *453 |  | 05.54.09.00.00.00.00.00 | TAP-69540 | TAP-76328 | [TAP-69540_FLOWRIDERS] ¦ [Simulink][Flow Riders] Update Unit tests for SIL/PIL compatibility | User Story | Done | Advanced Instruments - Flow Riders | FLOWRIDERS | Child Task | User Stories | 56.5 | 53.5 | 56.5 | 67.8 | 3 | 100%
TAP-69540_HAPPYJAWS | 461 | *453 |  | 05.54.10.00.00.00.00.00 | TAP-69540 | TAP-76391 | [TAP-69540_HAPPYJAWS] ¦ [Tech Debt][Simulink][Happy Jaws] Update Unit tests for SIL/PIL compatibility | User Story | Done | Advanced Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 56.5 | 53.5 | 56.5 | 67.8 | 3 | 100%
TAP-69540_JACOBIANS | 462 | *453 |  | 05.54.20.00.00.00.00.00 | TAP-69540 | TAP-89453 | [TAP-69540_JACOBIANS] ¦ [Jacobians] Support Update MSC Unit tests for SIL/PIL compatibility for msc/mso tests | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 78.5 | 53.5 | 78.5 | 94.2 | 25 | 100%
TAP-69540_SCRUMBLEDORES | 463 | *453 |  | 05.54.21.00.00.00.00.00 | TAP-69540 | TAP-90508 | [TAP-69540_SCRUMBLEDORES] ¦ [SPIKE] Explore benefits of usage of Iterations and Parameter Overrides for unit tests | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 78.5 | 53.5 | 78.5 | 94.2 | 25 | 100%
TAP-71958 | 464 | *1 |  | 05.55.00.00.00.00.00.00 |  | TAP-71958 | [TAP-71958] ¦ [v3.0][Enabler] IDU Standalones Automation Enhancements - Part 1 | Feature | Done |  |  | Parent Task | User Stories | 32.25 | 32.25 | 1 hr | 1 hr | 0 | 100%
TAP-71958_COSSACKS | 465 | *464 |  | 05.55.01.00.00.00.00.00 | TAP-71958 | TAP-74861 | [TAP-71958_COSSACKS] ¦ [CI] Create bamboo plan for test execution against IDU standalone setup | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 32.25 | 32.25 | 32.25 | 38.7 | 0 | 100%
TAP-71958_SIRIUS | 466 | *464 |  | 05.55.02.00.00.00.00.00 | TAP-71958 | TAP-71929 | [TAP-71958_SIRIUS] ¦ Testability file deployment script for IDU standalones (Part 1) | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 32.25 | 32.25 | 32.25 | 38.7 | 0 | 100%
TAP-71958_CROCNROLL | 467 | *464 |  | 05.55.04.00.00.00.00.00 | TAP-71958 | TAP-75571 | [TAP-71958_CROCNROLL] ¦ [CrocNRoll] Reserve SP for IDU Standalone Automation Enhancements | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 35.5 | 32.25 | 35.5 | 42.6 | 3.25 | 100%
TAP-71958_EDISON | 468 | *464 |  | 05.55.08.00.00.00.00.00 | TAP-71958 | TAP-83350 | [TAP-71958_EDISON] ¦ [v3.0][Edison]IDU Standalone Deployment Plan for "Formal Verification" | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 44.5 | 32.25 | 44.5 | 53.4 | 12.25 | 100%
TAP-113411 | 469 | *9 |  | 05.56.00.00.00.00.00.00 |  | TAP-113411 | [TAP-113411] ¦ [RPE] Fix Design Documentation | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-113411_SUNRISERS | 470 | *469 |  | 05.56.01.00.00.00.00.00 | TAP-113411 | TAP-115316 | [TAP-113411_SUNRISERS] ¦ Review the conversion of SWIs from word to markdown in the ein_ng/doc/design - RASA | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-113411_NEXUS | 471 | *469 |  | 05.56.02.00.00.00.00.00 | TAP-113411 | TAP-115329 | [TAP-113411_NEXUS] ¦ Review the conversion of SWIs from word to markdown in the ein_ng/doc/design - ACAD | User Story | Done | Released Product Engineering - Nexus | NEXUS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-113411_DRUSHTI | 472 | *469 |  | 05.56.03.00.00.00.00.00 | TAP-113411 | TAP-115318 | [TAP-113411_DRUSHTI] ¦ Review the conversion of SWIs from word to markdown in the ein_ng/doc/design - GUI | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-122378 | 473 | *7 |  | 05.57.00.00.00.00.00.00 |  | TAP-122378 | [TAP-122378] ¦ [V4][RC1] Update Setup Arm Latency test duration as per new requirement | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-122378_SUNRISERS | 474 | *473 |  | 05.57.01.00.00.00.00.00 | TAP-122378 | TAP-122314 | [TAP-122378_SUNRISERS] ¦ [Sunrisers] NOTCODE-540 latency self test time update | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-113539 | 475 | *7 |  | 05.58.00.00.00.00.00.00 |  | TAP-113539 | [TAP-113539] ¦ ESAT v2 - Continued Improvement ESAT v2 (PI14) - Product Security | Feature | Done |  |  | Parent Task | User Stories | 101 | 101 | 1 hr | 1 hr | 0 | 100%
TAP-113539_ASTRANPSDEVELOPERS | 476 | *475 |  | 05.58.01.00.00.00.00.00 | TAP-113539 | TAP-113542 | [TAP-113539_ASTRANPSDEVELOPERS] ¦ ESAT v2 - Migrate file retreval code to websocket | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 101 | 101 | 101 | 121.2 | 0 | 100%
TAP-113539_TOOLSRULES | 477 | *475 |  | 05.58.05.00.00.00.00.00 | TAP-113539 | TAP-113805 | [TAP-113539_TOOLSRULES] ¦ ESAT v2: Logger should not lose messages during crash v4 | Issue | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 122 | 101 | 122 | 146.4 | 21 | 100%
TAP-113539_EDISON | 478 | *475 |  | 05.58.07.00.00.00.00.00 | TAP-113539 | TAP-90357 | [TAP-113539_EDISON] ¦ Individual Node Deployment using esat-v2 | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 125 | 101 | 125 | 150 | 24 | 100%
TAP-113539_CLASSY1 | 479 | *475 |  | 05.58.11.00.00.00.00.00 | TAP-113539 | TAP-114394 | [TAP-113539_CLASSY1] ¦ [CLASSY] Turn on explicit acknowledgements for ESAT topics | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 137 | 101 | 137 | 164.4 | 36 | 100%
TAP-113539_ATLAS | 480 | *475 |  | 05.58.28.00.00.00.00.00 | TAP-113539 | TAP-122040 | [TAP-113539_ATLAS] ¦ Update the signature verification leveraged by esat | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 177 | 101 | 177 | 212.4 | 76 | 100%
TAP-114202 | 481 | *7 |  | 05.59.00.00.00.00.00.00 |  | TAP-114202 | [TAP-114202] ¦ [IDP][Enabler] Infrastructure maintenance PI14 | Feature | Done |  |  | Parent Task | User Stories | 66.5 | 66.5 | 1 hr | 1 hr | 0 | 100%
TAP-114202_EDISON | 482 | *481 |  | 05.59.01.00.00.00.00.00 | TAP-114202 | TAP-112225 | [TAP-114202_EDISON] ¦ Update Windows Provisioning script with RTI/OpenSSL/WolfSSL/WolfSSH | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 66.5 | 66.5 | 66.5 | 79.8 | 0 | 100%
TAP-114202_REFRACT | 483 | *481 |  | 05.59.14.00.00.00.00.00 | TAP-114202 | TAP-114557 | [TAP-114202_REFRACT] ¦ [Infrastructure] Make SLDV analyzing for 1 model | User Story | Done | Shared Services - Refract | REFRACT | Child Task | User Stories | 92 | 66.5 | 92 | 110.4 | 25.5 | 100%
TAP-106648 | 484 | *7 |  | 05.60.00.00.00.00.00.00 |  | TAP-106648 | [TAP-106648] ¦ [V4.0][Tech Debt] PI14 - Fix Unit Verification (Foundation) | Feature | Done |  |  | Parent Task | User Stories | 64.1 | 64.1 | 1 hr | 1 hr | 0 | 100%
TAP-106648_CLASSY2 | 485 | *484 |  | 05.60.01.00.00.00.00.00 | TAP-106648 | TAP-99185 | [TAP-106648_CLASSY2] ¦ Automated Unit Test Failure Report: test_fast_faults failed | Issue | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 64.1 | 64.1 | 64.1 | 76.92 | 0 | 100%
TAP-106648_FRED | 486 | *484 |  | 05.60.06.00.00.00.00.00 | TAP-106648 | TAP-96973 | [TAP-106648_FRED] ¦ Automated Unit Test Failure Report: test_udp_session_secure failed | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 68.1 | 64.1 | 68.1 | 81.72 | 4 | 100%
TAP-106648_BOOSTERS | 487 | *484 |  | 05.60.07.00.00.00.00.00 | TAP-106648 | TAP-84396 | [TAP-106648_BOOSTERS] ¦ [Boosters] Automated Unit Test Failure Report: test_library_log_process_RelayStorageUnitTest failed | Issue | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 68.1 | 64.1 | 68.1 | 81.72 | 4 | 100%
TAP-106648_CLASSY1 | 488 | *484 |  | 05.60.17.00.00.00.00.00 | TAP-106648 | TAP-107499 | [TAP-106648_CLASSY1] ¦ Automated Unit Test Failure Report: test_communication_modern_dds_api_library failed | Issue | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 85.2 | 64.1 | 85.2 | 102.24 | 21.1 | 100%
TAP-106648_PLATFORMERS | 489 | *484 |  | 05.60.19.00.00.00.00.00 | TAP-106648 | TAP-110672 | [TAP-106648_PLATFORMERS] ¦ Fix test_configuration_manager if sequence_id is missing or corrupted | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 90.2 | 64.1 | 90.2 | 108.24 | 26.1 | 100%
TAP-106648_STORMCHASERS1 | 490 | *484 |  | 05.60.21.00.00.00.00.00 | TAP-106648 | TAP-114444 | [TAP-106648_STORMCHASERS1] ¦ Automated Unit Test Failure Report: test_alarms_link failed | Issue | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 91.2 | 64.1 | 91.2 | 109.44 | 27.1 | 100%
TAP-106648_STORMCHASERS2 | 491 | *484 |  | 05.60.23.00.00.00.00.00 | TAP-106648 | TAP-107108 | [TAP-106648_STORMCHASERS2] ¦ Automated Unit Test Failure Report: test_library_smc_galil failed | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 96.2 | 64.1 | 96.2 | 115.44 | 32.1 | 100%
TAP-106648_HORIZON | 492 | *484 |  | 05.60.25.00.00.00.00.00 | TAP-106648 | TAP-114194 | [TAP-106648_HORIZON] ¦ [Horizon] Automated Unit Test Failure Report: test_fse_controller_statemachine failed | Issue | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 97.7 | 64.1 | 97.7 | 117.24 | 33.6 | 100%
TAP-106648_ATLAS | 493 | *484 |  | 05.60.30.00.00.00.00.00 | TAP-106648 | TAP-122098 | [TAP-106648_ATLAS] ¦ Address outstanding Coverity issues | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 103.7 | 64.1 | 103.7 | 124.44 | 39.6 | 100%
TAP-106648_VISUAL | 494 | *484 |  | 05.60.33.00.00.00.00.00 | TAP-106648 | TAP-122332 | [TAP-106648_VISUAL] ¦ [v4.0][Visua] Fix static analysis issues and improve unit tests | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 107.7 | 64.1 | 107.7 | 129.24 | 43.6 | 100%
TAP-95494 | 495 | *7 |  | 05.61.00.00.00.00.00.00 |  | TAP-95494 | [TAP-95494] ¦ [IDP][V4.0] SW Integration QNX_x86_64 Ecosystem into Production | Feature | Done |  |  | Parent Task | User Stories | 230 | 230 | 1 hr | 1 hr | 0 | 100%
TAP-95494_SLEEPWALKERS | 496 | *495 |  | 05.61.01.00.00.00.00.00 | TAP-95494 | TAP-95714 | [TAP-95494_SLEEPWALKERS] ¦ [V4 transition]List Python libraries to be added to pypi-einstein-local/ | User Story | Done | Shared Services - Sleepwalkers | SLEEPWALKERS | Child Task | User Stories | 230 | 230 | 230 | 276 | 0 | 100%
TAP-95494_CASTLEBLACK | 497 | *495 |  | 05.61.02.00.00.00.00.00 | TAP-95494 | TAP-96007 | [TAP-95494_CASTLEBLACK] ¦ Extract Table for Safety Fault to Command Mapping for Integration Testing | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 230 | 230 | 230 | 276 | 0 | 100%
TAP-95494_EDISON | 498 | *495 |  | 05.61.25.00.00.00.00.00 | TAP-95494 | TAP-97034 | [TAP-95494_EDISON] ¦ Add Python libraries to pypi-einstein-local/ - fabric | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 322 | 230 | 322 | 386.4 | 92 | 100%
TAP-111461 | 499 | *7 |  | 06.01.01.00.00.00.00.00 |  | TAP-111461 | [TAP-111461] ¦ [V4.0] [Cyber] Peripheral deployment cleanup | Feature | Done |  |  | Parent Task | User Stories | 47.5 | 47.5 | 1 hr | 1 hr | 0 | 100%
TAP-111461_BOOSTERS | 500 | *499 |  | 06.01.01.01.00.00.00.00 | TAP-111461 | TAP-106936 | [TAP-111461_BOOSTERS] ¦ [V4][DM][V&V][Boosters] New Inogeni Deployment SW Test Enhancement [part 2] | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 47.5 | 47.5 | 47.5 | 57 | 0 | 100%
TAP-111461_PLATFORMERS | 501 | *499 |  | 06.01.01.04.00.00.00.00 | TAP-111461 | TAP-106047 | [TAP-111461_PLATFORMERS] ¦ [V4][Platformers][PM][V&V] Test Enhancement to support Bootstrap mode | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 61.5 | 47.5 | 61.5 | 73.8 | 14 | 100%
TAP-111461_TOOLSRULES | 502 | *499 |  | 06.01.01.07.00.00.00.00 | TAP-111461 | TAP-117655 | [TAP-111461_TOOLSRULES] ¦ ESAT needs more information to determine correct package for peripheral installs | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 71.5 | 47.5 | 71.5 | 85.8 | 24 | 100%
TAP-105342 | 503 | *7 |  | 06.01.02.00.00.00.00.00 |  | TAP-105342 | [TAP-105342] ¦ [Cyber][V4.0] Define and Create Test Build to support formal SW VV | Feature | Done |  |  | Parent Task | User Stories | 30 | 30 | 1 hr | 1 hr | 0 | 100%
TAP-105342_ATLAS | 504 | *503 |  | 06.01.02.01.00.00.00.00 | TAP-105342 | TAP-107498 | [TAP-105342_ATLAS] ¦ [Test Build][Atlas] Enable access to serial port on Qnx nodes (Zynq and X86) | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 30 | 30 | 30 | 36 | 0 | 100%
TAP-105342_HORIZON | 505 | *503 |  | 06.01.02.18.00.00.00.00 | TAP-105342 | TAP-106134 | [TAP-105342_HORIZON] ¦ [Cyber][TestBuild][Horizon] Disable Instrument Authentication in Test Build by default and allow instrument/SIM reprogramming | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 45 | 30 | 45 | 54 | 15 | 100%
TAP-105342_TOOLSRULES | 506 | *503 |  | 06.01.02.19.00.00.00.00 | TAP-105342 | TAP-120198 | [TAP-105342_TOOLSRULES] ¦ Add Cyberark connectivity to ESAT connection status indicator | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 45 | 30 | 45 | 54 | 15 | 100%
TAP-105342_EDISON | 507 | *503 |  | 06.01.02.22.00.00.00.00 | TAP-105342 | TAP-109888 | [TAP-105342_EDISON] ¦ [Cyber][TestBuild][DEVOPS] Test Build Bamboo Plan Pulls Old BSP | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 55 | 30 | 55 | 66 | 25 | 100%
TAP-111460 | 508 | *7 |  | 06.01.03.00.00.00.00.00 |  | TAP-111460 | [TAP-111460] ¦ [V4.0][V&V] Test User Notification when running non clinical software | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-111460_PLATFORMERS | 509 | *508 |  | 06.01.03.01.00.00.00.00 | TAP-111460 | TAP-106311 | [TAP-111460_PLATFORMERS] ¦ [Cyber][Platformers] [V&V] Update TCs to match the changed requirements: Notification for mismatched software | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 10 | 10 | 10 | 12 | 0 | 100%
TAP-87417 | 510 | *7 |  | 06.01.04.00.00.00.00.00 |  | TAP-87417 | [TAP-87417] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun Batch2 and Test Fix - Foundation | Feature | Done |  |  | Parent Task | User Stories | 207.5 | 207.5 | 1 hr | 1 hr | 0 | 100%
TAP-87417_ATLAS | 511 | *510 |  | 06.01.04.01.00.00.00.00 | TAP-87417 | TAP-95032 | [TAP-87417_ATLAS] ¦ [Cyber][Atlas] cyber/staging branch QNX OS BSP missing shell commands on ORTI | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 207.5 | 207.5 | 207.5 | 249 | 0 | 100%
TAP-87417_BOOSTERS | 512 | *510 |  | 06.01.04.02.00.00.00.00 | TAP-87417 | TAP-96248 | [TAP-87417_BOOSTERS] ¦ [Boosters] Archive automated JAMA test designs after export to Eintests | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 207.5 | 207.5 | 207.5 | 249 | 0 | 100%
TAP-87417_CLASSY1 | 513 | *510 |  | 06.01.04.03.00.00.00.00 | TAP-87417 | TAP-95935 | [TAP-87417_CLASSY1] ¦ [Cyber][CLASSY1] Communication (DDS, UDP) tests: pre-EC1 Dryrun - Sprint 6 | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 207.5 | 207.5 | 207.5 | 249 | 0 | 100%
TAP-87417_FRED | 514 | *510 |  | 06.01.04.04.00.00.00.00 | TAP-87417 | TAP-99290 | [TAP-87417_FRED] ¦ [Cyber][Fred][V&V] pre-EC1 Dryrun: TC build-fixes on develop (pre-cyber) | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 207.5 | 207.5 | 207.5 | 249 | 0 | 100%
TAP-87417_STORMCHASERS1 | 515 | *510 |  | 06.01.04.05.00.00.00.00 | TAP-87417 | TAP-72296 | [TAP-87417_STORMCHASERS1] ¦ [V4.0][SC1] Part 3 update automated JAMA test cases after designs export to Eintests | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 207.5 | 207.5 | 207.5 | 249 | 0 | 100%
TAP-87417_PLATFORMERS | 516 | *510 |  | 06.01.04.10.01.00.00.00 | TAP-87417 | TAP-87433 | [TAP-87417_PLATFORMERS] ¦ [V4][Platformers][V&V] eintests release/t3 to develop sync-up | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 219.5 | 207.5 | 219.5 | 263.4 | 12 | 100%
TAP-87417_STORMCHASERS2 | 517 | *510 |  | 06.01.04.11.02.00.00.00 | TAP-87417 | TAP-104276 | [TAP-87417_STORMCHASERS2] ¦ [V4.0][SC2] Export V4.0 Manual TPs and Check for Errors | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 230.5 | 207.5 | 230.5 | 276.6 | 23 | 100%
TAP-87417_HORIZON | 518 | *510 |  | 06.01.04.12.36.00.00.00 | TAP-87417 | TAP-86642 | [TAP-87417_HORIZON] ¦ [v4.0] TPSC subsystem verification plan update for v4.0 (was v3.0 before) | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 320 | 207.5 | 320 | 384 | 112.5 | 100%
TAP-87417_CLASSY2 | 519 | *510 |  | 06.01.04.13.17.00.00.00 | TAP-87417 | TAP-55737 | [TAP-87417_CLASSY2] ¦ [CLASSY2] Run and fix all SAFETY tests on the latest develop | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 355.5 | 207.5 | 355.5 | 426.6 | 148 | 100%
TAP-84549 | 520 | *7 |  | 06.01.05.00.00.00.00.00 |  | TAP-84549 | [TAP-84549] ¦ [Cyber][V4.0][V&V] Pre-EC1 Test Dryrun and Test Fix - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 140.125 | 140.125 | 1 hr | 1 hr | 0 | 100%
TAP-84549_BUGHUNTERS | 521 | *520 |  | 06.01.05.01.00.00.00.00 | TAP-84549 | TAP-86527 | [TAP-84549_BUGHUNTERS] ¦ [v4.0][BH] Assign Owner field for all MIL TC Jama items for respective scrums | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 140.125 | 140.125 | 140.125 | 168.15 | 0 | 100%
TAP-84549_CROCNROLL | 522 | *520 |  | 06.01.05.03.00.00.00.00 | TAP-84549 | TAP-95806 | [TAP-84549_CROCNROLL] ¦ [v4.0][CrocNRoll] pre-EC1 Dryrun for EIN-SWT_PROT-219 | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 141.125 | 140.125 | 141.125 | 169.35 | 1 | 100%
TAP-84549_I2E | 523 | *520 |  | 06.01.05.11.00.00.00.00 | TAP-84549 | TAP-97233 | [TAP-84549_I2E] ¦ [V4.0][I2E][V&V] Pre EC Dry run - RASA and IDU HAL (SRA HAL) Test Executions | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 150.625 | 140.125 | 150.625 | 180.75 | 10.5 | 100%
TAP-84549_JACOBIANS | 524 | *520 |  | 06.01.05.16.00.00.00.00 | TAP-84549 | TAP-99175 | [TAP-84549_JACOBIANS] ¦ [V4.0][Jacobians]Update tests for failed dry run tests in Prot-122 | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 161.125 | 140.125 | 161.125 | 193.35 | 21 | 100%
TAP-84549_PIXELPOETS | 525 | *520 |  | 06.01.05.24.00.00.00.00 | TAP-84549 | TAP-91777 | [TAP-84549_PIXELPOETS] ¦ [Enabler] pt2 - v4 - Continue to investigate and fix ATF abort core dump issue for | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 172.825 | 140.125 | 172.825 | 207.39 | 32.7 | 100%
TAP-84549_SCRUMBLEDORES | 526 | *520 |  | 06.01.05.34.00.00.00.00 | TAP-84549 | TAP-96891 | [TAP-84549_SCRUMBLEDORES] ¦ [v4.0][Scrumbledores] Test Case Updates and pre-EC1 Dryrun for EIN-SWT_PROT-92 | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 183.825 | 140.125 | 183.825 | 220.59 | 43.7 | 100%
TAP-84549_SUNRISERS | 527 | *520 |  | 06.01.05.49.00.00.00.00 | TAP-84549 | TAP-96254 | [TAP-84549_SUNRISERS] ¦ [Cyber][V4.0][V&V][Sunrisers] pre-EC1 Dryrun for SA EIN-SWT_PROT-21 | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 219.825 | 140.125 | 219.825 | 263.79 | 79.7 | 100%
TAP-84549_TEAMBD | 528 | *520 |  | 06.01.05.59.00.00.00.00 | TAP-84549 | TAP-95826 | [TAP-84549_TEAMBD] ¦ [TeamBD] Address deviation from 3.0 Formal for PROT-255: EIN-TC_SW-2416 | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 236.825 | 140.125 | 236.825 | 284.19 | 96.7 | 100%
TAP-83547 | 529 | *7 |  | 06.01.06.00.00.00.00.00 |  | TAP-83547 | [TAP-83547] ¦ [Cyber][V4.0][V&V] pre-EC1 Dryrun - Foundation | Feature | Done |  |  | Parent Task | User Stories | 52 | 52 | 1 hr | 1 hr | 0 | 100%
TAP-83547_ATLAS | 530 | *529 |  | 06.01.06.01.00.00.00.00 | TAP-83547 | TAP-86318 | [TAP-83547_ATLAS] ¦ [V4.0][Atlas] Dry Run Manual Tests on Cyber-Enabled V4.0 (Part 2) | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 52 | 52 | 52 | 62.4 | 0 | 100%
TAP-83547_PLATFORMERS | 531 | *529 |  | 06.01.06.04.00.00.00.00 | TAP-83547 | TAP-92703 | [TAP-83547_PLATFORMERS] ¦ [V4][Platformers][V&V] EIN-TC_SW-1464 Failure on p-003.000.004 | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 56 | 52 | 56 | 67.2 | 4 | 100%
TAP-83547_VISUAL | 532 | *529 |  | 06.01.06.12.00.00.00.00 | TAP-83547 | TAP-87632 | [TAP-83547_VISUAL] ¦ [v4.0][Visual] pre-EC1 ENDOSW TC201 Dry Run | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 75 | 52 | 75 | 90 | 23 | 100%
TAP-83547_COSSACKS | 533 | *529 |  | 06.01.06.14.01.00.00.00 | TAP-83547 | TAP-69658 | [TAP-83547_COSSACKS] ¦ [Cyber][CI] Create Test Execution Bamboo Project for Product Security Release (develop branch for v4) | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 77 | 52 | 77 | 92.4 | 25 | 100%
TAP-85483 | 534 | *7 |  | 06.01.07.00.00.00.00.00 |  | TAP-85483 | [TAP-85483] ¦ [Cyber][V4.0][Advanced Instruments] SW Verification - Improvements | Feature | Done |  |  | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-85483_BUGHUNTERS | 535 | *534 |  | 06.01.07.01.00.00.00.00 | TAP-85483 | TAP-91654 | [TAP-85483_BUGHUNTERS] ¦ [BH] MIL for ACA Confirm Placement - TD draft peer review | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 29 | 29 | 29 | 34.8 | 0 | 100%
TAP-85483_SCRUMBLEDORES | 536 | *534 |  | 06.01.07.02.00.00.00.00 | TAP-85483 | TAP-88366 | [TAP-85483_SCRUMBLEDORES] ¦ Dry Runs for Chico v2.4 update | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 29 | 29 | 29 | 34.8 | 0 | 100%
TAP-85483_PIXELPOETS | 537 | *534 |  | 06.01.07.03.04.00.00.00 | TAP-85483 | TAP-86253 | [TAP-85483_PIXELPOETS] ¦ [SPIKE] Investigate reconfiguring firewall for ATF | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 35 | 29 | 35 | 42 | 6 | 100%
TAP-57120 | 538 | *7 |  | 06.01.08.00.00.00.00.00 |  | TAP-57120 | [TAP-57120] ¦ [Cyber][V4.0][V&V] Investigation of DDS Secure and UDP Secure Impact on SW Testing - Foundation | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-57120_BOOSTERS | 539 | *538 |  | 06.01.08.01.00.00.00.00 | TAP-57120 | TAP-86585 | [TAP-57120_BOOSTERS] ¦ [Boosters] Investigate if any test cases were impacted by DDS Secure and UDP Secure enabling | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-57120_HORIZON | 540 | *538 |  | 06.01.08.02.00.00.00.00 | TAP-57120 | TAP-87353 | [TAP-57120_HORIZON] ¦ [Horizon] [ TC ] Investigate if any test cases were impacted by DDS Secure and UDP Secure enabling | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-57120_PLATFORMERS | 541 | *538 |  | 06.01.08.03.00.00.00.00 | TAP-57120 | TAP-87367 | [TAP-57120_PLATFORMERS] ¦ [V4][Platformers][V&V] Investigate the impact on Platformers test cases by UDP Secure/DDS Secure | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-57120_DOCUMENTOWNERS | 542 | *538 |  | 06.01.08.04.00.00.00.00 | TAP-57120 | TAP-92701 | [TAP-57120_DOCUMENTOWNERS] ¦ Investigation the feasibility for RTIDDSSPY Tool to Support DDS Secure | User Story | Done | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-84563 | 543 | *7 |  | 06.01.09.00.00.00.00.00 |  | TAP-84563 | [TAP-84563] ¦ [Cyber][V4.0][V&V] Investigation of DDS Secure and UDP Secure Impact on SW Testing - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-84563_PIXELPOETS | 544 | *543 |  | 06.01.09.01.00.00.00.00 | TAP-84563 | TAP-85062 | [TAP-84563_PIXELPOETS] ¦ [v4.0][SPIKE][Positron] GUI investigation of UDP secure impact on MGLM and ATF | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-85482 | 545 | *7 |  | 06.01.10.00.00.00.00.00 |  | TAP-85482 | [TAP-85482] ¦ [V4.0][Foundation][Cyber] SW Verification - Improvements | Feature | Done |  |  | Parent Task | User Stories | 71 | 71 | 1 hr | 1 hr | 0 | 100%
TAP-85482_STORMCHASERS1 | 546 | *545 |  | 06.01.10.01.00.00.00.00 | TAP-85482 | TAP-91276 | [TAP-85482_STORMCHASERS1] ¦ HW usage best practices document | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 71 | 71 | 71 | 85.2 | 0 | 100%
TAP-85482_COSSACKS | 547 | *545 |  | 06.01.10.02.00.00.00.00 | TAP-85482 | TAP-66845 | [TAP-85482_COSSACKS] ¦ [CI] Reduce qnx_7_1_0_armv7.tar.xz archive | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 71 | 71 | 71 | 85.2 | 0 | 100%
TAP-85482_STORMCHASERS2 | 548 | *545 |  | 06.01.10.03.01.00.00.00 | TAP-85482 | TAP-72290 | [TAP-85482_STORMCHASERS2] ¦ [V&V][SC]Moving automated test design from JAMA to Eintests part 1 | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 71 | 71 | 71 | 85.2 | 0 | 100%
TAP-85482_PLATFORMERS | 549 | *545 |  | 06.01.10.04.01.00.00.00 | TAP-85482 | TAP-74129 | [TAP-85482_PLATFORMERS] ¦ [V4][V&V] Draft Cybersecurity Test Strategy and V4 RC Test Plan | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 75 | 71 | 75 | 90 | 4 | 100%
TAP-85482_CLASSY2 | 550 | *545 |  | 06.01.10.04.03.00.00.00 | TAP-85482 | TAP-67931 | [TAP-85482_CLASSY2] ¦ [CLASSY] Remove unused debug.tgz archives in Safety BPs | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 76 | 71 | 76 | 91.2 | 5 | 100%
TAP-85482_ATLAS | 551 | *545 |  | 06.01.10.04.04.00.00.00 | TAP-85482 | TAP-86300 | [TAP-85482_ATLAS] ¦ Update Keystore Automated Test to use new Secure Directory Utility | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 76 | 71 | 76 | 91.2 | 5 | 100%
TAP-85482_TRIPLETEA | 552 | *545 |  | 06.01.10.05.01.00.00.00 | TAP-85482 | TAP-74850 | [TAP-85482_TRIPLETEA] ¦ PIA to Fallback to Other Selected Projects | User Story | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 81 | 71 | 81 | 97.2 | 10 | 100%
TAP-85484 | 553 | *7 |  | 06.01.11.00.00.00.00.00 |  | TAP-85484 | [TAP-85484] ¦ [V4.0][V&V][Cyber][Core Instruments] SW Verification - Improvements | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-85484_I2E | 554 | *553 |  | 06.01.11.01.00.00.00.00 | TAP-85484 | TAP-92800 | [TAP-85484_I2E] ¦ [v4.0][Ext Logger] Fix file creation issue for script and code | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-94634 | 555 | *7 |  | 06.01.12.00.00.00.00.00 |  | TAP-94634 | [TAP-94634] ¦ [Cyber][V4.0][V&V] Test TOOLS and Test Environment Update | Feature | Done |  |  | Parent Task | User Stories | 113.5 | 113.5 | 1 hr | 1 hr | 0 | 100%
TAP-94634_COSSACKS | 556 | *555 |  | 06.01.12.01.00.00.00.00 | TAP-94634 | TAP-99177 | [TAP-94634_COSSACKS] ¦ [CI] Disable RunTests phase for all ESWT bamboo plans on staging/cyber branch | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 113.5 | 113.5 | 113.5 | 136.2 | 0 | 100%
TAP-94634_EDISON | 557 | *555 |  | 06.01.12.12.00.00.00.00 | TAP-94634 | TAP-95006 | [TAP-94634_EDISON] ¦ [Cyber] Secure Communication Certificates and Configuration Docker Image for Linux Test Machines | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 141.5 | 113.5 | 141.5 | 169.8 | 28 | 100%
TAP-94634_TRIPLETEA | 558 | *555 |  | 06.01.12.13.00.00.00.00 | TAP-94634 | TAP-96841 | [TAP-94634_TRIPLETEA] ¦ Clean up legacy parts of NodeHierarchy interface | User Story | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 141.5 | 113.5 | 141.5 | 169.8 | 28 | 100%
TAP-67835 | 559 | *7 |  | 06.01.13.00.00.00.00.00 |  | TAP-67835 | [TAP-67835] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - CoreInstruments | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-67835_I2E | 560 | *559 |  | 06.01.13.01.00.00.00.00 | TAP-67835 | TAP-79116 | [TAP-67835_I2E] ¦ [Cyber][I2E] Update tools to use WolfSSH | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-67835_ORGANELLES | 561 | *559 |  | 06.01.13.02.00.00.00.00 | TAP-67835 | TAP-85970 | [TAP-67835_ORGANELLES] ¦ Update iSim V&V Tests to Use WolfSSH | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-67835_SIRIUS | 562 | *559 |  | 06.01.13.03.00.00.00.00 | TAP-67835 | TAP-87355 | [TAP-67835_SIRIUS] ¦ [V4.0][Sirius] Triage Sirius test cases for use of SSH | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-67834 | 563 | *7 |  | 06.01.14.00.00.00.00.00 |  | TAP-67834 | [TAP-67834] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - Foundation | Feature | Done |  |  | Parent Task | User Stories | 36 | 36 | 1 hr | 1 hr | 0 | 100%
TAP-67834_ATLAS | 564 | *563 |  | 06.01.14.01.00.00.00.00 | TAP-67834 | TAP-86328 | [TAP-67834_ATLAS] ¦ Execute tests updated for WolfSSH change | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 36 | 36 | 36 | 43.2 | 0 | 100%
TAP-67834_PLATFORMERS | 565 | *563 |  | 06.01.14.03.00.00.00.00 | TAP-67834 | TAP-92231 | [TAP-67834_PLATFORMERS] ¦ [V4][Platformers][V&V][PM] Update OpenSSH/SCP/SFTP impacted test cases to WolfSSH/WolfSFTP - Phase1 | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 41 | 36 | 41 | 49.2 | 5 | 100%
TAP-67834_COSSACKS | 566 | *563 |  | 06.01.14.06.00.00.00.00 | TAP-67834 | TAP-87613 | [TAP-67834_COSSACKS] ¦ [CI] Rework CI scripts to use wolfssh | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 52 | 36 | 52 | 62.4 | 16 | 100%
TAP-84546 | 567 | *7 |  | 06.01.15.00.00.00.00.00 |  | TAP-84546 | [TAP-84546] ¦ [Cyber][V4.0][V&V] Update SW Tests to Support SSH Mutual Authentication - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 34 | 34 | 1 hr | 1 hr | 0 | 100%
TAP-84546_JACOBIANS | 568 | *567 |  | 06.01.15.01.00.00.00.00 | TAP-84546 | TAP-86334 | [TAP-84546_JACOBIANS] ¦ [v4.0][Jacobians] Update manual tests to use WolfSSH/WolfSFTP | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 34 | 34 | 34 | 40.8 | 0 | 100%
TAP-84546_PIXELPOETS | 569 | *567 |  | 06.01.15.02.00.00.00.00 | TAP-84546 | TAP-86880 | [TAP-84546_PIXELPOETS] ¦ [v4.0][Positron] Update EIN-SWT_PROT-41 to use WolfSSH | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 34 | 34 | 34 | 40.8 | 0 | 100%
TAP-84546_SCRUMBLEDORES | 570 | *567 |  | 06.01.15.05.00.00.00.00 | TAP-84546 | TAP-85871 | [TAP-84546_SCRUMBLEDORES] ¦ [v4.0][Scrumbledores] Update manual tests to use WolfSSH/WolfSFTP - 2/3 | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 36 | 34 | 36 | 43.2 | 2 | 100%
TAP-84546_SUNRISERS | 571 | *567 |  | 06.01.15.10.00.00.00.00 | TAP-84546 | TAP-86384 | [TAP-84546_SUNRISERS] ¦ [v4.0][Sunrisers] Update manual tests to use WolfSSH | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 55 | 34 | 55 | 66 | 21 | 100%
TAP-105122 | 572 | *11 |  | 06.01.16.00.00.00.00.00 |  | TAP-105122 | [TAP-105122] ¦ [V4][RC1][V&V][Cyber] Test TOOLS and Test Environment Update Preparing for Formal V&V | Feature | Done |  |  | Parent Task | User Stories | 103 | 103 | 1 hr | 1 hr | 0 | 100%
TAP-105122_COSSACKS | 573 | *572 |  | 06.01.16.01.00.00.00.00 | TAP-105122 | TAP-94471 | [TAP-105122_COSSACKS] ¦ [CI] Update gather_deployment_logs.sh for v4 | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 103 | 103 | 103 | 123.6 | 0 | 100%
TAP-105122_EDISON | 574 | *572 |  | 06.01.16.28.00.00.00.00 | TAP-105122 | TAP-115481 | [TAP-105122_EDISON] ¦ wolfssh 1.4.16 in docker container has a connection issue to remote nodes | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 155 | 103 | 155 | 186 | 52 | 100%
TAP-105122_SEAMLESS | 575 | *572 |  | 06.01.16.29.00.00.00.00 | TAP-105122 | TAP-119072 | [TAP-105122_SEAMLESS] ¦ [VMs] [v4.0] NPS development for SMC emulator - Bug Fix | User Story | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 155 | 103 | 155 | 186 | 52 | 100%
TAP-105122_TRIPLETEA | 576 | *572 |  | 06.01.16.31.00.00.00.00 | TAP-105122 | TAP-114766 | [TAP-105122_TRIPLETEA] ¦ PET (protocol): Lists preconditions from another project | Issue | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 165 | 103 | 165 | 198 | 62 | 100%
TAP-88236 | 577 | *7 |  | 06.01.17.00.00.00.00.00 |  | TAP-88236 | [TAP-88236] ¦ [Cyber][V4.0][V&V] Engineering Candidate EC1 SW Test Dryrun and Test Failure Fix - Foundation | Feature | Done |  |  | Parent Task | User Stories | 322.5 | 322.5 | 1 hr | 1 hr | 0 | 100%
TAP-88236_ATLAS | 578 | *577 |  | 06.01.17.01.00.00.00.00 | TAP-88236 | TAP-96805 | [TAP-88236_ATLAS] ¦ [Cyber][Atlas][V&V] EC1 Dryrun - Part 1 | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 322.5 | 322.5 | 322.5 | 387 | 0 | 100%
TAP-88236_BOOSTERS | 579 | *577 |  | 06.01.17.08.00.00.00.00 | TAP-88236 | TAP-96803 | [TAP-88236_BOOSTERS] ¦ [Cyber][Boosters][V&V] EC1 Dryrun Result Publishing | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 336 | 322.5 | 336 | 403.2 | 13.5 | 100%
TAP-88236_CLASSY1 | 580 | *577 |  | 06.01.17.20.00.00.00.00 | TAP-88236 | TAP-102426 | [TAP-88236_CLASSY1] ¦ [Cyber][CLASSY1][V&V] PLACEHOLDER: EC1 Dryrun | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 388 | 322.5 | 388 | 465.6 | 65.5 | 100%
TAP-88236_CLASSY2 | 581 | *577 |  | 06.01.17.21.00.00.00.00 | TAP-88236 | TAP-55751 | [TAP-88236_CLASSY2] ¦ [CLASSY2][v4.0] Run and fix all USERNOT tests on latest develop | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 388 | 322.5 | 388 | 465.6 | 65.5 | 100%
TAP-88236_FRED | 582 | *577 |  | 06.01.17.27.00.00.00.00 | TAP-88236 | TAP-99127 | [TAP-88236_FRED] ¦ Try experimental staging/cyber bsp on old kontron hardware | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 411 | 322.5 | 411 | 493.2 | 88.5 | 100%
TAP-88236_HORIZON | 583 | *577 |  | 06.01.17.36.00.00.00.00 | TAP-88236 | TAP-96802 | [TAP-88236_HORIZON] ¦ [Cyber][Horizon][V&V] CART: EC1 Dryrun | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 419.5 | 322.5 | 419.5 | 503.4 | 97 | 100%
TAP-88236_PLATFORMERS | 584 | *577 |  | 06.01.17.42.00.00.00.00 | TAP-88236 | TAP-97345 | [TAP-88236_PLATFORMERS] ¦ [Cyber][Platformers][V&V][DM] EC1 Dryrun Deployment Manager test cases and failure fix for secure deployment - EtherCAT | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 428.5 | 322.5 | 428.5 | 514.2 | 106 | 100%
TAP-88236_STORMCHASERS1 | 585 | *577 |  | 06.01.17.60.00.00.00.00 | TAP-88236 | TAP-95960 | [TAP-88236_STORMCHASERS1] ¦ [Cyber][SC1] Update Impacted automation Test Items with cyber release Windows set | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 494.5 | 322.5 | 494.5 | 593.4 | 172 | 100%
TAP-88236_STORMCHASERS2 | 586 | *577 |  | 06.01.17.74.00.00.00.00 | TAP-88236 | TAP-95940 | [TAP-88236_STORMCHASERS2] ¦ [Cyber][SC2][V&V] Export SC manual protocols using latest tool | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 542.5 | 322.5 | 542.5 | 651 | 220 | 100%
TAP-88236_VISUAL | 587 | *577 |  | 06.01.17.91.00.00.00.00 | TAP-88236 | TAP-105976 | [TAP-88236_VISUAL] ¦ [v4.0][Visual][Spike] MSC mock fixes after DDS issue fixes (TAP- 104033) | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 591 | 322.5 | 591 | 709.2 | 268.5 | 100%
TAP-88236_COSSACKS | 588 | *577 |  | 06.01.17.96.00.00.00.00 | TAP-88236 | TAP-106792 | [TAP-88236_COSSACKS] ¦ [Cyber][V4.0][V&V][Cossacks] Execute Build Plans on v4.0 EC1 | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 603 | 322.5 | 603 | 723.6 | 280.5 | 100%
TAP-111448 | 589 | *7 |  | 06.01.18.00.00.00.00.00 |  | TAP-111448 | [TAP-111448] ¦ [Cyber][V4.0][V&V] Secure Deployment V&V | Feature | Done |  |  | Parent Task | User Stories | 26 | 26 | 1 hr | 1 hr | 0 | 100%
TAP-111448_PLATFORMERS | 590 | *589 |  | 06.01.18.01.00.00.00.00 | TAP-111448 | TAP-70508 | [TAP-111448_PLATFORMERS] ¦ [Cyber][Platformers][DM][V&V] V4 DM SSRs Test Coverage Update | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 26 | 26 | 26 | 31.2 | 0 | 100%
TAP-88387 | 591 | *7 |  | 06.01.19.00.00.00.00.00 |  | TAP-88387 | [TAP-88387] ¦ [Cyber][V4.0][V&V] Engineering Candidate EC1 SW Test Dryrun and Test Failure Fix - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 277.55 | 277.55 | 1 hr | 1 hr | 0 | 100%
TAP-88387_CROCNROLL | 592 | *591 |  | 06.01.19.01.00.00.00.00 | TAP-88387 | TAP-96797 | [TAP-88387_CROCNROLL] ¦ [Cyber][CrocNRoll][V&V] EC1 dry run EIN-SWT_PROT-223 | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 277.55 | 277.55 | 277.55 | 333.06 | 0 | 100%
TAP-88387_I2E | 593 | *591 |  | 06.01.19.16.00.00.00.00 | TAP-88387 | TAP-97421 | [TAP-88387_I2E] ¦ [v4.0][Cyber][I2E] - EC1 dry runs | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 294.05 | 277.55 | 294.05 | 352.86 | 16.5 | 100%
TAP-88387_JACOBIANS | 594 | *591 |  | 06.01.19.26.00.00.00.00 | TAP-88387 | TAP-96785 | [TAP-88387_JACOBIANS] ¦ [v4.0][Jacobians] EC1 dry-run for EIN-SWT_PROT-122 | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 315.05 | 277.55 | 315.05 | 378.06 | 37.5 | 100%
TAP-88387_ORGANELLES | 595 | *591 |  | 06.01.19.40.00.00.00.00 | TAP-88387 | TAP-96250 | [TAP-88387_ORGANELLES] ¦ [V4.0][Organelles][V&V] USFW pre-EC1 dryrun | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 348.25 | 277.55 | 348.25 | 417.9 | 70.7 | 100%
TAP-88387_PIXELPOETS | 596 | *591 |  | 06.01.19.49.00.00.00.00 | TAP-88387 | TAP-97580 | [TAP-88387_PIXELPOETS] ¦ [v4.0][Pixel Poets] Write ATF test for Covering SSRs in EIN-SWT_PROT-35 for Endoscope Flip | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 368.25 | 277.55 | 368.25 | 441.9 | 90.7 | 100%
TAP-88387_SCRUMBLEDORES | 597 | *591 |  | 06.01.19.78.00.00.00.00 | TAP-88387 | TAP-96898 | [TAP-88387_SCRUMBLEDORES] ¦ [v4.0][Scrumbledores] EC1 Dryrun for EIN-SWT_PROT-137 | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 416.25 | 277.55 | 416.25 | 499.5 | 138.7 | 100%
TAP-88387_SUNRISERS | 598 | *591 |  | 06.01.19.103.00.00.00.00 | TAP-88387 | TAP-97814 | [TAP-88387_SUNRISERS] ¦ [Cyber][V4.0][Sunrisers][V&V]Analyze the Test Issues found in Protocol Executions | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 469.25 | 277.55 | 469.25 | 563.1 | 191.7 | 100%
TAP-88387_TEAMBD | 599 | *591 |  | 06.01.19.122.00.00.00.00 | TAP-88387 | TAP-105268 | [TAP-88387_TEAMBD] ¦ [v4.0][TeamBD] EC1 Dry Run for EIN-SWT_PROT-213 | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 524.35 | 277.55 | 524.35 | 629.22 | 246.8 | 100%
TAP-88387_SIRIUS | 600 | *591 |  | 06.01.19.134.00.00.00.00 | TAP-88387 | TAP-103346 | [TAP-88387_SIRIUS] ¦ [v4.0] Update MIL test code as per EIN-SWI-315 updates | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 540.1 | 277.55 | 540.1 | 648.12 | 262.55 | 100%
TAP-87440 | 601 | *7 |  | 06.01.20.00.00.00.00.00 |  | TAP-87440 | [TAP-87440] ¦ [Cyber][V4.0][V&V] Update Test Items to Support Authenticated Communication - Foundation | Feature | Done |  |  | Parent Task | User Stories | 96 | 96 | 1 hr | 1 hr | 0 | 100%
TAP-87440_ATLAS | 602 | *601 |  | 06.01.20.01.00.00.00.00 | TAP-87440 | TAP-95805 | [TAP-87440_ATLAS] ¦ [Cyber][Atlas]Finalize WolfSSH, WolfSFTP, and sign_app info items | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 96 | 96 | 96 | 115.2 | 0 | 100%
TAP-87440_BOOSTERS | 603 | *601 |  | 06.01.20.04.00.00.00.00 | TAP-87440 | TAP-92696 | [TAP-87440_BOOSTERS] ¦ [Boosters] Update Impacted Test Items to Support DDS Secure/UDP Secure | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 99 | 96 | 99 | 118.8 | 3 | 100%
TAP-87440_CLASSY1 | 604 | *601 |  | 06.01.20.05.00.00.00.00 | TAP-87440 | TAP-106160 | [TAP-87440_CLASSY1] ¦ [v4.0][CLASSY] Secure DDS Usage Demo/Doc: Example Test Update and DDS Spy Tool Use with Secure DDS | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 99 | 96 | 99 | 118.8 | 3 | 100%
TAP-87440_CLASSY2 | 605 | *601 |  | 06.01.20.07.00.00.00.00 | TAP-87440 | TAP-96669 | [TAP-87440_CLASSY2] ¦ [CLASSY2] Re-check USERNOT V&V Tests after enabling UDP Secure | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 104 | 96 | 104 | 124.8 | 8 | 100%
TAP-87440_FRED | 606 | *601 |  | 06.01.20.12.00.00.00.00 | TAP-87440 | TAP-95954 | [TAP-87440_FRED] ¦ [Cyber][Fred] Update Impacted Test Items to DDS/UDP Secure | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 120 | 96 | 120 | 144 | 24 | 100%
TAP-87440_PLATFORMERS | 607 | *601 |  | 06.01.20.20.00.00.00.00 | TAP-87440 | TAP-97531 | [TAP-87440_PLATFORMERS] ¦ [v4][Platformers][DM][V&V] Update CommonCode and included shared modules with documentation and usage examples | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 131 | 96 | 131 | 157.2 | 35 | 100%
TAP-87440_VISUAL | 608 | *601 |  | 06.01.20.29.00.00.00.00 | TAP-87440 | TAP-87182 | [TAP-87440_VISUAL] ¦ [v4.0][Visual] Investigate if any test cases were impacted by DDS Secure and UDP Secure enabling | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 171 | 96 | 171 | 205.2 | 75 | 100%
TAP-87440_COSSACKS | 609 | *601 |  | 06.01.20.31.00.00.00.00 | TAP-87440 | TAP-106990 | [TAP-87440_COSSACKS] ¦ [CI] Set up automated test execution using WolfSSH and non-WolfSSH Chico configuration | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 173 | 96 | 173 | 207.6 | 77 | 100%
TAP-87440_EDISON | 610 | *601 |  | 06.01.20.33.00.00.00.00 | TAP-87440 | TAP-107107 | [TAP-87440_EDISON] ¦ [WolfSSH] Update the WolfSSH in build environment | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 174 | 96 | 174 | 208.8 | 78 | 100%
TAP-86973 | 611 | *7 |  | 06.01.21.00.00.00.00.00 |  | TAP-86973 | [TAP-86973] ¦ [Cyber][V4.0][V&V] Update Test Items to Support Authenticated Communication - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 57.5 | 57.5 | 1 hr | 1 hr | 0 | 100%
TAP-86973_BUGHUNTERS | 612 | *611 |  | 06.01.21.01.00.00.00.00 | TAP-86973 | TAP-95950 | [TAP-86973_BUGHUNTERS] ¦ [v4.0][Bug Hunters] DDS/UDP Secure and Secure EtherCAT Training | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 57.5 | 57.5 | 57.5 | 69 | 0 | 100%
TAP-86973_CROCNROLL | 613 | *611 |  | 06.01.21.02.00.00.00.00 | TAP-86973 | TAP-97914 | [TAP-86973_CROCNROLL] ¦ [V4.0][CrocNRoll] Support IDU Standalone cybersecurity updates | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 57.5 | 57.5 | 57.5 | 69 | 0 | 100%
TAP-86973_I2E | 614 | *611 |  | 06.01.21.03.00.00.00.00 | TAP-86973 | TAP-102036 | [TAP-86973_I2E] ¦ [Cyber][I2E] Update IDU tools WolfSSH common code strings to new name | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 57.5 | 57.5 | 57.5 | 69 | 0 | 100%
TAP-86973_JACOBIANS | 615 | *611 |  | 06.01.21.04.00.00.00.00 | TAP-86973 | TAP-96752 | [TAP-86973_JACOBIANS] ¦ [V4.0][Jacobians] Investigate and Update swiv Common Code based on Chico and WolfSSH | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 57.5 | 57.5 | 57.5 | 69 | 0 | 100%
TAP-86973_PIXELPOETS | 616 | *611 |  | 06.01.21.09.00.00.00.00 | TAP-86973 | TAP-96892 | [TAP-86973_PIXELPOETS] ¦ [v4.0][SPIKE] Investigate running ethercat_master_maintenance-4.0.0 for EIN-SWT_PROT-43 | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 65 | 57.5 | 65 | 78 | 7.5 | 100%
TAP-86973_SCRUMBLEDORES | 617 | *611 |  | 06.01.21.28.00.00.00.00 | TAP-86973 | TAP-96972 | [TAP-86973_SCRUMBLEDORES] ¦ [v4.0][Organelles] Update DDS/UDP Secure and WolfSSH for EIN-TC_SW-536 | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 104 | 57.5 | 104 | 124.8 | 46.5 | 100%
TAP-106162 | 618 | *7 |  | 06.01.22.00.00.00.00.00 |  | TAP-106162 | [TAP-106162] ¦ [Cyber][V&V] Test certificate expiration notifications | Feature | Done |  |  | Parent Task | User Stories | 59 | 59 | 1 hr | 1 hr | 0 | 100%
TAP-106162_INFRAWARRIORS | 619 | *618 |  | 06.01.22.01.00.00.00.00 | TAP-106162 | TAP-95755 | [TAP-106162_INFRAWARRIORS] ¦ [Cyber][Platformers][SystemMonitor][V&V] Create Tests EIN-TC_SW-3797/ CYB-TC_SW-3833 for CYB-SSR_PROCESS-96 Certificate Expired - ACA | User Story | Done | Released Product Engineering - Infrawarriors | INFRAWARRIORS | Child Task | User Stories | 59 | 59 | 59 | 70.8 | 0 | 100%
TAP-88231 | 620 | *7 |  | 06.01.23.00.00.00.00.00 |  | TAP-88231 | [TAP-88231] ¦ [V4][RC1][V&V] [Cyber] Post-EC1 SW Test Dryrun and Test Failure Fix on Test Build - Foundation | Feature | Done |  |  | Parent Task | User Stories | 398 | 398 | 1 hr | 1 hr | 0 | 100%
TAP-88231_ATLAS | 621 | *620 |  | 06.01.23.01.00.00.00.00 | TAP-88231 | TAP-96775 | [TAP-88231_ATLAS] ¦ [Cyber][Atlas][V&V] EC2 Dryrun - Part 1 | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 398 | 398 | 398 | 477.6 | 0 | 100%
TAP-88231_BOOSTERS | 622 | *620 |  | 06.01.23.11.00.00.00.00 | TAP-88231 | TAP-96777 | [TAP-88231_BOOSTERS] ¦ [Cyber][Boosters][V&V] PLACEHOLDER: EC2 Dryrun | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 419 | 398 | 419 | 502.8 | 21 | 100%
TAP-88231_CLASSY1 | 623 | *620 |  | 06.01.23.32.00.00.00.00 | TAP-88231 | TAP-114797 | [TAP-88231_CLASSY1] ¦ [Classy] Dry run Sprint 1 | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 483 | 398 | 483 | 579.6 | 85 | 100%
TAP-88231_CLASSY2 | 624 | *620 |  | 06.01.23.49.00.00.00.00 | TAP-88231 | TAP-114768 | [TAP-88231_CLASSY2] ¦ [CLASSY2] Fix USERNOT SIL test cases | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 542 | 398 | 542 | 650.4 | 144 | 100%
TAP-88231_FRED | 625 | *620 |  | 06.01.23.60.00.00.00.00 | TAP-88231 | TAP-96801 | [TAP-88231_FRED] ¦ [Cyber][Fred][V&V] EC1 Dryrun: Results in Jama | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 597 | 398 | 597 | 716.4 | 199 | 100%
TAP-88231_HORIZON | 626 | *620 |  | 06.01.23.67.00.00.00.00 | TAP-88231 | TAP-106454 | [TAP-88231_HORIZON] ¦ [Cyber][Horizon][V&V][DevDoesVnV] Report EC2 Dryrun Results | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 607.5 | 398 | 607.5 | 729 | 209.5 | 100%
TAP-88231_PLATFORMERS | 627 | *620 |  | 06.01.23.74.00.00.00.00 | TAP-88231 | TAP-95768 | [TAP-88231_PLATFORMERS] ¦ [Cyber][Platformers][V&V][NTWK-PERSTG] Dryrun NTWK and PERSTG test cases and Fix failure | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 614.5 | 398 | 614.5 | 737.4 | 216.5 | 100%
TAP-88231_STORMCHASERS1 | 628 | *620 |  | 06.01.23.96.00.00.00.00 | TAP-88231 | TAP-105066 | [TAP-88231_STORMCHASERS1] ¦ [Cyber][StormChaser1][V&V] Automation pre-EC2 Dryrun and Test Failure Fix | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 682.5 | 398 | 682.5 | 819 | 284.5 | 100%
TAP-88231_STORMCHASERS2 | 629 | *620 |  | 06.01.23.107.00.00.00.00 | TAP-88231 | TAP-96781 | [TAP-88231_STORMCHASERS2] ¦ [Cyber][StormChasers2][V&V] EC2 Dry run manual tests | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 709.5 | 398 | 709.5 | 851.4 | 311.5 | 100%
TAP-88231_VISUAL | 630 | *620 |  | 06.01.23.113.00.00.00.00 | TAP-88231 | TAP-119126 | [TAP-88231_VISUAL] ¦ [v4.0][Visual][V&V] EC2 Dryrun after TAP-113124-Part2 | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 727 | 398 | 727 | 872.4 | 329 | 100%
TAP-88231_COSSACKS | 631 | *620 |  | 06.01.23.124.00.00.00.00 | TAP-88231 | TAP-114931 | [TAP-88231_COSSACKS] ¦ [CI] EC2 - Deploy system36 and Config EC2 dryrun | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 762 | 398 | 762 | 914.4 | 364 | 100%
TAP-88386 | 632 | *7 |  | 06.01.24.00.00.00.00.00 |  | TAP-88386 | [TAP-88386] ¦ [V4][RC1][V&V] [Cyber] Post-EC1 SW Test Dryrun and Test Failure Fix on Test Build - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 156.45 | 156.45 | 1 hr | 1 hr | 0 | 100%
TAP-88386_FUSION | 633 | *632 |  | 06.01.24.01.00.00.00.00 | TAP-88386 | TAP-105463 | [TAP-88386_FUSION] ¦ [v4.0][Fusion] EC2 Dryrun protocol EIN-SWT_PROT-42 system deactivation startup | User Story | Done | Advanced Instruments - Fusion | FUSION | Child Task | User Stories | 156.45 | 156.45 | 156.45 | 187.74 | 0 | 100%
TAP-88386_I2E | 634 | *632 |  | 06.01.24.09.00.00.00.00 | TAP-88386 | TAP-113421 | [TAP-88386_I2E] ¦ [v4.0][I2E][V&V] Fix Pre-EC2 V&V Dry Run Results | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 165.45 | 156.45 | 165.45 | 198.54 | 9 | 100%
TAP-88386_JACOBIANS | 635 | *632 |  | 06.01.24.22.00.00.00.00 | TAP-88386 | TAP-96784 | [TAP-88386_JACOBIANS] ¦ [v4.0][Jacobians] Practice Post EC1 Dryrun for one of the Manual Protocols | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 198.45 | 156.45 | 198.45 | 238.14 | 42 | 100%
TAP-88386_MACHETE | 636 | *632 |  | 06.01.24.31.00.00.00.00 | TAP-88386 | TAP-105464 | [TAP-88386_MACHETE] ¦ [v4.0][Machete][GUI] EC2 Dryrun protocol EIN-SWT_PROT-45 instrument name | User Story | Done | Advanced Instruments - Machete | MACHETE | Child Task | User Stories | 218.45 | 156.45 | 218.45 | 262.14 | 62 | 100%
TAP-88386_PIXELPOETS | 637 | *632 |  | 06.01.24.36.00.00.00.00 | TAP-88386 | TAP-105461 | [TAP-88386_PIXELPOETS] ¦ [v4.0][Pixel Poets] EC2 Dryrun protocol EIN-SWT_PROT-38 acad arm id/functional alarm | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 224.45 | 156.45 | 224.45 | 269.34 | 68 | 100%
TAP-88386_SCRUMBLEDORES | 638 | *632 |  | 06.01.24.50.00.00.00.00 | TAP-88386 | TAP-96786 | [TAP-88386_SCRUMBLEDORES] ¦ [Cyber][Scrumbledores][V&V] EC2 and EC3 Dryruns for Impacted Test Cases (Part 1) | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 242.45 | 156.45 | 242.45 | 290.94 | 86 | 100%
TAP-88386_TEAMBD | 639 | *632 |  | 06.01.24.78.00.00.00.00 | TAP-88386 | TAP-115080 | [TAP-88386_TEAMBD] ¦ [Cyber][TeamBD][V&V] JAMA Execution Practice EIN-SWT_PROT-223 for v4.0 EC2 | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 300.65 | 156.45 | 300.65 | 360.78 | 144.2 | 100%
TAP-105883 | 640 | *7 |  | 06.01.25.00.00.00.00.00 |  | TAP-105883 | [TAP-105883] ¦ [Cyber][V4.0][V&V] Test Automation of Controls Nominal Behavior SSRs | Feature | Done |  |  | Parent Task | User Stories | 88.25 | 88.25 | 1 hr | 1 hr | 0 | 100%
TAP-105883_BUGHUNTERS | 641 | *640 |  | 06.01.25.01.00.00.00.00 | TAP-105883 | TAP-105930 | [TAP-105883_BUGHUNTERS] ¦ [v4.0][BH] Convert EIN-TC_SW-1319 to MIL approach - Test strategy | User Story | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 88.25 | 88.25 | 88.25 | 105.9 | 0 | 100%
TAP-105883_CROCNROLL | 642 | *640 |  | 06.01.25.17.00.00.00.00 | TAP-105883 | TAP-95889 | [TAP-105883_CROCNROLL] ¦ [v4.0][CrocNRoll] SysIL Test Updates for EIN-TC_SW-855 | User Story | Done | Advanced Instruments - CrocNRoll | CROCNROLL | Child Task | User Stories | 139.25 | 88.25 | 139.25 | 167.1 | 51 | 100%
TAP-105883_JACOBIANS | 643 | *640 |  | 06.01.25.19.00.00.00.00 | TAP-105883 | TAP-97155 | [TAP-105883_JACOBIANS] ¦ Create MIL test for Head Tracker Frozen Detection (1/2): Develop Test Strategy | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 141.25 | 88.25 | 141.25 | 169.5 | 53 | 100%
TAP-105883_SCRUMBLEDORES | 644 | *640 |  | 06.01.25.21.00.00.00.00 | TAP-105883 | TAP-105946 | [TAP-105883_SCRUMBLEDORES] ¦ [v4.0][Scrumbledores] Convert EIN-TC_SW-581 to MIL approach - Test strategy | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 146.25 | 88.25 | 146.25 | 175.5 | 58 | 100%
TAP-105883_SUNRISERS | 645 | *640 |  | 06.01.25.23.00.00.00.00 | TAP-105883 | TAP-106518 | [TAP-105883_SUNRISERS] ¦ [MIL][Sunrisers] Convert Manual Tests to MIL - EIN-SSR_RASW-323 | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 149.25 | 88.25 | 149.25 | 179.1 | 61 | 100%
TAP-88384 | 646 | *11 |  | 06.01.26.00.00.00.00.00 |  | TAP-88384 | [TAP-88384] ¦ [Cyber][V4.0][V&V] TRR Deliverables Preparation - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-88384_I2E | 647 | *646 |  | 06.01.26.01.00.00.00.00 | TAP-88384 | TAP-102260 | [TAP-88384_I2E] ¦ [V4.0][V&V][I2E] TRR Documents Soft Approved | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-87425 | 648 | *11 |  | 06.01.27.00.00.00.00.00 |  | TAP-87425 | [TAP-87425] ¦ [Cyber][V4.0][V&V] TRR Deliverables Preparation - Foundation | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-87425_ATLAS | 649 | *648 |  | 06.01.27.01.00.00.00.00 | TAP-87425 | TAP-96117 | [TAP-87425_ATLAS] ¦ [V4.0][Atlas] Create protocol documents for new tests | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-105169 | 650 | *7 |  | 06.01.28.00.00.00.00.00 |  | TAP-105169 | [TAP-105169] ¦ [Cyber][Platformers][V&V] V&V for Ethercat CM and expiration notifications | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-105169_PLATFORMERS | 651 | *650 |  | 06.01.28.01.00.00.00.00 | TAP-105169 | TAP-95759 | [TAP-105169_PLATFORMERS] ¦ [Cyber][Platformers][PM][V&V] Enhance Tests for EIN-SSR_PROCESS-46 / CYB-SSR_PROCESS-88 | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-108089 | 652 | *11 |  | 06.01.29.00.00.00.00.00 |  | TAP-108089 | [TAP-108089] ¦ [V4][RC1][V&V] TRR Project Wide Documents Release | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-108089_DOCUMENTOWNERS | 653 | *652 |  | 06.01.29.01.00.00.00.00 | TAP-108089 | TAP-95945 | [TAP-108089_DOCUMENTOWNERS] ¦ [Cyber] JAMA Merge - Product Security to Main Einstein Full project | User Story | Done | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-87421 | 654 | *11 |  | 06.01.30.00.00.00.00.00 |  | TAP-87421 | [TAP-87421] ¦ [V4][RC1][V&V] [Cyber] TRR Deliverables Release - Foundation | Feature | Done |  |  | Parent Task | User Stories | 201 | 201 | 1 hr | 1 hr | 0 | 100%
TAP-87421_ATLAS | 655 | *654 |  | 06.01.30.01.00.00.00.00 | TAP-87421 | TAP-102218 | [TAP-87421_ATLAS] ¦ [Cyber][V&V][Atlas] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 201 | 201 | 201 | 241.2 | 0 | 100%
TAP-87421_BOOSTERS | 656 | *654 |  | 06.01.30.14.00.00.00.00 | TAP-87421 | TAP-102219 | [TAP-87421_BOOSTERS] ¦ [Cyber][V&V][Boosters] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 226 | 201 | 226 | 271.2 | 25 | 100%
TAP-87421_CLASSY1 | 657 | *654 |  | 06.01.30.20.00.00.00.00 | TAP-87421 | TAP-102227 | [TAP-87421_CLASSY1] ¦ [Cyber][V&V][CLASSY1] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 237.5 | 201 | 237.5 | 285 | 36.5 | 100%
TAP-87421_CLASSY2 | 658 | *654 |  | 06.01.30.26.00.00.00.00 | TAP-87421 | TAP-114800 | [TAP-87421_CLASSY2] ¦ [Classy] Dry run Sprint 4 | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 251.5 | 201 | 251.5 | 301.8 | 50.5 | 100%
TAP-87421_FRED | 659 | *654 |  | 06.01.30.33.00.00.00.00 | TAP-87421 | TAP-124180 | [TAP-87421_FRED] ¦ Added possibility to use verified files in RASA hil config | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 271.5 | 201 | 271.5 | 325.8 | 70.5 | 100%
TAP-87421_HORIZON | 660 | *654 |  | 06.01.30.35.00.00.00.00 | TAP-87421 | TAP-122639 | [TAP-87421_HORIZON] ¦ [V4.0][V&V][Horizon] Cleanup JAMA after SWR_ACS-101 archival: Update: Revert this | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 272.5 | 201 | 272.5 | 327 | 71.5 | 100%
TAP-87421_PLATFORMERS | 661 | *654 |  | 06.01.30.36.00.00.00.00 | TAP-87421 | TAP-53197 | [TAP-87421_PLATFORMERS] ¦ [Cyber][platformers][V&V][CertM] Update Certificate Manager Testability Change Design Document | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 272.5 | 201 | 272.5 | 327 | 71.5 | 100%
TAP-87421_STORMCHASERS1 | 662 | *654 |  | 06.01.30.45.00.00.00.00 | TAP-87421 | TAP-112395 | [TAP-87421_STORMCHASERS1] ¦ [V4.0][[V&V][StormChasers1] Update manual Test Protocol documents in Jama | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 311.5 | 201 | 311.5 | 373.8 | 110.5 | 100%
TAP-87421_STORMCHASERS2 | 663 | *654 |  | 06.01.30.55.00.00.00.00 | TAP-87421 | TAP-102274 | [TAP-87421_STORMCHASERS2] ¦ [V4.0][V&V][StormChasers2] Create, review and release PROT-28 | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 335 | 201 | 335 | 402 | 134 | 100%
TAP-87421_VISUAL | 664 | *654 |  | 06.01.30.63.00.00.00.00 | TAP-87421 | TAP-102233 | [TAP-87421_VISUAL] ¦ [Cyber][V&V][Visual] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 351.5 | 201 | 351.5 | 421.8 | 150.5 | 100%
TAP-87421_COSSACKS | 665 | *654 |  | 06.01.30.65.00.00.00.00 | TAP-87421 | TAP-124059 | [TAP-87421_COSSACKS] ¦ [CI][v4.0][RC1][Cossacks][Chico] Check chico version for v4.0 RC1 | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 356.5 | 201 | 356.5 | 427.8 | 155.5 | 100%
TAP-87421_EDISON | 666 | *654 |  | 06.01.30.74.00.00.00.00 | TAP-87421 | TAP-115823 | [TAP-87421_EDISON] ¦ Integrate testability documents into EIN_NG | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 379.5 | 201 | 379.5 | 455.4 | 178.5 | 100%
TAP-87421_INBETWEENERS | 667 | *654 |  | 06.01.30.75.00.00.00.00 | TAP-87421 | TAP-121405 | [TAP-87421_INBETWEENERS] ¦ [v4.0] Update Testability Reference for TESTSWIs | User Story | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 379.5 | 201 | 379.5 | 455.4 | 178.5 | 100%
TAP-88385 | 668 | *15 | *11 | 06.01.31.00.00.00.00.00 |  | TAP-88385 | [TAP-88385] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - AdvancedInstruments | Feature | Groomed |  |  | Parent Task | User Stories | 245.75 | 1.5 | 1 hr | 1 hr | 244.25 | 0.6104%
TAP-88385_FUSION | 669 | *668 |  | 06.01.31.01.00.00.00.00 | TAP-88385 | TAP-115024 | [TAP-88385_FUSION] ¦ [v4.0][Fusion] V&V Formal Execution EIN-SWT_PROT - 39 acad notifications | User Story | Groomed | Advanced Instruments - Fusion | FUSION | Child Task | User Stories | 245.75 | 1.5 | 245.75 | 294.9 | 244.25 | 0.6104%
TAP-88385_I2E | 670 | *668 |  | 06.01.31.08.00.00.00.00 | TAP-88385 | TAP-102194 | [TAP-88385_I2E] ¦ [V4.0][I2E][V&V] Formal Test Execution on RC1 | User Story | In progress | Advanced Instruments - I2E | I2E | Child Task | User Stories | 273.75 | 1.5 | 273.75 | 328.5 | 272.25 | 0.5479%
TAP-88385_JACOBIANS | 671 | *668 |  | 06.01.31.10.00.00.00.00 | TAP-88385 | TAP-113942 | [TAP-88385_JACOBIANS] ¦ [V4.0][V&V][Jacobians] Formal Test Execution of EIN-SWT_PROT-122 over RC1 | User Story | In progress | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 275.75 | 1.5 | 275.75 | 330.9 | 274.25 | 0.544%
TAP-88385_PIXELPOETS | 672 | *668 |  | 06.01.31.16.00.00.00.00 | TAP-88385 | TAP-115060 | [TAP-88385_PIXELPOETS] ¦ [v4.0][PixelPoets] V&V Formal Execution - GUI Automation | User Story | Groomed | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 294.5 | 1.5 | 294.5 | 353.4 | 293 | 0.5093%
TAP-88385_REMUS | 673 | *668 |  | 06.01.31.25.00.00.00.00 | TAP-88385 | TAP-114277 | [TAP-88385_REMUS] ¦ [V4.0][V&V][Remus] Formal Test Execution for EIN-SWT_PROT-237 | User Story | In progress | Advanced Instruments - Remus | REMUS | Child Task | User Stories | 317.5 | 1.5 | 317.5 | 381 | 316 | 0.4724%
TAP-88385_ROMULUS | 674 | *668 |  | 06.01.31.45.00.00.00.00 | TAP-88385 | TAP-114282 | [TAP-88385_ROMULUS] ¦ [V4.0][V&V][Romulus] Formal Test Execution for EIN-SWT_PROT-91 | User Story | In progress | Advanced Instruments - Romulus | ROMULUS | Child Task | User Stories | 383 | 1.5 | 383 | 459.6 | 381.5 | 0.3916%
TAP-88385_TEAMBD | 675 | *668 |  | 06.01.31.74.00.00.00.00 | TAP-88385 | TAP-124559 | [TAP-88385_TEAMBD] ¦ [v4.0][TeamBD] Release IDU Subsystem Verification Report | User Story | Groomed | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 450.5 | 1.5 | 450.5 | 540.6 | 449 | 0.333%
TAP-87426 | 676 | *15 | *11 | 06.01.32.00.00.00.00.00 |  | TAP-87426 | [TAP-87426] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - Foundation | Feature | Groomed |  |  | Parent Task | User Stories | 202 | 19 | 1 hr | 1 hr | 183 | 9.406%
TAP-87426_ATLAS | 677 | *676 |  | 06.01.32.01.00.00.00.00 | TAP-87426 | TAP-115985 | [TAP-87426_ATLAS] ¦ [V4.0][V&V][ATLAS] Formal Test Execution on RC1 - QNX Zynq | User Story | In progress | Foundation - Atlas | ATLAS | Child Task | User Stories | 202 | 19 | 202 | 242.4 | 183 | 9.406%
TAP-87426_BOOSTERS | 678 | *676 |  | 06.01.32.07.00.00.00.00 | TAP-87426 | TAP-116117 | [TAP-87426_BOOSTERS] ¦ [V4.0][V&V][Boosters] Formal Test Execution on RC1 for KPI | User Story | In progress | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 218 | 19 | 218 | 261.6 | 199 | 8.716%
TAP-87426_CLASSY | 679 | *676 |  | 06.01.32.10.00.00.00.00 | TAP-87426 | TAP-102190 | [TAP-87426_CLASSY] ¦ [V4.0][V&V][CLASSY] Communication Formal Test Execution on RC1 | User Story | In progress | Foundation - Classy | CLASSY | Child Task | User Stories | 223 | 19 | 223 | 267.6 | 204 | 8.52%
TAP-87426_FRED | 680 | *676 |  | 06.01.32.16.00.00.00.00 | TAP-87426 | TAP-102204 | [TAP-87426_FRED] ¦ [V4.0][V&V][Fred] Formal Test Execution on RC1 | User Story | Open | Foundation - Fred | FRED | Child Task | User Stories | 242 | 19 | 242 | 290.4 | 223 | 7.851%
TAP-87426_HORIZON | 681 | *676 |  | 06.01.32.17.00.00.00.00 | TAP-87426 | TAP-102206 | [TAP-87426_HORIZON] ¦ [V4.0][V&V][Horizon] Formal Test Execution on RC1 | User Story | In progress | Foundation - Horizon | HORIZON | Child Task | User Stories | 242 | 19 | 242 | 290.4 | 223 | 7.851%
TAP-87426_PLATFORMERS | 682 | *676 |  | 06.01.32.18.00.00.00.00 | TAP-87426 | TAP-122265 | [TAP-87426_PLATFORMERS] ¦ [V&V][Cyber][Platformers][PLACEHOLDER] Holding VV Capacity to fix any upcomming bamboo failures pre-TRR | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 242 | 19 | 242 | 290.4 | 223 | 100%
TAP-87426_STORMCHASERS | 683 | *676 |  | 06.01.32.26.00.00.00.00 | TAP-87426 | TAP-115389 | [TAP-87426_STORMCHASERS] ¦ [V4.0][V&V][SC] RE00518748 Test Protocol - SC Monitoring: SCDC and Scaler Communication Loss Detection - Manual execution on RC1 | User Story | In progress | Foundation - Storm Chasers | STORMCHASERS | Child Task | User Stories | 277 | 19 | 277 | 332.4 | 258 | 6.859%
TAP-87426_VISUAL | 684 | *676 |  | 06.01.32.35.00.00.00.00 | TAP-87426 | TAP-123534 | [TAP-87426_VISUAL] ¦ [V4.0][Visual][V&V] Test cycle creation and publish the test results to Jama | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 337 | 19 | 337 | 404.4 | 318 | 100%
TAP-87426_COSSACKS | 685 | *676 |  | 06.01.32.38.00.00.00.00 | TAP-87426 | TAP-116740 | [TAP-87426_COSSACKS] ¦ [CI] Enable hw discovery and version table in ESWTNG BPs | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 343 | 19 | 343 | 411.6 | 324 | 100%
TAP-87426_POWERSTORMERS | 686 | *676 |  | 06.01.32.43.00.00.00.00 | TAP-87426 | TAP-123850 | [TAP-87426_POWERSTORMERS] ¦ Request to update PowerBI dashboard for V4 release | User Story | Open | Shared Services - Power Stormers | POWERSTORMERS | Child Task | User Stories | 355 | 19 | 355 | 426 | 336 | 5.352%
TAP-87426_TRIPLETEA | 687 | *676 |  | 06.01.32.44.00.00.00.00 | TAP-87426 | TAP-125999 | [TAP-87426_TRIPLETEA] ¦ [Chico] Make a more precise logging of errors | User Story | Groomed | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 355 | 19 | 355 | 426 | 336 | 5.352%
TAP-113928 | 688 | *15 |  | 06.01.33.00.00.00.00.00 |  | TAP-113928 | [TAP-113928] ¦ [V4.0][RC1][V&V] Formal Test Execution on RC1 - CoreInstruments | Feature | Groomed |  |  | Parent Task | User Stories | 61 | 1 | 1 hr | 1 hr | 60 | 1.639%
TAP-113928_HAPPYJAWS | 689 | *688 |  | 06.01.33.01.00.00.00.00 | TAP-113928 | TAP-125681 | [TAP-113928_HAPPYJAWS] ¦ [Cyber][Happy Jaws][V&V] Upgrade IDU Standalone(s) to v4 RC1 Formal Build | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 61 | 1 | 61 | 73.2 | 60 | 100%
TAP-113928_PUPPETEERS | 690 | *688 |  | 06.01.33.05.00.00.00.00 | TAP-113928 | TAP-126598 | [TAP-113928_PUPPETEERS] ¦ [V4.0][RC1][V&V][Puppeteers][SPIKE] Formal Test Execution on RC1 - CoreInstruments | User Story | In progress | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 73 | 1 | 73 | 87.6 | 72 | 1.37%
TAP-113928_SIRIUS | 691 | *688 |  | 06.01.33.16.00.00.00.00 | TAP-113928 | TAP-114698 | [TAP-113928_SIRIUS] ¦ [v4.0][Sirius] Formal Execution of EIN-SWT_PROT-216 | User Story | In progress | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 108 | 1 | 108 | 129.6 | 107 | 0.9259%
TAP-88621 | 692 | *11 |  | 06.01.34.00.00.00.00.00 |  | TAP-88621 | [TAP-88621] ¦ [V4][RC1][V&V] [Cyber] TRR Deliverables Release - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 152 | 152 | 1 hr | 1 hr | 0 | 100%
TAP-88621_FUSION | 693 | *692 |  | 06.01.34.01.00.00.00.00 | TAP-88621 | TAP-118423 | [TAP-88621_FUSION] ¦ [V&V][Fusion]New TC/TD for new MSC SSR | User Story | Done | Advanced Instruments - Fusion | FUSION | Child Task | User Stories | 152 | 152 | 152 | 182.4 | 0 | 100%
TAP-88621_I2E | 694 | *692 |  | 06.01.34.04.00.00.00.00 | TAP-88621 | TAP-102236 | [TAP-88621_I2E] ¦ [Cyber][V&V][I2E] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 154 | 152 | 154 | 184.8 | 2 | 100%
TAP-88621_JACOBIANS | 695 | *692 |  | 06.01.34.11.00.00.00.00 | TAP-88621 | TAP-102237 | [TAP-88621_JACOBIANS] ¦ [Cyber][V&V][Jacobians] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 163 | 152 | 163 | 195.6 | 11 | 100%
TAP-88621_MACHETE | 696 | *692 |  | 06.01.34.20.00.00.00.00 | TAP-88621 | TAP-122582 | [TAP-88621_MACHETE] ¦ [V4.0][PixelPoets] Export and release EIN-SWT_PROT-43 to Agile | User Story | Done | Advanced Instruments - Machete | MACHETE | Child Task | User Stories | 177 | 152 | 177 | 212.4 | 25 | 100%
TAP-88621_PIXELPOETS | 697 | *692 |  | 06.01.34.21.00.00.00.00 | TAP-88621 | TAP-102239 | [TAP-88621_PIXELPOETS] ¦ [Cyber][V&V][PixelPoets] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 177 | 152 | 177 | 212.4 | 25 | 100%
TAP-88621_SCRUMBLEDORES | 698 | *692 |  | 06.01.34.37.00.00.00.00 | TAP-88621 | TAP-102240 | [TAP-88621_SCRUMBLEDORES] ¦ [Cyber][V&V][Scrumbledores] JAMA Merge for MIL Items | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 198 | 152 | 198 | 237.6 | 46 | 100%
TAP-88621_TEAMBD | 699 | *692 |  | 06.01.34.67.00.00.00.00 | TAP-88621 | TAP-102242 | [TAP-88621_TEAMBD] ¦ [Cyber][V&V][TeamBD] JAMA Merge - Support for Product Security to Einstein JAMA Merge | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 273 | 152 | 273 | 327.6 | 121 | 100%
TAP-125121 | 700 | *13 |  | 06.01.35.00.00.00.00.00 |  | TAP-125121 | [TAP-125121] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - AdvancedInstr | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-125126 | 701 | *15 |  | 06.01.36.00.00.00.00.00 |  | TAP-125126 | [TAP-125126] ¦ [V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - AdvancedInstr | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-125127 | 702 | *15 |  | 06.01.38.00.00.00.00.00 |  | TAP-125127 | [TAP-125127] ¦ [V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - CoreInstr | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-125125 | 703 | *15 |  | 06.01.39.00.00.00.00.00 |  | TAP-125125 | [TAP-125125] ¦ 🚩[V4.0][RC2][Cyber][V&V] Formal Test Execution on RC2 - Foundation | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-125120 | 704 | *13 |  | 06.01.41.00.00.00.00.00 |  | TAP-125120 | [TAP-125120] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - Foundation | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-125122 | 705 | *13 |  | 06.01.42.00.00.00.00.00 |  | TAP-125122 | [TAP-125122] ¦ [V4.0][RC2][Cyber][V&V] RC2 TRR Deliverables Release - CoreInstr | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-115485 | 706 | *9 |  | 06.02.01.01.00.00.00.00 |  | TAP-115485 | [TAP-115485] ¦ [Cyber] Tracking Documentation For Design Planning | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-115485_ATLAS | 707 | *706 |  | 06.02.01.01.01.00.00.00 | TAP-115485 | TAP-115487 | [TAP-115485_ATLAS] ¦ EIN Modeling Standards | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-115485_DOCUMENTOWNERS | 708 | *706 |  | 06.02.01.01.03.00.00.00 | TAP-115485 | TAP-115489 | [TAP-115485_DOCUMENTOWNERS] ¦ EIN Software Level of Concern | User Story | Open | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-115498 | 709 | *9 |  | 06.02.01.02.00.00.00.00 |  | TAP-115498 | [TAP-115498] ¦ [Cyber] Tracking Documentation For Design Inputs | Feature | PROPOSED |  |  | Parent Task | User Stories | 4.5 | 4.5 | 1 hr | 1 hr | 0 | 100%
TAP-115498_DOCUMENTOWNERS | 710 | *709 |  | 06.02.01.02.01.00.00.00 | TAP-115498 | TAP-115500 | [TAP-115498_DOCUMENTOWNERS] ¦ Software Requirements Traceability Matrix | User Story | Done | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 4.5 | 4.5 | 4.5 | 5.4 | 0 | 100%
TAP-115498_FRED | 711 | *709 |  | 06.02.01.02.03.00.00.00 | TAP-115498 | TAP-115502 | [TAP-115498_FRED] ¦ SRA PS/PL Interfaces | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 4.5 | 4.5 | 4.5 | 5.4 | 0 | 100%
TAP-115498_TOOLSRULES | 712 | *709 |  | 06.02.01.02.05.00.00.00 | TAP-115498 | TAP-115506 | [TAP-115498_TOOLSRULES] ¦ ESAT Software Architecture v4 | User Story | Open | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 4.5 | 4.5 | 4.5 | 5.4 | 0 | 100%
TAP-115498_CASTLEBLACK | 713 | *709 |  | 06.02.01.02.10.00.00.00 | TAP-115498 | TAP-103927 | [TAP-115498_CASTLEBLACK] ¦ [Compliance] Update SW Architecture document for v4.0 | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 4.5 | 4.5 | 4.5 | 5.4 | 0 | 100%
TAP-115498_HORIZON | 714 | *709 |  | 06.02.01.02.11.00.00.00 | TAP-115498 | TAP-106758 | [TAP-115498_HORIZON] ¦ [Cyber][V4.0][V&V] Cart/TPSC/FSE EOL Impact Analysis on Software Tests | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 4.5 | 4.5 | 4.5 | 5.4 | 0 | 100%
TAP-115511 | 715 | *17 |  | 06.02.01.03.00.00.00.00 |  | TAP-115511 | [TAP-115511] ¦ [V4.0][RC1][Cyber][Project Wide V&V Reports] Tracking Documentation For Design Verification | Feature | Accepted |  |  | Parent Task | User Stories | 28 | 3 | 1 hr | 1 hr | 25 | 10.71%
TAP-115511_DOCUMENTOWNERS | 716 | *715 |  | 06.02.01.03.01.00.00.00 | TAP-115511 | TAP-115512 | [TAP-115511_DOCUMENTOWNERS] ¦ Unresolved and Resolved Anomalies List | User Story | Open | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 28 | 3 | 28 | 33.6 | 25 | 10.71%
TAP-115511_PLATFORMERS | 717 | *715 |  | 06.02.01.03.02.00.00.00 | TAP-115511 | TAP-115513 | [TAP-115511_PLATFORMERS] ¦ Master Software Verification Report | User Story | Open | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 28 | 3 | 28 | 33.6 | 25 | 10.71%
TAP-115511_ATLAS | 718 | *715 |  | 06.02.01.03.05.00.00.00 | TAP-115511 | TAP-115519 | [TAP-115511_ATLAS] ¦ Update EIN Software Verification Hardware Inventory for v4.0 | User Story | Open | Foundation - Atlas | ATLAS | Child Task | User Stories | 33 | 3 | 33 | 39.6 | 30 | 9.091%
TAP-115511_FRED | 719 | *715 |  | 06.02.01.03.10.00.00.00 | TAP-115511 | TAP-122080 | [TAP-115511_FRED] ¦ [v4.0][Fred] Run Fred Integration Tests / HW Unit Tests | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 44 | 3 | 44 | 52.8 | 41 | 100%
TAP-115511_ASTRANPSVALIDATORS | 720 | *715 |  | 06.02.01.03.11.00.00.00 | TAP-115511 | TAP-116288 | [TAP-115511_ASTRANPSVALIDATORS] ¦ [4.0 RC1] RAS tool list | User Story | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task | User Stories | 44 | 3 | 44 | 52.8 | 41 | 100%
TAP-115768 | 721 | *9 | *388 | 06.02.01.04.00.00.00.00 |  | TAP-115768 | [TAP-115768] ¦ [V4][RC1] BRR Deliverables Release - AdvancedInstruments | Feature | Done |  |  | Parent Task | User Stories | 45 | 45 | 1 hr | 1 hr | 0 | 100%
TAP-115768_JACOBIANS | 722 | *721 |  | 06.02.01.04.01.00.00.00 | TAP-115768 | TAP-115952 | [TAP-115768_JACOBIANS] ¦ [Jacobians] v4.0 BRR | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-115768_I2E | 723 | *721 |  | 06.02.01.04.02.00.00.00 | TAP-115768 | TAP-115332 | [TAP-115768_I2E] ¦ [v4.0][I2E] Review all FMs for EIN-SWI-285 and EIN-SWI-168 | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-115768_TEAMBD | 724 | *721 |  | 06.02.01.04.03.00.00.00 | TAP-115768 | TAP-115482 | [TAP-115768_TEAMBD] ¦ [V4.0] SWI-178 and SWI-179 V4.0 cFMEA Review | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-115768_PIXELPOETS | 725 | *721 |  | 06.02.01.04.04.00.00.00 | TAP-115768 | TAP-115479 | [TAP-115768_PIXELPOETS] ¦ [v4.0][Pixel Poets] Review GUI Failure Modes for v4.0 | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-115768_SCRUMBLEDORES | 726 | *721 |  | 06.02.01.04.05.00.00.00 | TAP-115768 | TAP-115168 | [TAP-115768_SCRUMBLEDORES] ¦ [Scrumbledores] Finalize FMs from RAS-6950 and review impacted SWIs | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-115768_HAPPYJAWS | 727 | *721 |  | 06.02.01.04.06.00.00.00 | TAP-115768 | TAP-115461 | [TAP-115768_HAPPYJAWS] ¦ Review Happy Jaw SWIs (Updated) | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-115637 | 728 | *9 |  | 06.02.01.05.00.00.00.00 |  | TAP-115637 | [TAP-115637] ¦ [Cyber] Tracking Documentation For Design Outputs | Feature | PROPOSED |  |  | Parent Task | User Stories | 2 | 1 | 1 hr | 1 hr | 1 | 50%
TAP-115637_TOOLSRULES | 729 | *728 |  | 06.02.01.05.01.00.00.00 | TAP-115637 | TAP-115638 | [TAP-115637_TOOLSRULES] ¦ Software Tool Validation Plan | User Story | Open | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 2 | 1 | 2 | 2.4 | 1 | 50%
TAP-115637_ATLAS | 730 | *728 |  | 06.02.01.05.02.00.00.00 | TAP-115637 | TAP-115642 | [TAP-115637_ATLAS] ¦ Detailed Design Description | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 2 | 1 | 2 | 2.4 | 1 | 100%
TAP-115637_PLATFORMERS | 731 | *728 |  | 06.02.01.05.05.00.00.00 | TAP-115637 | TAP-115650 | [TAP-115637_PLATFORMERS] ¦ Software System Verification Plan | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 2 | 1 | 2 | 2.4 | 1 | 100%
TAP-115637_CASTLEBLACK | 732 | *728 |  | 06.02.01.05.06.00.00.00 | TAP-115637 | TAP-115651 | [TAP-115637_CASTLEBLACK] ¦ [Compliance] Software Item to Software Design Document Trace Matrix for V4.0 | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 2 | 1 | 2 | 2.4 | 1 | 100%
TAP-115695 | 733 | *11 |  | 06.02.01.06.00.00.00.00 |  | TAP-115695 | [TAP-115695] ¦ [Cyber] Tracking Documentation For Design Outputs - EIN V4.0 Unit Verification Checklists | Feature | Done |  |  | Parent Task | User Stories | 37 | 37 | 1 hr | 1 hr | 0 | 100%
TAP-115695_CLASSY1 | 734 | *733 |  | 06.02.01.06.01.00.00.00 | TAP-115695 | TAP-115696 | [TAP-115695_CLASSY1] ¦ [CLASSY] EIN-SWI-12 Software Unit(s) Verification Checklist | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 37 | 37 | 37 | 44.4 | 0 | 100%
TAP-115695_I2E | 735 | *733 |  | 06.02.01.06.02.00.00.00 | TAP-115695 | TAP-115697 | [TAP-115695_I2E] ¦ EIN-SWI-285 Software Unit(s) Verification Checklist | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 37 | 37 | 37 | 44.4 | 0 | 100%
TAP-115695_PLATFORMERS | 736 | *733 |  | 06.02.01.06.03.00.00.00 | TAP-115695 | TAP-115699 | [TAP-115695_PLATFORMERS] ¦ EIN-SWI-351 process::Node Deployment Manager Unit Verification Checklist | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 37 | 37 | 37 | 44.4 | 0 | 100%
TAP-115695_BOOSTERS | 737 | *733 |  | 06.02.01.06.14.00.00.00 | TAP-115695 | TAP-115377 | [TAP-115695_BOOSTERS] ¦ [Boosters] Update and release Data Access ,Logging , Data Recorder unit tests checklist | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 47 | 37 | 47 | 56.4 | 10 | 100%
TAP-115695_STORMCHASERS2 | 738 | *733 |  | 06.02.01.06.16.00.00.00 | TAP-115695 | TAP-96900 | [TAP-115695_STORMCHASERS2] ¦ [V4.0][SC2] Unit verification checklists for SWI-51, 52, 54, 56, 345 | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 50 | 37 | 50 | 60 | 13 | 100%
TAP-115695_CLASSY2 | 739 | *733 |  | 06.02.01.06.17.00.00.00 | TAP-115695 | TAP-116356 | [TAP-115695_CLASSY2] ¦ [CLASSY2] EIN-SWI-331 Software Unit(s) Verification Checklist | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 50 | 37 | 50 | 60 | 13 | 100%
TAP-115718 | 740 | *11 |  | 06.02.01.07.00.00.00.00 |  | TAP-115718 | [TAP-115718] ¦ [Cyber] Tracking Documentation For EIN V4.0 Readiness Reviews BOM | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-115718_DOCUMENTOWNERS | 741 | *740 |  | 06.02.01.07.01.00.00.00 | TAP-115718 | TAP-115719 | [TAP-115718_DOCUMENTOWNERS] ¦ EIN V4.0 Build Release Readiness Review | User Story | Done | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-115722 | 742 | *9 |  | 06.02.01.08.00.00.00.00 |  | TAP-115722 | [TAP-115722] ¦ [Cyber] Tracking Documentation For EIN V4.0 SW Design Reviews | Feature | Done |  |  | Parent Task | User Stories | 41 | 41 | 1 hr | 1 hr | 0 | 100%
TAP-115722_ATLAS | 743 | *742 |  | 06.02.01.08.01.00.00.00 | TAP-115722 | TAP-115723 | [TAP-115722_ATLAS] ¦ QNX x86 Secure Boot, Data Protections, and OS Hardening Technical Review | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 41 | 41 | 41 | 49.2 | 0 | 100%
TAP-115722_CLASSY1 | 744 | *742 |  | 06.02.01.08.04.00.00.00 | TAP-115722 | TAP-115728 | [TAP-115722_CLASSY1] ¦ [CLASSY]DDS Authentication Technical Review | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 47 | 41 | 47 | 56.4 | 6 | 100%
TAP-115722_PLATFORMERS | 745 | *742 |  | 06.02.01.08.05.00.00.00 | TAP-115722 | TAP-115730 | [TAP-115722_PLATFORMERS] ¦ Certificate Manager Technical Review | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 47 | 41 | 47 | 56.4 | 6 | 100%
TAP-115722_BOOSTERS | 746 | *742 |  | 06.02.01.08.08.00.00.00 | TAP-115722 | TAP-115733 | [TAP-115722_BOOSTERS] ¦ [Boosters] Data Access and Logging Technical Review | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 53 | 41 | 53 | 63.6 | 12 | 100%
TAP-115722_CLASSY2 | 747 | *742 |  | 06.02.01.08.09.00.00.00 | TAP-115722 | TAP-114859 | [TAP-115722_CLASSY2] ¦ [CLASSY] Conduct meeting for CDR SWI-12 SWI-576 Communication DDS and UDP | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 53 | 41 | 53 | 63.6 | 12 | 100%
TAP-115722_FRED | 748 | *742 |  | 06.02.01.08.14.00.00.00 | TAP-115722 | TAP-115337 | [TAP-115722_FRED] ¦ Prepare and hold EtherCAT SDR | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 63 | 41 | 63 | 75.6 | 22 | 100%
TAP-115735 | 749 | *9 |  | 06.02.01.09.00.00.00.00 |  | TAP-115735 | [TAP-115735] ¦ [Cyber] Tracking Documentation For EIN V4.0 Product Risk Management | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-115735_DOCUMENTOWNERS | 750 | *749 |  | 06.02.01.09.01.00.00.00 | TAP-115735 | TAP-115736 | [TAP-115735_DOCUMENTOWNERS] ¦ EIN Software Risk Management Plan | User Story | Open | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-115742 | 751 | *9 |  | 06.02.01.10.00.00.00.00 |  | TAP-115742 | [TAP-115742] ¦ [Cyber] Tracking Documentation For Design Transfer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-115742_DOCUMENTOWNERS | 752 | *751 |  | 06.02.01.10.01.00.00.00 | TAP-115742 | TAP-115743 | [TAP-115742_DOCUMENTOWNERS] ¦ Software Metrics | User Story | Open | Outside ART - DocumentOwners | DOCUMENTOWNERS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-105163 | 753 | *5 |  | 06.02.02.01.00.00.00.00 |  | TAP-105163 | [TAP-105163] ¦ [v4.0][Cyber] NPS development for Advanced Instruments scrum teams in PI13 | Feature | Done |  |  | Parent Task | User Stories | 40 | 40 | 1 hr | 1 hr | 0 | 100%
TAP-105163_PIXELPOETS | 754 | *753 |  | 06.02.02.01.01.00.00.00 | TAP-105163 | TAP-94599 | [TAP-105163_PIXELPOETS] ¦ [v4.0] [PixelPoets] NPS development for EDGE tool | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 40 | 40 | 40 | 48 | 0 | 100%
TAP-105163_JACOBIANS | 755 | *753 |  | 06.02.02.01.03.01.00.00 | TAP-105163 | TAP-86279 | [TAP-105163_JACOBIANS] ¦ [Jacobians] Support TACO.py Project- Sprint 1 | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 41 | 40 | 41 | 49.2 | 1 | 100%
TAP-105163_SUNRISERS | 756 | *753 |  | 06.02.02.01.03.06.00.00 | TAP-105163 | TAP-86703 | [TAP-105163_SUNRISERS] ¦ [Sunrisers] Support TACO.py Project- part4 | User Story | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 45 | 40 | 45 | 54 | 5 | 100%
TAP-105163_I2E | 757 | *753 |  | 06.02.02.01.04.00.00.00 | TAP-105163 | TAP-106435 | [TAP-105163_I2E] ¦ [v4.0][I2E] IduUsageCounter Tool Validation Support | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 58 | 40 | 58 | 69.6 | 18 | 100%
TAP-96204 | 758 | *1 |  | 06.02.02.02.00.00.00.00 |  | TAP-96204 | [TAP-96204] ¦ [v4.0][Cyber] NPS development for I2E, Jacobians, Scrumbledores, TeamBD, Pixel Poets - PI12 | Feature | Done |  |  | Parent Task | User Stories | 27 | 27 | 1 hr | 1 hr | 0 | 100%
TAP-96204_I2E | 759 | *758 |  | 06.02.02.02.01.00.00.00 | TAP-96204 | TAP-94738 | [TAP-96204_I2E] ¦ [v4.0] [I2E] NPS Development for IDU CMD GUI Tool | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 27 | 27 | 27 | 32.4 | 0 | 100%
TAP-96204_SCRUMBLEDORES | 760 | *758 |  | 06.02.02.02.07.00.00.00 | TAP-96204 | TAP-94601 | [TAP-96204_SCRUMBLEDORES] ¦ [v4.0][Scrumbledores] NPS development for Error Recovery tool | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 33 | 27 | 33 | 39.6 | 6 | 100%
TAP-96204_PIXELPOETS | 761 | *758 |  | 06.02.02.02.10.00.00.00 | TAP-96204 | TAP-94588 | [TAP-96204_PIXELPOETS] ¦ [v4.0] [PixelPoets] NPS development for Burn CPU tool | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 36 | 27 | 36 | 43.2 | 9 | 100%
TAP-96204_TEAMBD | 762 | *758 |  | 06.02.02.02.13.00.00.00 | TAP-96204 | TAP-96598 | [TAP-96204_TEAMBD] ¦ [v4.0][TeamBD] Update GenerateVersionTable script for IDU Standalone for WolfSSH changes | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 39 | 27 | 39 | 46.8 | 12 | 100%
TAP-83444 | 763 | *7 |  | 06.02.02.03.00.00.00.00 |  | TAP-83444 | [TAP-83444] ¦ [v4.0] [Cyber] NPS Validation for BRR/TRR - PI11 | Feature | Done |  |  | Parent Task | User Stories | 1 | 1 | 1 hr | 1 hr | 0 | 100%
TAP-83444_ASTRANPSVALIDATORS | 764 | *763 |  | 06.02.02.03.01.00.00.00 | TAP-83444 | TAP-87142 | [TAP-83444_ASTRANPSVALIDATORS] ¦ Validation Estimations/Planning for v4.0 | User Story | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task | User Stories | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-105160 | 765 | *7 |  | 06.02.02.04.00.00.00.00 |  | TAP-105160 | [TAP-105160] ¦ [Cyber][V4.0] NPS development for Triple tea - PI13 | Feature | Done |  |  | Parent Task | User Stories | 18 | 18 | 1 hr | 1 hr | 0 | 100%
TAP-105160_TRIPLETEA | 766 | *765 |  | 06.02.02.04.01.00.00.00 | TAP-105160 | TAP-95078 | [TAP-105160_TRIPLETEA] ¦ [v4.0] Submission of TVR and Checklist for chico validation | User Story | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 18 | 18 | 18 | 21.6 | 0 | 100%
TAP-96051 | 767 | *7 |  | 06.02.02.05.00.00.00.00 |  | TAP-96051 | [TAP-96051] ¦ [Cyber][V4.0] NPS development for Inbetweeners - PI12 | Feature | Done |  |  | Parent Task | User Stories | 14 | 14 | 1 hr | 1 hr | 0 | 100%
TAP-96051_INBETWEENERS | 768 | *767 |  | 06.02.02.05.01.00.00.00 | TAP-96051 | TAP-96053 | [TAP-96051_INBETWEENERS] ¦ [v4.0] NPS development for msc_error_injector_runtime_tool | User Story | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 14 | 14 | 14 | 16.8 | 0 | 100%
TAP-105534 | 769 | *7 |  | 06.02.02.06.00.00.00.00 |  | TAP-105534 | [TAP-105534] ¦ [Cyber][V4.0] NPS development for FRED team | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-105534_FRED | 770 | *769 |  | 06.02.02.06.01.00.00.00 | TAP-105534 | TAP-95066 | [TAP-105534_FRED] ¦ [v4.0][Fred] NPS development for Ethercat Master File Transfer | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-94624 | 771 | *1 |  | 06.02.02.07.00.00.00.00 |  | TAP-94624 | [TAP-94624] ¦ [Cyber][V4.0] NPS development for CLASSY team - PI12 | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-94624_CLASSY2 | 772 | *771 |  | 06.02.02.07.01.00.00.00 | TAP-94624 | TAP-95058 | [TAP-94624_CLASSY2] ¦ [v4.0] NPS development for Alarms Code Generator and Jama Logging Code Generator | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-94624_CLASSY1 | 773 | *771 |  | 06.02.02.07.02.00.00.00 | TAP-94624 | TAP-95059 | [TAP-94624_CLASSY1] ¦ [v4.0] NPS development of DDS Spy tool | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-105053 | 774 | *7 |  | 06.02.02.08.00.00.00.00 |  | TAP-105053 | [TAP-105053] ¦ [Cyber][V4.0] NPS development for Inbetweeners - PI13 | Feature | Done |  |  | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-105053_INBETWEENERS | 775 | *774 |  | 06.02.02.08.01.00.00.00 | TAP-105053 | TAP-96052 | [TAP-105053_INBETWEENERS] ¦ [v4.0] NPS development for error Injectors - PI13 | User Story | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 29 | 29 | 29 | 34.8 | 0 | 100%
TAP-105053_FRED | 776 | *774 |  | 06.02.02.08.19.00.00.00 | TAP-105053 | TAP-110821 | [TAP-105053_FRED] ¦ shmio_dumper does not gracefully shut down on SIGINT | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 53 | 29 | 53 | 63.6 | 24 | 100%
TAP-90275 | 777 | *11 |  | 06.02.02.09.00.00.00.00 |  | TAP-90275 | [TAP-90275] ¦ [v4.0] NPS validation for BRR/TRR - RC1 | Feature | Done |  |  | Parent Task | User Stories | 361 | 361 | 1 hr | 1 hr | 0 | 100%
TAP-90275_ASTRANPSVALIDATORS | 778 | *777 |  | 06.02.02.09.01.00.00.00 | TAP-90275 | TAP-103172 | [TAP-90275_ASTRANPSVALIDATORS] ¦ [v4.0] NPS validation for the unit verification tool suite | User Story | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task | User Stories | 361 | 361 | 361 | 433.2 | 0 | 100%
TAP-90275_PIXELPOETS | 779 | *777 |  | 06.02.02.09.63.00.00.00 | TAP-90275 | TAP-123643 | [TAP-90275_PIXELPOETS] ¦ [v4.0] [Pixel Poets] Formal execution of MGLM validation test | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 715 | 361 | 715 | 858 | 354 | 100%
TAP-96135 | 780 | *7 |  | 06.02.02.10.00.00.00.00 |  | TAP-96135 | [TAP-96135] ¦ [Cyber][V4.0] NPS development for Tools Rules team - PI12 | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-96135_ASTRANPSDEVELOPERS | 781 | *780 |  | 06.02.02.10.01.00.00.00 | TAP-96135 | TAP-95057 | [TAP-96135_ASTRANPSDEVELOPERS] ¦ [v4.0] NPS development for Generate Version Table | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-116341 | 782 | *15 |  | 06.02.03.01.00.00.00.00 |  | TAP-116341 | [TAP-116341] ¦ [SOUP][v4.0][Cyber] [IW] SOUP SQR Agile Release | Feature | Accepted |  |  | Parent Task | User Stories | 100 | 0 | 1 hr | 1 hr | 100 | 0%
TAP-116341_DRUSHTI | 783 | *782 |  | 06.02.03.01.01.00.00.00 | TAP-116341 | TAP-126572 | [TAP-116341_DRUSHTI] ¦ [Drushti] [v4.0] SOUP SQR Document Creation Part3 | User Story | Groomed | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 100 | 0 | 100 | 120 | 100 | 0%
TAP-116341_ICONICS | 784 | *782 |  | 06.02.03.01.20.00.00.00 | TAP-116341 | TAP-126463 | [TAP-116341_ICONICS] ¦ [v4.0] [SOUP-29] C and C++ Runtime Arm : SOUP SQR DQE Review | User Story | Open | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 124.5 | 0 | 124.5 | 149.4 | 124.5 | 0%
TAP-116341_INFRAWARRIORS | 785 | *782 |  | 06.02.03.01.26.00.00.00 | TAP-116341 | TAP-89690 | [TAP-116341_INFRAWARRIORS] ¦ [v4.0] [SOUP-4] Libcurl : SOUP SQR Document Creation | User Story | In progress | Released Product Engineering - Infrawarriors | INFRAWARRIORS | Child Task | User Stories | 130.5 | 0 | 130.5 | 156.6 | 130.5 | 0%
TAP-116341_NEXUS | 786 | *782 |  | 06.02.03.01.62.00.00.00 | TAP-116341 | TAP-118121 | [TAP-116341_NEXUS] ¦ [v4.0] [SOUP-26] MIMIC Trainer : SOUP DQE SQR review | User Story | Groomed | Released Product Engineering - Nexus | NEXUS | Child Task | User Stories | 157.5 | 0 | 157.5 | 189 | 157.5 | 0%
TAP-116341_STELLARS | 787 | *782 |  | 06.02.03.01.82.00.00.00 | TAP-116341 | TAP-126470 | [TAP-116341_STELLARS] ¦ [v4.0] [SOUP-35] Motive : SOUP SQR DQE Review | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 177 | 0 | 177 | 212.4 | 177 | 0%
TAP-116341_TECHTITANS | 788 | *782 |  | 06.02.03.01.85.00.00.00 | TAP-116341 | TAP-126474 | [TAP-116341_TECHTITANS] ¦ [v4.0] [SOUP-38] Zlib : SOUP SQR DQE Review | User Story | Open | Released Product Engineering - Tech Titans | TECHTITANS | Child Task | User Stories | 179 | 0 | 179 | 214.8 | 179 | 0%
TAP-123260 | 789 | *17 |  | 06.02.03.02.00.00.00.00 |  | TAP-123260 | [TAP-123260] ¦ [SOUP][V4.0][DVR] SOUP Verification activities | Feature | Accepted |  |  | Parent Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-123260_ICONICS | 790 | *789 |  | 06.02.03.02.01.00.00.00 | TAP-123260 | TAP-126182 | [TAP-123260_ICONICS] ¦ {Spike} {Soup} Support from devops team execution of dry runs | User Story | Groomed | Released Product Engineering - Iconics | ICONICS | Child Task | User Stories | 13 | 0 | 13 | 15.6 | 13 | 0%
TAP-116345 | 791 | *15 |  | 06.02.03.03.00.00.00.00 |  | TAP-116345 | [TAP-116345] ¦ [V4.0][PI15] SOUP complete analysis - Foundation ART | Feature | Accepted |  |  | Parent Task | User Stories | 23 | 3 | 1 hr | 1 hr | 20 | 13.04%
TAP-116345_CLASSY | 792 | *791 |  | 06.02.03.03.01.00.00.00 | TAP-116345 | TAP-89899 | [TAP-116345_CLASSY] ¦ [v4.0] OpenSSL : KV Complete Analysis and Review | User Story | Done | Foundation - Classy | CLASSY | Child Task | User Stories | 23 | 3 | 23 | 27.6 | 20 | 100%
TAP-116345_PLATFORMERS | 793 | *791 |  | 06.02.03.03.05.00.00.00 | TAP-116345 | TAP-89911 | [TAP-116345_PLATFORMERS] ¦ [v4.0] WolfSSL : KV Complete Analysis and Review | User Story | Groomed | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 42 | 3 | 42 | 50.4 | 39 | 7.143%
TAP-96719 | 794 | *17 |  | 06.02.03.04.00.00.00.00 |  | TAP-96719 | [TAP-96719] ¦ [v4.0][Cyber][PI13] SOUP Initial analysis | Feature | Done |  |  | Parent Task | User Stories | 140 | 140 | 1 hr | 1 hr | 0 | 100%
TAP-96719_SOUPERTROOPERS | 795 | *794 |  | 06.02.03.04.01.00.00.00 | TAP-96719 | TAP-89918 | [TAP-96719_SOUPERTROOPERS] ¦ [v4.0] JsonCPP : Creation and Review of KA and KV spreadsheets | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 140 | 140 | 140 | 168 | 0 | 100%
TAP-96675 | 796 | *17 |  | 06.02.03.05.00.00.00.00 |  | TAP-96675 | [TAP-96675] ¦ [v4.0][Cyber][PI13] SOUP complete analysis - Foundation ART | Feature | Done |  |  | Parent Task | User Stories | 46 | 46 | 1 hr | 1 hr | 0 | 100%
TAP-96675_ATLAS | 797 | *796 |  | 06.02.03.05.01.00.00.00 | TAP-96675 | TAP-89796 | [TAP-96675_ATLAS] ¦ [v4.0] QNX Neutrino RTOS - zynq/x86 : KV Complete Analysis and Review | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 46 | 46 | 46 | 55.2 | 0 | 100%
TAP-96675_BOOSTERS | 798 | *796 |  | 06.02.03.05.03.00.00.00 | TAP-96675 | TAP-89712 | [TAP-96675_BOOSTERS] ¦ [v4.0] libssh2 : KV Complete Analysis and Review | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 47 | 46 | 47 | 56.4 | 1 | 100%
TAP-96675_FRED | 799 | *796 |  | 06.02.03.05.07.00.00.00 | TAP-96675 | TAP-89638 | [TAP-96675_FRED] ¦ [v4.0] STM32Cube HAL : KA Complete Analysis and Review | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 54 | 46 | 54 | 64.8 | 8 | 100%
TAP-96675_SOUPERTROOPERS | 800 | *796 |  | 06.02.03.05.15.00.00.00 | TAP-96675 | TAP-89923 | [TAP-96675_SOUPERTROOPERS] ¦ [v4.0] JsonCPP : KV Complete Analysis and Review | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 61 | 46 | 61 | 73.2 | 15 | 100%
TAP-96675_STORMCHASERS1 | 801 | *796 |  | 06.02.03.05.21.00.00.00 | TAP-96675 | TAP-89844 | [TAP-96675_STORMCHASERS1] ¦ [v4.0] Eigen : KA Complete Analysis and Review | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 71 | 46 | 71 | 85.2 | 25 | 100%
TAP-96675_STORMCHASERS2 | 802 | *796 |  | 06.02.03.05.23.00.00.00 | TAP-96675 | TAP-89861 | [TAP-96675_STORMCHASERS2] ¦ [v4.0] dsPIC33EP_Core : KV Complete Analysis and Review | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 74 | 46 | 74 | 88.8 | 28 | 100%
TAP-96675_VISUAL | 803 | *796 |  | 06.02.03.05.29.00.00.00 | TAP-96675 | TAP-89996 | [TAP-96675_VISUAL] ¦ [v4.0] Thrift : KV Complete Analysis and Review | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 80 | 46 | 80 | 96 | 34 | 100%
TAP-83010 | 804 | *17 |  | 06.02.03.06.00.00.00.00 |  | TAP-83010 | [TAP-83010] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - Advanced Instruments ART | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-83010_ORGANELLES | 805 | *804 |  | 06.02.03.06.01.00.00.00 | TAP-83010 | TAP-96698 | [TAP-83010_ORGANELLES] ¦ [v4.0] NVidia PhysX Physics Engine : KA Complete Analysis and Review | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-95434 | 806 | *17 |  | 06.02.03.07.00.00.00.00 |  | TAP-95434 | [TAP-95434] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - Foundation ART | Feature | Done |  |  | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-95434_BOOSTERS | 807 | *806 |  | 06.02.03.07.01.00.00.00 | TAP-95434 | TAP-89736 | [TAP-95434_BOOSTERS] ¦ [v4.0] SQLite : KV Complete Analysis and Review | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 29 | 29 | 29 | 34.8 | 0 | 100%
TAP-95434_FRED | 808 | *806 |  | 06.02.03.07.07.00.00.00 | TAP-95434 | TAP-89602 | [TAP-95434_FRED] ¦ [v4.0] C and C++ Runtime Arm : KA Complete Analysis and Review | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 43.5 | 29 | 43.5 | 52.2 | 14.5 | 100%
TAP-95434_PLATFORMERS | 809 | *806 |  | 06.02.03.07.13.00.00.00 | TAP-95434 | TAP-89960 | [TAP-95434_PLATFORMERS] ¦ [v4.0] SNMP : KV Complete Analysis and Review | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 48.5 | 29 | 48.5 | 58.2 | 19.5 | 100%
TAP-106670 | 810 | *17 |  | 06.02.03.08.00.00.00.00 |  | TAP-106670 | [TAP-106670] ¦ [v4.0][Cyber][PI14] SOUP complete analysis - Foundation ART | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-106670_ATLAS | 811 | *810 |  | 06.02.03.08.01.00.00.00 | TAP-106670 | TAP-89747 | [TAP-106670_ATLAS] ¦ [v4.0] DisplayLink USB Windows : KA Complete Analysis and Review | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-106670_SOUPERTROOPERS | 812 | *810 |  | 06.02.03.08.14.00.00.00 | TAP-106670 | TAP-116362 | [TAP-106670_SOUPERTROOPERS] ¦ [v4.0] [Maintenance] OpenSSH : KV Complete Analysis and Review | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 37 | 21 | 37 | 44.4 | 16 | 100%
TAP-95432 | 813 | *17 |  | 06.02.03.09.00.00.00.00 |  | TAP-95432 | [TAP-95432] ¦ [v4.0][Cyber][PI12] SOUP Initial analysis | Feature | Done |  |  | Parent Task | User Stories | 101 | 101 | 1 hr | 1 hr | 0 | 100%
TAP-95432_SOUPERTROOPERS | 814 | *813 |  | 06.02.03.09.01.00.00.00 | TAP-95432 | TAP-89932 | [TAP-95432_SOUPERTROOPERS] ¦ [V4.0] Libarchive : KA SOUP Initial Analysis and Review | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 101 | 101 | 101 | 121.2 | 0 | 100%
TAP-72332 | 815 | *17 |  | 06.02.03.10.00.00.00.00 |  | TAP-72332 | [TAP-72332] ¦ [V4.0][Cyber][PI13] SOUP V&V Tasks | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-72332_SOUPERTROOPERS | 816 | *815 |  | 06.02.03.10.01.00.00.00 | TAP-72332 | TAP-105573 | [TAP-72332_SOUPERTROOPERS] ¦ [V4.0] Update SOUP V&V Scripts to Automate verification of SOUP versions using OS_detais.txt | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-113388 | 817 | *15 |  | 06.02.03.11.00.00.00.00 |  | TAP-113388 | [TAP-113388] ¦ [V4.0][Cyber][PI14] SOUP V&V Tasks [BRR/TRR] | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-113388_SOUPERTROOPERS | 818 | *817 |  | 06.02.03.11.01.00.00.00 | TAP-113388 | TAP-97901 | [TAP-113388_SOUPERTROOPERS] ¦ [V4.0] Update the Build scripts for v4.0 to reflect the new SOUP version checks | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-103997 | 819 | *17 |  | 06.02.03.13.00.00.00.00 |  | TAP-103997 | [TAP-103997] ¦ [v4.0][Cyber][PI13] SOUP complete analysis - Advanced Instruments ART | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-103997_ORGANELLES | 820 | *819 |  | 06.02.03.13.01.00.00.00 | TAP-103997 | TAP-96708 | [TAP-103997_ORGANELLES] ¦ [v4.0] Surgical Science : KA Complete Analysis and Review | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-97857 | 821 | *17 |  | 06.02.03.14.00.00.00.00 |  | TAP-97857 | [TAP-97857] ¦ [v4.0][Cyber][PI12] SOUP complete analysis - RPE ART | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-97857_DRUSHTI | 822 | *821 |  | 06.02.03.14.01.00.00.00 | TAP-97857 | TAP-96713 | [TAP-97857_DRUSHTI] ¦ [Drushti] [v4.0] QT : KV Complete Analysis and Review | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-95435 | 823 | *17 |  | 06.02.03.15.00.00.00.00 |  | TAP-95435 | [TAP-95435] ¦ [v4.0][Cyber][PI13] SOUP SQR Agile Release | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-95435_SOUPERTROOPERS | 824 | *823 |  | 06.02.03.15.01.00.00.00 | TAP-95435 | TAP-89738 | [TAP-95435_SOUPERTROOPERS] ¦ [v4.0] SQLite : SOUP SQR Document Creation and Review | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-106240 | 825 | *17 |  | 06.02.03.16.00.00.00.00 |  | TAP-106240 | [TAP-106240] ¦ [v4.0][Cyber][PI14] SOUP SQR Agile Release | Feature | Done |  |  | Parent Task | User Stories | 65.5 | 65.5 | 1 hr | 1 hr | 0 | 100%
TAP-106240_SOUPERTROOPERS | 826 | *825 |  | 06.02.03.16.01.00.00.00 | TAP-106240 | TAP-90031 | [TAP-106240_SOUPERTROOPERS] ¦ [v4.0] NVidia PhysX Physics Engine : SOUP SQR Document Creation | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 65.5 | 65.5 | 65.5 | 78.6 | 0 | 100%
TAP-2133 | 827 | *841,1 |  | 06.05.02.01.01.00.00.00 |  | TAP-2133 | [TAP-2133] ¦ [Cyber] Prototype Chain of Trust boot up for QNX x86 platform on 7.1 OS | Feature | Done |  |  | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-2133_ATLAS | 828 | *827 |  | 06.05.02.01.01.01.00.00 | TAP-2133 | TAP-416 | [TAP-2133_ATLAS] ¦ Initial investigation to the EFI switch strategy | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 29 | 29 | 29 | 34.8 | 0 | 100%
TAP-12357 | 829 | *841,1 |  | 06.05.02.01.02.00.00.00 |  | TAP-12357 | [TAP-12357] ¦ [Cyber] Implement chain of trust on QNX x86 platform | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-12357_ATLAS | 830 | *829 |  | 06.05.02.01.02.01.00.00 | TAP-12357 | TAP-33471 | [TAP-12357_ATLAS] ¦ Test Case ICG-TC_SW-88: QNX x86 node shall not mount unauthenticated application image | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-17155 | 831 | *841,1 |  | 06.05.02.01.03.00.00.00 |  | TAP-17155 | [TAP-17155] ¦ [Cyber] SPIKE Investigate needs for Unique/Non-Unique BIOS passwords on each system | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-17155_ATLAS | 832 | *831 |  | 06.05.02.01.03.01.00.00 | TAP-17155 | TAP-28168 | [TAP-17155_ATLAS] ¦ Investigate needs for Unique/Non-Unique BIOS passwords on each system | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-12358 | 833 | *841,1 |  | 06.05.02.01.04.00.00.00 |  | TAP-12358 | [TAP-12358] ¦ [Cyber] Implement fallback mechanism for verification failures for QNX x86 | Feature | Done |  |  | Parent Task | User Stories | 35 | 35 | 1 hr | 1 hr | 0 | 100%
TAP-12358_ATLAS | 834 | *833 |  | 06.05.02.01.04.01.00.00 | TAP-12358 | TAP-34419 | [TAP-12358_ATLAS] ¦ Test Case for Fallback QNX x86 Secure Boot (CYB-SSR_EXEC-337) | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 35 | 35 | 35 | 42 | 0 | 100%
TAP-12361 | 835 | *841,1 |  | 06.05.02.01.05.00.00.00 |  | TAP-12361 | [TAP-12361] ¦ [Cyber] Investigate Hard coded secrets in QNX x86 platforms | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-12361_ATLAS | 836 | *835 |  | 06.05.02.01.05.01.00.00 | TAP-12361 | TAP-35168 | [TAP-12361_ATLAS] ¦ [SPIKE] Finalize plans for configuration file authentication | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 10 | 10 | 10 | 12 | 0 | 100%
TAP-2135 | 837 | *841,1 |  | 06.05.02.01.06.00.00.00 |  | TAP-2135 | [TAP-2135] ¦ [Cyber] Hardware failure handling enhancement for QNX 7.1 x86 OS | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-2135_ATLAS | 838 | *837 |  | 06.05.02.01.06.01.00.00 | TAP-2135 | TAP-47470 | [TAP-2135_ATLAS] ¦ [SPIKE] Stress test UPS HID interface | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-12360 | 839 | *841,1 |  | 06.05.02.01.07.00.00.00 |  | TAP-12360 | [TAP-12360] ¦ [Cyber] Implement TPM usage in QNX x86 | Feature | Done |  |  | Parent Task | User Stories | 30 | 30 | 1 hr | 1 hr | 0 | 100%
TAP-12360_ATLAS | 840 | *839 |  | 06.05.02.01.07.01.00.00 | TAP-12360 | TAP-27632 | [TAP-12360_ATLAS] ¦ Prepare TPM developer test procedure and design details for V&V team | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 30 | 30 | 30 | 36 | 0 | 100%
TAP-58662 | 841 | *842,1 | *827,829,831,833,835,837,839 | 06.05.02.01.08.00.00.00 |  | TAP-58662 | [TAP-58662] ¦ [Cyber] Micro-Penetration Test by 3rd Party for QNX x86 Secure Boot | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-13749 | 842 | *1 | *841 | 06.05.02.01.09.00.00.00 |  | TAP-13749 | [TAP-13749] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 - chain of trust | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-13749_ATLAS | 843 | *842 |  | 06.05.02.01.09.01.00.00 | TAP-13749 | TAP-58881 | [TAP-13749_ATLAS] ¦ [SPIKE] EM.11 Investigate sensitive data found in NVMe | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-70864 | 844 | *1 |  | 06.05.02.01.11.00.00.00 |  | TAP-70864 | [TAP-70864] ¦ [Cyber] Operations and Service support planning for bsp changes | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-70864_ATLAS | 845 | *844 |  | 06.05.02.01.11.01.00.00 | TAP-70864 | TAP-79195 | [TAP-70864_ATLAS] ¦ [Spike] Read and Understand Cart Manufacturing test protocol for QNX 7.1 BSP | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-72558 | 846 | *3 |  | 06.05.02.01.12.00.00.00 |  | TAP-72558 | [TAP-72558] ¦ [Boosters][Cyber] Integrate WolfSSH in Data Access and miscellaneous logging improvement | Feature | Done |  |  | Parent Task | User Stories | 59 | 59 | 1 hr | 1 hr | 0 | 100%
TAP-72558_BOOSTERS | 847 | *846 |  | 06.05.02.01.12.01.00.00 | TAP-72558 | TAP-95346 | [TAP-72558_BOOSTERS] ¦ [Boosters] Update DA Design Document when WolfSSH SWI is created | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 59 | 59 | 59 | 70.8 | 0 | 100%
TAP-13750 | 848 | *9 |  | 06.05.02.01.13.00.00.00 |  | TAP-13750 | [TAP-13750] ¦ [Cyber] Finish the QA, V&V tasks related to QNX x86 OS for Cyber release | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-13750_ATLAS | 849 | *848 |  | 06.05.02.01.13.01.00.00 | TAP-13750 | TAP-106569 | [TAP-13750_ATLAS] ¦ [Enabler] QNX x86 SFMEA Review | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-2134 | 850 | *852,1 |  | 06.05.02.02.01.00.00.00 |  | TAP-2134 | [TAP-2134] ¦ [Cyber] Implement secure storage for QNX x86 7.1 OS platform | Feature | Done |  |  | Parent Task | User Stories | 32 | 32 | 1 hr | 1 hr | 0 | 100%
TAP-2134_ATLAS | 851 | *850 |  | 06.05.02.02.01.01.00.00 | TAP-2134 | TAP-34122 | [TAP-2134_ATLAS] ¦ Investigate the Not Support issue on fsencrypt in the latest docker image | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 32 | 32 | 32 | 38.4 | 0 | 100%
TAP-58909 | 852 | *853,1 | *850 | 06.05.02.02.02.00.00.00 |  | TAP-58909 | [TAP-58909] ¦ [Cyber] Micro-Penetration Test by 3rd Party for QNX x86 Data Protection | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-58919 | 853 | *1 | *852 | 06.05.02.02.03.00.00.00 |  | TAP-58919 | [TAP-58919] ¦ [Cyber] Implement micro-penetration testing findings for QNX x86 Data Protections | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-4982 | 854 | *1 |  | 06.05.02.03.01.00.00.00 |  | TAP-4982 | [TAP-4982] ¦ [Cyber] Least privilege mechanism on QNX x86 node | Feature | Done |  |  | Parent Task | User Stories | 194 | 194 | 1 hr | 1 hr | 0 | 100%
TAP-4982_ATLAS | 855 | *854 |  | 06.05.02.03.01.01.00.00 | TAP-4982 | TAP-71454 | [TAP-4982_ATLAS] ¦ [SPIKE] Start EIN application under a non-root account | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 194 | 194 | 194 | 232.8 | 0 | 100%
TAP-4982_BOOSTERS | 856 | *854 |  | 06.05.02.03.01.27.00.00 | TAP-4982 | TAP-59064 | [TAP-4982_BOOSTERS] ¦ [Boosters] Include security policy error file in system logs | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 340 | 194 | 340 | 408 | 146 | 100%
TAP-4982_PLATFORMERS | 857 | *854 |  | 06.05.02.03.01.28.00.00 | TAP-4982 | TAP-59560 | [TAP-4982_PLATFORMERS] ¦ [Platformers][ICG][Cyber] Security policy enabled always in release builds | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 340 | 194 | 340 | 408 | 146 | 100%
TAP-58840 | 858 | *861,1 |  | 06.05.02.03.02.00.00.00 |  | TAP-58840 | [TAP-58840] ¦ [Cyber] QNX x86: WolfSSH Integration | Feature | Done |  |  | Parent Task | User Stories | 73 | 73 | 1 hr | 1 hr | 0 | 100%
TAP-58840_ATLAS | 859 | *858 |  | 06.05.02.03.02.01.00.00 | TAP-58840 | TAP-64156 | [TAP-58840_ATLAS] ¦ [Enabler] Create prototype software SFTP wrapper library for WolfSSH | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 73 | 73 | 73 | 87.6 | 0 | 100%
TAP-58840_EDISON | 860 | *858 |  | 06.05.02.03.02.11.00.00 | TAP-58840 | TAP-63958 | [TAP-58840_EDISON] ¦ Create wolfssh/wolfssl debian packages and update docker image | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 136 | 73 | 136 | 163.2 | 63 | 100%
TAP-12359 | 861 | *1 | *858 | 06.05.02.03.03.00.00.00 |  | TAP-12359 | [TAP-12359] ¦ [Cyber] Implement OS Hardening of QNX x86 nodes (SSH, SFTP, USB, etc) | Feature | Done |  |  | Parent Task | User Stories | 137.5 | 137.5 | 1 hr | 1 hr | 0 | 100%
TAP-12359_ATLAS | 862 | *861 |  | 06.05.02.03.03.01.00.00 | TAP-12359 | TAP-72834 | [TAP-12359_ATLAS] ¦ [SPIKE] Prototype SMC IOMMU support | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 137.5 | 137.5 | 137.5 | 165 | 0 | 100%
TAP-12359_BOOSTERS | 863 | *861 |  | 06.05.02.03.03.34.00.00 | TAP-12359 | TAP-55427 | [TAP-12359_BOOSTERS] ¦ [Boosters] Create test design for ICG-TC_SW-144 Data Access: Encryption at Transit | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 257.5 | 137.5 | 257.5 | 309 | 120 | 100%
TAP-12359_FRED | 864 | *861 |  | 06.05.02.03.03.36.00.00 | TAP-12359 | TAP-70563 | [TAP-12359_FRED] ¦ Prototype EtherCAT driver to support IOMMU | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 264.5 | 137.5 | 264.5 | 317.4 | 127 | 100%
TAP-12359_SOUPERTROOPERS | 865 | *861 |  | 06.05.02.03.03.37.00.00 | TAP-12359 | TAP-79941 | [TAP-12359_SOUPERTROOPERS] ¦ SOUP: Update Acontis SOUP to 3.1.4.11 for release 4.0 | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 264.5 | 137.5 | 264.5 | 317.4 | 127 | 100%
TAP-12359_EDISON | 866 | *861 |  | 06.05.02.03.03.38.00.00 | TAP-12359 | TAP-79812 | [TAP-12359_EDISON] ¦ Update Acontis Soup to 3.1.4.11 | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 264.5 | 137.5 | 264.5 | 317.4 | 127 | 100%
TAP-70489 | 867 | *869,5 |  | 06.05.02.03.04.00.00.00 |  | TAP-70489 | [TAP-70489] ¦ [Cyber] Micro-Penetration Test Readiness and Support by 3rd Party for QNX x86 OS Hardening | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-70489_ATLAS | 868 | *867 |  | 06.05.02.03.04.01.00.00 | TAP-70489 | TAP-97198 | [TAP-70489_ATLAS] ¦ Create instruction for supporting pen test | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-70490 | 869 | *5 | *867 | 06.05.02.03.05.00.00.00 |  | TAP-70490 | [TAP-70490] ¦ 🚩[Cyber] Implement Fixes for Findings in Micro Penetration Testing for QNX x86 OS Hardening | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-70490_ATLAS | 870 | *869 |  | 06.05.02.03.05.01.00.00 | TAP-70490 | TAP-114173 | [TAP-70490_ATLAS] ¦ Remove undesired dir access of restrictedshelluser for WolfSFTP | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-1005 | 871 | *885,1 |  | 06.05.03.01.01.00.00.00 |  | TAP-1005 | [TAP-1005] ¦ [Cyber] Create obfuscated secret key during run time | Feature | Done |  |  | Parent Task | User Stories | 90 | 90 | 1 hr | 1 hr | 0 | 100%
TAP-1005_BART | 872 | *871 |  | 06.05.03.01.01.01.00.00 | TAP-1005 | TAP-2464 | [TAP-1005_BART] ¦ Understand Scrambling and descrambling of Obfuscated Key in PL | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 90 | 90 | 90 | 108 | 0 | 100%
TAP-1182 | 873 | *885,1 |  | 06.05.03.01.02.00.00.00 |  | TAP-1182 | [TAP-1182] ¦ [Cyber] [Enabler] Define road map for Zynq Authenticated boot | Feature | Done |  |  | Parent Task | User Stories | 36 | 36 | 1 hr | 1 hr | 0 | 100%
TAP-1182_ATLAS | 874 | *873 |  | 06.05.03.01.02.01.00.00 | TAP-1182 | TAP-3460 | [TAP-1182_ATLAS] ¦ [spike] Define the format of the PL obfuscated key | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 36 | 36 | 36 | 43.2 | 0 | 100%
TAP-1182_BART | 875 | *873 |  | 06.05.03.01.02.17.00.00 | TAP-1182 | TAP-9076 | [TAP-1182_BART] ¦ [Spike] Determine if using a unique hardware register is available to PL to seed creation of of PS_KEY | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 70 | 36 | 70 | 84 | 34 | 100%
TAP-7423 | 876 | *885,1 |  | 06.05.03.01.03.00.00.00 |  | TAP-7423 | [TAP-7423] ¦ [Cyber] Establish Chain of trust on zynq platform | Feature | Done |  |  | Parent Task | User Stories | 167.5 | 167.5 | 1 hr | 1 hr | 0 | 100%
TAP-7423_ATLAS | 877 | *876 |  | 06.05.03.01.03.01.00.00 | TAP-7423 | TAP-39032 | [TAP-7423_ATLAS] ¦ CYB-TC_SW-1438: Create test case for Chain of Trust FSBL to IPL | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 167.5 | 167.5 | 167.5 | 201 | 0 | 100%
TAP-7423_BART | 878 | *876 |  | 06.05.03.01.03.30.00.00 | TAP-7423 | TAP-39326 | [TAP-7423_BART] ¦ [Cyber] Support SW team for debugging CART ocm key read | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 315 | 167.5 | 315 | 378 | 147.5 | 100%
TAP-7423_PLATFORMERS | 879 | *876 |  | 06.05.03.01.03.34.00.00 | TAP-7423 | TAP-64286 | [TAP-7423_PLATFORMERS] ¦ [Cyber][Platformers] Update QNX ARM deployment procedure | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 320 | 167.5 | 320 | 384 | 152.5 | 100%
TAP-12362 | 880 | *885,1 |  | 06.05.03.01.04.00.00.00 |  | TAP-12362 | [TAP-12362] ¦ [Cyber] Implement fallback for qnx armv7 nodes | Feature | Done |  |  | Parent Task | User Stories | 18 | 18 | 1 hr | 1 hr | 0 | 100%
TAP-12362_ATLAS | 881 | *880 |  | 06.05.03.01.04.01.00.00 | TAP-12362 | TAP-55414 | [TAP-12362_ATLAS] ¦ [Spike] Review work of Boot Diagnostic driver | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 18 | 18 | 18 | 21.6 | 0 | 100%
TAP-83759 | 882 | *1,885 |  | 06.05.03.01.05.00.00.00 |  | TAP-83759 | [TAP-83759] ¦ [Critical][Cyber][V4.0] Investigate and Fix Backup OS | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-83759_ATLAS | 883 | *882 |  | 06.05.03.01.05.01.00.00 | TAP-83759 | TAP-88550 | [TAP-83759_ATLAS] ¦ RASA primary OS failure after j-tag programming (develop) | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-83759_FRED | 884 | *882 |  | 06.05.03.01.05.05.00.00 | TAP-83759 | TAP-83624 | [TAP-83759_FRED] ¦ [Spike] Investigate broken Backup OS in develop | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 13 | 8 | 13 | 15.6 | 5 | 100%
TAP-58663 | 885 | *887,1 | *871,873,876,880,891,882 | 06.05.03.01.06.00.00.00 |  | TAP-58663 | [TAP-58663] ¦ [Cyber] Micro-Penetration Readiness and Test by 3rd Party for QNX Zynq | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-58663_ATLAS | 886 | *885 |  | 06.05.03.01.06.01.00.00 | TAP-58663 | TAP-101748 | [TAP-58663_ATLAS] ¦ Fixes for FSBL after pen test review | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-13752 | 887 | *5 | *885 | 06.05.03.01.07.00.00.00 |  | TAP-13752 | [TAP-13752] ¦ [Cyber] Implementation penetration testing finding for QNX armv7 nodes | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-13752_ATLAS | 888 | *887 |  | 06.05.03.01.07.01.00.00 | TAP-13752 | TAP-105375 | [TAP-13752_ATLAS] ¦ Change Back up BSP to not have a shell | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-13753 | 889 | *9 |  | 06.05.03.01.08.00.00.00 |  | TAP-13753 | [TAP-13753] ¦ [Cyber] Finish cyber analysis, V&V, and QA related tasks for QNX Armv7 OS | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-13753_ATLAS | 890 | *889 |  | 06.05.03.01.08.01.00.00 | TAP-13753 | TAP-58516 | [TAP-13753_ATLAS] ¦ [Enabler] Finalize QNX ARM Design Documents | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-13751 | 891 | *885,1 |  | 06.05.03.02.01.00.00.00 |  | TAP-13751 | [TAP-13751] ¦ [Cyber] Implement secure key storage for QNX armv7 | Feature | Done |  |  | Parent Task | User Stories | 82 | 82 | 1 hr | 1 hr | 0 | 100%
TAP-13751_ATLAS | 892 | *891 |  | 06.05.03.02.01.01.00.00 | TAP-13751 | TAP-34375 | [TAP-13751_ATLAS] ¦ Zynq Secure Key store: define new flash layout | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 82 | 82 | 82 | 98.4 | 0 | 100%
TAP-13751_BART | 893 | *891 |  | 06.05.03.02.01.14.00.00 | TAP-13751 | TAP-55174 | [TAP-13751_BART] ¦ [cyber]PL improperly writes to the OCM causing odd writing behavior | Issue | Done | Foundation - Bart | BART | Child Task | User Stories | 155 | 82 | 155 | 186 | 73 | 100%
TAP-13751_EDISON | 894 | *891 |  | 06.05.03.02.01.17.00.00 | TAP-13751 | TAP-27176 | [TAP-13751_EDISON] ¦ PL integration with QNX build | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 158 | 82 | 158 | 189.6 | 76 | 100%
TAP-84498 | 895 | *1 |  | 06.05.03.03.01.00.00.00 |  | TAP-84498 | [TAP-84498] ¦ [Cyber]User Separation for Zynq nodes | Feature | Done |  |  | Parent Task | User Stories | 33.5 | 33.5 | 1 hr | 1 hr | 0 | 100%
TAP-84498_ATLAS | 896 | *895 |  | 06.05.03.03.01.01.00.00 | TAP-84498 | TAP-79679 | [TAP-84498_ATLAS] ¦ [SPIKE] Define Multiuser support for QNX arm | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 33.5 | 33.5 | 33.5 | 40.2 | 0 | 100%
TAP-105165 | 897 | *1 |  | 06.05.03.03.02.00.00.00 |  | TAP-105165 | [TAP-105165] ¦ Improvements for Finalizing Cyber Development | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-105165_ASTRANPSDEVELOPERS | 898 | *897 |  | 06.05.03.03.02.01.00.00 | TAP-105165 | TAP-102512 | [TAP-105165_ASTRANPSDEVELOPERS] ¦ Update ESAT to support agnostic path instead of signature path | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-105165_ATLAS | 899 | *897 |  | 06.05.03.03.02.02.00.00 | TAP-105165 | TAP-101605 | [TAP-105165_ATLAS] ¦ Update deployment manager to use agnostic path instead of signature path | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-76492 | 900 | *1 |  | 06.05.03.03.03.00.00.00 |  | TAP-76492 | [TAP-76492] ¦ [Cyber] Increase Security of Key exchange | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-76492_ATLAS | 901 | *900 |  | 06.05.03.03.03.01.00.00 | TAP-76492 | TAP-87768 | [TAP-76492_ATLAS] ¦ Define Approach to update secure directory utility to support a single call | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-7424 | 902 | *1 |  | 06.05.03.03.04.00.00.00 |  | TAP-7424 | [TAP-7424] ¦ [Cyber] QNX7 Arm OS hardening | Feature | Done |  |  | Parent Task | User Stories | 133.5 | 133.5 | 1 hr | 1 hr | 0 | 100%
TAP-7424_ATLAS | 903 | *902 |  | 06.05.03.03.04.01.00.00 | TAP-7424 | TAP-97187 | [TAP-7424_ATLAS] ¦ [Spike] Fully define scope of restrictedshelluser | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 133.5 | 133.5 | 133.5 | 160.2 | 0 | 100%
TAP-7424_BART | 904 | *902 |  | 06.05.03.03.04.42.00.00 | TAP-7424 | TAP-71459 | [TAP-7424_BART] ¦ [Cyber] jtag monitor test on the hardware | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 256 | 133.5 | 256 | 307.2 | 122.5 | 100%
TAP-7424_FRED | 905 | *902 |  | 06.05.03.03.04.45.00.00 | TAP-7424 | TAP-35633 | [TAP-7424_FRED] ¦ Deployment to joint secondaries not working | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 259 | 133.5 | 259 | 310.8 | 125.5 | 100%
TAP-58839 | 906 | *1 |  | 06.05.03.03.05.00.00.00 |  | TAP-58839 | [TAP-58839] ¦ [Cyber] QNX Zynq: WolfSSH Integration | Feature | Done |  |  | Parent Task | User Stories | 25.5 | 25.5 | 1 hr | 1 hr | 0 | 100%
TAP-58839_ATLAS | 907 | *906 |  | 06.05.03.03.05.01.00.00 | TAP-58839 | TAP-72281 | [TAP-58839_ATLAS] ¦ Update BSP Build to retrieve WolfSSH and WolfSSL dependencies from docker image | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 25.5 | 25.5 | 25.5 | 30.6 | 0 | 100%
TAP-58839_EDISON | 908 | *906 |  | 06.05.03.03.05.09.00.00 | TAP-58839 | TAP-76351 | [TAP-58839_EDISON] ¦ Update QNX (x86 & Zynq) BSP build Containers to include WolfSSL and WolfSSH packages | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 48.5 | 25.5 | 48.5 | 58.2 | 23 | 100%
TAP-73977 | 909 | *3 |  | 06.05.03.03.06.00.00.00 |  | TAP-73977 | [TAP-73977] ¦ [Cyber] PL key obfuscation and storage hardening | Feature | Done |  |  | Parent Task | User Stories | 89.5 | 89.5 | 1 hr | 1 hr | 0 | 100%
TAP-73977_ATLAS | 910 | *909 |  | 06.05.03.03.06.01.00.00 | TAP-73977 | TAP-97407 | [TAP-73977_ATLAS] ¦ [v4.0][cyber] Secure Backup Image testing | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 89.5 | 89.5 | 89.5 | 107.4 | 0 | 100%
TAP-73977_BART | 911 | *909 |  | 06.05.03.03.06.03.00.00 | TAP-73977 | TAP-97514 | [TAP-73977_BART] ¦ [v4.0][Cyber] create testing strategy for Keywriter update unit test in jama | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 92.5 | 89.5 | 92.5 | 111 | 3 | 100%
TAP-1743 | 912 | *924,1 |  | 06.05.04.01.01.00.00.00 |  | TAP-1743 | [TAP-1743] ¦ [Cyber] Certificate(s) to install as PK onWindows systems | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-1744 | 913 | *924,1 |  | 06.05.04.01.02.00.00.00 |  | TAP-1744 | [TAP-1744] ¦ [Cyber] 3 versions of UEFI firmware for testing Windows secure boot | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-2423 | 914 | *924,1 |  | 06.05.04.01.03.00.00.00 |  | TAP-2423 | [TAP-2423] ¦ [Cyber] Update 3rd party libraries and components on Windows Bamboo agents for v2.0 | Feature | Done |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-2423_TOOLSRULES | 915 | *914 |  | 06.05.04.01.03.01.00.00 | TAP-2423 | TAP-7612 | [TAP-2423_TOOLSRULES] ¦ DevOps: add flatbuffer 1.12 to Windows environment | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-2423_EDISON | 916 | *914 |  | 06.05.04.01.03.02.00.00 | TAP-2423 | TAP-2240 | [TAP-2423_EDISON] ¦ Update 3rd party libraries and components on Windows Bamboo agents for v2.0 - Visual Studio 2019 (gcc 8.3.0) | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-1745 | 917 | *924,1 |  | 06.05.04.01.04.00.00.00 |  | TAP-1745 | [TAP-1745] ¦ [Cyber] Kontron specific instructions on updating the TPM certificate stores | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-1742 | 918 | *924,1 |  | 06.05.04.01.05.00.00.00 |  | TAP-1742 | [TAP-1742] ¦ [Cyber] Define Strategy and Architecture for Windows Cyber Security | Feature | Done |  |  | Parent Task | User Stories | 71 | 71 | 1 hr | 1 hr | 0 | 100%
TAP-1742_ATLAS | 919 | *918 |  | 06.05.04.01.05.01.00.00 | TAP-1742 | TAP-58545 | [TAP-1742_ATLAS] ¦ [SPIKE] Determine if deploying a WIM OS image looses BitLocker protection | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 71 | 71 | 71 | 85.2 | 0 | 100%
TAP-12365 | 920 | *924,1 |  | 06.05.04.01.06.00.00.00 |  | TAP-12365 | [TAP-12365] ¦ [Cyber] Implement chain of trust on the Windows Platform | Feature | Done |  |  | Parent Task | User Stories | 52.5 | 52.5 | 1 hr | 1 hr | 0 | 100%
TAP-12365_ATLAS | 921 | *920 |  | 06.05.04.01.06.01.00.00 | TAP-12365 | TAP-35019 | [TAP-12365_ATLAS] ¦ Investigate default certificates and new certificate enrollment in windows os | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 52.5 | 52.5 | 52.5 | 63 | 0 | 100%
TAP-63713 | 922 | *1,924 |  | 06.05.04.01.07.00.00.00 |  | TAP-63713 | [TAP-63713] ¦ [Cyber] Implement Authentic Code Execution on the Windows Platform | Feature | Done |  |  | Parent Task | User Stories | 35 | 35 | 1 hr | 1 hr | 0 | 100%
TAP-63713_ATLAS | 923 | *922 |  | 06.05.04.01.07.01.00.00 | TAP-63713 | TAP-91613 | [TAP-63713_ATLAS] ¦ WDAC prevent the Natural Point driver for Opti Track from loading | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 35 | 35 | 35 | 42 | 0 | 100%
TAP-58664 | 924 | *926,5 | *912,913,914,917,918,920,922 | 06.05.04.01.08.00.00.00 |  | TAP-58664 | [TAP-58664] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Windows x86 | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-58664_ATLAS | 925 | *924 |  | 06.05.04.01.08.01.00.00 | TAP-58664 | TAP-104892 | [TAP-58664_ATLAS] ¦ [Enabler] Penetration testing support | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-13756 | 926 | *5 | *924 | 06.05.04.01.09.00.00.00 |  | TAP-13756 | [TAP-13756] ¦ [Cyber] Implement penetration testing findings for Windows OS | Feature | Done |  |  | Parent Task | User Stories | 52.5 | 52.5 | 1 hr | 1 hr | 0 | 100%
TAP-13756_ATLAS | 927 | *926 |  | 06.05.04.01.09.01.00.00 | TAP-13756 | TAP-115415 | [TAP-13756_ATLAS] ¦ [Cyber][Win10] Non-Admin Medtronic User - Dev test and Delivery to develop | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 52.5 | 52.5 | 52.5 | 63 | 0 | 100%
TAP-13758 | 928 | *9 |  | 06.05.04.01.10.00.00.00 |  | TAP-13758 | [TAP-13758] ¦ [Cyber] Finish the QA tasks related to Windows for Cyber release | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-13758_ATLAS | 929 | *928 |  | 06.05.04.01.10.01.00.00 | TAP-13758 | TAP-74897 | [TAP-13758_ATLAS] ¦ Integration test new Simbionix build with UAC enabled | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-12370 | 930 | *1 |  | 06.05.04.02.01.00.00.00 |  | TAP-12370 | [TAP-12370] ¦ [Cyber] Implement secure storage on windows platform | Feature | Done |  |  | Parent Task | User Stories | 36 | 36 | 1 hr | 1 hr | 0 | 100%
TAP-12370_ATLAS | 931 | *930 |  | 06.05.04.02.01.01.00.00 | TAP-12370 | TAP-35047 | [TAP-12370_ATLAS] ¦ Test Design for Windows Secure Storage Requirements - SCDC | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 36 | 36 | 36 | 43.2 | 0 | 100%
TAP-12367 | 932 | *1 |  | 06.05.04.03.01.00.00.00 |  | TAP-12367 | [TAP-12367] ¦ [Cyber] Implement least privilege strategy for the windows platform | Feature | Done |  |  | Parent Task | User Stories | 83 | 83 | 1 hr | 1 hr | 0 | 100%
TAP-12367_ATLAS | 933 | *932 |  | 06.05.04.03.01.01.00.00 | TAP-12367 | TAP-99180 | [TAP-12367_ATLAS] ¦ Update Deployment for new Esat Deployment Directory | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 83 | 83 | 83 | 99.6 | 0 | 100%
TAP-12368 | 934 | *1 |  | 06.05.04.03.02.00.00.00 |  | TAP-12368 | [TAP-12368] ¦ [Cyber] Windows OS Interface Hardening | Feature | Done |  |  | Parent Task | User Stories | 110 | 110 | 1 hr | 1 hr | 0 | 100%
TAP-12368_ATLAS | 935 | *934 |  | 06.05.04.03.02.01.00.00 | TAP-12368 | TAP-97001 | [TAP-12368_ATLAS] ¦ Win 10 Production OS hardening (in addition to Engineering settings) | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 110 | 110 | 110 | 132 | 0 | 100%
TAP-12369 | 936 | *1 |  | 06.05.04.03.03.00.00.00 |  | TAP-12369 | [TAP-12369] ¦ [Cyber] Investigate hard coded secrets on Windows Platform | Feature | Done |  |  | Parent Task | User Stories | 1 | 1 | 1 hr | 1 hr | 0 | 100%
TAP-12369_ATLAS | 937 | *936 |  | 06.05.04.03.03.01.00.00 | TAP-12369 | TAP-85380 | [TAP-12369_ATLAS] ¦ (Windows) Remove AuditGPBackup and search for any hardcoded secrets on the system | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-58837 | 938 | *1 |  | 06.05.04.03.04.00.00.00 |  | TAP-58837 | [TAP-58837] ¦ [Cyber] Windows: WolfSSH Integration | Feature | Done |  |  | Parent Task | User Stories | 35 | 35 | 1 hr | 1 hr | 0 | 100%
TAP-58837_ATLAS | 939 | *938 |  | 06.05.04.03.04.01.00.00 | TAP-58837 | TAP-91700 | [TAP-58837_ATLAS] ¦ Investigate Wolfssh Build Requirements with Devops' Current Wolfssl Requirements | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 35 | 35 | 35 | 42 | 0 | 100%
TAP-58837_EDISON | 940 | *938 |  | 06.05.04.03.04.11.00.00 | TAP-58837 | TAP-94278 | [TAP-58837_EDISON] ¦ support wolfssh and wolfssl build for windows | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 66 | 35 | 66 | 79.2 | 31 | 100%
TAP-104858 | 941 | *5 |  | 06.05.04.03.05.00.00.00 |  | TAP-104858 | [TAP-104858] ¦ [Cyber] WinOS Data and network protection | Feature | Done |  |  | Parent Task | User Stories | 14.1 | 14.1 | 1 hr | 1 hr | 0 | 100%
TAP-104858_ATLAS | 942 | *941 |  | 06.05.04.03.05.01.00.00 | TAP-104858 | TAP-104314 | [TAP-104858_ATLAS] ¦ [SPIKE] Support Kontron UEFI changes for BitLocker DMAR/PCR7 support | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 14.1 | 14.1 | 14.1 | 16.92 | 0 | 100%
TAP-76410 | 943 | *966,1 |  | 06.05.05.01.01.00.00.00 |  | TAP-76410 | [TAP-76410] ¦ [Cyber] Integrate secure EtherCAT into system | Feature | Done |  |  | Parent Task | User Stories | 34 | 34 | 1 hr | 1 hr | 0 | 100%
TAP-76410_BART | 944 | *943 |  | 06.05.05.01.01.01.00.00 | TAP-76410 | TAP-83944 | [TAP-76410_BART] ¦ [v2.1] Support SW team to debug HMAC signature failure issue | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 34 | 34 | 34 | 40.8 | 0 | 100%
TAP-76410_FRED | 945 | *943 |  | 06.05.05.01.01.03.00.00 | TAP-76410 | TAP-91693 | [TAP-76410_FRED] ¦ [Spike] Investigate if /einstein/application path is necessary for FoE upload exceptions and remove it if possible | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 35 | 34 | 35 | 42 | 1 | 100%
TAP-58458 | 946 | *966,1 |  | 06.05.05.01.02.00.00.00 |  | TAP-58458 | [TAP-58458] ¦ [Cyber] Update Secure Communication Library | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-177 | 947 | *966,1 |  | 06.05.05.01.03.00.00.00 |  | TAP-177 | [TAP-177] ¦ [Cyber] Design Secure EtherCAT Communication | Feature | Done |  |  | Parent Task | User Stories | 66 | 66 | 1 hr | 1 hr | 0 | 100%
TAP-177_BART | 948 | *947 |  | 06.05.05.01.03.01.00.00 | TAP-177 | TAP-71258 | [TAP-177_BART] ¦ [HMAC] Verification of HMAC | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 66 | 66 | 66 | 79.2 | 0 | 100%
TAP-177_FRED | 949 | *947 |  | 06.05.05.01.03.19.00.00 | TAP-177 | TAP-51551 | [TAP-177_FRED] ¦ [Cyber] Debug PL Hmac | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 88 | 66 | 88 | 105.6 | 22 | 100%
TAP-177_HORIZON | 950 | *947 |  | 06.05.05.01.03.27.00.00 | TAP-177 | TAP-38251 | [TAP-177_HORIZON] ¦ [Cyber] Design mechanism for handshake for EtherCAT Part 2 - transport authentication packets | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 109 | 66 | 109 | 130.8 | 43 | 100%
TAP-4936 | 951 | *966,1 |  | 06.05.05.01.04.00.00.00 |  | TAP-4936 | [TAP-4936] ¦ [Cyber] Implement Secure EtherCAT cyclic communication and cybersecurity framework | Feature | Done |  |  | Parent Task | User Stories | 46 | 46 | 1 hr | 1 hr | 0 | 100%
TAP-4936_BART | 952 | *951 |  | 06.05.05.01.04.01.00.00 | TAP-4936 | TAP-49513 | [TAP-4936_BART] ¦ [Cyber] Support SW team with HMAC debug | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 46 | 46 | 46 | 55.2 | 0 | 100%
TAP-4936_FRED | 953 | *951 |  | 06.05.05.01.04.05.00.00 | TAP-4936 | TAP-71639 | [TAP-4936_FRED] ¦ [TechDebt] clean up library common secure communication | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 50 | 46 | 50 | 60 | 4 | 100%
TAP-55077 | 954 | *966,1 |  | 06.05.05.01.05.00.00.00 |  | TAP-55077 | [TAP-55077] ¦ [Cyber] SPIKE Investigate and Architect the Solution to Authenticate File Over Ethercat Communications Risk: R021 | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-55077_FRED | 955 | *954 |  | 06.05.05.01.05.01.00.00 | TAP-55077 | TAP-64747 | [TAP-55077_FRED] ¦ Decide between strategy one or strategy two for authenticated EtherCAT FoE | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-71075 | 956 | *966,1 |  | 06.05.05.01.06.00.00.00 |  | TAP-71075 | [TAP-71075] ¦ [Cyber] Implement Authenticated File Over Ethercat Communications | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-71075_FRED | 957 | *956 |  | 06.05.05.01.06.01.00.00 | TAP-71075 | TAP-73771 | [TAP-71075_FRED] ¦ Sign and verify EtherCAT FoE file transfers | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-71074 | 958 | *966,1 |  | 06.05.05.01.07.00.00.00 |  | TAP-71074 | [TAP-71074] ¦ [v4.0][Cyber] Implement EtherCAT security for the acyclic communication path | Feature | Done |  |  | Parent Task | User Stories | 24 | 24 | 1 hr | 1 hr | 0 | 100%
TAP-71074_FRED | 959 | *958 |  | 06.05.05.01.07.01.00.00 | TAP-71074 | TAP-99128 | [TAP-71074_FRED] ¦ Create an event id and log replay attack in EtherCAT Communication | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 24 | 24 | 24 | 28.8 | 0 | 100%
TAP-83828 | 960 | *1 |  | 06.05.05.01.08.00.00.00 |  | TAP-83828 | [TAP-83828] ¦ [Cyber] Ethercat Master updates to support RASA Testers and Manufacturing | Feature | Done |  |  | Parent Task | User Stories | 34 | 34 | 1 hr | 1 hr | 0 | 100%
TAP-83828_FRED | 961 | *960 |  | 06.05.05.01.08.01.00.00 | TAP-83828 | TAP-84561 | [TAP-83828_FRED] ¦ enable ethercat_master_maintenance to support EoE and FoE for unsecured nodes | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 34 | 34 | 34 | 40.8 | 0 | 100%
TAP-83633 | 962 | *7 |  | 06.05.05.01.09.00.00.00 |  | TAP-83633 | [TAP-83633] ¦ [V4.0][Cyber][Tech Debt] Complete Test Infrastructure for Secure EtherCAT | Feature | Done |  |  | Parent Task | User Stories | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100%
TAP-83633_FRED | 963 | *962 |  | 06.05.05.01.09.01.00.00 | TAP-83633 | TAP-91485 | [TAP-83633_FRED] ¦ [Spike] Investigate if v4.0 (EtherCAT-)requirements enable tests and cover data integrity | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 27.5 | 27.5 | 27.5 | 33 | 0 | 100%
TAP-95486 | 964 | *7 |  | 06.05.05.01.10.00.00.00 |  | TAP-95486 | [TAP-95486] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Authentication Tests for FoE and Cyclic | Feature | Done |  |  | Parent Task | User Stories | 30 | 30 | 1 hr | 1 hr | 0 | 100%
TAP-95486_FRED | 965 | *964 |  | 06.05.05.01.10.01.00.00 | TAP-95486 | TAP-95658 | [TAP-95486_FRED] ¦ Implementation of FoE Authentication Tests | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 30 | 30 | 30 | 36 | 0 | 100%
TAP-58669 | 966 | *968,13 | *951,956,947,954,958,946,943 | 06.05.05.01.11.00.00.00 |  | TAP-58669 | [TAP-58669] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Ethercat/SSL | Feature | Done |  |  | Parent Task | User Stories | 5.5 | 5.5 | 1 hr | 1 hr | 0 | 100%
TAP-58669_FRED | 967 | *966 |  | 06.05.05.01.11.01.00.00 | TAP-58669 | TAP-114470 | [TAP-58669_FRED] ¦ Define SW Setup for EC Penetration Tests: Build Type, Certificates, Deployment | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 5.5 | 5.5 | 5.5 | 6.6 | 0 | 100%
TAP-58670 | 968 | *13 | *966 | 06.05.05.01.12.00.00.00 |  | TAP-58670 | [TAP-58670] ¦ [Cyber] Correct penetration testing findings for Ethercat/SSL | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-106190 | 969 | *7 |  | 06.05.05.01.13.00.00.00 |  | TAP-106190 | [TAP-106190] ¦ 🚩[v4.0][Cyber] EtherCAT SSC<->Master Anti-Replay Tests for Ayclic | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-106190_FRED | 970 | *969 |  | 06.05.05.01.13.01.00.00 | TAP-106190 | TAP-105910 | [TAP-106190_FRED] ¦ Anti-Replay Test Design Draft Acyclic | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-106193 | 971 | *7 |  | 06.05.05.01.14.00.00.00 |  | TAP-106193 | [TAP-106193] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Anti-Replay Tests for FoE | Feature | Done |  |  | Parent Task | User Stories | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-106193_FRED | 972 | *971 |  | 06.05.05.01.14.01.00.00 | TAP-106193 | TAP-105909 | [TAP-106193_FRED] ¦ Anti-Replay Test Design Draft FoE | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-97725 | 973 | *7 |  | 06.05.05.01.15.00.00.00 |  | TAP-97725 | [TAP-97725] ¦ [v4.0][Cyber] EtherCAT SSC<->Master Authentication Tests for Ayclic | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-97725_FRED | 974 | *973 |  | 06.05.05.01.15.01.00.00 | TAP-97725 | TAP-95660 | [TAP-97725_FRED] ¦ Implementation of Acyclic Authentication Tests | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-95051 | 975 | *7 |  | 06.05.05.01.16.00.00.00 |  | TAP-95051 | [TAP-95051] ¦ [v4.0][Sentinel][Cyber] EtherCAT Stability Improvements + Test Fixes | Feature | Done |  |  | Parent Task | User Stories | 85 | 85 | 1 hr | 1 hr | 0 | 100%
TAP-95051_BART | 976 | *975 |  | 06.05.05.01.16.01.00.00 | TAP-95051 | TAP-96281 | [TAP-95051_BART] ¦ [Bart] Fix EIN-TM-1283: Support Fred team to debug J5 actual brake current | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 85 | 85 | 85 | 102 | 0 | 100%
TAP-95051_FRED | 977 | *975 |  | 06.05.05.01.16.03.00.00 | TAP-95051 | TAP-98993 | [TAP-95051_FRED] ¦ Add missing case that cover pure autorun after FoE downloading in EC FoE eintest | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 89 | 85 | 89 | 106.8 | 4 | 100%
TAP-95051_SOUPERTROOPERS | 978 | *975 |  | 06.05.05.01.16.39.00.00 | TAP-95051 | TAP-117569 | [TAP-95051_SOUPERTROOPERS] ¦ [v4.0][SOUP] EC-Master: Revalidate Acontis SOUP: Upgrade to 3.1.5.02 | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 157 | 85 | 157 | 188.4 | 72 | 100%
TAP-95051_EDISON | 979 | *975 |  | 06.05.05.01.16.40.00.00 | TAP-95051 | TAP-117568 | [TAP-95051_EDISON] ¦ [Edison] Integrate Acontis 3.1.5.02 in Docker | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 157 | 85 | 157 | 188.4 | 72 | 100%
TAP-149 | 980 | *1066,1 |  | 06.05.05.02.01.00.00.00 |  | TAP-149 | [TAP-149] ¦ [Cyber] Secure UDP | Feature | Done |  |  | Parent Task | User Stories | 14 | 14 | 1 hr | 1 hr | 0 | 100%
TAP-149_CLASSY1 | 981 | *980 |  | 06.05.05.02.01.01.00.00 | TAP-149 | TAP-358 | [TAP-149_CLASSY1] ¦ Integrate handshake for UDP classes | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 14 | 14 | 14 | 16.8 | 0 | 100%
TAP-141 | 982 | *1066,1 |  | 06.05.05.02.02.00.00.00 |  | TAP-141 | [TAP-141] ¦ [Cyber] UDP library new features | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-141_CLASSY1 | 983 | *982 |  | 06.05.05.02.02.01.00.00 | TAP-141 | TAP-426 | [TAP-141_CLASSY1] ¦ UDP Spy Tool | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-158 | 984 | *1066,1 |  | 06.05.05.02.03.00.00.00 |  | TAP-158 | [TAP-158] ¦ [Cyber] Secure Communication Library | Feature | Done |  |  | Parent Task | User Stories | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-158_FRED | 985 | *984 |  | 06.05.05.02.03.01.00.00 | TAP-158 | TAP-236 | [TAP-158_FRED] ¦ Refactor Secure Comm interface | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-158_CASTLEBLACK | 986 | *984 |  | 06.05.05.02.03.08.00.00 | TAP-158 | TAP-6297 | [TAP-158_CASTLEBLACK] ¦ SWI for WolfSSL | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 20 | 12 | 20 | 24 | 8 | 100%
TAP-193 | 987 | *1066,1 |  | 06.05.05.02.04.00.00.00 |  | TAP-193 | [TAP-193] ¦ [Cyber] Investigate DDS Domains | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-193_CLASSY1 | 988 | *987 |  | 06.05.05.02.04.01.00.00 | TAP-193 | TAP-424 | [TAP-193_CLASSY1] ¦ Investigate replacing domains with partitions on armv7 nodes | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-178 | 989 | *1066,1 |  | 06.05.05.02.05.00.00.00 |  | TAP-178 | [TAP-178] ¦ [Cyber] Communication Library New Interface Phase 1 | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-178_CLASSY1 | 990 | *989 |  | 06.05.05.02.05.01.00.00 | TAP-178 | TAP-346 | [TAP-178_CLASSY1] ¦ Implement UDP library to use new interface | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-115 | 991 | *1066,1 |  | 06.05.05.02.06.00.00.00 |  | TAP-115 | [TAP-115] ¦ [Cyber] Communication Middleware Layer Phase 2 | Feature | Done |  |  | Parent Task | User Stories | 57 | 57 | 1 hr | 1 hr | 0 | 100%
TAP-115_CLASSY1 | 992 | *991 |  | 06.05.05.02.06.01.00.00 | TAP-115 | TAP-2702 | [TAP-115_CLASSY1] ¦ Design user facing communication interface | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 57 | 57 | 57 | 68.4 | 0 | 100%
TAP-133 | 993 | *1066,1 |  | 06.05.05.02.07.00.00.00 |  | TAP-133 | [TAP-133] ¦ [Cyber] [Spike] DDS Secure Feasibility | Feature | Done |  |  | Parent Task | User Stories | 23 | 23 | 1 hr | 1 hr | 0 | 100%
TAP-133_CLASSY1 | 994 | *993 |  | 06.05.05.02.07.01.00.00 | TAP-133 | TAP-2653 | [TAP-133_CLASSY1] ¦ DDS Secure feasibility testing on QNX 7.1 | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 23 | 23 | 23 | 27.6 | 0 | 100%
TAP-125 | 995 | *1066,1 |  | 06.05.05.02.08.00.00.00 |  | TAP-125 | [TAP-125] ¦ [Cyber] Integrate Communication Library Interface in Alarms | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-125_CLASSY1 | 996 | *995 |  | 06.05.05.02.08.01.00.00 | TAP-125 | TAP-395 | [TAP-125_CLASSY1] ¦ Integrate new DDS communication interface in Alarms | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-1010 | 997 | *1066,1 |  | 06.05.05.02.09.00.00.00 |  | TAP-1010 | [TAP-1010] ¦ [Cyber] Cleanup usage of DDS Domains | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-25137 | 998 | *1066,1 |  | 06.05.05.02.10.00.00.00 |  | TAP-25137 | [TAP-25137] ¦ [Cyber][Arch]Improve Testability of New Communication Libraries (UDP) | Feature | Done |  |  | Parent Task | User Stories | 89 | 89 | 1 hr | 1 hr | 0 | 100%
TAP-25137_CLASSY1 | 999 | *998 |  | 06.05.05.02.10.01.00.00 | TAP-25137 | TAP-46312 | [TAP-25137_CLASSY1] ¦ Test Code refactoring (improvements) | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 89 | 89 | 89 | 106.8 | 0 | 100%
TAP-55466 | 1000 | *1066,1 |  | 06.05.05.02.11.00.00.00 |  | TAP-55466 | [TAP-55466] ¦ [Cyber][Arch]Improve Testability of New Communication Libraries (DDS) (Phase 1) | Feature | Done |  |  | Parent Task | User Stories | 43 | 43 | 1 hr | 1 hr | 0 | 100%
TAP-55466_CLASSY1 | 1001 | *1000 |  | 06.05.05.02.11.01.00.00 | TAP-55466 | TAP-36684 | [TAP-55466_CLASSY1] ¦ Implement Test Case CYB-TC_SW-1436 Communication - CRC - DDS [EIN-SSR_COMM-4] | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 43 | 43 | 43 | 51.6 | 0 | 100%
TAP-55466_COSSACKS | 1002 | *1000 |  | 06.05.05.02.11.07.00.00 | TAP-55466 | TAP-47621 | [TAP-55466_COSSACKS] ¦ [CI] Create bamboo plan to run new dds communication tests | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 68 | 43 | 68 | 81.6 | 25 | 100%
TAP-55473 | 1003 | *1066,1 |  | 06.05.05.02.12.00.00.00 |  | TAP-55473 | [TAP-55473] ¦ [Cyber] [Arch] [Enabler] [Storm Chasers] Communication library update: head tracking | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-55473_CLASSY1 | 1004 | *1003 |  | 06.05.05.02.12.01.00.00 | TAP-55473 | TAP-47722 | [TAP-55473_CLASSY1] ¦ Integration new dds library into head tracking communication subsystem | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-55473_STORMCHASERS1 | 1005 | *1003 |  | 06.05.05.02.12.02.00.00 | TAP-55473 | TAP-18681 | [TAP-55473_STORMCHASERS1] ¦ Update SC Head Tracking application to the new Communication Library | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-55557 | 1006 | *1066,1 |  | 06.05.05.02.13.00.00.00 |  | TAP-55557 | [TAP-55557] ¦ [Cyber] [Arch] [Enabler] Supporting integration of new communication library | Feature | Done |  |  | Parent Task | User Stories | 30 | 30 | 1 hr | 1 hr | 0 | 100%
TAP-55557_CLASSY1 | 1007 | *1006 |  | 06.05.05.02.13.01.00.00 | TAP-55557 | TAP-55413 | [TAP-55557_CLASSY1] ¦ [Spike] figure out replacement for AckCheckWriters | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 30 | 30 | 30 | 36 | 0 | 100%
TAP-55557_STORMCHASERS | 1008 | *1006 |  | 06.05.05.02.13.06.00.00 | TAP-55557 | TAP-18687 | [TAP-55557_STORMCHASERS] ¦ Update SMC E-box Monitor application to the new Communication Library | User Story | Done | Foundation - Storm Chasers | STORMCHASERS | Child Task | User Stories | 47 | 30 | 47 | 56.4 | 17 | 100%
TAP-55463 | 1009 | *1066,1 |  | 06.05.05.02.14.00.00.00 |  | TAP-55463 | [TAP-55463] ¦ [Cyber] [Arch] [Enabler][Fred] Integrate new communication library into ACS communication | Feature | Done |  |  | Parent Task | User Stories | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-55463_FRED | 1010 | *1009 |  | 06.05.05.02.14.01.00.00 | TAP-55463 | TAP-48110 | [TAP-55463_FRED] ¦ [ACS Stability] Use New Communication Library in ACS | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-55464 | 1011 | *1066,1 |  | 06.05.05.02.15.00.00.00 |  | TAP-55464 | [TAP-55464] ¦ [Cyber] [Arch] [Enabler] [Boosters] Communication library update: configuration | Feature | Done |  |  | Parent Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-55464_BOOSTERS | 1012 | *1011 |  | 06.05.05.02.15.01.00.00 | TAP-55464 | TAP-47709 | [TAP-55464_BOOSTERS] ¦ [Boosters] Integration new dds library into configuration_communication subsystem | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 31 | 31 | 31 | 37.2 | 0 | 100%
TAP-55464_PLATFORMERS | 1013 | *1011 |  | 06.05.05.02.15.04.00.00 | TAP-55464 | TAP-65606 | [TAP-55464_PLATFORMERS] ¦ [Cyber][Platformers][V&V][CM] Config Configuration Manager test bamboo execution | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 48 | 31 | 48 | 57.6 | 17 | 100%
TAP-71118 | 1014 | *1066,1 |  | 06.05.05.02.16.00.00.00 |  | TAP-71118 | [TAP-71118] ¦ [V4.0][Cyber] PI10 New Communication Library Wrapper (Foundation) | Feature | Done |  |  | Parent Task | User Stories | 238.5 | 238.5 | 1 hr | 1 hr | 0 | 100%
TAP-71118_STORMCHASERS1 | 1015 | *1014 |  | 06.05.05.02.16.01.00.00 | TAP-71118 | TAP-72646 | [TAP-71118_STORMCHASERS1] ¦ SC Scaler Monitor application NOTCODE_71 investigation | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 238.5 | 238.5 | 238.5 | 286.2 | 0 | 100%
TAP-71118_CASTLEBLACK | 1016 | *1014 |  | 06.05.05.02.16.03.00.00 | TAP-71118 | TAP-74397 | [TAP-71118_CASTLEBLACK] ¦ Hold workshop with teams to support migration to comms library | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 239.5 | 238.5 | 239.5 | 287.4 | 1 | 100%
TAP-71118_PLATFORMERS | 1017 | *1014 |  | 06.05.05.02.16.04.01.00 | TAP-71118 | TAP-74913 | [TAP-71118_PLATFORMERS] ¦ [Cyber] Integration new dds library into Certificate communication subsystem | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 239.5 | 238.5 | 239.5 | 287.4 | 1 | 100%
TAP-71118_BOOSTERS | 1018 | *1014 |  | 06.05.05.02.16.05.01.00 | TAP-71118 | TAP-73862 | [TAP-71118_BOOSTERS] ¦ [Boosters] Update Logging subsystem communication to use new API | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 241.5 | 238.5 | 241.5 | 289.8 | 3 | 100%
TAP-71118_CLASSY1 | 1019 | *1014 |  | 06.05.05.02.16.05.03.00 | TAP-71118 | TAP-73963 | [TAP-71118_CLASSY1] ¦ [CLASSY] Update alarms and notification communication to use new API | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 245.5 | 238.5 | 245.5 | 294.6 | 7 | 100%
TAP-71118_FRED | 1020 | *1014 |  | 06.05.05.02.16.07.01.00 | TAP-71118 | TAP-73967 | [TAP-71118_FRED] ¦ Update S-Fuction DDSv2 block API to prepare for new DDS API | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 335.5 | 238.5 | 335.5 | 402.6 | 97 | 100%
TAP-71118_HORIZON | 1021 | *1014 |  | 06.05.05.02.16.10.01.00 | TAP-71118 | TAP-55503 | [TAP-71118_HORIZON] ¦ [Comm] Investigate strategy system integration test for new communication library | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 355.5 | 238.5 | 355.5 | 426.6 | 117 | 100%
TAP-71118_STORMCHASERS2 | 1022 | *1014 |  | 06.05.05.02.16.11.03.00 | TAP-71118 | TAP-76539 | [TAP-71118_STORMCHASERS2] ¦ [V4.0][SC2] Attend the new comm library workshop (May 11) | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 374.5 | 238.5 | 374.5 | 449.4 | 136 | 100%
TAP-71118_VISUAL | 1023 | *1014 |  | 06.05.05.02.16.12.01.00 | TAP-71118 | TAP-56931 | [TAP-71118_VISUAL] ¦ [SPIKE][Visual] Integration new dds library into storz communication subsystem - code proposition (0.5 SP left) | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 375 | 238.5 | 375 | 450 | 136.5 | 100%
TAP-72563 | 1024 | *1066,1 |  | 06.05.05.02.17.00.00.00 |  | TAP-72563 | [TAP-72563] ¦ [V4.0][Cyber]PI10 New Communication Library Wrapper (Instrumentation) | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-72563_ORGANELLES | 1025 | *1024 |  | 06.05.05.02.17.01.00.00 | TAP-72563 | TAP-75267 | [TAP-72563_ORGANELLES] ¦ [Reflect] Attend Comms Library Workshop | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-72563_SCRUMBLEDORES | 1026 | *1024 |  | 06.05.05.02.17.03.00.00 | TAP-72563 | TAP-74802 | [TAP-72563_SCRUMBLEDORES] ¦ [Scrumbledores] Comms Library Workshop | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 17 | 16 | 17 | 20.4 | 1 | 100%
TAP-79110 | 1027 | *1 |  | 06.05.05.02.18.00.00.00 |  | TAP-79110 | [TAP-79110] ¦ [V4.0] [Comms] [Cyber] New communication library update and migration (PI12) | Feature | Done |  |  | Parent Task | User Stories | 499.5 | 499.5 | 1 hr | 1 hr | 0 | 100%
TAP-79110_TEAMBD | 1028 | *1027 |  | 06.05.05.02.18.01.00.00 | TAP-79110 | TAP-96744 | [TAP-79110_TEAMBD] ¦ [Cyber] SPIKE - Update Comms Loss Checks - MSC (Part 2) | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 499.5 | 499.5 | 499.5 | 599.4 | 0 | 100%
TAP-79110_FRED | 1029 | *1027 |  | 06.05.05.02.18.02.00.00 | TAP-79110 | TAP-91303 | [TAP-79110_FRED] ¦ Reliable DDS Simulink writers re-use input port 1 | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 499.5 | 499.5 | 499.5 | 599.4 | 0 | 100%
TAP-79110_PLATFORMERS | 1030 | *1027 |  | 06.05.05.02.18.03.00.00 | TAP-79110 | TAP-96014 | [TAP-79110_PLATFORMERS] ¦ [Cyber][[Platformers][PM] RASA Tools DDS COMM library update and migration | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 499.5 | 499.5 | 499.5 | 599.4 | 0 | 100%
TAP-79110_STORMCHASERS2 | 1031 | *1027 |  | 06.05.05.02.18.06.00.00 | TAP-79110 | TAP-96854 | [TAP-79110_STORMCHASERS2] ¦ [V4.0][SC2] Fix SC automated tests that failed because of latest changes related to the new communication library | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 510.5 | 499.5 | 510.5 | 612.6 | 11 | 100%
TAP-79110_VISUAL | 1032 | *1027 |  | 06.05.05.02.18.10.00.00 | TAP-79110 | TAP-97613 | [TAP-79110_VISUAL] ¦ [v4.0][Visual] Reducing the number of DDS topics in storz subsytem based on architecture patterns and new DDS library. Fluorescence topic. | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 522.5 | 499.5 | 522.5 | 627 | 23 | 100%
TAP-79110_CLASSY1 | 1033 | *1027 |  | 06.05.05.02.18.16.01.00 | TAP-79110 | TAP-88854 | [TAP-79110_CLASSY1] ¦ Implement change to configuration manager | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 532.5 | 499.5 | 532.5 | 639 | 33 | 100%
TAP-79110_COSSACKS | 1034 | *1027 |  | 06.05.05.02.18.17.07.00 | TAP-79110 | TAP-88540 | [TAP-79110_COSSACKS] ¦ [CI] Investigate issue with lower B system | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 593.5 | 499.5 | 593.5 | 712.2 | 94 | 100%
TAP-79110_STORMCHASERS1 | 1035 | *1027 |  | 06.05.05.02.18.18.07.00 | TAP-79110 | TAP-91877 | [TAP-79110_STORMCHASERS1] ¦ [v4.0][SC1] Update SC ergonomic automated tests to the new Communication Library | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 632.5 | 499.5 | 632.5 | 759 | 133 | 100%
TAP-79110_CASTLEBLACK | 1036 | *1027 |  | 06.05.05.02.18.22.01.00 | TAP-79110 | TAP-85424 | [TAP-79110_CASTLEBLACK] ¦ Support Risk Analysis for Teams with Ack Check Writer | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 785.5 | 499.5 | 785.5 | 942.6 | 286 | 100%
TAP-79110_HORIZON | 1037 | *1027 |  | 06.05.05.02.18.24.01.00 | TAP-79110 | TAP-55500 | [TAP-79110_HORIZON] ¦ Integrate new DDS library into TPSC communication subsystem | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 795.5 | 499.5 | 795.5 | 954.6 | 296 | 100%
TAP-79110_CLASSY2 | 1038 | *1027 |  | 06.05.05.02.18.24.02.00 | TAP-79110 | TAP-65733 | [TAP-79110_CLASSY2] ¦ [CLASSY] Support Horizon team comm library update | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 795.5 | 499.5 | 795.5 | 954.6 | 296 | 100%
TAP-79110_TOOLSRULES | 1039 | *1027 |  | 06.05.05.02.18.31.01.00 | TAP-79110 | TAP-74145 | [TAP-79110_TOOLSRULES] ¦ Integration new dds library into ESAT communication subsystem | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 956 | 499.5 | 956 | 1147.2 | 456.5 | 100%
TAP-85853 | 1040 | *1 |  | 06.05.05.02.19.00.00.00 |  | TAP-85853 | [TAP-85853] ¦ [Cyber][V4.0] ADV INST Complete migration of subsystem to new communication library | Feature | Done |  |  | Parent Task | User Stories | 120 | 120 | 1 hr | 1 hr | 0 | 100%
TAP-85853_JACOBIANS | 1041 | *1040 |  | 06.05.05.02.19.01.00.00 | TAP-85853 | TAP-97555 | [TAP-85853_JACOBIANS] ¦ [V4.0][Jacobians] Support merge of DDS Updates | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 120 | 120 | 120 | 144 | 0 | 100%
TAP-85853_ORGANELLES | 1042 | *1040 |  | 06.05.05.02.19.02.00.00 | TAP-85853 | TAP-96479 | [TAP-85853_ORGANELLES] ¦ [Organelles] [SPIKE] Update Comms Loss Checks - SRA | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 120 | 120 | 120 | 144 | 0 | 100%
TAP-85853_SCRUMBLEDORES | 1043 | *1040 |  | 06.05.05.02.19.03.00.00 | TAP-85853 | TAP-97574 | [TAP-85853_SCRUMBLEDORES] ¦ [V4.0] [Scrumbledores] Support merge of DDS Updates to Develop | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 120 | 120 | 120 | 144 | 0 | 100%
TAP-85853_TEAMBD | 1044 | *1040 |  | 06.05.05.02.19.04.00.00 | TAP-85853 | TAP-96478 | [TAP-85853_TEAMBD] ¦ [TeamBD] [SPIKE] [Part 1] Update Comms Loss Checks - MSC | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 120 | 120 | 120 | 144 | 0 | 100%
TAP-85853_PIXELPOETS | 1045 | *1040 |  | 06.05.05.02.19.06.01.00 | TAP-85853 | TAP-64203 | [TAP-85853_PIXELPOETS] ¦ [Positron][Spike] Investigate comms loss requirements | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 125 | 120 | 125 | 150 | 5 | 100%
TAP-85853_DRUSHTI | 1046 | *1040 |  | 06.05.05.02.19.06.04.00 | TAP-85853 | TAP-65738 | [TAP-85853_DRUSHTI] ¦ [Drushti] Implementation of Communication library update for gui part 2 | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 129 | 120 | 129 | 154.8 | 9 | 100%
TAP-85853_ATLAS | 1047 | *1040 |  | 06.05.05.02.19.06.08.00 | TAP-85853 | TAP-83031 | [TAP-85853_ATLAS] ¦ Code generation to support idlxmlgen gui tool | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 143 | 120 | 143 | 171.6 | 23 | 100%
TAP-58886 | 1048 | *1,1066 |  | 06.05.05.02.20.00.00.00 |  | TAP-58886 | [TAP-58886] ¦ [Comms] [Cyber] Enable secure DDS communication | Feature | Done |  |  | Parent Task | User Stories | 42 | 42 | 1 hr | 1 hr | 0 | 100%
TAP-58886_ATLAS | 1049 | *1048 |  | 06.05.05.02.20.01.00.00 | TAP-58886 | TAP-86623 | [TAP-58886_ATLAS] ¦ Use WolfSSH identity certificate for DDS secure | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 42 | 42 | 42 | 50.4 | 0 | 100%
TAP-58886_CLASSY1 | 1050 | *1048 |  | 06.05.05.02.20.03.00.00 | TAP-58886 | TAP-58937 | [TAP-58886_CLASSY1] ¦ Package security libraries with nodes packages | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 43 | 42 | 43 | 51.6 | 1 | 100%
TAP-58886_EDISON | 1051 | *1048 |  | 06.05.05.02.20.07.00.00 | TAP-58886 | TAP-86764 | [TAP-58886_EDISON] ¦ Strategy for signing permissions file for secure dds work | Issue | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 61 | 42 | 61 | 73.2 | 19 | 100%
TAP-58884 | 1052 | *1,1066 |  | 06.05.05.02.21.00.00.00 |  | TAP-58884 | [TAP-58884] ¦ [Comms] [Cyber] Re-Design and Enable secure UDP communication | Feature | Done |  |  | Parent Task | User Stories | 47 | 47 | 1 hr | 1 hr | 0 | 100%
TAP-58884_CLASSY2 | 1053 | *1052 |  | 06.05.05.02.21.01.00.00 | TAP-58884 | TAP-83680 | [TAP-58884_CLASSY2] ¦ integrate secure UDP to safety network | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 47 | 47 | 47 | 56.4 | 0 | 100%
TAP-58884_FRED | 1054 | *1052 |  | 06.05.05.02.21.03.00.00 | TAP-58884 | TAP-93405 | [TAP-58884_FRED] ¦ Merge ssl wrapper and enable Secure UDP lib for Win | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 49 | 47 | 49 | 58.8 | 2 | 100%
TAP-58884_HORIZON | 1055 | *1052 |  | 06.05.05.02.21.15.00.00 | TAP-58884 | TAP-86567 | [TAP-58884_HORIZON] ¦ [Horizon] Investigate UDP Usage on Cart | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 80 | 47 | 80 | 96 | 33 | 100%
TAP-95056 | 1056 | *1 |  | 06.05.05.02.22.00.00.00 |  | TAP-95056 | [TAP-95056] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability and Performance Improvement | Feature | Done |  |  | Parent Task | User Stories | 85 | 85 | 1 hr | 1 hr | 0 | 100%
TAP-95056_CLASSY1 | 1057 | *1056 |  | 06.05.05.02.22.01.00.00 | TAP-95056 | TAP-97076 | [TAP-95056_CLASSY1] ¦ [CLASSY1] System integration test for comm library - Sprint 1 | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 85 | 85 | 85 | 102 | 0 | 100%
TAP-95056_FRED | 1058 | *1056 |  | 06.05.05.02.22.17.00.00 | TAP-95056 | TAP-103036 | [TAP-95056_FRED] ¦ Move Simulink DDS block reader initialization to time of first usage | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 159 | 85 | 159 | 190.8 | 74 | 100%
TAP-95056_HORIZON | 1059 | *1056 |  | 06.05.05.02.22.18.00.00 | TAP-95056 | TAP-103917 | [TAP-95056_HORIZON] ¦ Cart shutting down during deployment | Issue | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 159 | 85 | 159 | 190.8 | 74 | 100%
TAP-95056_POWERSTORMERS | 1060 | *1056 |  | 06.05.05.02.22.19.00.00 | TAP-95056 | TAP-101885 | [TAP-95056_POWERSTORMERS] ¦ Logs show spamming of EIN-FAILURE-1444 (msc cycle overuns) during normal teleop | Issue | Done | Shared Services - Power Stormers | POWERSTORMERS | Child Task | User Stories | 159 | 85 | 159 | 190.8 | 74 | 100%
TAP-7888 | 1061 | *3 |  | 06.05.05.02.23.00.00.00 |  | TAP-7888 | [TAP-7888] ¦ [Cyber] Communication Middleware Layer 3 | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-88364 | 1062 | *5 |  | 06.05.05.02.24.00.00.00 |  | TAP-88364 | [TAP-88364] ¦ [Cyber] [V4.0 RC2] Upgrade RTI DDS to latest patch level Version 6.0.1.35 | Feature | Done |  |  | Parent Task | User Stories | 60 | 60 | 1 hr | 1 hr | 0 | 100%
TAP-88364_GPT1 | 1063 | *1062 |  | 06.05.05.02.24.01.00.00 | TAP-88364 | TAP-107986 | [TAP-88364_GPT1] ¦ [GPT-1][Devops] Update docker container for QNX with new DDS libraries | User Story | Done | Foundation - GPT1 | GPT1 | Child Task | User Stories | 60 | 60 | 60 | 72 | 0 | 100%
TAP-88364_SOUPERTROOPERS | 1064 | *1062 |  | 06.05.05.02.24.11.00.00 | TAP-88364 | TAP-109156 | [TAP-88364_SOUPERTROOPERS] ¦ SOUP: DDS Version update | User Story | Done | Foundation - Souper Troopers | SOUPERTROOPERS | Child Task | User Stories | 104 | 60 | 104 | 124.8 | 44 | 100%
TAP-88364_VISUAL | 1065 | *1062 |  | 06.05.05.02.24.13.00.00 | TAP-88364 | TAP-109221 | [TAP-88364_VISUAL] ¦ [Visual][V4.0 EC3] Investigate impact of DDS version update on V&V test | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 105 | 60 | 105 | 126 | 45 | 100%
TAP-58672 | 1066 | *13 | *1024,1014,980,982,984,987,989,991,993,995,997,998,1000,1003,1006,1009,1011,1048,1052 | 06.05.05.02.25.00.00.00 |  | TAP-58672 | [TAP-58672] ¦ [Cyber] Micro-Penetration Test by 3rd Party for DDS/UDP | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-58672_CLASSY1 | 1067 | *1066 |  | 06.05.05.02.25.01.00.00 | TAP-58672 | TAP-114806 | [TAP-58672_CLASSY1] ¦ [CLASSY1] Support process of penetration tests findings for DDS (hw-setup/documentation) | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-58672_CLASSY2 | 1068 | *1066 |  | 06.05.05.02.25.02.00.00 | TAP-58672 | TAP-114808 | [TAP-58672_CLASSY2] ¦ [CLASSY2] Support process of penetration tests findings for UDP (hw-setup/documentation) | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-58672_FRED | 1069 | *1066 |  | 06.05.05.02.25.03.00.00 | TAP-58672 | TAP-115172 | [TAP-58672_FRED] ¦ [FRED] Support process of penetration test setup for UDP (HW + SW Setup and Documentation) | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-103513 | 1070 | *3 |  | 06.05.05.02.26.00.00.00 |  | TAP-103513 | [TAP-103513] ¦ [V4.0][Cyber][Comms][CLASSY] New Comms Library Stability fixes and performance improvement (PI13) | Feature | Done |  |  | Parent Task | User Stories | 66.5 | 66.5 | 1 hr | 1 hr | 0 | 100%
TAP-103513_CLASSY1 | 1071 | *1070 |  | 06.05.05.02.26.01.00.00 | TAP-103513 | TAP-106474 | [TAP-103513_CLASSY1] ¦ CLASSY1 CFMEA and SFMEA training | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 66.5 | 66.5 | 66.5 | 79.8 | 0 | 100%
TAP-103513_CLASSY2 | 1072 | *1070 |  | 06.05.05.02.26.15.00.00 | TAP-103513 | TAP-113226 | [TAP-103513_CLASSY2] ¦ Automated JAMA Alarms/Log pull for develop | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 122.5 | 66.5 | 122.5 | 147 | 56 | 100%
TAP-103513_HORIZON | 1073 | *1070 |  | 06.05.05.02.26.16.00.00 | TAP-103513 | TAP-101689 | [TAP-103513_HORIZON] ¦ [Spike] Root-cause why Notcode-59 triggers during INIT | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 122.5 | 66.5 | 122.5 | 147 | 56 | 100%
TAP-105505 | 1074 | *5 |  | 06.05.05.02.27.00.00.00 |  | TAP-105505 | [TAP-105505] ¦ [Cyber][Adv Instruments] Miscelleneous communication library update and integration | Feature | Done |  |  | Parent Task | User Stories | 39.5 | 39.5 | 1 hr | 1 hr | 0 | 100%
TAP-105505_ORGANELLES | 1075 | *1074 |  | 06.05.05.02.27.01.00.00 | TAP-105505 | TAP-96743 | [TAP-105505_ORGANELLES] ¦ [Organelles] Finish SRA Update of SRAArmStatus | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 39.5 | 39.5 | 39.5 | 47.4 | 0 | 100%
TAP-105505_PIXELPOETS | 1076 | *1074 |  | 06.05.05.02.27.02.00.00 | TAP-105505 | TAP-103249 | [TAP-105505_PIXELPOETS] ¦ Refactor Topic Cache | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 39.5 | 39.5 | 39.5 | 47.4 | 0 | 100%
TAP-105505_TEAMBD | 1077 | *1074 |  | 06.05.05.02.27.11.00.00 | TAP-105505 | TAP-107296 | [TAP-105505_TEAMBD] ¦ [Cyber] Fix the False Triggering of Comm Loss | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 57.5 | 39.5 | 57.5 | 69 | 18 | 100%
TAP-103503 | 1078 | *5 |  | 06.05.05.02.28.00.00.00 |  | TAP-103503 | [TAP-103503] ¦ [4.0] [Foundation] Miscellaneous communication library update and integration | Feature | Done |  |  | Parent Task | User Stories | 112.5 | 112.5 | 1 hr | 1 hr | 0 | 100%
TAP-103503_BOOSTERS | 1079 | *1078 |  | 06.05.05.02.28.01.00.00 | TAP-103503 | TAP-111609 | [TAP-103503_BOOSTERS] ¦ [Boosters] Cleanup usage of old participant profiles | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 112.5 | 112.5 | 112.5 | 135 | 0 | 100%
TAP-103503_CLASSY1 | 1080 | *1078 |  | 06.05.05.02.28.02.00.00 | TAP-103503 | TAP-96674 | [TAP-103503_CLASSY1] ¦ [CLASSY] Fix EinTests/Tests/Common/Test_CommunicationLibrary/Test_DDS V&V tests to use Secure Communication - DDS | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 112.5 | 112.5 | 112.5 | 135 | 0 | 100%
TAP-103503_CLASSY2 | 1081 | *1078 |  | 06.05.05.02.28.16.00.00 | TAP-103503 | TAP-108906 | [TAP-103503_CLASSY2] ¦ Tsim node coming up in malfunction (system monitor dies) during EC1 ISIM testing | Issue | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 162.5 | 112.5 | 162.5 | 195 | 50 | 100%
TAP-103503_FRED | 1082 | *1078 |  | 06.05.05.02.28.17.00.00 | TAP-103503 | TAP-103770 | [TAP-103503_FRED] ¦ Update arm_display_bridge DDS communication to new comms library | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 162.5 | 112.5 | 162.5 | 195 | 50 | 100%
TAP-103503_HORIZON | 1083 | *1078 |  | 06.05.05.02.28.18.00.00 | TAP-103503 | TAP-90371 | [TAP-103503_HORIZON] ¦ [TechDebt] Deprecate old TPSC, FSE, and ACS comms libraries | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 162.5 | 112.5 | 162.5 | 195 | 50 | 100%
TAP-103503_STORMCHASERS2 | 1084 | *1078 |  | 06.05.05.02.28.19.00.00 | TAP-103503 | TAP-91589 | [TAP-103503_STORMCHASERS2] ¦ [v4.0][SC2] Update the SwitchControls DDS to send all events (new and existing) in one message, update DeactivationRequest topic to use DeactivationRequest data structure | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 162.5 | 112.5 | 162.5 | 195 | 50 | 100%
TAP-103503_VISUAL | 1085 | *1078 |  | 06.05.05.02.28.30.00.00 | TAP-103503 | TAP-106213 | [TAP-103503_VISUAL] ¦ [v4.0][visual]merge to develop staging/TAP-104607-msc-storz-communication-loss-feature branch | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 196.5 | 112.5 | 196.5 | 235.8 | 84 | 100%
TAP-87345 | 1086 | *5 |  | 06.05.05.02.29.00.00.00 |  | TAP-87345 | [TAP-87345] ¦ [Comms][V4.0][Cyber] Comms Libraries stability fixes and miscelleneous enhancements | Feature | Done |  |  | Parent Task | User Stories | 56 | 56 | 1 hr | 1 hr | 0 | 100%
TAP-87345_CLASSY1 | 1087 | *1086 |  | 06.05.05.02.29.01.00.00 | TAP-87345 | TAP-115325 | [TAP-87345_CLASSY1] ¦ [CLASSY] Stability issues fixing Sprint1 | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 56 | 56 | 56 | 67.2 | 0 | 100%
TAP-87345_CLASSY2 | 1088 | *1086 |  | 06.05.05.02.29.08.00.00 | TAP-87345 | TAP-113399 | [TAP-87345_CLASSY2] ¦ [CLASSY]Cleaning up test_central_indicator_manager | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 72 | 56 | 72 | 86.4 | 16 | 100%
TAP-87345_FRED | 1089 | *1086 |  | 06.05.05.02.29.10.00.00 | TAP-87345 | TAP-105710 | [TAP-87345_FRED] ¦ [Fred] Cleanup QoS in UDP library | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 80 | 56 | 80 | 96 | 24 | 100%
TAP-87345_STORMCHASERS2 | 1090 | *1086 |  | 06.05.05.02.29.13.00.00 | TAP-87345 | TAP-117303 | [TAP-87345_STORMCHASERS2] ¦ [V4.0][SC2] Move the motion_detection_tool code from eintests to ein_ng diagnostic | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 84 | 56 | 84 | 100.8 | 28 | 100%
TAP-85431 | 1091 | *5 |  | 06.05.05.02.30.00.00.00 |  | TAP-85431 | [TAP-85431] ¦ [V4.0][Cyber][CLASSY] Documentation update for new communication library | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-85431_STORMCHASERS1 | 1092 | *1091 |  | 06.05.05.02.30.01.00.00 | TAP-85431 | TAP-87314 | [TAP-85431_STORMCHASERS1] ¦ [SC1][V4.0] Release Unit tests verification checklists (SWI-65, SWI-370) | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-85431_STORMCHASERS2 | 1093 | *1091 |  | 06.05.05.02.30.02.00.00 | TAP-85431 | TAP-87477 | [TAP-85431_STORMCHASERS2] ¦ [SC2]V4.0 SFMEA Review in Polarion | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-85431_CASTLEBLACK | 1094 | *1091 |  | 06.05.05.02.30.04.00.00 | TAP-85431 | TAP-96211 | [TAP-85431_CASTLEBLACK] ¦ Detailed Communication Roadmap and Strategy beyond 4.0 | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 15 | 13 | 15 | 18 | 2 | 100%
TAP-106775 | 1095 | *9 |  | 06.05.05.02.31.00.00.00 |  | TAP-106775 | [TAP-106775] ¦ [V4.0][Cyber][CLASY] Documentation update for new communication library (PI14) | Feature | Done |  |  | Parent Task | User Stories | 49 | 49 | 1 hr | 1 hr | 0 | 100%
TAP-106775_CLASSY1 | 1096 | *1095 |  | 06.05.05.02.31.01.00.00 | TAP-106775 | TAP-114288 | [TAP-106775_CLASSY1] ¦ [V4.0] [CLASSY] Communication library subsystem SFMEA | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 49 | 49 | 49 | 58.8 | 0 | 100%
TAP-106775_CLASSY2 | 1097 | *1095 |  | 06.05.05.02.31.05.00.00 | TAP-106775 | TAP-107832 | [TAP-106775_CLASSY2] ¦ CLASSY2 CFMEA and SFMEA training | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 69 | 49 | 69 | 82.8 | 20 | 100%
TAP-106775_FRED | 1098 | *1095 |  | 06.05.05.02.31.09.00.00 | TAP-106775 | TAP-112394 | [TAP-106775_FRED] ¦ [Fred] Finalize UDP Session creation FMEA | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 80 | 49 | 80 | 96 | 31 | 100%
TAP-85792 | 1099 | *5 |  | 06.05.05.02.32.00.00.00 |  | TAP-85792 | [TAP-85792] ¦ [V4.0][Cyber] Secure UDP Completion and V&V | Feature | Done |  |  | Parent Task | User Stories | 71 | 71 | 1 hr | 1 hr | 0 | 100%
TAP-85792_CLASSY1 | 1100 | *1099 |  | 06.05.05.02.32.01.00.00 | TAP-85792 | TAP-103566 | [TAP-85792_CLASSY1] ¦ [CLASSY] Update Test Case EIN-TC_SW-2561 to correspond updated UDP comm lob implementation | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 71 | 71 | 71 | 85.2 | 0 | 100%
TAP-85792_CLASSY2 | 1101 | *1099 |  | 06.05.05.02.32.04.00.00 | TAP-85792 | TAP-96593 | [TAP-85792_CLASSY2] ¦ [SPIKE] Investigate CLASSY owned Tools required updates for secure UDP communication | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 78 | 71 | 78 | 93.6 | 7 | 100%
TAP-85792_FRED | 1102 | *1099 |  | 06.05.05.02.32.10.00.00 | TAP-85792 | TAP-96149 | [TAP-85792_FRED] ¦ [Fred] UDP authentication should cover CRC and sequence number in UDPMessage | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 101 | 71 | 101 | 121.2 | 30 | 100%
TAP-85792_HORIZON | 1103 | *1099 |  | 06.05.05.02.32.21.00.00 | TAP-85792 | TAP-111506 | [TAP-85792_HORIZON] ¦ [Horizon] Remove EIN-NOTCODE-480 (udp ping remnant) | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 131 | 71 | 131 | 157.2 | 60 | 100%
TAP-95824 | 1104 | *7 |  | 06.05.05.02.33.00.00.00 |  | TAP-95824 | [TAP-95824] ¦ [Cyber][V4.0] Refactor communication data corruption related requirements and tests | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-95824_SCRUMBLEDORES | 1105 | *1104 |  | 06.05.05.02.33.01.00.00 | TAP-95824 | TAP-95828 | [TAP-95824_SCRUMBLEDORES] ¦ [Scrumbledores][V4.0] MSC Data Corruption Checks - Refactor or archive and update corresponding FM, test document | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-95456 | 1106 | *7 |  | 06.05.05.02.34.00.00.00 |  | TAP-95456 | [TAP-95456] ¦ [Cyber][V4.0] Refactor communication data corruption related requirements and tests | Feature | Done |  |  | Parent Task | User Stories | 42 | 42 | 1 hr | 1 hr | 0 | 100%
TAP-95456_CLASSY1 | 1107 | *1106 |  | 06.05.05.02.34.01.00.00 | TAP-95456 | TAP-95590 | [TAP-95456_CLASSY1] ¦ Refactor EIN-SSR_COMM-4 to include not transmission of corrupted data | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 42 | 42 | 42 | 50.4 | 0 | 100%
TAP-95456_CLASSY2 | 1108 | *1106 |  | 06.05.05.02.34.06.00.00 | TAP-95456 | TAP-85511 | [TAP-95456_CLASSY2] ¦ [CLASSY] Re-implement DDS V&V test EIN-TC_SW-3739 (CYB-TC_SW-1483) for EIN-SSR_COMM-4 update | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 67 | 42 | 67 | 80.4 | 25 | 100%
TAP-95456_STORMCHASERS1 | 1109 | *1106 |  | 06.05.05.02.34.07.00.00 | TAP-95456 | TAP-95797 | [TAP-95456_STORMCHASERS1] ¦ Refactor or archive EIN-SSR_SCSW-718 and update corresponding FM, test document | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 67 | 42 | 67 | 80.4 | 25 | 100%
TAP-55467 | 1110 | *1 |  | 06.05.05.03.01.00.00.00 |  | TAP-55467 | [TAP-55467] ¦ [Cyber] SPIKE Investigate the use on FTP on the Hugo system | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-109370 | 1111 | *3 |  | 06.05.05.03.02.00.00.00 |  | TAP-109370 | [TAP-109370] ¦ [Cyber] Upgrade the wolfssh to 1.4.16 | Feature | Done |  |  | Parent Task | User Stories | 14 | 14 | 1 hr | 1 hr | 0 | 100%
TAP-109370_ATLAS | 1112 | *1111 |  | 06.05.05.03.02.01.00.00 | TAP-109370 | TAP-113959 | [TAP-109370_ATLAS] ¦ Maintenance Script for Upgrading Windows Wolfssh on Old Systems | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 14 | 14 | 14 | 16.8 | 0 | 100%
TAP-109370_EDISON | 1113 | *1111 |  | 06.05.05.03.02.06.00.00 | TAP-109370 | TAP-109565 | [TAP-109370_EDISON] ¦ Update to wolfssl 5.6.6 and wolfssh 1.4.16 for QNX/Linux/Windows | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 22 | 14 | 22 | 26.4 | 8 | 100%
TAP-58613 | 1114 | *1 |  | 06.05.05.04.01.00.00.00 |  | TAP-58613 | [TAP-58613] ¦ [Cyber] [SPIKE] Review acceptability of current password strategy for UPS and Network Switch Risk: R024 | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-58613_ATLAS | 1115 | *1114 |  | 06.05.05.04.01.01.00.00 | TAP-58613 | TAP-96597 | [TAP-58613_ATLAS] ¦ [Cyber][Platformers] [Enabler] UPS and Network Switch Password Storage Approach Investigation | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 10 | 10 | 10 | 12 | 0 | 100%
TAP-6961 | 1116 | *1165,1 |  | 06.05.06.01.00.00.00.00 |  | TAP-6961 | [TAP-6961] ¦ [Cyber] EMBSW - Instrument Authentication Infrastructure | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-6961_HORIZON | 1117 | *1116 |  | 06.05.06.01.01.00.00.00 | TAP-6961 | TAP-15594 | [TAP-6961_HORIZON] ¦ Finalize Instrument Authentication Architecture Plan | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-1306 | 1118 | *1165,1 |  | 06.05.06.02.00.00.00.00 |  | TAP-1306 | [TAP-1306] ¦ [Cyber] EMBSW - Instrument Identification Refactor | Feature | Done |  |  | Parent Task | User Stories | 36 | 36 | 1 hr | 1 hr | 0 | 100%
TAP-1306_HORIZON | 1119 | *1118 |  | 06.05.06.02.01.00.00.00 | TAP-1306 | TAP-12812 | [TAP-1306_HORIZON] ¦ Review one-wire bus search algorithm error handling | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 36 | 36 | 36 | 43.2 | 0 | 100%
TAP-34960 | 1120 | *1165,1 |  | 06.05.06.03.00.00.00.00 |  | TAP-34960 | [TAP-34960] ¦ [Cyber] Instrument Authentication Prototype and De-risking | Feature | Done |  |  | Parent Task | User Stories | 26 | 26 | 1 hr | 1 hr | 0 | 100%
TAP-34960_I2E | 1121 | *1120 |  | 06.05.06.03.01.00.00.00 | TAP-34960 | TAP-39659 | [TAP-34960_I2E] ¦ [1W-AuthRead][SPIKE]Debugging and Testing on hardware (2) | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 26 | 26 | 26 | 31.2 | 0 | 100%
TAP-34960_HORIZON | 1122 | *1120 |  | 06.05.06.03.02.00.00.00 | TAP-34960 | TAP-39658 | [TAP-34960_HORIZON] ¦ [1W-AuthRead][SPIKE]Debugging and Testing on hardware (1) | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 26 | 26 | 26 | 31.2 | 0 | 100%
TAP-25616 | 1123 | *1165,1 |  | 06.05.06.04.00.00.00.00 |  | TAP-25616 | [TAP-25616] ¦ [Cyber] Instrument Authentication Infrastructure Workshop | Feature | Done |  |  | Parent Task | User Stories | 19 | 19 | 1 hr | 1 hr | 0 | 100%
TAP-25616_I2E | 1124 | *1123 |  | 06.05.06.04.01.00.00.00 | TAP-25616 | TAP-47715 | [TAP-25616_I2E] ¦ Review Existing Instrument ID Software Architecture | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 19 | 19 | 19 | 22.8 | 0 | 100%
TAP-25616_ATLAS | 1125 | *1123 |  | 06.05.06.04.05.00.00.00 | TAP-25616 | TAP-49658 | [TAP-25616_ATLAS] ¦ [SPIKE] Participate in Instrument Authentication Workshop | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 23 | 19 | 23 | 27.6 | 4 | 100%
TAP-25616_BART | 1126 | *1123 |  | 06.05.06.04.06.00.00.00 | TAP-25616 | TAP-49518 | [TAP-25616_BART] ¦ [Bart] Instrument Authentication Infrastructure Workshop | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 23 | 19 | 23 | 27.6 | 4 | 100%
TAP-25616_HORIZON | 1127 | *1123 |  | 06.05.06.04.07.00.00.00 | TAP-25616 | TAP-39662 | [TAP-25616_HORIZON] ¦ Hold workshop for brainstorming infrastructure details (Joe) | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 23 | 19 | 23 | 27.6 | 4 | 100%
TAP-25616_CASTLEBLACK | 1128 | *1123 |  | 06.05.06.04.11.00.00.00 | TAP-25616 | TAP-37291 | [TAP-25616_CASTLEBLACK] ¦ [Architecture] Attend Instrument Authentication Infrastructure Workshop | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 28 | 19 | 28 | 33.6 | 9 | 100%
TAP-159 | 1129 | *1165,1 |  | 06.05.06.05.00.00.00.00 |  | TAP-159 | [TAP-159] ¦ [Cyber] Instrument Hardware Authentication Implementation | Feature | Done |  |  | Parent Task | User Stories | 37 | 37 | 1 hr | 1 hr | 0 | 100%
TAP-159_HORIZON | 1130 | *1129 |  | 06.05.06.05.01.00.00.00 | TAP-159 | TAP-62757 | [TAP-159_HORIZON] ¦ [Cyber] Review and address differences between RAS-1285 and embsw-instrument-authentication staging branches | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 37 | 37 | 37 | 44.4 | 0 | 100%
TAP-159_PROBABLYSTILLEMBED | 1131 | *1129 |  | 06.05.06.05.08.00.00.00 | TAP-159 | TAP-8090 | [TAP-159_PROBABLYSTILLEMBED] ¦ Technical Design Review | User Story | Done | Foundation - ProbablyStillEmbed | PROBABLYSTILLEMBED | Child Task | User Stories | 70 | 37 | 70 | 84 | 33 | 100%
TAP-55120 | 1132 | *1165,1 |  | 06.05.06.06.00.00.00.00 |  | TAP-55120 | [TAP-55120] ¦ [Cyber] Instrument Authentication Design Inputs | Feature | Done |  |  | Parent Task | User Stories | 4.5 | 4.5 | 1 hr | 1 hr | 0 | 100%
TAP-55120_HORIZON | 1133 | *1132 |  | 06.05.06.06.01.00.00.00 | TAP-55120 | TAP-57405 | [TAP-55120_HORIZON] ¦ [Cyber] Review Draft Instrument Authentication Requirements | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 4.5 | 4.5 | 4.5 | 5.4 | 0 | 100%
TAP-54936 | 1134 | *1165,1 |  | 06.05.06.07.00.00.00.00 |  | TAP-54936 | [TAP-54936] ¦ [Cyber] Instrument Authentication Hash Computation | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-54936_BART | 1135 | *1134 |  | 06.05.06.07.01.00.00.00 | TAP-54936 | TAP-56379 | [TAP-54936_BART] ¦ [cyber] Review PS-PL Interface document for Instrument Authentication | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-54936_HORIZON | 1136 | *1134 |  | 06.05.06.07.03.00.00.00 | TAP-54936 | TAP-68586 | [TAP-54936_HORIZON] ¦ Generate test vector for PL testing | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 6 | 4 | 6 | 7.2 | 2 | 100%
TAP-55141 | 1137 | *1165,1 |  | 06.05.06.08.00.00.00.00 |  | TAP-55141 | [TAP-55141] ¦ [Cyber] SPIKE Instrument Authentication Secret Storage and Build Integration | Feature | Done |  |  | Parent Task | User Stories | 25 | 25 | 1 hr | 1 hr | 0 | 100%
TAP-55141_EDISON | 1138 | *1137 |  | 06.05.06.08.01.00.00.00 | TAP-55141 | TAP-55096 | [TAP-55141_EDISON] ¦ [Spike] Instrument Authentication Secret Storage and Build Integration | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 25 | 25 | 25 | 30 | 0 | 100%
TAP-28790 | 1139 | *1165,1 |  | 06.05.06.09.00.00.00.00 |  | TAP-28790 | [TAP-28790] ¦ [Cyber] Instrument Memory Authentication Implementation | Feature | Done |  |  | Parent Task | User Stories | 49.5 | 49.5 | 1 hr | 1 hr | 0 | 100%
TAP-28790_HORIZON | 1140 | *1139 |  | 06.05.06.09.01.00.00.00 | TAP-28790 | TAP-63956 | [TAP-28790_HORIZON] ¦ Integration test for OneWireDriver authentication features | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 49.5 | 49.5 | 49.5 | 59.4 | 0 | 100%
TAP-58335 | 1141 | *1165,1 |  | 06.05.06.10.00.00.00.00 |  | TAP-58335 | [TAP-58335] ¦ [Cyber] Instrument Authentication Error Handling (Data Validation) | Feature | Done |  |  | Parent Task | User Stories | 33 | 33 | 1 hr | 1 hr | 0 | 100%
TAP-58335_I2E | 1142 | *1141 |  | 06.05.06.10.01.00.00.00 | TAP-58335 | TAP-72517 | [TAP-58335_I2E] ¦ Resolve merge conflicts for EIN FAILURE Updates | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 33 | 33 | 33 | 39.6 | 0 | 100%
TAP-58335_CLASSY1 | 1143 | *1141 |  | 06.05.06.10.05.00.00.00 | TAP-58335 | TAP-71212 | [TAP-58335_CLASSY1] ¦ Update Jama Export Tool to allow exports from Product Security Jama Project (Part 1) | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 54 | 33 | 54 | 64.8 | 21 | 100%
TAP-58335_FRED | 1144 | *1141 |  | 06.05.06.10.07.00.00.00 | TAP-58335 | TAP-16986 | [TAP-58335_FRED] ¦ Instrument Authentication EtherCAT Updates | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 55 | 33 | 55 | 66 | 22 | 100%
TAP-58335_HORIZON | 1145 | *1141 |  | 06.05.06.10.09.00.00.00 | TAP-58335 | TAP-67448 | [TAP-58335_HORIZON] ¦ [Horizon] Support authentication error handling work | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 58 | 33 | 58 | 69.6 | 25 | 100%
TAP-58439 | 1146 | *1,1165 |  | 06.05.06.11.00.00.00.00 |  | TAP-58439 | [TAP-58439] ¦ [Cyber] Instrument Authentication SHA256 PL Acceleration | Feature | Done |  |  | Parent Task | User Stories | 93 | 93 | 1 hr | 1 hr | 0 | 100%
TAP-58439_BART | 1147 | *1146 |  | 06.05.06.11.01.00.00.00 | TAP-58439 | TAP-96983 | [TAP-58439_BART] ¦ [Cyber] Test instrument authentication in IDU and RASA/CTF | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 93 | 93 | 93 | 111.6 | 0 | 100%
TAP-58439_HORIZON | 1148 | *1146 |  | 06.05.06.11.26.00.00.00 | TAP-58439 | TAP-75023 | [TAP-58439_HORIZON] ¦ [Sentinel][InstAuth][Horizon] EIN-SWI-168 Device Detection Timing Evaluation | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 149.5 | 93 | 149.5 | 179.4 | 56.5 | 100%
TAP-71057 | 1149 | *1,1165 |  | 06.05.06.12.00.00.00.00 |  | TAP-71057 | [TAP-71057] ¦ [Cyber] Merge staging/instrument-authentication into develop | Feature | Done |  |  | Parent Task | User Stories | 14.5 | 14.5 | 1 hr | 1 hr | 0 | 100%
TAP-71057_HORIZON | 1150 | *1149 |  | 06.05.06.12.01.00.00.00 | TAP-71057 | TAP-75014 | [TAP-71057_HORIZON] ¦ [Cyber] Device Protections Definition Kickoff | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 14.5 | 14.5 | 14.5 | 17.4 | 0 | 100%
TAP-69072 | 1151 | *1,1165 |  | 06.05.06.13.00.00.00.00 |  | TAP-69072 | [TAP-69072] ¦ [Cyber] Instrument Authentication Failure System Response | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-69072_I2E | 1152 | *1151 |  | 06.05.06.13.01.00.00.00 | TAP-69072 | TAP-81741 | [TAP-69072_I2E] ¦ [Cyber][v4.0] Test Case updates for System Failure Response | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-69072_CLASSY1 | 1153 | *1151 |  | 06.05.06.13.04.00.00.00 | TAP-69072 | TAP-76533 | [TAP-69072_CLASSY1] ¦ [Cyber][Classy] Jama Pull for Instrument Auth | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 23 | 15 | 23 | 27.6 | 8 | 100%
TAP-55121 | 1154 | *1,1165 |  | 06.05.06.14.00.00.00.00 |  | TAP-55121 | [TAP-55121] ¦ [Cyber] Instrument Authentication Penetration Testing Readiness | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-55121_HORIZON | 1155 | *1154 |  | 06.05.06.14.01.00.00.00 | TAP-55121 | TAP-75012 | [TAP-55121_HORIZON] ¦ [Sentinel] [InstAuth] Penetration Testing Data and Image Preparation | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-71054 | 1156 | *1,1165 |  | 06.05.06.15.00.00.00.00 |  | TAP-71054 | [TAP-71054] ¦ [Cyber] Instrument Authentication Error Handling (Data Authentication) | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-71054_HORIZON | 1157 | *1156 |  | 06.05.06.15.01.00.00.00 | TAP-71054 | TAP-86267 | [TAP-71054_HORIZON] ¦ [Sentinel] [InstAuth] Instrument Authentication Error sFMEA Review | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-58349 | 1158 | *1 |  | 06.05.06.16.00.00.00.00 |  | TAP-58349 | [TAP-58349] ¦ [Cyber] Instrument Authentication Legacy Device Support | Feature | Done |  |  | Parent Task | User Stories | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100%
TAP-58349_ATLAS | 1159 | *1158 |  | 06.05.06.16.01.00.00.00 | TAP-58349 | TAP-97012 | [TAP-58349_ATLAS] ¦ [Enabler] Create a PI showcase demo for the feature | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 27.5 | 27.5 | 27.5 | 33 | 0 | 100%
TAP-58349_HORIZON | 1160 | *1158 |  | 06.05.06.16.05.00.00.00 | TAP-58349 | TAP-97412 | [TAP-58349_HORIZON] ¦ Critical Design Review Preparation | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 37.5 | 27.5 | 37.5 | 45 | 10 | 100%
TAP-82020 | 1161 | *1 |  | 06.05.06.17.00.00.00.00 |  | TAP-82020 | [TAP-82020] ¦ [Cyber] Production Plan for Instrument Authentication | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-82020_BART | 1162 | *1161 |  | 06.05.06.17.01.00.00.00 | TAP-82020 | TAP-82048 | [TAP-82020_BART] ¦ Integration of Secret from CyberArk with PL builds | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-82020_HORIZON | 1163 | *1161 |  | 06.05.06.17.02.00.00.00 | TAP-82020 | TAP-82024 | [TAP-82020_HORIZON] ¦ [Spike] Transfer strategy for M secret to Maxim to Medtornic | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-82020_EDISON | 1164 | *1161 |  | 06.05.06.17.03.00.00.00 | TAP-82020 | TAP-82027 | [TAP-82020_EDISON] ¦ Integration of M-secret Decryption strategy with PL Build Plan | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-58647 | 1165 | *1166,1 | *1116,1118,1120,1123,1129,1132,1134,1137,1139,1141,1146,1149,1151,1154,1156 | 06.05.06.18.00.00.00.00 |  | TAP-58647 | [TAP-58647] ¦ [Cyber] Micro-Penetration Test by 3rd Party for Basic Instrument Authentication | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-58656 | 1166 | *3 | *1165 | 06.05.06.19.00.00.00.00 |  | TAP-58656 | [TAP-58656] ¦ [Cyber][Sentinel][Inst Auth] Implement Fixes for Findings in Micro Penetration Testing | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-58656_ATLAS | 1167 | *1166 |  | 06.05.06.19.01.00.00.00 | TAP-58656 | TAP-103810 | [TAP-58656_ATLAS] ¦ Delete M-Secret: Instrument Authentication Architecture Document Update | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-58656_HORIZON | 1168 | *1166 |  | 06.05.06.19.05.00.00.00 | TAP-58656 | TAP-103248 | [TAP-58656_HORIZON] ¦ Instrument Authentication Notcode Integration Test | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 19 | 13 | 19 | 22.8 | 6 | 100%
TAP-58337 | 1169 | *7 |  | 06.05.06.20.00.00.00.00 |  | TAP-58337 | [TAP-58337] ¦ [Cyber] Instrument Authentication V&V Testing | Feature | Done |  |  | Parent Task | User Stories | 11 | 11 | 1 hr | 1 hr | 0 | 100%
TAP-58337_HORIZON | 1170 | *1169 |  | 06.05.06.20.01.00.00.00 | TAP-58337 | TAP-92789 | [TAP-58337_HORIZON] ¦ Update EIN-TC_SW-3555 to include corruption fixes checks | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 11 | 11 | 11 | 13.2 | 0 | 100%
TAP-58350 | 1171 | *9 |  | 06.05.06.21.00.00.00.00 |  | TAP-58350 | [TAP-58350] ¦ [Cyber] Instrument Authentication Documents and Critical Design Review | Feature | Done |  |  | Parent Task | User Stories | 7.5 | 7.5 | 1 hr | 1 hr | 0 | 100%
TAP-58350_BART | 1172 | *1171 |  | 06.05.06.21.01.00.00.00 | TAP-58350 | TAP-105649 | [TAP-58350_BART] ¦ [Bart][InstAuth] Prepare Bart part for CDR | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 7.5 | 7.5 | 7.5 | 9 | 0 | 100%
TAP-58350_HORIZON | 1173 | *1171 |  | 06.05.06.21.02.00.00.00 | TAP-58350 | TAP-97415 | [TAP-58350_HORIZON] ¦ Release CDR Documentation and Meeting Minutes | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 7.5 | 7.5 | 7.5 | 9 | 0 | 100%
TAP-58350_EDISON | 1174 | *1171 |  | 06.05.06.21.07.00.00.00 | TAP-58350 | TAP-105650 | [TAP-58350_EDISON] ¦ [Edison][InstAuth] Prepare Edison part for CDR | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 12.5 | 7.5 | 12.5 | 15 | 5 | 100%
TAP-83346 | 1175 | *13 |  | 06.05.06.22.00.00.00.00 |  | TAP-83346 | [TAP-83346] ¦ [Cyber] Switch to Production Key Secrets | Feature | Accepted |  |  | Parent Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 0%
TAP-83346_EDISON | 1176 | *1175 |  | 06.05.06.22.01.00.00.00 | TAP-83346 | TAP-83347 | [TAP-83346_EDISON] ¦ Update bamboo plan to use Production Secret | User Story | In progress | Shared Services - Edison | EDISON | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-1758 | 1177 | *1 |  | 06.05.07.01.00.00.00.00 |  | TAP-1758 | [TAP-1758] ¦ [Cyber] Define and implement USB whitelisting policies across all nodes | Feature | Done |  |  | Parent Task | User Stories | 22 | 22 | 1 hr | 1 hr | 0 | 100%
TAP-1758_ATLAS | 1178 | *1177 |  | 06.05.07.01.01.00.00.00 | TAP-1758 | TAP-75634 | [TAP-1758_ATLAS] ¦ implement USB whitelisting policies on Windows | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 22 | 22 | 22 | 26.4 | 0 | 100%
TAP-12356 | 1179 | *3 |  | 06.05.07.02.00.00.00.00 |  | TAP-12356 | [TAP-12356] ¦ [Cyber] Update network switch configuration for cyber release | Feature | Done |  |  | Parent Task | User Stories | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-12356_ATLAS | 1180 | *1179 |  | 06.05.07.02.01.00.00.00 | TAP-12356 | TAP-103158 | [TAP-12356_ATLAS] ¦ Add unicast packet flooding disabling support | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-12356_BOOSTERS | 1181 | *1179 |  | 06.05.07.02.02.00.00.00 | TAP-12356 | TAP-96387 | [TAP-12356_BOOSTERS] ¦ [Boosters] [Spike] Update network switch configuration for cyber release | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-113853 | 1182 | *7 |  | 06.05.08.01.00.00.00.00 |  | TAP-113853 | [TAP-113853] ¦ [Cyber] Continued NPS work for Product Security Release (PI 14) | Feature | Done |  |  | Parent Task | User Stories | 32 | 32 | 1 hr | 1 hr | 0 | 100%
TAP-113853_ASTRANPSDEVELOPERS | 1183 | *1182 |  | 06.05.08.01.01.00.00.00 | TAP-113853 | TAP-105857 | [TAP-113853_ASTRANPSDEVELOPERS] ¦ [ESAT] SCDC Enable/Disable kiosk | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 32 | 32 | 32 | 38.4 | 0 | 100%
TAP-113853_TOOLSRULES | 1184 | *1182 |  | 06.05.08.01.08.00.00.00 | TAP-113853 | TAP-122696 | [TAP-113853_TOOLSRULES] ¦ ESAT v2: peripheral config updates were not being triggered by ESAT | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 50 | 32 | 50 | 60 | 18 | 100%
TAP-70569 | 1185 | *1 |  | 06.05.08.02.00.00.00.00 |  | TAP-70569 | [TAP-70569] ¦ [Cyber] Formalize use of WolfSSH in ESAT and Data Access | Feature | Done |  |  | Parent Task | User Stories | 32 | 32 | 1 hr | 1 hr | 0 | 100%
TAP-70569_ATLAS | 1186 | *1185 |  | 06.05.08.02.01.00.00.00 | TAP-70569 | TAP-97014 | [TAP-70569_ATLAS] ¦ [Enabler] Create a PI showcase demo for the feature | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 32 | 32 | 32 | 38.4 | 0 | 100%
TAP-70569_BOOSTERS | 1187 | *1185 |  | 06.05.08.02.05.00.00.00 | TAP-70569 | TAP-96476 | [TAP-70569_BOOSTERS] ¦ [Boosters] Deactivation fails with Malfunction | Issue | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 39 | 32 | 39 | 46.8 | 7 | 100%
TAP-70569_TOOLSRULES | 1188 | *1185 |  | 06.05.08.02.07.00.00.00 | TAP-70569 | TAP-70871 | [TAP-70569_TOOLSRULES] ¦ [Prod Security] Modify ESAT V2 to use WolfSSH instead of SSH Pt1 | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 47 | 32 | 47 | 56.4 | 15 | 100%
TAP-25610 | 1189 | *1 |  | 06.05.08.03.00.00.00.00 |  | TAP-25610 | [TAP-25610] ¦ [Cyber] Prepare ESAT-2 for Cybersecurity Release | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-25610_TOOLSRULES | 1190 | *1189 |  | 06.05.08.03.01.00.00.00 | TAP-25610 | TAP-29981 | [TAP-25610_TOOLSRULES] ¦ [ICG] Create installer for container based node.js esat | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-104060 | 1191 | *5 |  | 06.05.08.04.00.00.00.00 |  | TAP-104060 | [TAP-104060] ¦ [V2.1] [Cyber] Certificate Installation Usability Improvements For Contract Manufacturer | Feature | Done |  |  | Parent Task | User Stories | 58 | 58 | 1 hr | 1 hr | 0 | 100%
TAP-104060_ASTRANPSDEVELOPERS | 1192 | *1191 |  | 06.05.08.04.01.00.00.00 | TAP-104060 | TAP-104888 | [TAP-104060_ASTRANPSDEVELOPERS] ¦ ESAT v2 JPS Screening Tool does not install with v2 | Issue | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 58 | 58 | 58 | 69.6 | 0 | 100%
TAP-104060_PLATFORMERS | 1193 | *1191 |  | 06.05.08.04.02.00.00.00 | TAP-104060 | TAP-104077 | [TAP-104060_PLATFORMERS] ¦ [V2.1][Platformers] TB returns appropriate error codes | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 58 | 58 | 58 | 69.6 | 0 | 100%
TAP-104060_TOOLSRULES | 1194 | *1191 |  | 06.05.08.04.04.00.00.00 | TAP-104060 | TAP-102084 | [TAP-104060_TOOLSRULES] ¦ ESAT v2 - create separate launch scripts for debugging purposes | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 63 | 58 | 63 | 75.6 | 5 | 100%
TAP-104830 | 1195 | *5 |  | 06.05.08.05.00.00.00.00 |  | TAP-104830 | [TAP-104830] ¦ [Cyber] ESAT v2 - Migrating from v1 to v2 | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-104830_TOOLSRULES | 1196 | *1195 |  | 06.05.08.05.01.00.00.00 | TAP-104830 | TAP-104394 | [TAP-104830_TOOLSRULES] ¦ Provide Confluence instructions/Guidance for ESAT on Linux V2 | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-104832 | 1197 | *5 |  | 06.05.08.06.00.00.00.00 |  | TAP-104832 | [TAP-104832] ¦ [Cyber] ESAT v2 Continued Stabilization of ESAT v2 (PI13) | Feature | Done |  |  | Parent Task | User Stories | 144 | 144 | 1 hr | 1 hr | 0 | 100%
TAP-104832_ASTRANPSDEVELOPERS | 1198 | *1197 |  | 06.05.08.06.01.00.00.00 | TAP-104832 | TAP-100689 | [TAP-104832_ASTRANPSDEVELOPERS] ¦ Refactor JS ESAT : Replace implementation of sendFileFunc with websocket file streaming | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 144 | 144 | 144 | 172.8 | 0 | 100%
TAP-104832_ATLAS | 1199 | *1197 |  | 06.05.08.06.10.00.00.00 | TAP-104832 | TAP-108907 | [TAP-104832_ATLAS] ¦ v4 Isim deployment fails due to libcurl issue | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 183 | 144 | 183 | 219.6 | 39 | 100%
TAP-104832_TOOLSRULES | 1200 | *1197 |  | 06.05.08.06.11.00.00.00 | TAP-104832 | TAP-97558 | [TAP-104832_TOOLSRULES] ¦ ESAT v2 - Ensure that ESAT in v4 Develop successfully performs certificate installation | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 183 | 144 | 183 | 219.6 | 39 | 100%
TAP-83501 | 1201 | *17 |  | 06.05.08.07.00.00.00.00 |  | TAP-83501 | [TAP-83501] ¦ [v4.0] [Cyber] Update ESAT scripts to work with product security release | Feature | Done |  |  | Parent Task | User Stories | 71 | 71 | 1 hr | 1 hr | 0 | 100%
TAP-83501_ASTRANPSDEVELOPERS | 1202 | *1201 |  | 06.05.08.07.01.00.00.00 | TAP-83501 | TAP-95559 | [TAP-83501_ASTRANPSDEVELOPERS] ¦ [SPIKE] Observe the trajectory functionality both in standalone and full system | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 71 | 71 | 71 | 85.2 | 0 | 100%
TAP-83501_TOOLSRULES | 1203 | *1201 |  | 06.05.08.07.14.00.00.00 | TAP-83501 | TAP-91305 | [TAP-83501_TOOLSRULES] ¦ [Cyber] Ensure that websocket comm between worker and client is local only | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 135 | 71 | 135 | 162 | 64 | 100%
TAP-103080 | 1204 | *13 |  | 06.05.08.08.00.00.00.00 |  | TAP-103080 | [TAP-103080] ¦ [Cyber] ESAT v2, Support Field Service Use of CyberArk | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-103080_TOOLSRULES | 1205 | *1204 |  | 06.05.08.08.01.00.00.00 | TAP-103080 | TAP-109450 | [TAP-103080_TOOLSRULES] ¦ ESAT v2: CyberArk: Spike - decide on methodology for creation of passwords, barcodes and QR Codes | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-103080_BUILDERS | 1206 | *1204 |  | 06.05.08.08.03.00.00.00 | TAP-103080 | TAP-110862 | [TAP-103080_BUILDERS] ¦ switch info reader for serial number | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 20 | 15 | 20 | 24 | 5 | 100%
TAP-94851 | 1207 | *3 |  | 06.05.08.09.00.00.00.00 |  | TAP-94851 | [TAP-94851] ¦ [Cyber] Continued ESAT v2 support, PI 12 | Feature | Done |  |  | Parent Task | User Stories | 100 | 100 | 1 hr | 1 hr | 0 | 100%
TAP-94851_TOOLSRULES | 1208 | *1207 |  | 06.05.08.09.01.00.00.00 | TAP-94851 | TAP-99103 | [TAP-94851_TOOLSRULES] ¦ ESAT v2 - Installer file name should include the git hash code | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 100 | 100 | 100 | 120 | 0 | 100%
TAP-94851_EDISON | 1209 | *1207 |  | 06.05.08.09.32.00.00.00 | TAP-94851 | TAP-96518 | [TAP-94851_EDISON] ¦ Make Wolf SSH/SSL libraries position independent | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 193 | 100 | 193 | 231.6 | 93 | 100%
TAP-42212 | 1210 | *13 |  | 06.05.08.10.00.00.00.00 |  | TAP-42212 | [TAP-42212] ¦ [Cyber] Penetration test ESAT and its interfaces for the Cybersecurity Release | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-42213 | 1211 | *13 |  | 06.05.08.11.00.00.00.00 |  | TAP-42213 | [TAP-42213] ¦ [Cyber] Patch vulnerabilities discovered in penetration test report for cybersecurity ESAT solution | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-943 | 1212 | *1 |  | 06.05.09.01.01.00.00.00 |  | TAP-943 | [TAP-943] ¦ [Cyber] System Configuration Enforcement | Feature | Done |  |  | Parent Task | User Stories | 85 | 85 | 1 hr | 1 hr | 0 | 100%
TAP-943_PLATFORMERS | 1213 | *1212 |  | 06.05.09.01.01.01.00.00 | TAP-943 | TAP-12669 | [TAP-943_PLATFORMERS] ¦ Create golden configuration hashes | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 85 | 85 | 85 | 102 | 0 | 100%
TAP-12344 | 1214 | *1 |  | 06.05.09.01.02.00.00.00 |  | TAP-12344 | [TAP-12344] ¦ [KontronEOL] [Cyber] Finalize Configuration Enforcement on all nodes | Feature | Done |  |  | Parent Task | User Stories | 90 | 90 | 1 hr | 1 hr | 0 | 100%
TAP-12344_PLATFORMERS | 1215 | *1214 |  | 06.05.09.01.02.01.00.00 | TAP-12344 | TAP-12844 | [TAP-12344_PLATFORMERS] ¦ [Cyber][platformers][V&V][PM] CYB-TD_SW-81 (EIN-TD_SW-1745): PROCESS: System Monitor software build type check | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 90 | 90 | 90 | 108 | 0 | 100%
TAP-14178 | 1216 | *1 |  | 06.05.09.01.03.00.00.00 |  | TAP-14178 | [TAP-14178] ¦ [Cyber] Add non-clinical element to GUI software | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-14178_PIXELPOETS | 1217 | *1216 |  | 06.05.09.01.03.01.00.00 | TAP-14178 | TAP-74007 | [TAP-14178_PIXELPOETS] ¦ [CYBER][Positron] Common Pop-Up for ORTI | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-83682 | 1218 | *1 |  | 06.05.09.01.04.00.00.00 |  | TAP-83682 | [TAP-83682] ¦ [Cyber][v4.0] Finalize the non-clinical overlay for the GUI | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-83682_PIXELPOETS | 1219 | *1218 |  | 06.05.09.01.04.01.00.00 | TAP-83682 | TAP-104755 | [TAP-83682_PIXELPOETS] ¦ Create TC for non-clinical mode | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-12345 | 1220 | *5 |  | 06.05.09.01.05.00.00.00 |  | TAP-12345 | [TAP-12345] ¦ [V4.0][Cyber] Implement User Notification when running non clinical software | Feature | Done |  |  | Parent Task | User Stories | 63 | 63 | 1 hr | 1 hr | 0 | 100%
TAP-12345_ATLAS | 1221 | *1220 |  | 06.05.09.01.05.01.00.00 | TAP-12345 | TAP-84215 | [TAP-12345_ATLAS] ¦ [Cyber] When launching in Non-production boot provide a file that communicates that we launched in a non-production manner | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 63 | 63 | 63 | 75.6 | 0 | 100%
TAP-12345_CLASSY2 | 1222 | *1220 |  | 06.05.09.01.05.02.00.00 | TAP-12345 | TAP-104815 | [TAP-12345_CLASSY2] ¦ [4.0][CLASSY2]Alarms network doesnot support NOTECODEs higher than 1000 | Issue | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 63 | 63 | 63 | 75.6 | 0 | 100%
TAP-12345_PLATFORMERS | 1223 | *1220 |  | 06.05.09.01.05.03.00.00 | TAP-12345 | TAP-95758 | [TAP-12345_PLATFORMERS] ¦ [Cyber][Platformers][PM][V&V] Test Case EIN-TC_SW-3790 / CYB-TC_SW-3828 for TOWER Non Clinical Software and Mismatch Detection | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 63 | 63 | 63 | 75.6 | 0 | 100%
TAP-115130 | 1224 | *9 |  | 06.05.09.02.01.00.00.00 |  | TAP-115130 | [TAP-115130] ¦ [V4.0] [BRR] [Cyber] Platformers Documentation Updates | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-115130_PLATFORMERS | 1225 | *1224 |  | 06.05.09.02.01.01.00.00 | TAP-115130 | TAP-114918 | [TAP-115130_PLATFORMERS] ¦ [V4][Platformers] Certificate Manager FMEA catch up | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-113289 | 1226 | *5 |  | 06.05.09.02.02.00.00.00 |  | TAP-113289 | [TAP-113289] ¦ [V4.0][Cyber] Certificate Cleanup and Stability | Feature | Done |  |  | Parent Task | User Stories | 57 | 57 | 1 hr | 1 hr | 0 | 100%
TAP-113289_FRED | 1227 | *1226 |  | 06.05.09.02.02.01.00.00 | TAP-113289 | TAP-115911 | [TAP-113289_FRED] ¦ [V4][Fred] Ethercat handshake failure with wrong certificate | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 57 | 57 | 57 | 68.4 | 0 | 100%
TAP-113289_PLATFORMERS | 1228 | *1226 |  | 06.05.09.02.02.02.00.00 | TAP-113289 | TAP-97013 | [TAP-113289_PLATFORMERS] ¦ [Enabler] Create a PI showcase demo for the feature | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 57 | 57 | 57 | 68.4 | 0 | 100%
TAP-113289_TOOLSRULES | 1229 | *1226 |  | 06.05.09.02.02.11.00.00 | TAP-113289 | TAP-115146 | [TAP-113289_TOOLSRULES] ¦ [V4][ToolsRules]ESAT should be able to install certs to simulators | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 82 | 57 | 82 | 98.4 | 25 | 100%
TAP-113289_EDISON | 1230 | *1226 |  | 06.05.09.02.02.16.00.00 | TAP-113289 | TAP-114926 | [TAP-113289_EDISON] ¦ [V4][Edison] Add firefox to Linux docker container | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 102 | 57 | 102 | 122.4 | 45 | 100%
TAP-72510 | 1231 | *1 |  | 06.05.09.02.03.00.00.00 |  | TAP-72510 | [TAP-72510] ¦ [Cyber][V4] Certificate manager design changes | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-72510_PLATFORMERS | 1232 | *1231 |  | 06.05.09.02.03.01.00.00 | TAP-72510 | TAP-78726 | [TAP-72510_PLATFORMERS] ¦ [V3][Platformers] Certificate manager fails to create CSR if key already exists | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 15 | 15 | 15 | 18 | 0 | 100%
TAP-17759 | 1233 | *1 |  | 06.05.09.02.04.00.00.00 |  | TAP-17759 | [TAP-17759] ¦ [Cyber] Ethercat certificate manager | Feature | Done |  |  | Parent Task | User Stories | 28 | 28 | 1 hr | 1 hr | 0 | 100%
TAP-17759_PLATFORMERS | 1234 | *1233 |  | 06.05.09.02.04.01.00.00 | TAP-17759 | TAP-92871 | [TAP-17759_PLATFORMERS] ¦ [Cyber][Platformers][CertM][V&V] EtherCAT-CertM: EtherCAT Certificate Manager Test Approach Planning | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 28 | 28 | 28 | 33.6 | 0 | 100%
TAP-12346 | 1235 | *3 |  | 06.05.09.02.05.00.00.00 |  | TAP-12346 | [TAP-12346] ¦ [Cyber] Implement certificate expiration notifications | Feature | Done |  |  | Parent Task | User Stories | 26 | 26 | 1 hr | 1 hr | 0 | 100%
TAP-12346_PLATFORMERS | 1236 | *1235 |  | 06.05.09.02.05.01.00.00 | TAP-12346 | TAP-95757 | [TAP-12346_PLATFORMERS] ¦ [Cyber][Platformers][PM][V&V] Create notification receiver testability for certificate expiration/expiring notifications | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 26 | 26 | 26 | 31.2 | 0 | 100%
TAP-56916 | 1237 | *3 |  | 06.05.09.02.06.00.00.00 |  | TAP-56916 | [TAP-56916] ¦ [V4] [Cyber] Support for unified Medtronic hugo_id certificate | Feature | Done |  |  | Parent Task | User Stories | 76 | 76 | 1 hr | 1 hr | 0 | 100%
TAP-56916_ATLAS | 1238 | *1237 |  | 06.05.09.02.06.01.00.00 | TAP-56916 | TAP-102112 | [TAP-56916_ATLAS] ¦ [Spike] WolfSSL support for SAN field in CSR | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 76 | 76 | 76 | 91.2 | 0 | 100%
TAP-56916_CLASSY1 | 1239 | *1237 |  | 06.05.09.02.06.05.00.00 | TAP-56916 | TAP-105543 | [TAP-56916_CLASSY1] ¦ [V4] Use hugo_id certificate for Secure DDS | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 80 | 76 | 80 | 96 | 4 | 100%
TAP-56916_CLASSY2 | 1240 | *1237 |  | 06.05.09.02.06.06.00.00 | TAP-56916 | TAP-105542 | [TAP-56916_CLASSY2] ¦ [V4] Use hugo_id certificate for Secure UDP | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 80 | 76 | 80 | 96 | 4 | 100%
TAP-56916_FRED | 1241 | *1237 |  | 06.05.09.02.06.07.00.00 | TAP-56916 | TAP-105545 | [TAP-56916_FRED] ¦ [V4] Use hugo_id certificate for Secure Ethercat | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 80 | 76 | 80 | 96 | 4 | 100%
TAP-56916_PLATFORMERS | 1242 | *1237 |  | 06.05.09.02.06.11.00.00 | TAP-56916 | TAP-96977 | [TAP-56916_PLATFORMERS] ¦ [V4][Platformers] Add hugo_id certificate to all nodes | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 87 | 76 | 87 | 104.4 | 11 | 100%
TAP-56916_TOOLSRULES | 1243 | *1237 |  | 06.05.09.02.06.26.00.00 | TAP-56916 | TAP-112339 | [TAP-56916_TOOLSRULES] ¦ [V4] Align ESAT with Certificate changes | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 125 | 76 | 125 | 150 | 49 | 100%
TAP-168 | 1244 | *1 |  | 06.05.09.03.01.00.00.00 |  | TAP-168 | [TAP-168] ¦ [Cyber] Deployment manager Interface Updates | Feature | Done |  |  | Parent Task | User Stories | 78 | 78 | 1 hr | 1 hr | 0 | 100%
TAP-168_PLATFORMERS | 1245 | *1244 |  | 06.05.09.03.01.01.00.00 | TAP-168 | TAP-1960 | [TAP-168_PLATFORMERS] ¦ Investigate UPS Firmware Downgrade | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 78 | 78 | 78 | 93.6 | 0 | 100%
TAP-168_TOOLSRULES | 1246 | *1244 |  | 06.05.09.03.01.04.00.00 | TAP-168 | TAP-3055 | [TAP-168_TOOLSRULES] ¦ Unit Tests for deployment updates | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 78 | 78 | 78 | 93.6 | 0 | 100%
TAP-8250 | 1247 | *1 |  | 06.05.09.03.02.00.00.00 |  | TAP-8250 | [TAP-8250] ¦ [KontronEOL][Cyber][DM] Peripheral deployment support | Feature | Done |  |  | Parent Task | User Stories | 184 | 184 | 1 hr | 1 hr | 0 | 100%
TAP-8250_PLATFORMERS | 1248 | *1247 |  | 06.05.09.03.02.01.00.00 | TAP-8250 | TAP-13590 | [TAP-8250_PLATFORMERS] ¦ [V&V][DM] Adjust DM tests to changes from TAP-11322 | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 184 | 184 | 184 | 220.8 | 0 | 100%
TAP-1753 | 1249 | *1 |  | 06.05.09.03.03.00.00.00 |  | TAP-1753 | [TAP-1753] ¦ [Cyber] Define strategy and implement secure deployment of packages | Feature | Done |  |  | Parent Task | User Stories | 22 | 22 | 1 hr | 1 hr | 0 | 100%
TAP-1753_FRED | 1250 | *1249 |  | 06.05.09.03.03.01.00.00 | TAP-1753 | TAP-367 | [TAP-1753_FRED] ¦ Joint Sec Verify deployment packages | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 22 | 22 | 22 | 26.4 | 0 | 100%
TAP-1753_PLATFORMERS | 1251 | *1249 |  | 06.05.09.03.03.02.00.00 | TAP-1753 | TAP-67833 | [TAP-1753_PLATFORMERS] ¦ [Cyber][Platformers][V&V] Requirement Analysis - Product Security Deployment SSRs | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 22 | 22 | 22 | 26.4 | 0 | 100%
TAP-1753_EDISON | 1252 | *1249 |  | 06.05.09.03.03.07.00.00 | TAP-1753 | TAP-8247 | [TAP-1753_EDISON] ¦ Build server support for secure deployment | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 38 | 22 | 38 | 45.6 | 16 | 100%
TAP-8252 | 1253 | *3 |  | 06.05.09.03.04.00.00.00 |  | TAP-8252 | [TAP-8252] ¦ [Cyber] Support for peripheral deployment | Feature | Done |  |  | Parent Task | User Stories | 107 | 107 | 1 hr | 1 hr | 0 | 100%
TAP-8252_BOOSTERS | 1254 | *1253 |  | 06.05.09.03.04.01.00.00 | TAP-8252 | TAP-96386 | [TAP-8252_BOOSTERS] ¦ [Boosters] [Spike] Investigate deployment manager subsystem | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 107 | 107 | 107 | 128.4 | 0 | 100%
TAP-8252_PLATFORMERS | 1255 | *1253 |  | 06.05.09.03.04.08.00.00 | TAP-8252 | TAP-98794 | [TAP-8252_PLATFORMERS] ¦ [v4][DM][Platformers] Align DM peripherals with latest version of inogeni_control tool | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 140 | 107 | 140 | 168 | 33 | 100%
TAP-8252_TOOLSRULES | 1256 | *1253 |  | 06.05.09.03.04.13.00.00 | TAP-8252 | TAP-61947 | [TAP-8252_TOOLSRULES] ¦ [ICG] System State Tab Updates to Display Peripherals | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 154 | 107 | 154 | 184.8 | 47 | 100%
TAP-42170 | 1257 | *3 |  | 06.05.09.03.05.00.00.00 |  | TAP-42170 | [TAP-42170] ¦ [V4.0][Cyber] Secure Deployment | Feature | Done |  |  | Parent Task | User Stories | 111.5 | 111.5 | 1 hr | 1 hr | 0 | 100%
TAP-42170_ASTRANPSDEVELOPERS | 1258 | *1257 |  | 06.05.09.03.05.01.00.00 | TAP-42170 | TAP-53510 | [TAP-42170_ASTRANPSDEVELOPERS] ¦ [Cyber] ESAT V1 to send sig files to nodes instead of checksum files | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 111.5 | 111.5 | 111.5 | 133.8 | 0 | 100%
TAP-42170_ATLAS | 1259 | *1257 |  | 06.05.09.03.05.03.00.00 | TAP-42170 | TAP-103531 | [TAP-42170_ATLAS] ¦ Update boiler plate code in EventDispatcher.cpp | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 119.5 | 111.5 | 119.5 | 143.4 | 8 | 100%
TAP-42170_PLATFORMERS | 1260 | *1257 |  | 06.05.09.03.05.05.00.00 | TAP-42170 | TAP-62368 | [TAP-42170_PLATFORMERS] ¦ [Cyber][Platformers][DM][V&V] Test Enhancement: Update DM HIL EIN-TD_SW-1258/EIN-TC_SW-1463 to verify secure deployment | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 121.5 | 111.5 | 121.5 | 145.8 | 10 | 100%
TAP-42170_EDISON | 1261 | *1257 |  | 06.05.09.03.05.23.00.00 | TAP-42170 | TAP-96660 | [TAP-42170_EDISON] ¦ Generate sig file for engineering build artifacts | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 202.5 | 111.5 | 202.5 | 243 | 91 | 100%
TAP-59531 | 1262 | *3 |  | 06.05.09.03.06.00.00.00 |  | TAP-59531 | [TAP-59531] ¦ [Cyber] Deployment Support for QNX arm | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-108253 | 1263 | *5 |  | 06.05.09.03.07.00.00.00 |  | TAP-108253 | [TAP-108253] ¦ [Cyber] Release Build Testing with Engineering Keys | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-108253_ATLAS | 1264 | *1263 |  | 06.05.09.03.07.01.00.00 | TAP-108253 | TAP-115958 | [TAP-108253_ATLAS] ¦ [Enabler] Create modified release image for Windows to support Release testing | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-68 | 1265 | *1 |  | 06.05.09.04.01.00.00.00 |  | TAP-68 | [TAP-68] ¦ [KontronEOL] [ICG] [Cyber] v2 / QNX 7.1 Build Environment Support - Part 2 | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-68_EDISON | 1266 | *1265 |  | 06.05.09.04.01.01.00.00 | TAP-68 | TAP-2370 | [TAP-68_EDISON] ¦ Create Build plans [ARM, Windows, Deployment packages] for EIN NG | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-2578 | 1267 | *1 |  | 06.05.09.04.02.00.00.00 |  | TAP-2578 | [TAP-2578] ¦ [ICG] [Cyber] Signing system for Einstein Phase 1 | Feature | Done |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-8581 | 1268 | *1 |  | 06.05.09.04.03.00.00.00 |  | TAP-8581 | [TAP-8581] ¦ [ICG] [Cyber] Certificate Management (UEFI) and Secure Boot Detection | Feature | Done |  |  | Parent Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-8581_ATLAS | 1269 | *1268 |  | 06.05.09.04.03.01.00.00 | TAP-8581 | TAP-16975 | [TAP-8581_ATLAS] ¦ Prototype turning on UEFI secure boot using remote upgrade | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 31 | 31 | 31 | 37.2 | 0 | 100%
TAP-8581_EDISON | 1270 | *1268 |  | 06.05.09.04.03.08.00.00 | TAP-8581 | TAP-8571 | [TAP-8581_EDISON] ¦ Prototyping Signing Server for signing EFI | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 53 | 31 | 53 | 63.6 | 22 | 100%
TAP-20257 | 1271 | *1 |  | 06.05.09.04.04.00.00.00 |  | TAP-20257 | [TAP-20257] ¦ [Cyber] Security enhancement for binary production and CI infrastructure | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-20257_ATLAS | 1272 | *1271 |  | 06.05.09.04.04.01.00.00 | TAP-20257 | TAP-17816 | [TAP-20257_ATLAS] ¦ Binary security analysis for Einstein product | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-55053 | 1273 | *1 |  | 06.05.09.04.05.00.00.00 |  | TAP-55053 | [TAP-55053] ¦ [Cyber] SPIKE Investigate and Detail the Product Security Impacts to Test and Resolutions Risk: R019 - Foundation | Feature | Done |  |  | Parent Task | User Stories | 43 | 43 | 1 hr | 1 hr | 0 | 100%
TAP-55053_ATLAS | 1274 | *1273 |  | 06.05.09.04.05.01.00.00 | TAP-55053 | TAP-75411 | [TAP-55053_ATLAS] ¦ [Spike][Atlas][V&V] Identify tests that need to be updated to WolfSSH | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 43 | 43 | 43 | 51.6 | 0 | 100%
TAP-55053_FRED | 1275 | *1273 |  | 06.05.09.04.05.06.00.00 | TAP-55053 | TAP-71823 | [TAP-55053_FRED] ¦ [Cyber][SPIKE] Investigate and Estimate effort to update ssh/scp/sftp usage in tests/testabilityChanges and RASA_Tools | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 51 | 43 | 51 | 61.2 | 8 | 100%
TAP-55053_HORIZON | 1276 | *1273 |  | 06.05.09.04.05.07.00.00 | TAP-55053 | TAP-80386 | [TAP-55053_HORIZON] ¦ [Spike][Horizon][V&V] Identify tests that need to be updated to WolfSSH | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 51 | 43 | 51 | 61.2 | 8 | 100%
TAP-55053_PLATFORMERS | 1277 | *1273 |  | 06.05.09.04.05.08.00.00 | TAP-55053 | TAP-70783 | [TAP-55053_PLATFORMERS] ¦ [Cyber][Platformers][SPIKE] CM/DM/PM/UPS/NTWK/PERSTG/CertM effort estimation for updating ssh usage | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 51 | 43 | 51 | 61.2 | 8 | 100%
TAP-55053_COSSACKS | 1278 | *1273 |  | 06.05.09.04.05.11.00.00 | TAP-55053 | TAP-78765 | [TAP-55053_COSSACKS] ¦ [CI] Deploy LowerB system with V4 | User Story | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 61 | 43 | 61 | 73.2 | 18 | 100%
TAP-55053_TRIPLETEA | 1279 | *1273 |  | 06.05.09.04.05.14.00.00 | TAP-55053 | TAP-70774 | [TAP-55053_TRIPLETEA] ¦ [Cyber][TripleTea] Chico and eintestframwork effort estimation for updating ssh usage | User Story | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 68 | 43 | 68 | 81.6 | 25 | 100%
TAP-71880 | 1280 | *1 |  | 06.05.09.04.06.00.00.00 |  | TAP-71880 | [TAP-71880] ¦ [Cyber][SPIKE] Investigate and Detail the SSH update in SW V&V - Instrumentation | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-71880_I2E | 1281 | *1280 |  | 06.05.09.04.06.01.00.00 | TAP-71880 | TAP-76043 | [TAP-71880_I2E] ¦ [I2E][SPIKE][Cyber] Investigate V&V tests impacted by SSH updates | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-71880_JACOBIANS | 1282 | *1280 |  | 06.05.09.04.06.03.00.00 | TAP-71880 | TAP-74449 | [TAP-71880_JACOBIANS] ¦ [Jacobians] Investigate Tests for SSH | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 17 | 16 | 17 | 20.4 | 1 | 100%
TAP-71880_ORGANELLES | 1283 | *1280 |  | 06.05.09.04.06.05.00.00 | TAP-71880 | TAP-75379 | [TAP-71880_ORGANELLES] ¦ [Reflect][V&V] Identify iSim tests that need to be updated to use WolfSSH | User Story | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 20 | 16 | 20 | 24 | 4 | 100%
TAP-71880_SCRUMBLEDORES | 1284 | *1280 |  | 06.05.09.04.06.07.00.00 | TAP-71880 | TAP-76428 | [TAP-71880_SCRUMBLEDORES] ¦ [SPIKE][Scrumbledores] Investigate and Detail the SSH update in SW V&V | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 23 | 16 | 23 | 27.6 | 7 | 100%
TAP-53454 | 1285 | *1 |  | 06.05.09.04.07.00.00.00 |  | TAP-53454 | [TAP-53454] ¦ [Cyber] Centralize engineering key for Windows/Zynq | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-53454_ATLAS | 1286 | *1285 |  | 06.05.09.04.07.01.00.00 | TAP-53454 | TAP-53455 | [TAP-53454_ATLAS] ¦ Use artifactory engineering key for Zynq | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-53456 | 1287 | *3 |  | 06.05.09.04.08.00.00.00 |  | TAP-53456 | [TAP-53456] ¦ [Cyber] Production signing infrastructure setup | Feature | Done |  |  | Parent Task | User Stories | 37 | 37 | 1 hr | 1 hr | 0 | 100%
TAP-53456_ATLAS | 1288 | *1287 |  | 06.05.09.04.08.01.00.00 | TAP-53456 | TAP-112655 | [TAP-53456_ATLAS] ¦ Remove the usage of EC_*NON_PROD.PEM from build process | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 37 | 37 | 37 | 44.4 | 0 | 100%
TAP-53456_EDISON | 1289 | *1287 |  | 06.05.09.04.08.05.00.00 | TAP-53456 | TAP-53457 | [TAP-53456_EDISON] ¦ Build API for Einstein Windows/Yocto/Zynq app package/image signing | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 47 | 37 | 47 | 56.4 | 10 | 100%
TAP-96136 | 1290 | *3 |  | 06.05.09.04.09.00.00.00 |  | TAP-96136 | [TAP-96136] ¦ [Cyber][IDP][V4.0] Build Infrastructure Signing | Feature | Done |  |  | Parent Task | User Stories | 22 | 22 | 1 hr | 1 hr | 0 | 100%
TAP-96136_ATLAS | 1291 | *1290 |  | 06.05.09.04.09.01.00.00 | TAP-96136 | TAP-97199 | [TAP-96136_ATLAS] ¦ [SPIKE] Support DevOps on building the signing infrastructure | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 22 | 22 | 22 | 26.4 | 0 | 100%
TAP-96136_EDISON | 1292 | *1290 |  | 06.05.09.04.09.02.00.00 | TAP-96136 | TAP-96138 | [TAP-96136_EDISON] ¦ document where different files are signed in bamboo for ein_ng repo | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 22 | 22 | 22 | 26.4 | 0 | 100%
TAP-28462 | 1293 | *5 |  | 06.05.09.04.10.00.00.00 |  | TAP-28462 | [TAP-28462] ¦ [Cyber] Provide Production Signing | Feature | Done |  |  | Parent Task | User Stories | 80 | 80 | 1 hr | 1 hr | 0 | 100%
TAP-28462_ATLAS | 1294 | *1293 |  | 06.05.09.04.10.01.00.00 | TAP-28462 | TAP-89470 | [TAP-28462_ATLAS] ¦ [SPIKE] Review and document codesigning APIs | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 80 | 80 | 80 | 96 | 0 | 100%
TAP-28462_EDISON | 1295 | *1293 |  | 06.05.09.04.10.19.00.00 | TAP-28462 | TAP-117465 | [TAP-28462_EDISON] ¦ Fix qnx x86 bsp production sign logic | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 141 | 80 | 141 | 169.2 | 61 | 100%
TAP-84668 | 1296 | *13 |  | 06.05.09.04.11.00.00.00 |  | TAP-84668 | [TAP-84668] ¦ [Cyber] Support for Product variants for Project Sentinel | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-84668_EDISON | 1297 | *1296 |  | 06.05.09.04.11.01.00.00 | TAP-84668 | TAP-90539 | [TAP-84668_EDISON] ¦ Parallelize image creation and packaging for QNX x86 | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-83453 | 1298 | *1 |  | 06.05.10.01.00.00.00.00 |  | TAP-83453 | [TAP-83453] ¦ [Cyber] Allow front port network connection in Operable state | Feature | Done |  |  | Parent Task | User Stories | 21 | 21 | 1 hr | 1 hr | 0 | 100%
TAP-83453_ASTRANPSDEVELOPERS | 1299 | *1298 |  | 06.05.10.01.01.00.00.00 | TAP-83453 | TAP-96963 | [TAP-83453_ASTRANPSDEVELOPERS] ¦ Integration of System Monitor changes with ESAT | User Story | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 21 | 21 | 21 | 25.2 | 0 | 100%
TAP-83453_ATLAS | 1300 | *1298 |  | 06.05.10.01.03.00.00.00 | TAP-83453 | TAP-96966 | [TAP-83453_ATLAS] ¦ [Enabler] Requirement clarification and update | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 29 | 21 | 29 | 34.8 | 8 | 100%
TAP-84353 | 1301 | *1 |  | 06.05.10.02.00.00.00.00 |  | TAP-84353 | [TAP-84353] ¦ [Cyber] BSP armv7 updates to support Manufacturing/Field Service | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-84353_ATLAS | 1302 | *1301 |  | 06.05.10.02.01.00.00.00 | TAP-84353 | TAP-97015 | [TAP-84353_ATLAS] ¦ [Enabler] Create a PI showcase demo for the feature | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-84354 | 1303 | *3 |  | 06.05.10.03.00.00.00.00 |  | TAP-84354 | [TAP-84354] ¦ [Cyber] Windows BSP updates to support Manufacturing | Feature | Done |  |  | Parent Task | User Stories | 16.1 | 16.1 | 1 hr | 1 hr | 0 | 100%
TAP-84354_ATLAS | 1304 | *1303 |  | 06.05.10.03.01.00.00.00 | TAP-84354 | TAP-97054 | [TAP-84354_ATLAS] ¦ [Spike] (Windows) Move All Configuration Files to E:\eisntein\config From Elsewhere in the System | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 16.1 | 16.1 | 16.1 | 19.32 | 0 | 100%
TAP-84352 | 1305 | *3 |  | 06.05.10.04.00.00.00.00 |  | TAP-84352 | [TAP-84352] ¦ [Cyber] Certificate Bootstrap mode | Feature | Done |  |  | Parent Task | User Stories | 43 | 43 | 1 hr | 1 hr | 0 | 100%
TAP-84352_ATLAS | 1306 | *1305 |  | 06.05.10.04.01.00.00.00 | TAP-84352 | TAP-113294 | [TAP-84352_ATLAS] ¦ [V4] Update Windows firewall configuration on existing systems | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 43 | 43 | 43 | 51.6 | 0 | 100%
TAP-84352_CLASSY1 | 1307 | *1305 |  | 06.05.10.04.03.00.00.00 | TAP-84352 | TAP-111052 | [TAP-84352_CLASSY1] ¦ Communication with insecure domain usage do not work with between QNX and Windows node | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 43 | 43 | 43 | 51.6 | 0 | 100%
TAP-84352_PLATFORMERS | 1308 | *1305 |  | 06.05.10.04.04.00.00.00 | TAP-84352 | TAP-103629 | [TAP-84352_PLATFORMERS] ¦ [V4][Platformers] Create sequence diagrams | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 43 | 43 | 43 | 51.6 | 0 | 100%
TAP-84351 | 1309 | *3 |  | 06.05.10.05.00.00.00.00 |  | TAP-84351 | [TAP-84351] ¦ [Cyber] BSP x86 updates to support Manufacturing/Field Support | Feature | Done |  |  | Parent Task | User Stories | 41 | 41 | 1 hr | 1 hr | 0 | 100%
TAP-84351_ATLAS | 1310 | *1309 |  | 06.05.10.05.01.00.00.00 | TAP-84351 | TAP-97373 | [TAP-84351_ATLAS] ¦ Define the use case/functionality of restrictedshelluser | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 41 | 41 | 41 | 49.2 | 0 | 100%
TAP-84384 | 1311 | *5 |  | 06.05.10.06.00.00.00.00 |  | TAP-84384 | [TAP-84384] ¦ [Cyber] FRU replacement application for updating ORTI switch and ups configuration | Feature | Done |  |  | Parent Task | User Stories | 77.6 | 77.6 | 1 hr | 1 hr | 0 | 100%
TAP-84384_ATLAS | 1312 | *1311 |  | 06.05.10.06.01.00.00.00 | TAP-84384 | TAP-97031 | [TAP-84384_ATLAS] ¦ [ENABLER] Integration test for the FRU replacement application Tool | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 77.6 | 77.6 | 77.6 | 93.12 | 0 | 100%
TAP-84357 | 1313 | *13 |  | 06.05.10.07.00.00.00.00 |  | TAP-84357 | [TAP-84357] ¦ [Cyber] Tool for installing certificates on FRU/ HLA Programming | Feature | Accepted |  |  | Parent Task | User Stories | 12 | 0 | 1 hr | 1 hr | 12 | 0%
TAP-84357_ATLAS | 1314 | *1313 |  | 06.05.10.07.01.00.00.00 | TAP-84357 | TAP-84609 | [TAP-84357_ATLAS] ¦ [Spike] Discuss with ESAT and Certificate Manager team how to support standalone setups for certificate management at Manufacturing | User Story | Open | Foundation - Atlas | ATLAS | Child Task | User Stories | 12 | 0 | 12 | 14.4 | 12 | 0%
TAP-84357_PLATFORMERS | 1315 | *1313 |  | 06.05.10.07.03.00.00.00 | TAP-84357 | TAP-84612 | [TAP-84357_PLATFORMERS] ¦ [Platformers] Teneo bridge updates to support standalone setups on Programming Stations | User Story | Open | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 14 | 0 | 14 | 16.8 | 14 | 0%
TAP-82906 | 1316 | *13 |  | 06.05.10.08.00.00.00.00 |  | TAP-82906 | [TAP-82906] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 2 (Development and Testing) - PI13 | Feature | Done |  |  | Parent Task | User Stories | 27.5 | 27.5 | 1 hr | 1 hr | 0 | 100%
TAP-82906_BUILDERS | 1317 | *1316 |  | 06.05.10.08.01.00.00.00 | TAP-82906 | TAP-110658 | [TAP-82906_BUILDERS] ¦ [Spike] Investigate Combined Secondary Primary Deployment through ESAT | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 27.5 | 27.5 | 27.5 | 33 | 0 | 100%
TAP-84376 | 1318 | *13 | *3 | 06.05.10.09.00.00.00.00 |  | TAP-84376 | [TAP-84376] ¦ [Cyber] Dry Run of FRU replacements for US launch | Feature | Done |  |  | Parent Task | User Stories | 33 | 33 | 1 hr | 1 hr | 0 | 100%
TAP-84376_BUILDERS | 1319 | *1318 |  | 06.05.10.09.01.00.00.00 | TAP-84376 | TAP-85024 | [TAP-84376_BUILDERS] ¦ Dry run of IDU replacement | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 33 | 33 | 33 | 39.6 | 0 | 100%
TAP-84366 | 1320 | *13 |  | 06.05.10.10.00.00.00.00 |  | TAP-84366 | [TAP-84366] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 1(Initial Development and Investigation) | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-84366_BUILDERS | 1321 | *1320 |  | 06.05.10.10.01.00.00.00 | TAP-84366 | TAP-84618 | [TAP-84366_BUILDERS] ¦ Update scripts to fetch the current system configuration before programming | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 10 | 10 | 10 | 12 | 0 | 100%
TAP-84366_EDISON | 1322 | *1320 |  | 06.05.10.10.08.00.00.00 | TAP-84366 | TAP-95991 | [TAP-84366_EDISON] ¦ Create bamboo plan to support v2 to v4 migration | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 16 | 10 | 16 | 19.2 | 6 | 100%
TAP-103615 | 1323 | *13 |  | 06.05.10.11.00.00.00.00 |  | TAP-103615 | [TAP-103615] ¦ [Cyber] Briefcase Method Prototyping | Feature | Done |  |  | Parent Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-103615_BUILDERS | 1324 | *1323 |  | 06.05.10.11.01.00.00.00 | TAP-103615 | TAP-110663 | [TAP-103615_BUILDERS] ¦ Test Z-Slide Primary Deployment for Briefcase | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 17 | 17 | 17 | 20.4 | 0 | 100%
TAP-105519 | 1325 | *13 | *3 | 06.05.10.12.00.00.00.00 |  | TAP-105519 | [TAP-105519] ¦ [Cyber] Field Upgrade Support for Project Sentinel Phase 2 (Development and Testing) - PI14 | Feature | Done |  |  | Parent Task | User Stories | 56.5 | 56.5 | 1 hr | 1 hr | 0 | 100%
TAP-105519_ATLAS | 1326 | *1325 |  | 06.05.10.12.01.00.00.00 | TAP-105519 | TAP-84485 | [TAP-105519_ATLAS] ¦ Add peripheral version check tool to bsp to support debugging | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 56.5 | 56.5 | 56.5 | 67.8 | 0 | 100%
TAP-105519_BUILDERS | 1327 | *1325 |  | 06.05.10.12.02.00.00.00 | TAP-105519 | TAP-114907 | [TAP-105519_BUILDERS] ¦ Create Work Instruction for BIOS Updates | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 56.5 | 56.5 | 56.5 | 67.8 | 0 | 100%
TAP-104008 | 1328 | *19 |  | 06.05.10.13.00.00.00.00 |  | TAP-104008 | [TAP-104008] ¦ [Cyber] 4.0 IDU Manufacturing Updates | Feature | In progress |  |  | Parent Task | User Stories | 6 | 2 | 1 hr | 1 hr | 4 | 33.33%
TAP-104008_BUILDERS | 1329 | *1328 |  | 06.05.10.13.01.00.00.00 | TAP-104008 | TAP-104719 | [TAP-104008_BUILDERS] ¦ In Line Tester - JTAG J6 | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 6 | 2 | 6 | 7.2 | 4 | 100%
TAP-85190 | 1330 | *19 |  | 06.05.10.14.00.00.00.00 |  | TAP-85190 | [TAP-85190] ¦ [Cyber] Transfer of Misc. integration tools to PLXS | Feature | Accepted |  |  | Parent Task | User Stories | 12 | 0 | 1 hr | 1 hr | 12 | 0%
TAP-85190_BUILDERS | 1331 | *1330 |  | 06.05.10.14.01.00.00.00 | TAP-85190 | TAP-85196 | [TAP-85190_BUILDERS] ¦ Provide work instructions for EOL burn-in | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 12 | 0 | 12 | 14.4 | 12 | 0%
TAP-84497 | 1332 | *19 |  | 06.05.10.15.00.00.00.00 |  | TAP-84497 | [TAP-84497] ¦ [Cyber] Manufacturing SRA BSP to support rasa and idu testers | Feature | Done |  |  | Parent Task | User Stories | 33 | 33 | 1 hr | 1 hr | 0 | 100%
TAP-84497_ATLAS | 1333 | *1332 |  | 06.05.10.15.01.00.00.00 | TAP-84497 | TAP-95781 | [TAP-84497_ATLAS] ¦ Atlas support to run manufacturing script on SRA manufacturing tester BSP | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 33 | 33 | 33 | 39.6 | 0 | 100%
TAP-84497_FRED | 1334 | *1332 |  | 06.05.10.15.11.00.00.00 | TAP-84497 | TAP-99253 | [TAP-84497_FRED] ¦ Test if SRA_Init image works on the IDU node and is deployable with esat | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 53 | 33 | 53 | 63.6 | 20 | 100%
TAP-84497_HORIZON | 1335 | *1332 |  | 06.05.10.15.12.00.00.00 | TAP-84497 | TAP-94971 | [TAP-84497_HORIZON] ¦ [Horizon] SRA IDU Standalone fixture configuration support with cyber enabled | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 53 | 33 | 53 | 63.6 | 20 | 100%
TAP-84497_BUILDERS | 1336 | *1332 |  | 06.05.10.15.13.00.00.00 | TAP-84497 | TAP-101044 | [TAP-84497_BUILDERS] ¦ Determine new EtherCAT file transfer mechanism in SRA manufacturing tester node | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 53 | 33 | 53 | 63.6 | 20 | 100%
TAP-84358 | 1337 | *19 |  | 06.05.10.16.00.00.00.00 |  | TAP-84358 | [TAP-84358] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 1 - PI12 (before validation) | Feature | Done |  |  | Parent Task | User Stories | 19 | 19 | 1 hr | 1 hr | 0 | 100%
TAP-84358_BUILDERS | 1338 | *1337 |  | 06.05.10.16.01.00.00.00 | TAP-84358 | TAP-100643 | [TAP-84358_BUILDERS] ¦ Learn the test to pass with old PCBA | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 19 | 19 | 19 | 22.8 | 0 | 100%
TAP-84360 | 1339 | *19 |  | 06.05.10.17.00.00.00.00 |  | TAP-84360 | [TAP-84360] ¦ [Cyber] Base Programming Station OS updates | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-84360_BUILDERS | 1340 | *1339 |  | 06.05.10.17.01.00.00.00 | TAP-84360 | TAP-85128 | [TAP-84360_BUILDERS] ¦ Dry run of the Base Programming Station Creation Work Instructions | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-84363 | 1341 | *19 |  | 06.05.10.18.00.00.00.00 |  | TAP-84363 | [TAP-84363] ¦ [Cyber] SC/iSIM Programming Station Updates for Manufacturing | Feature | Accepted |  |  | Parent Task | User Stories | 27 | 0 | 1 hr | 1 hr | 27 | 0%
TAP-84363_BUILDERS | 1342 | *1341 |  | 06.05.10.18.01.00.00.00 | TAP-84363 | TAP-85132 | [TAP-84363_BUILDERS] ¦ Dry run of the SC Programming Station Creation Work Instructions | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 27 | 0 | 27 | 32.4 | 27 | 0%
TAP-84361 | 1343 | *19 |  | 06.05.10.19.00.00.00.00 |  | TAP-84361 | [TAP-84361] ¦ [Cyber] Tower Programming Station Updates for Manufacturing | Feature | In progress |  |  | Parent Task | User Stories | 10.5 | 5 | 1 hr | 1 hr | 5.5 | 47.62%
TAP-84361_BUILDERS | 1344 | *1343 |  | 06.05.10.19.01.00.00.00 | TAP-84361 | TAP-84409 | [TAP-84361_BUILDERS] ¦ Updates to FSE/TPSC Programming scripts to support deploying release build via manufacturing bsp | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 10.5 | 5 | 10.5 | 12.6 | 5.5 | 47.62%
TAP-84362 | 1345 | *19 |  | 06.05.10.20.00.00.00.00 |  | TAP-84362 | [TAP-84362] ¦ [Cyber] Cart Programming Station Updates for Manufacturing | Feature | Groomed |  |  | Parent Task | User Stories | 15 | 0 | 1 hr | 1 hr | 15 | 0%
TAP-84362_BUILDERS | 1346 | *1345 |  | 06.05.10.20.01.00.00.00 | TAP-84362 | TAP-85226 | [TAP-84362_BUILDERS] ¦ Work Instruction Updates | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 15 | 0 | 15 | 18 | 15 | 0%
TAP-84367 | 1347 | *19 |  | 06.05.10.21.00.00.00.00 |  | TAP-84367 | [TAP-84367] ¦ [Cyber] Dry Run of SC Functional Tests at Manufacturing | Feature | Accepted |  |  | Parent Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 0%
TAP-84367_BUILDERS | 1348 | *1347 |  | 06.05.10.21.01.00.00.00 | TAP-84367 | TAP-85139 | [TAP-84367_BUILDERS] ¦ Dry run of the FCT 14 | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-83129 | 1349 | *19 |  | 06.05.10.22.00.00.00.00 |  | TAP-83129 | [TAP-83129] ¦ [Cyber] Investigate password programming functions | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-83129_BUILDERS | 1350 | *1349 |  | 06.05.10.22.01.00.00.00 | TAP-83129 | TAP-83133 | [TAP-83129_BUILDERS] ¦ [Builders][Spike] Finalize the CyberArk python library as backend | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-81647 | 1351 | *19 |  | 06.05.10.23.00.00.00.00 |  | TAP-81647 | [TAP-81647] ¦ [Cyber] Create Manufacturing BSP for cart/tpsc/fse to support FCT | Feature | Done |  |  | Parent Task | User Stories | 61 | 61 | 1 hr | 1 hr | 0 | 100%
TAP-81647_ATLAS | 1352 | *1351 |  | 06.05.10.23.01.00.00.00 | TAP-81647 | TAP-95647 | [TAP-81647_ATLAS] ¦ Background application run as root to receive commands to run manufacturing test scripts | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 61 | 61 | 61 | 73.2 | 0 | 100%
TAP-97718 | 1353 | *19 |  | 06.05.10.24.00.00.00.00 |  | TAP-97718 | [TAP-97718] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - commanders - PI13 | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-97718_BUILDERS | 1354 | *1353 |  | 06.05.10.24.01.00.00.00 | TAP-97718 | TAP-8728 | [TAP-97718_BUILDERS] ¦ [MFG][Spike] Update torque sensor calibration routine | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-88670 | 1355 | *19 |  | 06.05.10.25.00.00.00.00 |  | TAP-88670 | [TAP-88670] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - SRA installation | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-88670_BUILDERS | 1356 | *1355 |  | 06.05.10.25.01.00.00.00 | TAP-88670 | TAP-85156 | [TAP-88670_BUILDERS] ¦ FCTMech - Updates to SRA computer to support authenticated communication | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-88672 | 1357 | *19 |  | 06.05.10.26.00.00.00.00 |  | TAP-88672 | [TAP-88672] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - commanders - PI12 | Feature | Done |  |  | Parent Task | User Stories | 16 | 16 | 1 hr | 1 hr | 0 | 100%
TAP-88672_BUILDERS | 1358 | *1357 |  | 06.05.10.26.01.00.00.00 | TAP-88672 | TAP-85033 | [TAP-88672_BUILDERS] ¦ [Builders] Modify IDU final position in FRU tester | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 16 | 16 | 16 | 19.2 | 0 | 100%
TAP-88676 | 1359 | *19 |  | 06.05.10.27.00.00.00.00 |  | TAP-88676 | [TAP-88676] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Communication | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-88676_BUILDERS | 1360 | *1359 |  | 06.05.10.27.01.00.00.00 | TAP-88676 | TAP-86853 | [TAP-88676_BUILDERS] ¦ Communication from tester PC (Windows) to QNX PC needs to be signed/updated | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-88673 | 1361 | *19 |  | 06.05.10.28.00.00.00.00 |  | TAP-88673 | [TAP-88673] ¦ [Cyber] FCT35 Cage, Mech, FRU - deployment | Feature | In progress |  |  | Parent Task | User Stories | 87.5 | 39 | 1 hr | 1 hr | 48.5 | 44.57%
TAP-88673_FRED | 1362 | *1361 |  | 06.05.10.28.01.00.00.00 | TAP-88673 | TAP-121550 | [TAP-88673_FRED] ¦ Create Generic Secondary Image for Manufacturing on 4.0 | User Story | In progress | Foundation - Fred | FRED | Child Task | User Stories | 87.5 | 39 | 87.5 | 105 | 48.5 | 44.57%
TAP-88673_TOOLSRULES | 1363 | *1361 |  | 06.05.10.28.04.00.00.00 | TAP-88673 | TAP-96596 | [TAP-88673_TOOLSRULES] ¦ [Cyber] ESAT support for RASA install in Manufacturing - concept design | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 91.5 | 39 | 91.5 | 109.8 | 52.5 | 100%
TAP-88673_BUILDERS | 1364 | *1361 |  | 06.05.10.28.05.00.00.00 | TAP-88673 | TAP-125469 | [TAP-88673_BUILDERS] ¦ Python barebone Deploy on 1 RASA node Engineering build after RC1 using root user | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 91.5 | 39 | 91.5 | 109.8 | 52.5 | 42.62%
TAP-88679 | 1365 | *19 |  | 06.05.10.29.00.00.00.00 |  | TAP-88679 | [TAP-88679] ¦ [Cyber] FCT35 Cage, Mech, FRU - LabView/Windows application | Feature | Accepted |  |  | Parent Task | User Stories | 21 | 0 | 1 hr | 1 hr | 21 | 0%
TAP-88679_BUILDERS | 1366 | *1365 |  | 06.05.10.29.01.00.00.00 | TAP-88679 | TAP-124170 | [TAP-88679_BUILDERS] ¦ Support Updates to Mech Tester Software | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 21 | 0 | 21 | 25.2 | 21 | 0%
TAP-88681 | 1367 | *19 |  | 06.05.10.30.00.00.00.00 |  | TAP-88681 | [TAP-88681] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Full Testing | Feature | Accepted |  |  | Parent Task | User Stories | 50 | 0 | 1 hr | 1 hr | 50 | 0%
TAP-88681_BUILDERS | 1368 | *1367 |  | 06.05.10.30.01.00.00.00 | TAP-88681 | TAP-85244 | [TAP-88681_BUILDERS] ¦ Dry run of FRU Tester | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 50 | 0 | 50 | 60 | 50 | 0%
TAP-83134 | 1369 | *19 |  | 06.05.10.31.00.00.00.00 |  | TAP-83134 | [TAP-83134] ¦ [Cyber] Investigate feasiblity of CyberArk REST API Integration | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-83134_BUILDERS | 1370 | *1369 |  | 06.05.10.31.01.00.00.00 | TAP-83134 | TAP-83135 | [TAP-83134_BUILDERS] ¦ [Builders][Spike] Review CyberArk documentation | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-83144 | 1371 | *19 |  | 06.05.10.32.00.00.00.00 |  | TAP-83144 | [TAP-83144] ¦ [Cyber] Investigate feasibility of CyberArk agent based Integration | Feature | Done |  |  | Parent Task | User Stories | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-83144_BUILDERS | 1372 | *1371 |  | 06.05.10.32.01.00.00.00 | TAP-83144 | TAP-83147 | [TAP-83144_BUILDERS] ¦ [Builders][Spike] Test account and environment setup | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-84364 | 1373 | *19 |  | 06.05.10.33.00.00.00.00 |  | TAP-84364 | [TAP-84364] ¦ [Cyber] Tower FRU Programming Station Updates | Feature | Accepted |  |  | Parent Task | User Stories | 17 | 0 | 1 hr | 1 hr | 17 | 0%
TAP-84364_BUILDERS | 1374 | *1373 |  | 06.05.10.33.01.00.00.00 | TAP-84364 | TAP-85217 | [TAP-84364_BUILDERS] ¦ Work Instruction Updates | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 17 | 0 | 17 | 20.4 | 17 | 0%
TAP-84365 | 1375 | *19 |  | 06.05.10.34.00.00.00.00 |  | TAP-84365 | [TAP-84365] ¦ [Cyber] SC FRU Programming Station Updates | Feature | Accepted |  |  | Parent Task | User Stories | 2 | 0 | 1 hr | 1 hr | 2 | 0%
TAP-84365_BUILDERS | 1376 | *1375 |  | 06.05.10.34.01.00.00.00 | TAP-84365 | TAP-84675 | [TAP-84365_BUILDERS] ¦ QNX x86 programming step updates to support unique passwords | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 2 | 0 | 2 | 2.4 | 2 | 0%
TAP-97710 | 1377 | *19 |  | 06.05.10.35.00.00.00.00 |  | TAP-97710 | [TAP-97710] ¦ [Cyber] Functional Tester Updates for Manufacturing Phase 1 - PI13 (before validation) | Feature | Done |  |  | Parent Task | User Stories | 31.5 | 31.5 | 1 hr | 1 hr | 0 | 100%
TAP-97710_BUILDERS | 1378 | *1377 |  | 06.05.10.35.01.00.00.00 | TAP-97710 | TAP-104937 | [TAP-97710_BUILDERS] ¦ Test to Pass Fixture and Procedure for New TPSC Board | User Story | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 31.5 | 31.5 | 31.5 | 37.8 | 0 | 100%
TAP-126486 | 1379 | *19 |  | 06.05.10.36.00.00.00.00 |  | TAP-126486 | [TAP-126486] ¦ [Cyber] 4.0 IDU Manufacturing Deployment Updates PI16 | Feature | PROPOSED |  |  | Parent Task | User Stories | 14 | 0 | 1 hr | 1 hr | 14 | 0%
TAP-126486_BUILDERS | 1380 | *1379 |  | 06.05.10.36.01.00.00.00 | TAP-126486 | TAP-104727 | [TAP-126486_BUILDERS] ¦ Certificate management - J6 | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 14 | 0 | 14 | 16.8 | 14 | 0%
TAP-126416 | 1381 | *19 |  | 06.05.10.37.00.00.00.00 |  | TAP-126416 | [TAP-126416] ¦ [Cyber] FCT35 Cage, Mech, FRU - LabView/Windows application (PI16) | Feature | PROPOSED |  |  | Parent Task | User Stories | 17 | 0 | 1 hr | 1 hr | 17 | 0%
TAP-126416_BUILDERS | 1382 | *1381 |  | 06.05.10.37.01.00.00.00 | TAP-126416 | TAP-101940 | [TAP-126416_BUILDERS] ¦ [Builders] More positions tested for pinch sensors in SF4 | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 17 | 0 | 17 | 20.4 | 17 | 0%
TAP-88671 | 1383 | *21 |  | 06.05.10.38.00.00.00.00 |  | TAP-88671 | [TAP-88671] ¦ [Cyber] Programming Computers Final Release and Validation | Feature | Accepted |  |  | Parent Task | User Stories | 62 | 0 | 1 hr | 1 hr | 62 | 0%
TAP-88671_BUILDERS | 1384 | *1383 |  | 06.05.10.38.01.00.00.00 | TAP-88671 | TAP-85231 | [TAP-88671_BUILDERS] ¦ Cart Programming Computer Design Documentation Update | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 62 | 0 | 62 | 74.4 | 62 | 0%
TAP-85233 | 1385 | *21 |  | 06.05.10.39.00.00.00.00 |  | TAP-85233 | [TAP-85233] ¦ [Cyber] Manufacturing Integration of 4.0 | Feature | Accepted |  |  | Parent Task | User Stories | 50 | 0 | 1 hr | 1 hr | 50 | 0%
TAP-85233_BUILDERS | 1386 | *1385 |  | 06.05.10.39.01.00.00.00 | TAP-85233 | TAP-85235 | [TAP-85233_BUILDERS] ¦ Installation Support at Plexus | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 50 | 0 | 50 | 60 | 50 | 0%
TAP-85206 | 1387 | *21 |  | 06.05.10.40.00.00.00.00 |  | TAP-85206 | [TAP-85206] ¦ [Cyber] SW4.0 SW BOM Creation (for PLXS) | Feature | Accepted |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-85206_BUILDERS | 1388 | *1387 |  | 06.05.10.40.01.00.00.00 | TAP-85206 | TAP-85219 | [TAP-85206_BUILDERS] ¦ (Builders) SW 4.0 RC2 BOM Release (For PLXS) | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 30 | 0 | 30 | 36 | 30 | 0%
TAP-88682 | 1389 | *21 |  | 06.05.10.41.00.00.00.00 |  | TAP-88682 | [TAP-88682] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Work Instructions and TRS updates | Feature | Accepted |  |  | Parent Task | User Stories | 47 | 0 | 1 hr | 1 hr | 47 | 0%
TAP-88682_BUILDERS | 1390 | *1389 |  | 06.05.10.41.01.00.00.00 | TAP-88682 | TAP-85238 | [TAP-88682_BUILDERS] ¦ TRS changes | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 47 | 0 | 47 | 56.4 | 47 | 0%
TAP-88684 | 1391 | *21 |  | 06.05.10.42.00.00.00.00 |  | TAP-88684 | [TAP-88684] ¦ [Cyber] FCT35 Cage, Mech, FRU, IDU - Validation Support | Feature | Accepted |  |  | Parent Task | User Stories | 70 | 0 | 1 hr | 1 hr | 70 | 0%
TAP-88684_BUILDERS | 1392 | *1391 |  | 06.05.10.42.01.00.00.00 | TAP-88684 | TAP-85239 | [TAP-88684_BUILDERS] ¦ Validation for Mech tester | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 70 | 0 | 70 | 84 | 70 | 0%
TAP-84377 | 1393 | *21 |  | 06.05.10.43.00.00.00.00 |  | TAP-84377 | [TAP-84377] ¦ [Cyber] IT infrastructure setup at Plexus to support certificate management | Feature | Accepted |  |  | Parent Task | User Stories | 10 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-84377_BUILDERS | 1394 | *1393 |  | 06.05.10.43.01.00.00.00 | TAP-84377 | TAP-90241 | [TAP-84377_BUILDERS] ¦ Placeholder for Plexus Implementation | User Story | Open | Shared Services - Builders | BUILDERS | Child Task | User Stories | 10 | 0 | 10 | 12 | 10 | 0%
TAP-83152 | 1395 | *21 |  | 06.05.10.44.00.00.00.00 |  | TAP-83152 | [TAP-83152] ¦ [Cyber] Manufacturing Integration of Unique Password Programming | Feature | Accepted |  |  | Parent Task | User Stories | 25 | 0 | 1 hr | 1 hr | 25 | 0%
TAP-83152_BUILDERS | 1396 | *1395 |  | 06.05.10.44.01.00.00.00 | TAP-83152 | TAP-83155 | [TAP-83152_BUILDERS] ¦ [Builders][Spike] Work with Plexus Engineering Solutions on GSF updates | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 25 | 0 | 25 | 30 | 25 | 0%
TAP-125288 | 1397 | *23 |  | 06.05.10.45.00.00.00.00 |  | TAP-125288 | [TAP-125288] ¦ [Cyber] Finalize US Launch Work Instructions | Feature | In progress |  |  | Parent Task | User Stories | 27 | 6 | 1 hr | 1 hr | 21 | 22.22%
TAP-125288_BUILDERS | 1398 | *1397 |  | 06.05.10.45.01.00.00.00 | TAP-125288 | TAP-119675 | [TAP-125288_BUILDERS] ¦ Finalize Updates to Switch FRU Installation w/CyberArk on ESAT | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 27 | 6 | 27 | 32.4 | 21 | 22.22%
TAP-85224 | 1399 | *23 |  | 06.05.10.46.00.00.00.00 |  | TAP-85224 | [TAP-85224] ¦ [Cyber] Field Service Tools NPS Validation Support | Feature | In progress |  |  | Parent Task | User Stories | 49 | 0 | 1 hr | 1 hr | 49 | 0%
TAP-85224_BUILDERS | 1400 | *1399 |  | 06.05.10.46.01.00.00.00 | TAP-85224 | TAP-125235 | [TAP-85224_BUILDERS] ¦ NPS Validation Support for 2.2.3 Individual Brake Regeneration Scripts | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 49 | 0 | 49 | 58.8 | 49 | 0%
TAP-87779 | 1401 | *23 |  | 06.05.10.47.00.00.00.00 |  | TAP-87779 | [TAP-87779] ¦ [Cyber] HLA Upgrade Support for Project Sentinel Phase 3(Implementation and Validation) | Feature | In progress |  |  | Parent Task | User Stories | 61 | 11 | 1 hr | 1 hr | 50 | 18.03%
TAP-87779_BUILDERS | 1402 | *1401 |  | 06.05.10.47.01.00.00.00 | TAP-87779 | TAP-126426 | [TAP-87779_BUILDERS] ¦ Testing of RC1 Release before RC2 code freeze | User Story | Groomed | Shared Services - Builders | BUILDERS | Child Task | User Stories | 61 | 11 | 61 | 73.2 | 50 | 18.03%
TAP-87779_EDISON | 1403 | *1401 |  | 06.05.10.47.20.00.00.00 | TAP-87779 | TAP-125780 | [TAP-87779_EDISON] ¦ Build and Release Custom Packages for 4.0 Zynq Upgrades | User Story | Groomed | Shared Services - Edison | EDISON | Child Task | User Stories | 113 | 11 | 113 | 135.6 | 102 | 9.735%
TAP-118514 | 1404 | *21 |  | 06.05.10.48.00.00.00.00 |  | TAP-118514 | [TAP-118514] ¦ [Cyber] Finalize and Validate service procedures for OUS cyber launch. | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-118512 | 1405 | *21 |  | 06.05.10.49.00.00.00.00 |  | TAP-118512 | [TAP-118512] ¦ [Cyber] Developing Service Procedures for use after Plexus Transfer | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-118513 | 1406 | *21 |  | 06.05.10.50.00.00.00.00 |  | TAP-118513 | [TAP-118513] ¦ [Cyber] Developing HLA Field Upgrade Procedures for Service use | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-105489 | 1407 | *1 |  | 06.05.11.01.00.00.00.00 |  | TAP-105489 | [TAP-105489] ¦ [Cyber] Miscellaneous EC1 Blockers | Feature | Done |  |  | Parent Task | User Stories | 37.7 | 37.7 | 1 hr | 1 hr | 0 | 100%
TAP-105489_TEAMBD | 1408 | *1407 |  | 06.05.11.01.01.00.00.00 | TAP-105489 | TAP-101285 | [TAP-105489_TEAMBD] ¦ [Cyber] Notcode-287 (SC communications loss on MSC) showing up at startup | Issue | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 37.7 | 37.7 | 37.7 | 45.24 | 0 | 100%
TAP-105489_FOUNDATION | 1409 | *1407 |  | 06.05.11.01.02.00.00.00 | TAP-105489 | TAP-107992 | [TAP-105489_FOUNDATION] ¦ Notcode-479 (SIM not connected Arm sterile barrier open) triggering after arm hotswap | Issue | Done | Foundation | FOUNDATION | Child Task | User Stories | 37.7 | 37.7 | 37.7 | 45.24 | 0 | 100%
TAP-105489_ATLAS | 1410 | *1407 |  | 06.05.11.01.03.00.00.00 | TAP-105489 | TAP-98898 | [TAP-105489_ATLAS] ¦ Build Windows OS SCDC and SimPC from develop after staging/cyber merge | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 37.7 | 37.7 | 37.7 | 45.24 | 0 | 100%
TAP-105489_CLASSY1 | 1411 | *1407 |  | 06.05.11.01.14.00.00.00 | TAP-105489 | TAP-102482 | [TAP-105489_CLASSY1] ¦ Notcode-597 (msc observer: position control without handles unlocking) Blocking Teleop | Issue | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 49.4 | 37.7 | 49.4 | 59.28 | 11.7 | 100%
TAP-105489_HORIZON | 1412 | *1407 |  | 06.05.11.01.16.00.00.00 | TAP-105489 | TAP-106044 | [TAP-105489_HORIZON] ¦ [Spike] Cart Monitoring Thread Delay Investigation | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 57.4 | 37.7 | 57.4 | 68.88 | 19.7 | 100%
TAP-105489_SHAREDSERVICES | 1413 | *1407 |  | 06.05.11.01.17.00.00.00 | TAP-105489 | TAP-107837 | [TAP-105489_SHAREDSERVICES] ¦ String missing on recent develop (notcode 602 / EIN-STG-965) | Issue | Done | Shared Services | SHAREDSERVICES | Child Task | User Stories | 57.4 | 37.7 | 57.4 | 68.88 | 19.7 | 100%
TAP-105489_SEAMLESS | 1414 | *1407 |  | 06.05.11.01.18.00.00.00 | TAP-105489 | TAP-107010 | [TAP-105489_SEAMLESS] ¦ non-recoverable EIN-NOTCODE-443 on develop-2595 | Issue | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 57.4 | 37.7 | 57.4 | 68.88 | 19.7 | 100%
TAP-96772 | 1415 | *1 |  | 06.05.11.02.00.00.00.00 |  | TAP-96772 | [TAP-96772] ¦ Support collapse of staging/cyber to develop | Feature | Done |  |  | Parent Task | User Stories | 114 | 114 | 1 hr | 1 hr | 0 | 100%
TAP-96772_ATLAS | 1416 | *1415 |  | 06.05.11.02.01.00.00.00 | TAP-96772 | TAP-98939 | [TAP-96772_ATLAS] ¦ Sync staging/cyber with develop Nov2 | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 114 | 114 | 114 | 136.8 | 0 | 100%
TAP-96772_EDISON | 1417 | *1415 |  | 06.05.11.02.53.00.00.00 | TAP-96772 | TAP-96842 | [TAP-96772_EDISON] ¦ Create new wolfssh packages for all targets | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 222 | 114 | 222 | 266.4 | 108 | 100%
TAP-106940 | 1418 | *3 |  | 06.05.11.03.00.00.00.00 |  | TAP-106940 | [TAP-106940] ¦ [Cyber] Miscellaneous EC2 Blockers | Feature | Done |  |  | Parent Task | User Stories | 73.6 | 73.6 | 1 hr | 1 hr | 0 | 100%
TAP-106940_SCRUMBLEDORES | 1419 | *1418 |  | 06.05.11.03.01.00.00.00 | TAP-106940 | TAP-112488 | [TAP-106940_SCRUMBLEDORES] ¦ [SPIKE][v4.0][Scrumbledores] Marystein External Calibration Below Port Investigation | User Story | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 73.6 | 73.6 | 73.6 | 88.32 | 0 | 100%
TAP-106940_TEAMBD | 1420 | *1418 |  | 06.05.11.03.03.00.00.00 | TAP-106940 | TAP-108876 | [TAP-106940_TEAMBD] ¦ [TeamBD] Notcode-287 followup unit test | User Story | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 79.6 | 73.6 | 79.6 | 95.52 | 6 | 100%
TAP-106940_ATLAS | 1421 | *1418 |  | 06.05.11.03.04.00.00.00 | TAP-106940 | TAP-108003 | [TAP-106940_ATLAS] ¦ QNX Zynq BSP not building due to old docker container | Issue | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 79.6 | 73.6 | 79.6 | 95.52 | 6 | 100%
TAP-106940_CLASSY2 | 1422 | *1418 |  | 06.05.11.03.14.00.00.00 | TAP-106940 | TAP-107144 | [TAP-106940_CLASSY2] ¦ Fixing and refactoring failing unit tests for CentralLocalInterface class located in TestCentralLocalInterface.cpp | Issue | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 97.6 | 73.6 | 97.6 | 117.12 | 24 | 100%
TAP-106940_FRED | 1423 | *1418 |  | 06.05.11.03.16.00.00.00 | TAP-106940 | TAP-104939 | [TAP-106940_FRED] ¦ NOTCODE-295 SRA Input Latency Interrupting Teleop | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 105.6 | 73.6 | 105.6 | 126.72 | 32 | 100%
TAP-106940_HORIZON | 1424 | *1418 |  | 06.05.11.03.18.00.00.00 | TAP-106940 | TAP-108668 | [TAP-106940_HORIZON] ¦ Address TPSC Notcode-180 for EC2 | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 106.6 | 73.6 | 106.6 | 127.92 | 33 | 100%
TAP-106940_STORMCHASERS1 | 1425 | *1418 |  | 06.05.11.03.20.00.00.00 | TAP-106940 | TAP-110707 | [TAP-106940_STORMCHASERS1] ¦ [SC1][V4.0] Investigation of hotswapping surgeon console fails | User Story | Done | Foundation - Storm Chasers 1 | STORMCHASERS1 | Child Task | User Stories | 106.6 | 73.6 | 106.6 | 127.92 | 33 | 100%
TAP-106940_VISUAL | 1426 | *1418 |  | 06.05.11.03.21.00.00.00 | TAP-106940 | TAP-105974 | [TAP-106940_VISUAL] ¦ [v4.0][Visual] Fix integration tests for ENDOSW- part 2 | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 106.6 | 73.6 | 106.6 | 127.92 | 33 | 100%
TAP-106940_DRUSHTI | 1427 | *1418 |  | 06.05.11.03.32.00.00.00 | TAP-106940 | TAP-110498 | [TAP-106940_DRUSHTI] ¦ [v4][EC1] Retry Calibration brings user to Surgery Mode, doesn't recalibrate | Issue | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 124.6 | 73.6 | 124.6 | 149.52 | 51 | 100%
TAP-105164 | 1428 | *3 |  | 06.05.11.04.00.00.00.00 |  | TAP-105164 | [TAP-105164] ¦ [Cyber] Daily integration stability Issue | Feature | Done |  |  | Parent Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-105164_ATLAS | 1429 | *1428 |  | 06.05.11.04.01.00.00.00 | TAP-105164 | TAP-104294 | [TAP-105164_ATLAS] ¦ [Enabler] Create build to be used for jtag recovering joint nodes | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-105164_FRED | 1430 | *1428 |  | 06.05.11.04.02.00.00.00 | TAP-105164 | TAP-106519 | [TAP-105164_FRED] ¦ [Spike] Replicate issue TAP-103500 and analyze logs | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-86114 | 1431 | *5 |  | 06.05.11.05.00.00.00.00 |  | TAP-86114 | [TAP-86114] ¦ [Cyber] System Performance Analysis with cyber security features | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-86114_ATLAS | 1432 | *1431 |  | 06.05.11.05.01.00.00.00 | TAP-86114 | TAP-82586 | [TAP-86114_ATLAS] ¦ System 54 KPI Data Collection | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-86114_BOOSTERS | 1433 | *1431 |  | 06.05.11.05.02.00.00.00 | TAP-86114 | TAP-115766 | [TAP-86114_BOOSTERS] ¦ [Boosters] Add a continuous cpu load collector | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-106957 | 1434 | *5 |  | 06.05.11.06.00.00.00.00 |  | TAP-106957 | [TAP-106957] ¦ [Cyber] Miscellaneous EC3 Blockers | Feature | Done |  |  | Parent Task | User Stories | 102.5 | 102.5 | 1 hr | 1 hr | 0 | 100%
TAP-106957_SCRUMBLEDORES | 1435 | *1434 |  | 06.05.11.06.01.00.00.00 | TAP-106957 | TAP-113363 | [TAP-106957_SCRUMBLEDORES] ¦ [v4.0][USFW]EIN-SSR_MSC-586 Failure Clear on attach | Issue | Done | Advanced Instruments - Scrumbledores | SCRUMBLEDORES | Child Task | User Stories | 102.5 | 102.5 | 102.5 | 123 | 0 | 100%
TAP-106957_ATLAS | 1436 | *1434 |  | 06.05.11.06.02.00.00.00 | TAP-106957 | TAP-119816 | [TAP-106957_ATLAS] ¦ Windows SCDC and SimPC OS build broken | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 102.5 | 102.5 | 102.5 | 123 | 0 | 100%
TAP-106957_BOOSTERS | 1437 | *1434 |  | 06.05.11.06.25.00.00.00 | TAP-106957 | TAP-116118 | [TAP-106957_BOOSTERS] ¦ [Boosters] Investigate CPU load increase in ORTI/SMC | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 147 | 102.5 | 147 | 176.4 | 44.5 | 100%
TAP-106957_CLASSY2 | 1438 | *1434 |  | 06.05.11.06.28.00.00.00 | TAP-106957 | TAP-106181 | [TAP-106957_CLASSY2] ¦ [Classy2] Add event logging to UDP | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 153 | 102.5 | 153 | 183.6 | 50.5 | 100%
TAP-106957_HORIZON | 1439 | *1434 |  | 06.05.11.06.29.00.00.00 | TAP-106957 | TAP-112481 | [TAP-106957_HORIZON] ¦ [Spike] Reproduce failing Inogeni-detection with v4.0 SW System and Spartan 6 Inogeni | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 153 | 102.5 | 153 | 183.6 | 50.5 | 100%
TAP-106957_PLATFORMERS | 1440 | *1434 |  | 06.05.11.06.31.00.00.00 | TAP-106957 | TAP-117571 | [TAP-106957_PLATFORMERS] ¦ Console unable to transition out of standby if it reaches standby before tower and maintenance timeout occurs before tower standby | Issue | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 154 | 102.5 | 154 | 184.8 | 51.5 | 100%
TAP-106957_STORMCHASERS2 | 1441 | *1434 |  | 06.05.11.06.32.00.00.00 | TAP-106957 | TAP-96883 | [TAP-106957_STORMCHASERS2] ¦ [V4.0 EC2][SC2] Refactor/remove sc_common_communication_support and smc_communication libraries after MSC SW is updated with the new communication library | User Story | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 154 | 102.5 | 154 | 184.8 | 51.5 | 100%
TAP-106957_VISUAL | 1442 | *1434 |  | 06.05.11.06.33.00.00.00 | TAP-106957 | TAP-115012 | [TAP-106957_VISUAL] ¦ [v4.0][Visual] KS systems firmware upgrade. | Issue | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 154 | 102.5 | 154 | 184.8 | 51.5 | 100%
TAP-106957_EDISON | 1443 | *1434 |  | 06.05.11.06.38.00.00.00 | TAP-106957 | TAP-116003 | [TAP-106957_EDISON] ¦ Upgrade to use wolfssh 1.4.17 in build images | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 167 | 102.5 | 167 | 200.4 | 64.5 | 100%
TAP-106958 | 1444 | *7 |  | 06.05.11.07.00.00.00.00 |  | TAP-106958 | [TAP-106958] ¦ [Cyber] Miscellaneous RC1 Blockers | Feature | Done |  |  | Parent Task | User Stories | 218.4 | 218.4 | 1 hr | 1 hr | 0 | 100%
TAP-106958_I2E | 1445 | *1444 |  | 06.05.11.07.01.00.00.00 | TAP-106958 | TAP-121869 | [TAP-106958_I2E] ¦ [v4.0][I2E] Fix data recorder start permissions in SRAConfig_standalone_idu.json.in | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 218.4 | 218.4 | 218.4 | 262.08 | 0 | 100%
TAP-106958_MACHETE | 1446 | *1444 |  | 06.05.11.07.02.00.00.00 | TAP-106958 | TAP-110506 | [TAP-106958_MACHETE] ¦ [V4][Pixel Poets] Excessive ORTI+SCDC logs clean-up | Issue | Done | Advanced Instruments - Machete | MACHETE | Child Task | User Stories | 218.4 | 218.4 | 218.4 | 262.08 | 0 | 100%
TAP-106958_PIXELPOETS | 1447 | *1444 |  | 06.05.11.07.05.00.00.00 | TAP-106958 | TAP-104890 | [TAP-106958_PIXELPOETS] ¦ Not able to enter maintenance mode without Storz | Issue | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 222.4 | 218.4 | 222.4 | 266.88 | 4 | 100%
TAP-106958_COREINSTRUMENTS | 1448 | *1444 |  | 06.05.11.07.08.00.00.00 | TAP-106958 | TAP-105370 | [TAP-106958_COREINSTRUMENTS] ¦ Requesting teleop after instrument error triggeres subsystem non-recoverable error | Issue | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 225.4 | 218.4 | 225.4 | 270.48 | 7 | 100%
TAP-106958_ATLAS | 1449 | *1444 |  | 06.05.11.07.09.00.00.00 | TAP-106958 | TAP-116085 | [TAP-106958_ATLAS] ¦ Remove Old Wolf User Certs from Engineering Windows Build | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 225.4 | 218.4 | 225.4 | 270.48 | 7 | 100%
TAP-106958_BOOSTERS | 1450 | *1444 |  | 06.05.11.07.42.00.00.00 | TAP-106958 | TAP-118063 | [TAP-106958_BOOSTERS] ¦ Data access fails to delete files on SCDC | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 291.7 | 218.4 | 291.7 | 350.04 | 73.3 | 100%
TAP-106958_CLASSY1 | 1451 | *1444 |  | 06.05.11.07.49.00.00.00 | TAP-106958 | TAP-115327 | [TAP-106958_CLASSY1] ¦ [CLASSY] Stability issues fixes Sprint 3 | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 306.8 | 218.4 | 306.8 | 368.16 | 88.4 | 100%
TAP-106958_CLASSY2 | 1452 | *1444 |  | 06.05.11.07.53.00.00.00 | TAP-106958 | TAP-121117 | [TAP-106958_CLASSY2] ¦ [CLASSY] Remove spamming of log in alarm | User Story | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 329.8 | 218.4 | 329.8 | 395.76 | 111.4 | 100%
TAP-106958_FRED | 1453 | *1444 |  | 06.05.11.07.55.00.00.00 | TAP-106958 | TAP-107899 | [TAP-106958_FRED] ¦ Notcode 147 (RA MOTOR STATE ERROR) and Notcode 456 (MOTOR STATE BRAKE) appearing on Develop 2621+ | Issue | Done | Foundation - Fred | FRED | Child Task | User Stories | 342.8 | 218.4 | 342.8 | 411.36 | 124.4 | 100%
TAP-106958_HORIZON | 1454 | *1444 |  | 06.05.11.07.60.00.00.00 | TAP-106958 | TAP-52296 | [TAP-106958_HORIZON] ¦ Occurrence of NOTCODE-59 at system initialization after startup | Issue | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 357.8 | 218.4 | 357.8 | 429.36 | 139.4 | 100%
TAP-106958_PLATFORMERS | 1455 | *1444 |  | 06.05.11.07.63.00.00.00 | TAP-106958 | TAP-115155 | [TAP-106958_PLATFORMERS] ¦ [V4][Platformers]Create script to see certs type on system | User Story | Done | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 363.8 | 218.4 | 363.8 | 436.56 | 145.4 | 100%
TAP-106958_STORMCHASERS2 | 1456 | *1444 |  | 06.05.11.07.74.00.00.00 | TAP-106958 | TAP-119434 | [TAP-106958_STORMCHASERS2] ¦ Notcode-595/82 after SC Hotswap and Calibration | Issue | Done | Foundation - Storm Chasers 2 | STORMCHASERS2 | Child Task | User Stories | 386.8 | 218.4 | 386.8 | 464.16 | 168.4 | 100%
TAP-106958_TOOLSRULES | 1457 | *1444 |  | 06.05.11.07.77.00.00.00 | TAP-106958 | TAP-114920 | [TAP-106958_TOOLSRULES] ¦ [V4][ToolsRules] Esat V2 Linux startup script | User Story | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100%
TAP-106958_VISUAL | 1458 | *1444 |  | 06.05.11.07.78.00.00.00 | TAP-106958 | TAP-118402 | [TAP-106958_VISUAL] ¦ Investigate the Failures on develop(qnx710-x86_64) for UnitTest Report | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100%
TAP-106958_DRUSHTI | 1459 | *1444 |  | 06.05.11.07.79.00.00.00 | TAP-106958 | TAP-112409 | [TAP-106958_DRUSHTI] ¦ [Drushti][Spike][v4.0] Investigate Root Cause for Retry Calibration Redirecting Users to Surgery Mode Without Recalibration | User Story | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100%
TAP-106958_CASTLEBLACK | 1460 | *1444 |  | 06.05.11.07.80.00.00.00 | TAP-106958 | TAP-122936 | [TAP-106958_CASTLEBLACK] ¦ Update references.md | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100%
TAP-106958_EDISON | 1461 | *1444 |  | 06.05.11.07.81.00.00.00 | TAP-106958 | TAP-118588 | [TAP-106958_EDISON] ¦ Fix the cert locking logic in QNX x86 BSP | Issue | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100%
TAP-106958_SEAMLESS | 1462 | *1444 |  | 06.05.11.07.82.00.00.00 | TAP-106958 | TAP-118612 | [TAP-106958_SEAMLESS] ¦ Ethercat nodes deployment fails (frequent) | Issue | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100%
TAP-106958_OUTSIDEART | 1463 | *1444 |  | 06.05.11.07.83.00.00.00 | TAP-106958 | TAP-113464 | [TAP-106958_OUTSIDEART] ¦ Synchronize the NOTCODEs and Strings with Develop | Issue | Done | Outside ART | OUTSIDEART | Child Task | User Stories | 394.8 | 218.4 | 394.8 | 473.76 | 176.4 | 100%
TAP-116625 | 1464 | *13 |  | 06.05.11.08.00.00.00.00 |  | TAP-116625 | [TAP-116625] ¦ 🚩[V4.0][RC2][Cyber] Miscellaneous RC2 Blockers (ALL MERGES MUST HAVE OWN RAS TICKET!) | Feature | Accepted |  |  | Parent Task | User Stories | 31.5 | 6.5 | 1 hr | 1 hr | 25 | 20.63%
TAP-116625_ATLAS | 1465 | *1464 |  | 06.05.11.08.01.00.00.00 | TAP-116625 | TAP-119657 | [TAP-116625_ATLAS] ¦ [SPIKE]Investigate display config issues | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 31.5 | 6.5 | 31.5 | 37.8 | 25 | 100%
TAP-116625_HORIZON | 1466 | *1464 |  | 06.05.11.08.12.00.00.00 | TAP-116625 | TAP-125991 | [TAP-116625_HORIZON] ¦ [Horizon][Cart] Check potential 48Volt Requirements-Implementation Mismatch | User Story | In progress | Foundation - Horizon | HORIZON | Child Task | User Stories | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26%
TAP-116625_PLATFORMERS | 1467 | *1464 |  | 06.05.11.08.13.00.00.00 | TAP-116625 | TAP-125752 | [TAP-116625_PLATFORMERS] ¦ [V4.0][RC2][Platformers] Certmanager weird behavior when missing node id file | User Story | Open | Foundation - Platformers | PLATFORMERS | Child Task | User Stories | 53 | 6.5 | 53 | 63.6 | 46.5 | 12.26%
TAP-116625_EDISON | 1468 | *1464 |  | 06.05.11.08.14.00.00.00 | TAP-116625 | TAP-122243 | [TAP-116625_EDISON] ¦ Update the WolfSSH with the Provided Patch to Fix the Symlink Issue | User Story | Done | Shared Services - Edison | EDISON | Child Task | User Stories | 53 | 6.5 | 53 | 63.6 | 46.5 | 100%
TAP-87152 | 1469 | *3 |  | 06.06.01.01.00.00.00.00 |  | TAP-87152 | [TAP-87152] ¦ [V4.0][CTF EOL] Cart LED Driver Updates | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-87152_HORIZON | 1470 | *1469 |  | 06.06.01.01.01.00.00.00 | TAP-87152 | TAP-82987 | [TAP-87152_HORIZON] ¦ [CTF EOL] Cart LED driver application updates | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 10 | 10 | 10 | 12 | 0 | 100%
TAP-87151 | 1471 | *3 |  | 06.06.01.02.00.00.00.00 |  | TAP-87151 | [TAP-87151] ¦ [V4.0][CTF EOL] Requirements and Infrastructure | Feature | Done |  |  | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-87151_HORIZON | 1472 | *1471 |  | 06.06.01.02.01.00.00.00 | TAP-87151 | TAP-84259 | [TAP-87151_HORIZON] ¦ [CTF EOL] Set up staging branch and create bamboo build plan | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 29 | 29 | 29 | 34.8 | 0 | 100%
TAP-87153 | 1473 | *7 |  | 06.06.01.03.00.00.00.00 |  | TAP-87153 | [TAP-87153] ¦ [V4.0][CTF EOL] Integration and Solution Verification for CART | Feature | Done |  |  | Parent Task | User Stories | 45 | 45 | 1 hr | 1 hr | 0 | 100%
TAP-87153_HORIZON | 1474 | *1473 |  | 06.06.01.03.01.00.00.00 | TAP-87153 | TAP-83707 | [TAP-87153_HORIZON] ¦ [Horizon] CART rev1+rev2 integration test | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-87153_FRED | 1475 | *1473 |  | 06.06.01.03.02.00.00.00 | TAP-87153 | TAP-96687 | [TAP-87153_FRED] ¦ [Fred] CART: Deprecate Arm Cart Fan Check TD/TCs | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-87153_BART | 1476 | *1473 |  | 06.06.01.03.03.00.00.00 | TAP-87153 | TAP-96703 | [TAP-87153_BART] ¦ [v4.0][CTF EOL][BART] PL support for integration and verification | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 45 | 45 | 45 | 54 | 0 | 100%
TAP-87153_CLASSY1 | 1477 | *1473 |  | 06.06.01.03.30.00.00.00 | TAP-87153 | TAP-122720 | [TAP-87153_CLASSY1] ¦ [CLASSY] Extend the DDS domain cleanup management to cover static readers and writers | User Story | Done | Foundation - Classy 1 | CLASSY1 | Child Task | User Stories | 85 | 45 | 85 | 102 | 40 | 100%
TAP-82936 | 1478 | *3 |  | 06.06.01.04.00.00.00.00 |  | TAP-82936 | [TAP-82936] ¦ [V4.0][CTF EOL] Reliability and maintainability improvements | Feature | Done |  |  | Parent Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-82936_HORIZON | 1479 | *1478 |  | 06.06.01.04.01.00.00.00 | TAP-82936 | TAP-82984 | [TAP-82936_HORIZON] ¦ FSE application updates for the fan interface | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 17 | 17 | 17 | 20.4 | 0 | 100%
TAP-82936_FRED | 1480 | *1478 |  | 06.06.01.04.03.00.00.00 | TAP-82936 | TAP-77271 | [TAP-82936_FRED] ¦ [CTF EOL] Restructure Zynq Common HAL folders & decommission library_zynq | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 20 | 17 | 20 | 24 | 3 | 100%
TAP-87184 | 1481 | *7 |  | 06.06.01.05.00.00.00.00 |  | TAP-87184 | [TAP-87184] ¦ [V4.0][CTF EOL] Startup Changes and TPSC Application Upgrade for EOL | Feature | Done |  |  | Parent Task | User Stories | 31.5 | 31.5 | 1 hr | 1 hr | 0 | 100%
TAP-87184_HORIZON | 1482 | *1481 |  | 06.06.01.05.01.00.00.00 | TAP-87184 | TAP-82982 | [TAP-87184_HORIZON] ¦ TPSC application updates to read and manage hardware version | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 31.5 | 31.5 | 31.5 | 37.8 | 0 | 100%
TAP-92586 | 1483 | *3 |  | 06.06.01.06.00.00.00.00 |  | TAP-92586 | [TAP-92586] ¦ [V4.0][CTF EOL] Cart Application Upgrade for EOL | Feature | Done |  |  | Parent Task | User Stories | 27 | 27 | 1 hr | 1 hr | 0 | 100%
TAP-92586_FRED | 1484 | *1483 |  | 06.06.01.06.01.00.00.00 | TAP-92586 | TAP-82980 | [TAP-92586_FRED] ¦ Cart application update to manage hardware versions | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 27 | 27 | 27 | 32.4 | 0 | 100%
TAP-92586_HORIZON | 1485 | *1483 |  | 06.06.01.06.03.00.00.00 | TAP-92586 | TAP-82983 | [TAP-92586_HORIZON] ¦ Cart application updates for the fan interface | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 28 | 27 | 28 | 33.6 | 1 | 100%
TAP-93993 | 1486 | *5 |  | 06.06.01.07.00.00.00.00 |  | TAP-93993 | [TAP-93993] ¦ [V4.0][CTF EOL] FSE Application Upgrade for EOL | Feature | Done |  |  | Parent Task | User Stories | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-93993_HORIZON | 1487 | *1486 |  | 06.06.01.07.01.00.00.00 | TAP-93993 | TAP-82981 | [TAP-93993_HORIZON] ¦ FSE application update to read and manage hardware version | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-85050 | 1488 | *7 |  | 06.06.01.08.00.00.00.00 |  | TAP-85050 | [TAP-85050] ¦ [V4.0][CTF EOL] Finalize Documentation | Feature | Done |  |  | Parent Task | User Stories | 18 | 18 | 1 hr | 1 hr | 0 | 100%
TAP-85050_HORIZON | 1489 | *1488 |  | 06.06.01.08.01.00.00.00 | TAP-85050 | TAP-85059 | [TAP-85050_HORIZON] ¦ [Horizon] Prepare and Document SDR | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 18 | 18 | 18 | 21.6 | 0 | 100%
TAP-85050_BART | 1490 | *1488 |  | 06.06.01.08.02.00.00.00 | TAP-85050 | TAP-86745 | [TAP-85050_BART] ¦ [CTF EOL] Update zynq configuration and PS-PL interface document | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 18 | 18 | 18 | 21.6 | 0 | 100%
TAP-85050_FRED | 1491 | *1488 |  | 06.06.01.08.05.00.00.00 | TAP-85050 | TAP-104959 | [TAP-85050_FRED] ¦ [Fred] Take part in CTF EOL CDR | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 22 | 18 | 22 | 26.4 | 4 | 100%
TAP-82998 | 1492 | *3 |  | 06.06.01.09.00.00.00.00 |  | TAP-82998 | [TAP-82998] ¦ [V4.0][CTF EOL][Cyber] PL updates to support Embedded EOL Project | Feature | Done |  |  | Parent Task | User Stories | 56 | 56 | 1 hr | 1 hr | 0 | 100%
TAP-82998_BART | 1493 | *1492 |  | 06.06.01.09.01.00.00.00 | TAP-82998 | TAP-82999 | [TAP-82998_BART] ¦ Timestamp addition to PL for liveliness check support | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 56 | 56 | 56 | 67.2 | 0 | 100%
TAP-82998_HORIZON | 1494 | *1492 |  | 06.06.01.09.22.00.00.00 | TAP-82998 | TAP-79218 | [TAP-82998_HORIZON] ¦ [CTF EOL] Review PS-PL Interface Design | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 108.5 | 56 | 108.5 | 130.2 | 52.5 | 100%
TAP-82937 | 1495 | *3 |  | 06.06.01.10.00.00.00.00 |  | TAP-82937 | [TAP-82937] ¦ [V4.0][CTF EOL][Cyber] Manufacturing updates to support Embedded EOL Project | Feature | Done |  |  | Parent Task | User Stories | 30 | 30 | 1 hr | 1 hr | 0 | 100%
TAP-82937_ATLAS | 1496 | *1495 |  | 06.06.01.10.01.00.00.00 | TAP-82937 | TAP-83011 | [TAP-82937_ATLAS] ¦ Ability to load different FCT scripts based on the board variant | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 30 | 30 | 30 | 36 | 0 | 100%
TAP-82935 | 1497 | *3 |  | 06.06.01.11.00.00.00.00 |  | TAP-82935 | [TAP-82935] ¦ [V4.0][CTF EOL][Cyber] OS Updates to support Embedded EOL project | Feature | Done |  |  | Parent Task | User Stories | 7 | 7 | 1 hr | 1 hr | 0 | 100%
TAP-82935_ATLAS | 1498 | *1497 |  | 06.06.01.11.01.00.00.00 | TAP-82935 | TAP-111238 | [TAP-82935_ATLAS] ¦ Integrate new QNX final Cart/TPSC/FSE drivers into develop | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-70407 | 1499 | *3 |  | 06.06.01.12.00.00.00.00 |  | TAP-70407 | [TAP-70407] ¦ [V4.0][CTF EOL] Cart/TPSC/FSE continuing SW support for new boards spin off | Feature | Done |  |  | Parent Task | User Stories | 160 | 160 | 1 hr | 1 hr | 0 | 100%
TAP-70407_HORIZON | 1500 | *1499 |  | 06.06.01.12.01.01.00.00 | TAP-70407 | TAP-73850 | [TAP-70407_HORIZON] ¦ [CTF EOL] Identify Cart candidate functionality to be implemented in PL | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 160 | 160 | 160 | 192 | 0 | 100%
TAP-70407_MARVEL | 1501 | *1499 |  | 06.06.01.12.02.01.00.00 | TAP-70407 | TAP-74442 | [TAP-70407_MARVEL] ¦ [CTF EOL] Implement TPSC HAL layer | User Story | Done | Foundation - Marvel | MARVEL | Child Task | User Stories | 188 | 160 | 188 | 225.6 | 28 | 100%
TAP-70407_FRED | 1502 | *1499 |  | 06.06.01.12.02.05.00.00 | TAP-70407 | TAP-62056 | [TAP-70407_FRED] ¦ [CTF EOL][ACS Arch][Tech Debt] Remove loop delay from PollingColumnBrakeReader | User Story | Done | Foundation - Fred | FRED | Child Task | User Stories | 203 | 160 | 203 | 243.6 | 43 | 100%
TAP-70407_CASTLEBLACK | 1503 | *1499 |  | 06.06.01.12.02.07.00.00 | TAP-70407 | TAP-75421 | [TAP-70407_CASTLEBLACK] ¦ [CTF EOL] New SWIs for FSE and TPSC HAL | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 206 | 160 | 206 | 247.2 | 46 | 100%
TAP-70407_BART | 1504 | *1499 |  | 06.06.01.12.03.01.00.00 | TAP-70407 | TAP-75904 | [TAP-70407_BART] ¦ [v2.2][CTF EOL] Design I2C Changes for CTF bring-up | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 217 | 160 | 217 | 260.4 | 57 | 100%
TAP-70407_ATLAS | 1505 | *1499 |  | 06.06.01.12.10.00.00.00 | TAP-70407 | TAP-82683 | [TAP-70407_ATLAS] ¦ TAP-82682 - [Spike] SW support for new board spin off (SPRINT 6) | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 291 | 160 | 291 | 349.2 | 131 | 100%
TAP-87411 | 1506 | *3 |  | 06.06.01.13.00.00.00.00 |  | TAP-87411 | [TAP-87411] ¦ [V4.0][CTF EOL][Cyber] Prototype OS Updates to support Embedded EOL project | Feature | Done |  |  | Parent Task | User Stories | 26 | 26 | 1 hr | 1 hr | 0 | 100%
TAP-87411_ATLAS | 1507 | *1506 |  | 06.06.01.13.01.00.00.00 | TAP-87411 | TAP-82941 | [TAP-87411_ATLAS] ¦ Tool to read version information from PL in Embedded BSP | User Story | Done | Foundation - Atlas | ATLAS | Child Task | User Stories | 26 | 26 | 26 | 31.2 | 0 | 100%
TAP-97620 | 1508 | *7 |  | 06.06.01.14.00.00.00.00 |  | TAP-97620 | [TAP-97620] ¦ [V4.0][CTF EOL] Integration and Solution Verification TPSC | Feature | Done |  |  | Parent Task | User Stories | 13 | 13 | 1 hr | 1 hr | 0 | 100%
TAP-97620_HORIZON | 1509 | *1508 |  | 06.06.01.14.01.00.00.00 | TAP-97620 | TAP-101690 | [TAP-97620_HORIZON] ¦ [Horizon] TPSC: Add PL Liveliness Check TD/TCs | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 13 | 13 | 13 | 15.6 | 0 | 100%
TAP-97620_BART | 1510 | *1508 |  | 06.06.01.14.05.00.00.00 | TAP-97620 | TAP-83014 | [TAP-97620_BART] ¦ [CTF EOL]PL integration support | User Story | Done | Foundation - Bart | BART | Child Task | User Stories | 21 | 13 | 21 | 25.2 | 8 | 100%
TAP-106789 | 1511 | *7 |  | 06.06.01.15.00.00.00.00 |  | TAP-106789 | [TAP-106789] ¦ [V4.0][RC1][CTF EOL] Integration and Solution Verification FSE | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-106789_HORIZON | 1512 | *1511 |  | 06.06.01.15.01.00.00.00 | TAP-106789 | TAP-101725 | [TAP-106789_HORIZON] ¦ [Horizon] Add PCBA rev1+rev2 support for FSE EIN_TESTs | User Story | Done | Foundation - Horizon | HORIZON | Child Task | User Stories | 10 | 10 | 10 | 12 | 0 | 100%

## Log
DataTimeStamp | Event | Data | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
2024-08-28 17:19 | Start: | DANSAP Formatter, v1.6 | TAP-106789_HORIZON |  | TAP-95817
2024-08-28 17:19 | Input File: | Sentinel_Hugo_Produc_240802_1103 (Adam + with RefinementLevel).xls | TAP-106789_HORIZON |  | TAP-94622
2024-08-28 17:19 | Output File: | 2024-06-18_19-58-51_Project_Import_DS_86.xlsx | TAP-106789_HORIZON |  | TAP-94625
2024-08-28 17:19 | Info | Team Mapping for Jira Project converter - Copy2.xlsx | TAP-106789_HORIZON |  | TAP-96038
2024-08-28 17:19 | Processing: | Jira Data: Rows: 6601, Cols: 16 | TAP-106789_HORIZON |  | TAP-113927
2024-08-28 17:24 | Result: | Project Data: Rows: 1512, Cols: 20 | TAP-106789_HORIZON |  | TAP-114710
2024-08-28 17:24 | Processing Complete: | 314.5559959411621 seconds | TAP-106789_HORIZON |  | TAP-113325
|  |  | TAP-106789_HORIZON |  | TAP-114167
|  |  | TAP-106789_HORIZON |  | TAP-114725
|  |  | TAP-106789_HORIZON |  | TAP-113935
|  |  | TAP-106789_HORIZON |  | TAP-113936
|  |  | TAP-106789_HORIZON |  | TAP-112047
|  |  | TAP-106789_HORIZON |  | TAP-125115
|  |  | TAP-106789_HORIZON |  | TAP-125124
|  |  | TAP-106789_HORIZON |  | TAP-125261
|  |  | TAP-106789_HORIZON |  | TAP-125786
|  |  | TAP-106789_HORIZON |  | TAP-125128
|  |  | TAP-106789_HORIZON |  | TAP-113857
|  |  | TAP-106789_HORIZON |  | TAP-88107
|  |  | TAP-106789_HORIZON |  | TAP-88093
|  |  | TAP-106789_HORIZON | TAP-84495
|  |  | TAP-106789_HORIZON |  | TAP-84495
|  |  | TAP-106789_HORIZON | TAP-116701
|  |  | TAP-106789_HORIZON |  | TAP-106865
|  |  | TAP-106789_HORIZON | TAP-58661
|  |  | TAP-106789_HORIZON |  | TAP-73773
|  |  | TAP-106789_HORIZON |  | TAP-86143
|  |  | TAP-106789_HORIZON |  | TAP-79180
|  |  | TAP-106789_HORIZON | TAP-81765
|  |  | TAP-106789_HORIZON | TAP-97063
|  |  | TAP-106789_HORIZON |  | TAP-97079
|  |  | TAP-106789_HORIZON | TAP-94795

## Summary
Resource Names | Sum FDR
ICONICS | 310
CLASSY2 | 4467
SEAMLESS | 710
CLASSY1 | 4425
STELLARS | 364
PIXELPOETS | 3009
BOOSTERS | 4192
MARVEL | 425
SCRUMBLEDORES | 2165
ORGANELLES | 971
JACOBIANS | 1942
ATLAS | 7260
ELECTRON | 35
STORMCHASERS2 | 4045
PLATFORMERS | 6620
DRUSHTI | 1034
MIRAGE | 21
TEAMBD | 3024
HORIZON | 6426
SOUPERTROOPERS | 1089
EDISON | 5146
SIRIUS | 1068
I2E | 1893
SUNRISERS | 1297
ASTRANPSVALIDATORS | 528
CROCNROLL | 859
BUGHUNTERS | 535
DOCUMENTOWNERS | 157
ANGLERS | 0
FRED | 6751
CLASSY | 463
STORMCHASERS1 | 3217
HAPPYJAWS | 179
PUPPETEERS | 137
REFRACT | 142
TOOLSRULES | 3219
BUILDERS | 1367
ASTRANPSDEVELOPERS | 1016
VISUAL | 4724
STORMCHASERS | 425
TRIPLETEA | 943
ROMULUS | 391
REMUS | 325
BART | 1745
SLEEPWALKERS | 378
CASTLEBLACK | 2078
COSSACKS | 3520
REFLECT | 106
INBETWEENERS | 491
KTBR | 24
SWIFT | 72
FLOWRIDERS | 56.5
NEXUS | 178
INFRAWARRIORS | 189
FUSION | 553
MACHETE | 613
POWERSTORMERS | 514
TECHTITANS | 179
GPT1 | 60
PROBABLYSTILLEMBED | 70
FOUNDATION | 37.7
SHAREDSERVICES | 57.4
COREINSTRUMENTS | 225.4
OUTSIDEART | 394.8
Total FDR: | 2005688.95