## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete
TAP-121866 | 1 |  | 5,21,20,2,40,39,38,41,3,17 | 01.01.01.00.00.00.00.00 |  | TAP-121866 | [TAP-121866] ¦ [PnP][UFSW] Integration of Instrument Workflow Managers after removing build flag in develop | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121861 | 2 | 1 |  | 01.02.01.00.00.00.00.00 |  | TAP-121861 | [TAP-121861] ¦ [PnP][UFSW] Endoscope Workflow Manager Migration | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121857 | 3 | 1 | 12 | 01.02.02.00.00.00.00.00 |  | TAP-121857 | [TAP-121857] ¦ [PnP][UFSW] Croc Workflow Manager Migration | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121937 | 4 | 27,28 | 13 | 01.02.03.00.00.00.00.00 |  | TAP-121937 | [TAP-121937] ¦ [PnP][GUI] Isolate Language-related files for modularization | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121858 | 5 | 1 |  | 01.02.04.00.00.00.00.00 |  | TAP-121858 | [TAP-121858] ¦ [PnP][UFSW] Single Use Instrument Workflow Manager Migration | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121886 | 6 |  | 13,27,28 | 01.02.05.00.00.00.00.00 |  | TAP-121886 | [TAP-121886] ¦ [PnP][GUI] Isolate Instrument Indicator components to prepare for phase 2 | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 6 | 3 | 1 hr | 1 hr | 3 | 50%
TAP-114819 | 7 | 16 | 12 | 01.03.01.00.00.00.00.00 |  | TAP-114819 | [TAP-114819] ¦ [PnP] GUI - Pre Planning PnP Interface | Feature | Done | GUI | GUI | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-113463 | 8 | 16 | 12 | 01.03.02.00.00.00.00.00 |  | TAP-113463 | [TAP-113463] ¦ [PnP] GUI Testing Framework Improvements | Feature | Done | GUI | GUI | Parent Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-113896 | 9 | 16 | 13 | 01.03.03.00.00.00.00.00 |  | TAP-113896 | [TAP-113896] ¦ [PnP] GUI - SWI Updates Part 1 | Feature | Done | GUI | GUI | Parent Task | User Stories | 24 | 24 | 1 hr | 1 hr | 0 | 100%
TAP-115384 | 10 | 37 |  | 01.03.04.00.00.00.00.00 |  | TAP-115384 | [TAP-115384] ¦ [PnP][UFSW] Migrate to the DR Arch - Containers | Feature | Done | UFSW | UFSW | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-114464 | 11 | 16 | 13 | 01.03.05.00.00.00.00.00 |  | TAP-114464 | [TAP-114464] ¦ [PnP] GUI - SWI Updates Part 2 | Feature | Done | GUI | GUI | Parent Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-114992 | 12 | 7,16,17,8,3,38,39,40,41,13,29,46 | 10 | 01.03.06.00.00.00.00.00 |  | TAP-114992 | [TAP-114992] ¦ [PnP][UFSW] Migrate to the DR ACA Assembly Workflow Manager | Feature | Done | UFSW | UFSW | Parent Task | User Stories | 28 | 28 | 1 hr | 1 hr | 0 | 100%
TAP-103900 | 13 | 9,18,19,27,23,6,4,28,22,25,24,26 | 12 | 01.03.07.00.00.00.00.00 |  | TAP-103900 | [TAP-103900] ¦ [Arch][PnP] GUI - Migration of SWIs to MVC - Prep and Initial Candidates | Feature | Done | GUI | GUI | Parent Task | User Stories | 39 | 39 | 1 hr | 1 hr | 0 | 100%
TAP-114890 | 14 |  | 10 | 01.03.08.00.00.00.00.00 |  | TAP-114890 | [TAP-114890] ¦ [PnP][UFSW] Migrate the Manual Mode STM to the Don't Reboot architecture | Feature | Done | UFSW | UFSW | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-115011 | 15 |  | 10 | 01.03.09.00.00.00.00.00 |  | TAP-115011 | [TAP-115011] ¦ [PnP][UFSW] Migrate to the DR Bedside User Commands and Registration Workflow Managers | Feature | Done | UFSW | UFSW | Parent Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-125001 | 16 |  | 12,7,8,9,11 | 01.04.01.00.00.00.00.00 |  | TAP-125001 | [TAP-125001] ¦ [PnP][GUI] Rollover for PI14 PnP GUI work | Feature | Accepted | GUI | GUI | Parent Task | User Stories | 29 | 11 | 1 hr | 1 hr | 18 | 37.93%
TAP-124981 | 17 | 1 | 12 | 01.04.02.00.00.00.00.00 |  | TAP-124981 | [TAP-124981] ¦ [PnP][UFSW] PnP Set up For Don't Reboot SRA Refactor | Feature | Accepted | UFSW | UFSW | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-121911 | 18 | 27,28 | 13 | 01.04.03.00.00.00.00.00 |  | TAP-121911 | [TAP-121911] ¦ [PnP][GUI] Isolate Notification Indicator | Feature | Accepted | GUI | GUI | Parent Task | User Stories | 18 | 11 | 1 hr | 1 hr | 7 | 61.11%
TAP-121904 | 19 | 27,28 | 13 | 01.04.04.00.00.00.00.00 |  | TAP-121904 | [TAP-121904] ¦ [PnP][GUI] Isolate vision system components | Feature | Accepted | GUI | GUI | Parent Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 0%
TAP-121856 | 20 |  |  | 01.04.05.00.00.00.00.00 |  | TAP-121856 | [TAP-121856] ¦ [PnP][UFSW] LigaSure Workflow Manager Migration | Feature | In progress | UFSW | UFSW | Parent Task | User Stories | 64 | 23 | 1 hr | 1 hr | 41 | 35.94%
TAP-121860 | 21 | 1 |  | 01.04.06.00.00.00.00.00 |  | TAP-121860 | [TAP-121860] ¦ [PnP][UFSW] Core Wristed Instruments Workflow Manager Migration | Feature | Accepted | UFSW | UFSW | Parent Task | User Stories | 41 | 20 | 1 hr | 1 hr | 21 | 48.78%
TAP-121901 | 22 | 27,28 | 13 | 01.05.01.00.00.00.00.00 |  | TAP-121901 | [TAP-121901] ¦ [PnP][GUI] Isolate instrument and ergonomic settings | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121891 | 23 | 27,28 | 13 | 01.05.02.00.00.00.00.00 |  | TAP-121891 | [TAP-121891] ¦ [PnP][GUI] Isolate startup and calibration components | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-121921 | 24 | 27,28 | 13 | 01.05.03.00.00.00.00.00 |  | TAP-121921 | [TAP-121921] ¦ [PnP][GUI] Isolate ORTI process and display manager | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121927 | 25 | 27,28 | 13 | 01.05.04.00.00.00.00.00 |  | TAP-121927 | [TAP-121927] ¦ [PnP][GUI] Isolate S3D and STS process and display manager | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121873 | 26 | 27,28 | 13 | 01.05.05.00.00.00.00.00 |  | TAP-121873 | [TAP-121873] ¦ [PnP][GUI][Test] Implement Semi Automated SSR Coverage | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121871 | 27 | 6 | 13,18,19,23,22,24,4,25,26 | 01.05.06.00.00.00.00.00 |  | TAP-121871 | [TAP-121871] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 1 | Feature | Accepted | GUI | GUI | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121885 | 28 | 6 | 13,18,19,23,22,24,4,25,26 | 01.05.07.00.00.00.00.00 |  | TAP-121885 | [TAP-121885] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 2 | Feature | PROPOSED | GUI | GUI | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-125200 | 29 |  | 12 | 01.05.08.00.00.00.00.00 |  | TAP-125200 | [TAP-125200] ¦ [PnP][GUI] Create Product Architecture with Interface Specifications for Modularized Instrument Software Development | Feature | Accepted | GUI | GUI | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-129535 | 30 |  | 31,35 | 02.01.01.00.00.00.00.00 |  | TAP-129535 | [TAP-129535] ¦ [PnP][v4.2] Migrate embedded PnP updates to v4.2 - Adv Instrument ART | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-126357 | 31 | 30 | 34 | 02.01.02.00.00.00.00.00 |  | TAP-126357 | [TAP-126357] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Desired Data Pipeline | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 34 | 0 | 1 hr | 1 hr | 34 | 0%
TAP-130040 | 32 |  |  | 02.01.03.00.00.00.00.00 |  | TAP-130040 | [TAP-130040] ¦ [PnP][Zenith][Embedded] SRA HAL TC Updates Due to Data Pipeline Refactor | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-85741 | 33 | 34,63,35,65 |  | 02.02.01.00.00.00.00.00 |  | TAP-85741 | [TAP-85741] ¦ [PnP][Zenith][Embedded] Actual Transport and Application Layer Implementation and Memory Manager IDU Refactor | Feature | Done | Embedded | EMBEDDED | Parent Task | User Stories | 98 | 98 | 1 hr | 1 hr | 0 | 100%
TAP-121915 | 34 | 42,60,59,31,62 | 33 | 02.03.01.00.00.00.00.00 |  | TAP-121915 | [TAP-121915] ¦ [PnP][Zenith][Embedded] Desired Parameter Pipeline from SRA HAL to Instrumentation | Feature | Accepted | Embedded | EMBEDDED | Parent Task | User Stories | 53 | 8 | 1 hr | 1 hr | 45 | 15.09%
TAP-126005 | 35 | 30 | 33 | 02.03.02.00.00.00.00.00 |  | TAP-126005 | [TAP-126005] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Actual Data Pipeline | Feature | Accepted | Embedded | EMBEDDED | Parent Task | User Stories | 48 | 20 | 1 hr | 1 hr | 28 | 41.67%
TAP-99224 | 36 |  | 46 | 03.01.01.00.00.00.00.00 |  | TAP-99224 | [TAP-99224] ¦ [PnP] [Architecture] [Enabler][Controls] EIN-SWI-176 Croc Controller Refactor | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-103935 | 37 |  | 10 | 04.01.01.00.00.00.00.00 |  | TAP-103935 | [TAP-103935] ¦ [PnP][Arch][UFSW] MSC - Migrate Energy STM to Aux Fn Manager | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 37 | 9 | 1 hr | 1 hr | 28 | 24.32%
TAP-121902 | 38 | 1 | 12 | 04.02.01.00.00.00.00.00 |  | TAP-121902 | [TAP-121902] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Core Instruments | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121900 | 39 | 1 | 12 | 04.02.02.00.00.00.00.00 |  | TAP-121900 | [TAP-121900] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Croc Instruments | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121898 | 40 | 1 | 12 | 04.02.03.00.00.00.00.00 |  | TAP-121898 | [TAP-121898] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Ligasure Instruments | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-121905 | 41 | 1 | 12 | 04.02.04.00.00.00.00.00 |  | TAP-121905 | [TAP-121905] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Single Use Instruments | Feature | PROPOSED | UFSW | UFSW | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121922 | 42 | 56 | 34 | 04.03.01.00.00.00.00.00 |  | TAP-121922 | [TAP-121922] ¦ [PnP][Zenith][Embedded] Implement Instrumentation Latching within the SRA HAL/BSCM | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-103932 | 43 |  |  | 04.04.01.00.00.00.00.00 |  | TAP-103932 | [TAP-103932] ¦ [PnP][Arch][UFSW] Migrate IX STM Instrument Attachment to PnP SWIs | Feature | Done | UFSW | UFSW | Parent Task | User Stories | 51 | 51 | 1 hr | 1 hr | 0 | 100%
TAP-103933 | 44 |  |  | 04.04.02.00.00.00.00.00 |  | TAP-103933 | [TAP-103933] ¦ [PnP][Arch][UFSW] Migrate IX STM Internal/External Calibration to PnP SWIs | Feature | Done | UFSW | UFSW | Parent Task | User Stories | 18 | 18 | 1 hr | 1 hr | 0 | 100%
TAP-114308 | 45 | 60,59 | 46 | 04.04.03.00.00.00.00.00 |  | TAP-114308 | [TAP-114308] ¦ [PnP][Controls] Migration of IDU Controller SWIs | Feature | Done | Controls | CONTROLS | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-114299 | 46 | 45,50,51,36 | 12 | 04.04.04.00.00.00.00.00 |  | TAP-114299 | [TAP-114299] ¦ [PnP][Controls] Setup IDU Controller Container | Feature | Done | Controls | CONTROLS | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-121913 | 47 | 49,60,59 | 50,51 | 04.05.01.00.00.00.00.00 |  | TAP-121913 | [TAP-121913] ¦ [PnP][Controls] IDU Actuator Controller - Migration | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-121912 | 48 | 49,60,59 | 50,51 | 04.05.02.00.00.00.00.00 |  | TAP-121912 | [TAP-121912] ¦ [PnP][Controls] IDU Actuator Monitor - Migration | Feature | Accepted | Controls | CONTROLS | Parent Task | User Stories | 39 | 8 | 1 hr | 1 hr | 31 | 20.51%
TAP-121925 | 49 | 59,60 | 52,58,47,48,53,54,57 | 04.05.03.00.00.00.00.00 |  | TAP-121925 | [TAP-121925] ¦ [PnP][Controls] IDU Controller SysIL Verification - Migration | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 21 | 0 | 1 hr | 1 hr | 21 | 0%
TAP-121923 | 50 | 52,58,47,48,53,54,60,59,57 | 46 | 04.05.04.00.00.00.00.00 |  | TAP-121923 | [TAP-121923] ¦ [PnP][Controls] IDU Controller Debug Logging - Migration | Feature | Accepted | Controls | CONTROLS | Parent Task | User Stories | 5 | 3 | 1 hr | 1 hr | 2 | 60%
TAP-121920 | 51 | 52,58,47,48,53,54,60,59,57 | 46 | 04.05.05.00.00.00.00.00 |  | TAP-121920 | [TAP-121920] ¦ [PnP][Controls] IDU Controller Error Handler - Migration | Feature | Accepted | Controls | CONTROLS | Parent Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-121919 | 52 | 49,60,59 | 50,51 | 04.05.06.00.00.00.00.00 |  | TAP-121919 | [TAP-121919] ¦ [PnP][Controls] IDU Controller "Workflow Manager" - Migration | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 2 | 0 | 1 hr | 1 hr | 2 | 0%
TAP-121910 | 53 | 49,60,59 | 50,51 | 04.05.07.00.00.00.00.00 |  | TAP-121910 | [TAP-121910] ¦ [PnP][Controls] IDU Actuator Output Processing - Migration | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121908 | 54 | 49,60,59 | 50,51 | 04.05.08.00.00.00.00.00 |  | TAP-121908 | [TAP-121908] ¦ [PnP][Controls] IDU Actuator Input Processing - Migration | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121906 | 55 | 64 | 56 | 04.05.09.00.00.00.00.00 |  | TAP-121906 | [TAP-121906] ¦ [PnP][Arch][Enabler][Embedded] Integrate BSCM with Subsystems | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-97909 | 56 | 55,61 | 42 | 04.05.10.00.00.00.00.00 |  | TAP-97909 | [TAP-97909] ¦ [PnP][Zenith][Embedded] Implement Bedside Config Manager | Feature | Accepted | Embedded | EMBEDDED | Parent Task | User Stories | 16 | 0 | 1 hr | 1 hr | 16 | 0%
TAP-126766 | 57 | 49,60,59 | 50,51,58 | 04.05.11.00.00.00.00.00 |  | TAP-126766 | [TAP-126766] ¦ [PnP][Controls] Instrument Controller - Migration - Test Work | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 19 | 7 | 1 hr | 1 hr | 12 | 36.84%
TAP-121916 | 58 | 49,60,59,57 | 50,51 | 04.05.12.00.00.00.00.00 |  | TAP-121916 | [TAP-121916] ¦ [PnP][Controls] Instrument Controller - Migration - Dev Work | Feature | Accepted | Controls | CONTROLS | Parent Task | User Stories | 20 | 7 | 1 hr | 1 hr | 13 | 35%
TAP-121926 | 59 |  | 60,49,45,54,53,48,47,34,58,52,51,50,57 | 04.05.13.00.00.00.00.00 |  | TAP-121926 | [TAP-121926] ¦ [PnP][IDU][Controls] Merge to Develop Behind Build Flag | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121917 | 60 | 59 | 45,54,53,48,47,34,58,52,51,50,49,57 | 04.05.14.00.00.00.00.00 |  | TAP-121917 | [TAP-121917] ¦ [PnP][IDU][Controls] Preliminary Integration of M-IRR and Newton | Feature | PROPOSED | Controls | CONTROLS | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-94827 | 61 |  | 56 | 04.05.15.00.00.00.00.00 |  | TAP-94827 | [TAP-94827] ¦ [PnP][Architecture][Embedded] Update Tools to new Instrument Interfaces | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-122018 | 62 |  | 34 | 04.05.16.00.00.00.00.00 |  | TAP-122018 | [TAP-122018] ¦ [PnP][Arch][Test]HIL Testing for Embedded IDU Testing | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-84434 | 63 |  | 33 | 04.05.17.00.00.00.00.00 |  | TAP-84434 | [TAP-84434] ¦ [PnP][Arch][Enabler][Embedded] Create Infrastructure - Data Aggregator Interfaces | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121929 | 64 |  | 55 | 04.05.18.00.00.00.00.00 |  | TAP-121929 | [TAP-121929] ¦ [PnP][Zenith][Embedded] System Integration Testing for Controllers, IDU Primary, SRA HAL/BSCM | Feature | PROPOSED | Embedded | EMBEDDED | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-97775 | 65 |  | 33 | 04.05.19.00.00.00.00.00 |  | TAP-97775 | [TAP-97775] ¦ [PnP][V5.0][Embedded] GECAT for Instruments Data Transportation: S-function interfaces - Foundation Support | Feature | Accepted | Embedded | EMBEDDED | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%

## Log
DataTimeStamp | Event | Data | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
2024-09-04 21:41 | Start: | DANSAP Formatter, v1.6 | TAP-97775 |  | TAP-121864
2024-09-04 21:41 | Input File: | PnP_Categorized_240904_1601 (discipline updated).xls | TAP-97775 |  | TAP-121864
2024-09-04 21:41 | Output File: | 2024-06-18_19-58-51_Project_Import_DS_90.xlsx | TAP-97775 | TAP-121864
2024-09-04 21:41 | Info |  | TAP-97775 | TAP-121864
2024-09-04 21:41 | Processing: | Jira Data: Rows: 497, Cols: 16 | TAP-97775 | TAP-114818
2024-09-04 21:41 | Result: | Project Data: Rows: 65, Cols: 20 | TAP-97775 | TAP-121864
2024-09-04 21:41 | Processing Complete: | 12.03395962715149 seconds | TAP-97775 | TAP-121864
|  |  | TAP-97775 | TAP-103479
|  |  | TAP-97775 |  | TAP-121864
|  |  | TAP-97775 |  | TAP-121864
|  |  | TAP-97775 | TAP-94814
|  |  | TAP-97775 | TAP-106649

## Summary
Resource Names | Sum FDR
Total FDR: | 0