## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete
TAP-121866 | 1 |  | 9,41,39,3,78,76,74,80,5,33 | 01.01.01.00.00.00.00.00 |  | TAP-121866 | [TAP-121866] ¦ [PnP][UFSW] Integration of Instrument Workflow Managers after removing build flag in develop | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121866 | 2 | 1 |  | 01.01.01.01.00.00.00.00 | TAP-121866 | TAP-121879 | [TAP-121866] ¦ [PnP][UFSW] Integration of Instrument Workflow Managers after removing build flag in develop | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 40 | 70 | 0 | 0%
TAP-121861 | 3 | 1 |  | 01.02.01.00.00.00.00.00 |  | TAP-121861 | [TAP-121861] ¦ [PnP][UFSW] Endoscope Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121861 | 4 | 3 |  | 01.02.01.01.00.00.00.00 | TAP-121861 | TAP-121877 | [TAP-121861] ¦ [PnP][UFSW] Endoscope Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 30 | 0 | 20 | 40 | 30 | 0%
TAP-121857 | 5 | 1 | 23 | 01.02.02.00.00.00.00.00 |  | TAP-121857 | [TAP-121857] ¦ [PnP][UFSW] Croc Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121857 | 6 | 5 |  | 01.02.02.01.00.00.00.00 | TAP-121857 | TAP-121874 | [TAP-121857] ¦ [PnP][UFSW] Croc Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 40 | 100 | 0 | 0%
TAP-121937 | 7 | 53,55 | 25 | 01.02.03.00.00.00.00.00 |  | TAP-121937 | [TAP-121937] ¦ [PnP][GUI] Isolate Language-related files for modularization | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121937_GUI | 8 | 7 |  | 01.02.03.01.00.00.00.00 | TAP-121937 | TAP-114836 | [TAP-121937_GUI] ¦ [PnP] GUI - SWI Updates: Language | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 5 | 10 | 0 | 0%
TAP-121858 | 9 | 1 |  | 01.02.04.00.00.00.00.00 |  | TAP-121858 | [TAP-121858] ¦ [PnP][UFSW] Single Use Instrument Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121858 | 10 | 9 |  | 01.02.04.01.00.00.00.00 | TAP-121858 | TAP-121875 | [TAP-121858] ¦ [PnP][UFSW] Single Use Instrument Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 40 | 70 | 0 | 0%
TAP-121886 | 11 |  | 25,53,55 | 01.02.05.00.00.00.00.00 |  | TAP-121886 | [TAP-121886] ¦ [PnP][GUI] Isolate Instrument Indicator components to prepare for phase 2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 6 | 3 | 1 hr | 1 hr | 3 | 50%
TAP-121886_GUI | 12 | 11 |  | 01.02.05.01.00.00.00.00 | TAP-121886 | TAP-114824 | [TAP-121886_GUI] ¦ [PnP] [GUI] - SWI Updates: Surgery Header | User Story | Groomed | GUI | GUI | Child Task | User Stories | 6 | 3 | 30 | 60 | 3 | 50%
TAP-114819 | 13 | 31 | 23 | 01.03.01.00.00.00.00.00 |  | TAP-114819 | [TAP-114819] ¦ [PnP] GUI - Pre Planning PnP Interface | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-114819_GUI | 14 | 13 |  | 01.03.01.01.00.00.00.00 | TAP-114819 | TAP-112001 | [TAP-114819_GUI] ¦ [Spike][v5.0][GUI][PnP] Investigate adding new instruments on runtime part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-113463 | 15 | 31 | 23 | 01.03.02.00.00.00.00.00 |  | TAP-113463 | [TAP-113463] ¦ [PnP] GUI Testing Framework Improvements | Feature | Done |  |  | Parent Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-113463_GUI | 16 | 15 |  | 01.03.02.01.00.00.00.00 | TAP-113463 | TAP-114721 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Must] Plan new test framework architecture | User Story | Done | GUI | GUI | Child Task | User Stories | 31 | 31 | 1 hr | 1 hr | 0 | 100%
TAP-113896 | 17 | 31 | 25 | 01.03.03.00.00.00.00.00 |  | TAP-113896 | [TAP-113896] ¦ [PnP] GUI - SWI Updates Part 1 | Feature | Done |  |  | Parent Task | User Stories | 24 | 24 | 1 hr | 1 hr | 0 | 100%
TAP-113896_GUI | 18 | 17 |  | 01.03.03.01.00.00.00.00 | TAP-113896 | TAP-114462 | [TAP-113896_GUI] ¦ [PnP][zenith] GUI - SWI Updates: Common SWI | User Story | Done | GUI | GUI | Child Task | User Stories | 24 | 24 | 1 hr | 1 hr | 0 | 100%
TAP-115384 | 19 | 72 |  | 01.03.04.00.00.00.00.00 |  | TAP-115384 | [TAP-115384] ¦ [PnP][UFSW] Migrate to the DR Arch - Containers | Feature | Done |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-115384_UFSW | 20 | 19 |  | 01.03.04.01.00.00.00.00 | TAP-115384 | TAP-115874 | [TAP-115384_UFSW] ¦ [SPIKE] [zenith] Prototype container strategy for PnP vs Dont reboot | User Story | Done | UFSW | UFSW | Child Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-114464 | 21 | 31 | 25 | 01.03.05.00.00.00.00.00 |  | TAP-114464 | [TAP-114464] ¦ [PnP] GUI - SWI Updates Part 2 | Feature | Done |  |  | Parent Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-114464_GUI | 22 | 21 |  | 01.03.05.01.00.00.00.00 | TAP-114464 | TAP-113881 | [TAP-114464_GUI] ¦ [PnP] [GUI] - SWI Updates: System Configuration | User Story | Done | GUI | GUI | Child Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-114992 | 23 | 13,31,33,15,5,74,76,78,80,25,57,90 | 19 | 01.03.06.00.00.00.00.00 |  | TAP-114992 | [TAP-114992] ¦ [PnP][UFSW] Migrate to the DR ACA Assembly Workflow Manager | Feature | Done |  |  | Parent Task | User Stories | 28 | 28 | 1 hr | 1 hr | 0 | 100%
TAP-114992_UFSW | 24 | 23 |  | 01.03.06.01.00.00.00.00 | TAP-114992 | TAP-115128 | [TAP-114992_UFSW] ¦ [PnP][UFSW] Prototype Design/Translators/Interface for SRA Teleop ACA Assembly Workflow Manager Re-Factor | User Story | Done | UFSW | UFSW | Child Task | User Stories | 28 | 28 | 1 hr | 1 hr | 0 | 100%
TAP-103900 | 25 | 17,35,37,53,45,11,7,55,43,49,47,51 | 23 | 01.03.07.00.00.00.00.00 |  | TAP-103900 | [TAP-103900] ¦ [Arch][PnP] GUI - Migration of SWIs to MVC - Prep and Initial Candidates | Feature | Done |  |  | Parent Task | User Stories | 39 | 39 | 1 hr | 1 hr | 0 | 100%
TAP-103900_GUI | 26 | 25 |  | 01.03.07.02.00.00.00.00 | TAP-103900 | TAP-104269 | [TAP-103900_GUI] ¦ [Enabler][v5.0][PnP][PixelPoets] How will refactoring impact the translation tool | User Story | Done | GUI | GUI | Child Task | User Stories | 39 | 39 | 1 hr | 1 hr | 0 | 100%
TAP-114890 | 27 |  | 19 | 01.03.08.00.00.00.00.00 |  | TAP-114890 | [TAP-114890] ¦ [PnP][UFSW] Migrate the Manual Mode STM to the Don't Reboot architecture | Feature | Done |  |  | Parent Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-114890_UFSW | 28 | 27 |  | 01.03.08.01.00.00.00.00 | TAP-114890 | TAP-115076 | [TAP-114890_UFSW] ¦ [PnP][UFSW] Implement the Column, Insertion Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 29 | 29 | 1 hr | 1 hr | 0 | 100%
TAP-115011 | 29 |  | 19 | 01.03.09.00.00.00.00.00 |  | TAP-115011 | [TAP-115011] ¦ [PnP][UFSW] Migrate to the DR Bedside User Commands and Registration Workflow Managers | Feature | Done |  |  | Parent Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-115011_UFSW | 30 | 29 |  | 01.03.09.01.00.00.00.00 | TAP-115011 | TAP-115382 | [TAP-115011_UFSW] ¦ [zenith] Complete Initial Design for the Bedside Registration Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 17 | 17 | 1 hr | 1 hr | 0 | 100%
TAP-125001 | 31 |  | 23,13,15,17,21 | 01.04.01.00.00.00.00.00 |  | TAP-125001 | [TAP-125001] ¦ [PnP][GUI] Rollover for PI14 PnP GUI work | Feature | Accepted |  |  | Parent Task | User Stories | 29 | 11 | 1 hr | 1 hr | 18 | 37.93%
TAP-125001_GUI | 32 | 31 |  | 01.04.01.01.00.00.00.00 | TAP-125001 | TAP-125185 | [TAP-125001_GUI] ¦ [PnP][GUI][Fusion] Technical Design Review for Staging Branch Changes and Merge Strategy Approval | User Story | In progress | GUI | GUI | Child Task | User Stories | 29 | 11 | 1 hr | 1 hr | 18 | 37.93%
TAP-124981 | 33 | 1 | 23 | 01.04.02.00.00.00.00.00 |  | TAP-124981 | [TAP-124981] ¦ [PnP][UFSW] PnP Set up For Don't Reboot SRA Refactor | Feature | Accepted |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-124981_UFSW | 34 | 33 |  | 01.04.02.01.00.00.00.00 | TAP-124981 | TAP-125666 | [TAP-124981_UFSW] ¦ Initial design for the Local Power Constraints Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-121911 | 35 | 53,55 | 25 | 01.04.03.00.00.00.00.00 |  | TAP-121911 | [TAP-121911] ¦ [PnP][GUI] Isolate Notification Indicator | Feature | Accepted |  |  | Parent Task | User Stories | 18 | 11 | 1 hr | 1 hr | 7 | 61.11%
TAP-121911_GUI | 36 | 35 |  | 01.04.03.01.00.00.00.00 | TAP-121911 | TAP-114830 | [TAP-121911_GUI] ¦ [PnP] [GUI] - SWI Updates: Notification Indicator Part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 18 | 11 | 1 hr | 1 hr | 7 | 100%
TAP-121904 | 37 | 53,55 | 25 | 01.04.04.00.00.00.00.00 |  | TAP-121904 | [TAP-121904] ¦ [PnP][GUI] Isolate vision system components | Feature | Accepted |  |  | Parent Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 0%
TAP-121904_GUI | 38 | 37 |  | 01.04.04.01.00.00.00.00 | TAP-121904 | TAP-113893 | [TAP-121904_GUI] ¦ [PnP][GUI][Fusion] SWI Updates: Video Data | User Story | Groomed | GUI | GUI | Child Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 0%
TAP-121856 | 39 |  |  | 01.04.05.00.00.00.00.00 |  | TAP-121856 | [TAP-121856] ¦ [PnP][UFSW] LigaSure Workflow Manager Migration | Feature | In progress |  |  | Parent Task | User Stories | 64 | 23 | 1 hr | 1 hr | 41 | 35.94%
TAP-121856 | 40 | 39 |  | 01.04.05.01.00.00.00.00 | TAP-121856 | TAP-121872 | [TAP-121856] ¦ [PnP][UFSW] LigaSure Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 64 | 23 | 1 hr | 1 hr | 41 | 35.94%
TAP-121860 | 41 | 1 |  | 01.04.06.00.00.00.00.00 |  | TAP-121860 | [TAP-121860] ¦ [PnP][UFSW] Core Wristed Instruments Workflow Manager Migration | Feature | Accepted |  |  | Parent Task | User Stories | 41 | 20 | 1 hr | 1 hr | 21 | 48.78%
TAP-121860 | 42 | 41 |  | 01.04.06.01.00.00.00.00 | TAP-121860 | TAP-121876 | [TAP-121860] ¦ [PnP][UFSW] Core Wristed Instruments Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 41 | 20 | 1 hr | 1 hr | 21 | 48.78%
TAP-121901 | 43 | 53,55 | 25 | 01.05.01.00.00.00.00.00 |  | TAP-121901 | [TAP-121901] ¦ [PnP][GUI] Isolate instrument and ergonomic settings | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121901_GUI | 44 | 43 |  | 01.05.01.01.00.00.00.00 | TAP-121901 | TAP-114838 | [TAP-121901_GUI] ¦ [PnP] GUI - SWI Updates: Instrument Settings | User Story | Open | GUI | GUI | Child Task | User Stories | 5 | 0 | 25 | 60 | 5 | 0%
TAP-121891 | 45 | 53,55 | 25 | 01.05.02.00.00.00.00.00 |  | TAP-121891 | [TAP-121891] ¦ [PnP][GUI] Isolate startup and calibration components | Feature | PROPOSED |  |  | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-121891_GUI | 46 | 45 |  | 01.05.02.01.00.00.00.00 | TAP-121891 | TAP-114835 | [TAP-121891_GUI] ¦ [PnP] [GUI] - SWI Updates: System Component | User Story | Open | GUI | GUI | Child Task | User Stories | 8 | 0 | 25 | 40 | 8 | 0%
TAP-121921 | 47 | 53,55 | 25 | 01.05.03.00.00.00.00.00 |  | TAP-121921 | [TAP-121921] ¦ [PnP][GUI] Isolate ORTI process and display manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121921_GUI | 48 | 47 |  | 01.05.03.01.00.00.00.00 | TAP-121921 | TAP-114850 | [TAP-121921_GUI] ¦ [PnP] GUI - SWI Updates: ORTI Display | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 0%
TAP-121927 | 49 | 53,55 | 25 | 01.05.04.00.00.00.00.00 |  | TAP-121927 | [TAP-121927] ¦ [PnP][GUI] Isolate S3D and STS process and display manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121927_GUI | 50 | 49 |  | 01.05.04.01.00.00.00.00 | TAP-121927 | TAP-114846 | [TAP-121927_GUI] ¦ [PnP] GUI - SWI Updates: SID Screen Components | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 30 | 50 | 0 | 0%
TAP-121873 | 51 | 53,55 | 25 | 01.05.05.00.00.00.00.00 |  | TAP-121873 | [TAP-121873] ¦ [PnP][GUI][Test] Implement Semi Automated SSR Coverage | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121873 | 52 | 51 |  | 01.05.05.01.00.00.00.00 | TAP-121873 | TAP-121884 | [TAP-121873] ¦ [PnP][GUI][Test] Implement Semi Automated SSR Coverage | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 24 | 40 | 0 | 0%
TAP-121871 | 53 | 11 | 25,35,37,45,43,47,7,49,51 | 01.05.06.00.00.00.00.00 |  | TAP-121871 | [TAP-121871] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 1 | Feature | Accepted |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121871 | 54 | 53 |  | 01.05.06.01.00.00.00.00 | TAP-121871 | TAP-121883 | [TAP-121871] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 1 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 30 | 0 | 48 | 70 | 30 | 0%
TAP-121885 | 55 | 11 | 25,35,37,45,43,47,7,49,51 | 01.05.07.00.00.00.00.00 |  | TAP-121885 | [TAP-121885] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121885 | 56 | 55 |  | 01.05.07.01.00.00.00.00 | TAP-121885 | TAP-121887 | [TAP-121885] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 2 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 30 | 0 | 48 | 70 | 30 | 0%
TAP-125200 | 57 |  | 23 | 01.05.08.00.00.00.00.00 |  | TAP-125200 | [TAP-125200] ¦ [PnP][GUI] Create Product Architecture with Interface Specifications for Modularized Instrument Software Development | Feature | Accepted |  |  | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-125200_GUI | 58 | 57 |  | 01.05.08.01.00.00.00.00 | TAP-125200 | TAP-125351 | [TAP-125200_GUI] ¦ [PnP] GUI - Draft the Product Architecture for GUI | User Story | Groomed | GUI | GUI | Child Task | User Stories | 8 | 0 | 8 | 12 | 8 | 0%
TAP-129535 | 59 |  | 60,68 | 02.01.01.00.00.00.00.00 |  | TAP-129535 | [TAP-129535] ¦ [PnP][v4.2] Migrate embedded PnP updates to v4.2 - Adv Instrument ART | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-126357 | 60 | 59 | 66 | 02.01.02.00.00.00.00.00 |  | TAP-126357 | [TAP-126357] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Desired Data Pipeline | Feature | PROPOSED |  |  | Parent Task | User Stories | 34 | 0 | 1 hr | 1 hr | 34 | 0%
TAP-126357_EMBEDDED | 61 | 60 |  | 02.01.02.01.00.00.00.00 | TAP-126357 | TAP-126108 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] Dry run all IDU Primary TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 34 | 0 | 29 | 40 | 34 | 0%
TAP-130040 | 62 |  |  | 02.01.03.00.00.00.00.00 |  | TAP-130040 | [TAP-130040] ¦ [PnP][Zenith][Embedded] SRA HAL TC Updates Due to Data Pipeline Refactor | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-130040 | 63 | 62 |  | 02.01.03.01.00.00.00.00 | TAP-130040 | TAP-130041 | [TAP-130040] ¦ [PnP][Zenith][Embedded] SRA HAL TC Updates Due to Data Pipeline Refactor | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-85741 | 64 |  |  | 02.02.01.00.00.00.00.00 |  | TAP-85741 | [TAP-85741] ¦ [PnP][Zenith][Embedded] Actual Transport and Application Layer Implementation and Memory Manager IDU Refactor | Feature | Done |  |  | Parent Task | User Stories | 98 | 98 | 1 hr | 1 hr | 0 | 100%
TAP-85741_EMBEDDED | 65 | 64 |  | 02.02.01.01.00.00.00.00 | TAP-85741 | TAP-96951 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][I2E][IDU Primary][Enabler] Design Memory Manager for IDU Primary Instrument Parameter Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 98 | 98 | 1 hr | 1 hr | 0 | 100%
TAP-121915 | 66 |  | 64 | 02.03.01.00.00.00.00.00 |  | TAP-121915 | [TAP-121915] ¦ [PnP][Zenith][Embedded] Desired Parameter Pipeline from SRA HAL to Instrumentation | Feature | Accepted |  |  | Parent Task | User Stories | 53 | 8 | 1 hr | 1 hr | 45 | 15.09%
TAP-121915 | 67 | 66 |  | 02.03.01.01.00.00.00.00 | TAP-121915 | TAP-121955 | [TAP-121915] ¦ [PnP][Zenith][Embedded] Desired Parameter Pipeline from SRA HAL to Instrumentation | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 53 | 8 | 1 hr | 1 hr | 45 | 15.09%
TAP-126005 | 68 | 59 | 64 | 02.03.02.00.00.00.00.00 |  | TAP-126005 | [TAP-126005] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Actual Data Pipeline | Feature | Accepted |  |  | Parent Task | User Stories | 48 | 20 | 1 hr | 1 hr | 28 | 41.67%
TAP-126005_EMBEDDED | 69 | 68 |  | 02.03.02.01.00.00.00.00 | TAP-126005 | TAP-125098 | [TAP-126005_EMBEDDED] ¦ [PnP][zenith][Embedded] Integration Testing for Actual Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 48 | 20 | 1 hr | 1 hr | 28 | 100%
TAP-99224 | 70 |  | 90 | 03.01.01.00.00.00.00.00 |  | TAP-99224 | [TAP-99224] ¦ [PnP] [Architecture] [Enabler][Controls] EIN-SWI-176 Croc Controller Refactor | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-99224 | 71 | 70 |  | 03.01.01.01.00.00.00.00 | TAP-99224 | TAP-121522 | [TAP-99224] ¦ [PnP] [Architecture] [Enabler][Controls] EIN-SWI-176 Croc Controller Refactor | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 24 | 40 | 0 | 0%
TAP-103935 | 72 |  | 19 | 04.01.01.00.00.00.00.00 |  | TAP-103935 | [TAP-103935] ¦ [PnP][Arch][UFSW] MSC - Migrate Energy STM to Aux Fn Manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 37 | 9 | 1 hr | 1 hr | 28 | 24.32%
TAP-103935_UFSW | 73 | 72 |  | 04.01.01.01.00.00.00.00 | TAP-103935 | TAP-97705 | [TAP-103935_UFSW] ¦ [Scrumbledores] MSC plug and play concept architecture and prototyping | User Story | Done | UFSW | UFSW | Child Task | User Stories | 37 | 9 | 37 | 50 | 28 | 100%
TAP-121902 | 74 | 1 | 23 | 04.02.01.00.00.00.00.00 |  | TAP-121902 | [TAP-121902] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Core Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121902 | 75 | 74 |  | 04.02.01.01.00.00.00.00 | TAP-121902 | TAP-121944 | [TAP-121902] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Core Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-121900 | 76 | 1 | 23 | 04.02.02.00.00.00.00.00 |  | TAP-121900 | [TAP-121900] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Croc Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121900 | 77 | 76 |  | 04.02.02.01.00.00.00.00 | TAP-121900 | TAP-121942 | [TAP-121900] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Croc Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-121898 | 78 | 1 | 23 | 04.02.03.00.00.00.00.00 |  | TAP-121898 | [TAP-121898] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Ligasure Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-121898 | 79 | 78 |  | 04.02.03.01.00.00.00.00 | TAP-121898 | TAP-121941 | [TAP-121898] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Ligasure Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 3 | 3 | 50 | 65 | 0 | 100%
TAP-121905 | 80 | 1 | 23 | 04.02.04.00.00.00.00.00 |  | TAP-121905 | [TAP-121905] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Single Use Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121905 | 81 | 80 |  | 04.02.04.01.00.00.00.00 | TAP-121905 | TAP-121946 | [TAP-121905] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Single Use Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-121922 | 82 | 110 | 66 | 04.03.01.00.00.00.00.00 |  | TAP-121922 | [TAP-121922] ¦ [PnP][Zenith][Embedded] Implement Instrumentation Latching within the SRA HAL/BSCM | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121922 | 83 | 82 |  | 04.03.01.01.00.00.00.00 | TAP-121922 | TAP-121961 | [TAP-121922] ¦ [PnP][Zenith][Embedded] Implement Instrumentation Latching within the SRA HAL/BSCM | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 85 | 115 | 0 | 0%
TAP-103932 | 84 |  |  | 04.04.01.00.00.00.00.00 |  | TAP-103932 | [TAP-103932] ¦ [PnP][Arch][UFSW] Migrate IX STM Instrument Attachment to PnP SWIs | Feature | Done |  |  | Parent Task | User Stories | 51 | 51 | 1 hr | 1 hr | 0 | 100%
TAP-103932_UFSW | 85 | 84 |  | 04.04.01.01.00.00.00.00 | TAP-103932 | TAP-105843 | [TAP-103932_UFSW] ¦ [UFSW][Newton][PnP] Initial design and requirements set up/review | User Story | Done | UFSW | UFSW | Child Task | User Stories | 51 | 51 | 1 hr | 1 hr | 0 | 100%
TAP-103933 | 86 |  |  | 04.04.02.00.00.00.00.00 |  | TAP-103933 | [TAP-103933] ¦ [PnP][Arch][UFSW] Migrate IX STM Internal/External Calibration to PnP SWIs | Feature | Done |  |  | Parent Task | User Stories | 18 | 18 | 1 hr | 1 hr | 0 | 100%
TAP-103933_UFSW | 87 | 86 |  | 04.04.02.02.00.00.00.00 | TAP-103933 | TAP-106142 | [TAP-103933_UFSW] ¦ [Organelles][PnP][Spike] Draft Implementation plan for IX STM Internal/External Calibration migration | User Story | Done | UFSW | UFSW | Child Task | User Stories | 18 | 18 | 1 hr | 1 hr | 0 | 100%
TAP-114308 | 88 | 118,116 | 90 | 04.04.03.00.00.00.00.00 |  | TAP-114308 | [TAP-114308] ¦ [PnP][Controls] Migration of IDU Controller SWIs | Feature | Done |  |  | Parent Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-114308_CONTROLS | 89 | 88 |  | 04.04.03.03.00.00.00.00 | TAP-114308 | TAP-114494 | [TAP-114308_CONTROLS] ¦ [zenith] Data Corruption RCMs - Get Buy-In from Quality for Update | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 15 | 15 | 1 hr | 1 hr | 0 | 100%
TAP-114299 | 90 | 88,98,100,70 | 23 | 04.04.04.00.00.00.00.00 |  | TAP-114299 | [TAP-114299] ¦ [PnP][Controls] Setup IDU Controller Container | Feature | Done |  |  | Parent Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-114299_CONTROLS | 91 | 90 |  | 04.04.04.01.00.00.00.00 | TAP-114299 | TAP-114400 | [TAP-114299_CONTROLS] ¦ [zenith] Identify SWIs to Migrate, wrangle their signals inside container, 1/2 | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-121913 | 92 | 96,118,116 | 98,100 | 04.05.01.00.00.00.00.00 |  | TAP-121913 | [TAP-121913] ¦ [PnP][Controls] IDU Actuator Controller - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-121913 | 93 | 92 |  | 04.05.01.01.00.00.00.00 | TAP-121913 | TAP-121954 | [TAP-121913] ¦ [PnP][Controls] IDU Actuator Controller - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 1 | 0 | 12 | 15 | 1 | 0%
TAP-121912 | 94 | 96,118,116 | 98,100 | 04.05.02.00.00.00.00.00 |  | TAP-121912 | [TAP-121912] ¦ [PnP][Controls] IDU Actuator Monitor - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 39 | 8 | 1 hr | 1 hr | 31 | 20.51%
TAP-121912 | 95 | 94 |  | 04.05.02.01.00.00.00.00 | TAP-121912 | TAP-121953 | [TAP-121912] ¦ [PnP][Controls] IDU Actuator Monitor - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 39 | 8 | 10 | 15 | 31 | 20.51%
TAP-121925 | 96 | 116,118 | 102,114,92,94,104,106,112 | 04.05.03.00.00.00.00.00 |  | TAP-121925 | [TAP-121925] ¦ [PnP][Controls] IDU Controller SysIL Verification - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 21 | 0 | 1 hr | 1 hr | 21 | 0%
TAP-121925 | 97 | 96 |  | 04.05.03.01.00.00.00.00 | TAP-121925 | TAP-121963 | [TAP-121925] ¦ [PnP][Controls] IDU Controller SysIL Verification - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 21 | 0 | 21 | 30 | 21 | 0%
TAP-121923 | 98 | 102,114,92,94,104,106,118,116,112 | 90 | 04.05.04.00.00.00.00.00 |  | TAP-121923 | [TAP-121923] ¦ [PnP][Controls] IDU Controller Debug Logging - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 5 | 3 | 1 hr | 1 hr | 2 | 60%
TAP-121923 | 99 | 98 |  | 04.05.04.01.00.00.00.00 | TAP-121923 | TAP-121962 | [TAP-121923] ¦ [PnP][Controls] IDU Controller Debug Logging - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 5 | 3 | 10 | 15 | 2 | 60%
TAP-121920 | 100 | 102,114,92,94,104,106,118,116,112 | 90 | 04.05.05.00.00.00.00.00 |  | TAP-121920 | [TAP-121920] ¦ [PnP][Controls] IDU Controller Error Handler - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-121920 | 101 | 100 |  | 04.05.05.01.00.00.00.00 | TAP-121920 | TAP-121959 | [TAP-121920] ¦ [PnP][Controls] IDU Controller Error Handler - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 13 | 0 | 13 | 20 | 13 | 0%
TAP-121919 | 102 | 96,118,116 | 98,100 | 04.05.06.00.00.00.00.00 |  | TAP-121919 | [TAP-121919] ¦ [PnP][Controls] IDU Controller "Workflow Manager" - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 2 | 0 | 1 hr | 1 hr | 2 | 0%
TAP-121919 | 103 | 102 |  | 04.05.06.01.00.00.00.00 | TAP-121919 | TAP-121958 | [TAP-121919] ¦ [PnP][Controls] IDU Controller "Workflow Manager" - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 2 | 0 | 5 | 10 | 2 | 0%
TAP-121910 | 104 | 96,118,116 | 98,100 | 04.05.07.00.00.00.00.00 |  | TAP-121910 | [TAP-121910] ¦ [PnP][Controls] IDU Actuator Output Processing - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121910 | 105 | 104 |  | 04.05.07.01.00.00.00.00 | TAP-121910 | TAP-121951 | [TAP-121910] ¦ [PnP][Controls] IDU Actuator Output Processing - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 7 | 10 | 0 | 0%
TAP-121908 | 106 | 96,118,116 | 98,100 | 04.05.08.00.00.00.00.00 |  | TAP-121908 | [TAP-121908] ¦ [PnP][Controls] IDU Actuator Input Processing - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121908 | 107 | 106 |  | 04.05.08.01.00.00.00.00 | TAP-121908 | TAP-121949 | [TAP-121908] ¦ [PnP][Controls] IDU Actuator Input Processing - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 5 | 0 | 10 | 15 | 5 | 0%
TAP-121906 | 108 |  | 110 | 04.05.09.00.00.00.00.00 |  | TAP-121906 | [TAP-121906] ¦ [PnP][Arch][Enabler][Embedded] Integrate BSCM with Subsystems | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121906 | 109 | 108 |  | 04.05.09.01.00.00.00.00 | TAP-121906 | TAP-121947 | [TAP-121906] ¦ [PnP][Arch][Enabler][Embedded] Integrate BSCM with Subsystems | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 117 | 180 | 0 | 0%
TAP-97909 | 110 |  | 82 | 04.05.10.00.00.00.00.00 |  | TAP-97909 | [TAP-97909] ¦ [PnP][Zenith][Embedded] Implement Bedside Config Manager | Feature | Accepted |  |  | Parent Task | User Stories | 16 | 0 | 1 hr | 1 hr | 16 | 0%
TAP-97909_EMBEDDED | 111 | 110 |  | 04.05.10.01.00.00.00.00 | TAP-97909 | TAP-97616 | [TAP-97909_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Enabler] Cyclic EtherCAT SRA HAL Framework Update | User Story | Groomed | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 43 | 65 | 16 | 0%
TAP-126766 | 112 | 96,118,116 | 98,100,114 | 04.05.11.00.00.00.00.00 |  | TAP-126766 | [TAP-126766] ¦ [PnP][Controls] Instrument Controller - Migration - Test Work | Feature | PROPOSED |  |  | Parent Task | User Stories | 19 | 7 | 1 hr | 1 hr | 12 | 36.84%
TAP-126766 | 113 | 112 |  | 04.05.11.01.00.00.00.00 | TAP-126766 | TAP-121956 | [TAP-126766] ¦ [PnP][Controls] Instrument Controller - Migration - Test Work | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 19 | 7 | 20 | 30 | 12 | 36.84%
TAP-121916 | 114 | 96,118,116,112 | 98,100 | 04.05.12.00.00.00.00.00 |  | TAP-121916 | [TAP-121916] ¦ [PnP][Controls] Instrument Controller - Migration - Dev Work | Feature | Accepted |  |  | Parent Task | User Stories | 20 | 7 | 1 hr | 1 hr | 13 | 35%
TAP-121916 | 115 | 114 |  | 04.05.12.01.00.00.00.00 | TAP-121916 | TAP-121956 | [TAP-121916] ¦ [PnP][Controls] Instrument Controller - Migration - Dev Work | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 20 | 7 | 1 hr | 1 hr | 13 | 35%
TAP-121926 | 116 |  | 118,96,88,106,104,94,92,66,114,102,100,98,112 | 04.05.13.00.00.00.00.00 |  | TAP-121926 | [TAP-121926] ¦ [PnP][IDU][Controls] Merge to Develop Behind Build Flag | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121926 | 117 | 116 |  | 04.05.13.01.00.00.00.00 | TAP-121926 | TAP-121964 | [TAP-121926] ¦ [PnP][IDU][Controls] Merge to Develop Behind Build Flag | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 15 | 25 | 0 | 0%
TAP-121917 | 118 | 116 | 88,106,104,94,92,66,114,102,100,98,96,112 | 04.05.14.00.00.00.00.00 |  | TAP-121917 | [TAP-121917] ¦ [PnP][IDU][Controls] Preliminary Integration of M-IRR and Newton | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121917 | 119 | 118 |  | 04.05.14.01.00.00.00.00 | TAP-121917 | TAP-121957 | [TAP-121917] ¦ [PnP][IDU][Controls] Preliminary Integration of M-IRR and Newton | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 5 | 7 | 0 | 0%

## Log
DataTimeStamp | Event | Data | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
2024-09-09 12:06 | Start: | DANSAP Formatter, v1.6 | TAP-121917 |  | TAP-121864
2024-09-09 12:06 | Input File: | PnP_Categorized_240904_1601 (discipline+refinement level updated).xls | TAP-121917 |  | TAP-121864
2024-09-09 12:06 | Output File: | 2024-06-18_19-58-51_Project_Import_DS_95.xlsx | TAP-121917 | TAP-121864
2024-09-09 12:06 | Info |  | TAP-121917 | TAP-121864
2024-09-09 12:06 | Processing: | Jira Data: Rows: 484, Cols: 16 | TAP-121917 | TAP-114818
2024-09-09 12:06 | Result: | Project Data: Rows: 119, Cols: 20 | TAP-121917 | TAP-113642
2024-09-09 12:06 | Processing Complete: | 20.484707832336426 seconds | TAP-121917 | TAP-121864
|  |  | TAP-121917 | TAP-121864
|  |  | TAP-121917 | TAP-115465
|  |  | TAP-121917 |  | TAP-125195
|  |  | TAP-121917 | TAP-103479
|  |  | TAP-121917 |  | TAP-121864
|  |  | TAP-121917 |  | TAP-121864
|  |  | TAP-121917 | TAP-94814
|  |  | TAP-121917 | TAP-84434
|  |  | TAP-121917 | TAP-97775
|  |  | TAP-121917 | TAP-122018
|  |  | TAP-121917 | TAP-106649
|  |  | TAP-121917 | TAP-121929
|  |  | TAP-121917 | TAP-94827

## Summary
Resource Names | Sum FDR
UFSW | 377
GUI | 263
EMBEDDED | 324
CONTROLS | 152
Total FDR: | 4991