## Summary
Resource Names | Sum FDR
COREINSTRUMENTS | 47
SEAMLESS | 10
Total FDR: | 57

## Log
DataTimeStamp | Selector | Event | Data
2024-11-06 14:39 | TAP-94739 | Missing Unique ID Successor | TAP-97668
2024-11-06 14:39 | TAP-120097 | Missing Unique ID Predecessor | TAP-97668
2024-11-06 14:39 | TAP-111763 | Missing Unique ID Successor | TAP-113104
Input Data File Path: | C:\Users\sapird3\OneDrive - Medtronic PLC\IRR_Medium_Term_subset for testing3.xls
Input Mapping File Path: | C:\Users\sapird3\OneDrive - Medtronic PLC\Team Mapping for Jira Project converter.xlsx
Creation Date: | 11/06/2024
Latest Update: | 11/06/2024
Script Execution Time (sec): | 15.24 seconds
Script Execution Time (min): | 0.25 minutes

## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete | Milestone
TAP-94739 | 1 | 7 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  | Parent Task |  | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-94739_COREINSTRUMENTS | 2 | 1 |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-94739_COREINSTRUMENTS] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-120097 | 3 | 7 |  | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | In progress |  |  | Parent Task |  | 57.5 | 46.5 | 1 hr | 1 hr | 11 | 80.87%
TAP-120097_COREINSTRUMENTS | 4 | 3 |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-97689 | [TAP-120097_COREINSTRUMENTS] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | User Story | Open | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 8 | 5 | 8 | 9.6 | 3 | 62.5%
TAP-112077 | 5 | 7 |  | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  | Parent Task |  | 54 | 22 | 1 hr | 1 hr | 32 | 40.74%
TAP-112077_COREINSTRUMENTS | 6 | 5 |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 27 | 18 | 27 | 32.4 | 9 | 66.67%
TAP-111760 | 7 | 8 |  | 08.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111763 | 8 | 10 | 7 | 08.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-111763_SEAMLESS | 9 | 8 |  | 08.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0%
TAP-127945 | 10 |  | 8 | 08.03.00.00.00.00.00.00 |  | TAP-127945 | [TAP-127945] ¦ [Prochain][IRR] EC1 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%