## Summary
Resource Names | Sum FDR
COREINSTRUMENTS | 1349.5
EMBEDDED | 172
PUPPETEERS | 310
JACOBIANS | 336.25
CASTLEBLACK | 9
BOOSTERS | 22
BUGHUNTERS | 29
PIXELPOETS | 125
STELLARS | 9
USERFLOWSW | 123
DRUSHTI | 7
INBETWEENERS | 70
ZENITH | 1
NEPTUNE | 1
CLASSY2 | 10
SUNRISERS | 3
TEAMBD | 3
COSSACKS | 8
CLASSY | 18
BUILDERS | 22
ASTRANPSDEVELOPERS | 20
TOOLSRULES | 40
TRIPLETEA | 40
ASTRANPSVALIDATORS | 50
SEAMLESS | 41
Total FDR: | 2818.75

## Log
DataTimeStamp | Selector | Event | Data
2024-12-06 09:50 | TAP-97668_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111730_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-94966_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111554_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111569_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-112077_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-112077_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-124116_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-124116_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111721_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111723_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111723_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-94125_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-94125_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-95800_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-95800_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111740_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111740_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111751_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-130796_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-135038_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-111834_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-132587_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-134301_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-130665_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-123834_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 09:50 | TAP-125255_BOOSTERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-136909_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-136657_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-136657_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-111749_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-111749_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-111750_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-117678_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-112842 | Repeated Key | Previous Row: 251, Current: 371
2024-12-06 09:50 | TAP-136410_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-132462_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:50 | TAP-137313_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-137334_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-137337_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-137339_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-136914_BUGHUNTERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-133813_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-124475_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-137265_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-133906_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-134541_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-131594_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111747_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111747_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-113111_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-113111_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-113111_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-113123_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-114692_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-116170 | Repeated Key | Previous Row: 509, Current: 520
2024-12-06 09:51 | TAP-114689_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-130664_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-132912_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-90375_STELLARS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-90375_STELLARS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-90375_STELLARS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111861_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-132288 | Repeated Key | Previous Row: 528, Current: 565
2024-12-06 09:51 | TAP-132289 | Repeated Key | Previous Row: 529, Current: 566
2024-12-06 09:51 | TAP-111687_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111695_DRUSHTI | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111774_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111774_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-112080_INBETWEENERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111775_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-128530_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-128527_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-128527_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-133880_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-123863_NEPTUNE | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111656_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-132913_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-132913_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111838_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111838_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-104213_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111842_USERFLOWSW | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-112119_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111925_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111925_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111925_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111756_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111756_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111756_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111757_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 09:51 | TAP-111724_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111761_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-110382_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111762_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111748_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111764_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111766_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-112082_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-112093_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-112094_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC2
2024-12-06 09:51 | TAP-113100_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 09:51 | TAP-111900_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 09:51 | TAP-112042_BUILDERS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 09:51 | TAP-111692_TRIPLETEA | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 09:51 | TAP-112231_ASTRANPSVALIDATORS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 09:51 | TAP-112233_ASTRANPSVALIDATORS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 09:51 | TAP-112234_TOOLSRULES | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 09:51 | TAP-113127 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-111760 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-111760 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-127945 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-113104 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-113104 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-127946 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-137349 | Milestone not found in the dictionary | V4.2
2024-12-06 09:51 | TAP-137353 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111765 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111768 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111769 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:51 | TAP-111769 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 09:52 | TAP-120097 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-124062 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111554 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111569 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-112077 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-124116 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-124116 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111719 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111719 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111723 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-94125 | Missing Unique ID Successor | TAP-111753
2024-12-06 09:52 | TAP-94125 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-94125 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-95800 | Missing Unique ID Successor | TAP-111754
2024-12-06 09:52 | TAP-95800 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-95800 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111740 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111740 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111751 | Missing Unique ID Successor | TAP-111759
2024-12-06 09:52 | TAP-111751 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111751 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-130796 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-135038 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-111834 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-132587 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-134301 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-130665 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-123834 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-124472 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 09:52 | TAP-136909 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-136657 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111749 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111749 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111750 | Missing Unique ID Successor | TAP-111758
2024-12-06 09:52 | TAP-111750 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111750 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-117678 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-136410 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-132462 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-137313 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-137334 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-137337 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-137339 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-136914 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-133813 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-124475 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-137265 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-133906 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-134541 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-131594 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111747 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-113111 | Missing Unique ID Successor | TAP-111689
2024-12-06 09:52 | TAP-113111 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-113111 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-113123 | Missing Unique ID Successor | TAP-111689
2024-12-06 09:52 | TAP-113123 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-113123 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-113123 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-114692 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-114689 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-130664 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-132912 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-90375 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111861 | Missing Unique ID Successor | TAP-133471
2024-12-06 09:52 | TAP-111861 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111861 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111861 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111687 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111695 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-133272 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-112080 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-112080 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111775 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-128530 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-128527 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-133880 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-133880 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-138442 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111656 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-132913 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111838 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111838 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-104213 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-104213 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111842 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-112119 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111925 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111756 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111756 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111756 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111757 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111757 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111757 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111724 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 09:52 | TAP-111761 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111761 | Missing Unique ID Predecessor | TAP-111753
2024-12-06 09:52 | TAP-110382 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-110382 | Missing Unique ID Predecessor | TAP-111754
2024-12-06 09:52 | TAP-111762 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111748 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111764 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111764 | Missing Unique ID Predecessor | TAP-111758
2024-12-06 09:52 | TAP-111766 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111766 | Missing Unique ID Predecessor | TAP-111759
2024-12-06 09:52 | TAP-112082 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-112093 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-112094 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-113100 | Missing Unique ID Successor | V4.2 - RC2
2024-12-06 09:52 | TAP-111900 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 09:52 | TAP-112042 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 09:52 | TAP-111692 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 09:52 | TAP-112231 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 09:52 | TAP-112233 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 09:52 | TAP-112234 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 09:52 | TAP-113127 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 09:52 | TAP-111760 | Missing Unique ID Predecessor | TAP-129482
2024-12-06 09:52 | TAP-113104 | Missing Unique ID Predecessor | TAP-111772
2024-12-06 09:52 | TAP-113104 | Missing Unique ID Predecessor | TAP-111773
2024-12-06 09:52 | TAP-113104 | Missing Unique ID Predecessor | TAP-111642
2024-12-06 09:52 | TAP-113104 | Missing Unique ID Predecessor | TAP-112113
2024-12-06 09:52 | TAP-113104 | Missing Unique ID Predecessor | TAP-123818
2024-12-06 09:52 | TAP-113104 | Missing Unique ID Predecessor | TAP-111689
2024-12-06 09:52 | TAP-137349 | Missing Unique ID Predecessor | TAP-95983
2024-12-06 09:52 | TAP-137349 | Missing Unique ID Predecessor | TAP-123914
2024-12-06 09:52 | TAP-137349 | Missing Unique ID Predecessor | TAP-111753
2024-12-06 09:52 | TAP-137349 | Missing Unique ID Predecessor | TAP-111754
2024-12-06 09:52 | TAP-137349 | Missing Unique ID Predecessor | TAP-111758
2024-12-06 09:52 | TAP-137349 | Missing Unique ID Predecessor | TAP-111759
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-111753
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-111754
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-111758
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-111759
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-124484
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-109680
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-122269
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-125315
2024-12-06 09:52 | TAP-111765 | Missing Unique ID Predecessor | TAP-127798
2024-12-06 09:52 | TAP-111768 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111769 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111767 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 09:52 | TAP-111767 | Missing Unique ID Successor | V4.2 - RC1
Input Data File Path: | C:\Users\sapird3\Downloads\IRR_Medium_Term_NEW_241118_0948 (2).xls
Input Mapping File Path: | C:\Users\sapird3\Downloads\Team Mapping for Jira Project converter.xlsx
Creation Date: | 12/06/2024
Latest Update: | 12/06/2024
Script Execution Time (sec): | 131.42 seconds
Script Execution Time (min): | 2.19 minutes

## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete | Milestone
TAP-94739 | 1 | 3,252 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  | Parent Task |  | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-94739_COREINSTRUMENTS | 2 | 1 |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-94739_COREINSTRUMENTS] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-97668 | 3 | 5 | 1 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  | Parent Task |  | 32.5 | 32.5 | 1 hr | 1 hr | 0 | 100%
TAP-97668_COREINSTRUMENTS | 4 | 3 |  | 01.01.02.01.00.00.00.00 | TAP-97668 | TAP-111972 | [TAP-97668_COREINSTRUMENTS] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 32.5 | 32.5 | 32.5 | 39 | 0 | 100%
TAP-120097 | 5 | 252 | 3 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | Done |  |  | Parent Task |  | 46.5 | 46.5 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-120097_COREINSTRUMENTS | 6 | 5 |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-106674 | [TAP-120097_COREINSTRUMENTS] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 46.5 | 46.5 | 46.5 | 55.8 | 0 | 100% | V4.2 - EC1
TAP-111730 | 7 | 252,9 |  | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | Done |  |  | Parent Task |  | 20 | 20 | 1 hr | 1 hr | 0 | 100%
TAP-111730_COREINSTRUMENTS | 8 | 7 |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 | [TAP-111730_COREINSTRUMENTS] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 20 | 20 | 20 | 24 | 0 | 100%
TAP-124062 | 9 | 252 | 7 | 01.02.02.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | Done |  |  | Parent Task |  | 38 | 38 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-124062_COREINSTRUMENTS | 10 | 9 |  | 01.02.02.01.00.00.00.00 | TAP-124062 | TAP-116459 | [TAP-124062_COREINSTRUMENTS] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | User Story | Done | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 38 | 38 | 38 | 45.6 | 0 | 100% | V4.2 - EC1
TAP-94966 | 11 | 252 |  | 01.03.01.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | Done |  |  | Parent Task |  | 37 | 37 | 1 hr | 1 hr | 0 | 100%
TAP-94966_COREINSTRUMENTS | 12 | 11 |  | 01.03.01.01.00.00.00.00 | TAP-94966 | TAP-111781 | [TAP-94966_COREINSTRUMENTS] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 37 | 37 | 37 | 44.4 | 0 | 100%
TAP-111554 | 13 | 252 |  | 01.03.02.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness | Feature | Done |  |  | Parent Task |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-111554_COREINSTRUMENTS | 14 | 13 |  | 01.03.02.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554_COREINSTRUMENTS] ¦ [IRR][Enhancement] Improve Cutting Control Robustness | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 35 | 35 | 35 | 42 | 0 | 100% | V4.2 - EC1
TAP-111569 | 15 | 252 |  | 01.03.04.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] P1/P1+ Instrument Integration, Testing, Tuning, EC1 Design Reviews | Feature | Accepted |  |  | Parent Task |  | 59 | 27 | 1 hr | 1 hr | 32 | 45.76% | V4.2 - EC1
TAP-111569_COREINSTRUMENTS | 16 | 15 |  | 01.03.04.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569_COREINSTRUMENTS] ¦ [IRR][Enabler] P1/P1+ Instrument Integration, Testing, Tuning, EC1 Design Reviews | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 59 | 27 | 59 | 70.8 | 32 | 45.76% | V4.2 - EC1
TAP-112077 | 17 | 252 |  | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Done |  |  | Parent Task |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-112077_COREINSTRUMENTS | 18 | 17 |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 34 | 34 | 34 | 40.8 | 0 | 100% | V4.2 - EC1
TAP-124116 | 19 | 21,252 |  | 01.05.02.00.00.00.00.00 |  | TAP-124116 | [TAP-124116] ¦ [IRR][Enabler] Setup of EtherCAT DAQ module for Synchronized Data Acquisition | Feature | In progress |  |  | Parent Task |  | 13 | 0 | 1 hr | 1 hr | 13 | 0% | V4.2 - EC1
TAP-124116_EMBEDDED | 20 | 19 |  | 01.05.02.01.00.00.00.00 | TAP-124116 | TAP-124075 | [TAP-124116_EMBEDDED] ¦ [IRR][Enabler] Setup of EtherCAT DAQ module for Synchronized Data Acquisition | User Story | In progress | Foundation - Fred | EMBEDDED | Child Task |  | 13 | 0 | 13 | 15.6 | 13 | 0% | V4.2 - EC1
TAP-111719 | 21 | 264,252 | 19 | 01.05.03.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  | Parent Task |  | 7 | 2 | 1 hr | 1 hr | 5 | 28.57% | V4.2 - EC1
TAP-111719_EMBEDDED | 22 | 21 |  | 01.05.03.02.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_EMBEDDED] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 7 | 2 | 7 | 8.4 | 5 | 28.57% | V4.2 - EC1
TAP-111721 | 23 | 252 |  | 01.05.04.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | Done |  |  | Parent Task |  | 24.5 | 24.5 | 1 hr | 1 hr | 0 | 100%
TAP-111721_COREINSTRUMENTS | 24 | 23 |  | 01.05.04.01.00.00.00.00 | TAP-111721 | TAP-111917 | [TAP-111721_COREINSTRUMENTS] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 22.5 | 22.5 | 22.5 | 27 | 0 | 100%
TAP-111721_PUPPETEERS | 25 | 23 |  | 01.05.04.11.00.00.00.00 | TAP-111721 | TAP-123066 | [TAP-111721_PUPPETEERS] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-111723 | 26 | 252 |  | 01.05.05.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates RUFS lab ( no date continous lab) | Feature | Accepted |  |  | Parent Task |  | 5 | 0 | 1 hr | 1 hr | 5 | 0% | V4.2 - EC1
TAP-111723_COREINSTRUMENTS | 27 | 26 |  | 01.05.05.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723_COREINSTRUMENTS] ¦ [IRR][Enabler] Labs Support for Controller Updates RUFS lab ( no date continous lab) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 5 | 0 | 5 | 6 | 5 | 0% | V4.2 - EC1
TAP-94125 | 28 | 252 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | Done |  |  | Parent Task |  | 34 | 32 | 1 hr | 1 hr | 2 | 100% | V4.2 - EC1
TAP-94125_COREINSTRUMENTS | 29 | 28 |  | 01.06.01.02.00.00.00.00 | TAP-94125 | TAP-97748 | [TAP-94125_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | User Story | Done | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 32 | 32 | 32 | 38.4 | 0 | 100% | V4.2 - EC1
TAP-95800 | 30 | 252 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | Done |  |  | Parent Task |  | 46 | 46 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-95800_COREINSTRUMENTS | 31 | 30 |  | 01.06.02.02.00.00.00.00 | TAP-95800 | TAP-111779 | [TAP-95800_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 41 | 41 | 41 | 49.2 | 0 | 100% | V4.2 - EC1
TAP-95800_EMBEDDED | 32 | 30 |  | 01.06.02.21.00.00.00.00 | TAP-95800 | TAP-130566 | [TAP-95800_EMBEDDED] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | User Story | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 5 | 5 | 5 | 6 | 0 | 100% | V4.2 - EC1
TAP-111740 | 33 | 191,252 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | Done |  |  | Parent Task |  | 40.5 | 40.5 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-111740_COREINSTRUMENTS | 34 | 33 |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 40.5 | 40.5 | 40.5 | 48.6 | 0 | 100% | V4.2 - EC1
TAP-111751 | 35 | 252 |  | 01.06.04.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | Accepted |  |  | Parent Task |  | 20 | 3 | 1 hr | 1 hr | 17 | 15% | V4.2 - EC1
TAP-111751_COREINSTRUMENTS | 36 | 35 |  | 01.06.04.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 20 | 3 | 20 | 24 | 17 | 15% | V4.2 - EC1
TAP-130796 | 37 | 252 |  | 01.06.05.00.00.00.00.00 |  | TAP-130796 | [TAP-130796] ¦ [IRR][Phase 1b] Test Cleanup for IRR Controller Release | Feature | Done |  |  | Parent Task |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-130796_COREINSTRUMENTS | 38 | 37 |  | 01.06.05.01.00.00.00.00 | TAP-130796 | TAP-129700 | [TAP-130796_COREINSTRUMENTS] ¦ [IRR][Phase 1b] Test Cleanup for IRR Controller Release | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 16 | 16 | 16 | 19.2 | 0 | 100% | V4.2 - EC1
TAP-135038 | 39 | 252 |  | 01.06.06.00.00.00.00.00 |  | TAP-135038 | [TAP-135038] ¦ [IRR] Finalize Joint Controller | Feature | Done |  |  | Parent Task |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-135038_COREINSTRUMENTS | 40 | 39 |  | 01.06.06.01.00.00.00.00 | TAP-135038 | TAP-126529 | [TAP-135038_COREINSTRUMENTS] ¦ [IRR] Finalize Joint Controller | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 8 | 8 | 8 | 9.6 | 0 | 100% | V4.2 - EC1
TAP-111834 | 41 | 252 |  | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | Accepted |  |  | Parent Task |  | 17 | 14 | 1 hr | 1 hr | 3 | 82.35% | V4.2 - EC1
TAP-111834_JACOBIANS | 42 | 41 |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_JACOBIANS] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC1
TAP-111834_CASTLEBLACK | 43 | 41 |  | 01.07.01.02.00.00.00.00 | TAP-111834 | TAP-126232 | [TAP-111834_CASTLEBLACK] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 1 | 0 | 1 | 1.2 | 1 | 0% | V4.2 - EC1
TAP-111834_COREINSTRUMENTS | 44 | 41 |  | 01.07.01.03.00.00.00.00 | TAP-111834 | TAP-126522 | [TAP-111834_COREINSTRUMENTS] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 16 | 14 | 16 | 19.2 | 2 | 87.5% | V4.2 - EC1
TAP-132587 | 45 | 252 |  | 01.07.02.00.00.00.00.00 |  | TAP-132587 | [TAP-132587] ¦ [IRR] Support Workflow Updates for IRR Shears | Feature | Accepted |  |  | Parent Task |  | 13 | 0 | 1 hr | 1 hr | 13 | 0% | V4.2 - EC1
TAP-132587_PUPPETEERS | 46 | 45 |  | 01.07.02.01.00.00.00.00 | TAP-132587 | TAP-136339 | [TAP-132587_PUPPETEERS] ¦ [IRR] Support Workflow Updates for IRR Shears | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 13 | 0 | 13 | 15.6 | 13 | 0% | V4.2 - EC1
TAP-134301 | 47 | 252 |  | 01.07.03.00.00.00.00.00 |  | TAP-134301 | [TAP-134301] ¦ [IRR][JBO] Assess LSI Shears and JBO for Reliability+Workspace Impact | Feature | Done |  |  | Parent Task |  | 3 | 3 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-134301_JACOBIANS | 48 | 47 |  | 01.07.03.01.00.00.00.00 | TAP-134301 | TAP-136330 | [TAP-134301_JACOBIANS] ¦ [IRR][JBO] Assess LSI Shears and JBO for Reliability+Workspace Impact | User Story | Done | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 3 | 3 | 3 | 3.6 | 0 | 100% | V4.2 - EC1
TAP-130665 | 49 | 260 |  | 01.08.00.00.00.00.00.00 |  | TAP-130665 | [TAP-130665] ¦ [IRR] Kinematic Variant Management in Mini-Bedside Configuration Manager | Feature | Accepted |  |  | Parent Task |  | 45 | 5 | 1 hr | 1 hr | 40 | 11.11% | V4.2 - EC1
TAP-130665_EMBEDDED | 50 | 49 |  | 01.08.01.00.00.00.00.00 | TAP-130665 | TAP-129688 | [TAP-130665_EMBEDDED] ¦ [IRR] Kinematic Variant Management in Mini-Bedside Configuration Manager | User Story | Groomed | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 37 | 5 | 37 | 44.4 | 32 | 13.51% | V4.2 - EC1
TAP-130665_PUPPETEERS | 51 | 49 |  | 01.08.14.00.00.00.00.00 | TAP-130665 | TAP-136589 | [TAP-130665_PUPPETEERS] ¦ [IRR] Kinematic Variant Management in Mini-Bedside Configuration Manager | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 8 | 0 | 8 | 9.6 | 8 | 0% | V4.2 - EC1
TAP-123834 | 52 | 252 |  | 01.09.00.00.00.00.00.00 |  | TAP-123834 | [TAP-123834] ¦ [IRR] Migrate IRR SW to Post-Cyber Branch | Feature | Done |  |  | Parent Task |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-123834_COREINSTRUMENTS | 53 | 52 |  | 01.09.07.00.00.00.00.00 | TAP-123834 | TAP-126497 | [TAP-123834_COREINSTRUMENTS] ¦ [IRR] Migrate IRR SW to Post-Cyber Branch | User Story | Done | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 8 | 8 | 8 | 9.6 | 0 | 100% | V4.2 - EC1
TAP-124472 | 54 | 252 |  | 01.10.01.00.00.00.00.00 |  | TAP-124472 | [TAP-124472] ¦ [JBO] Productization of Kinematic Pipeline SWI_TeleopController | Feature | Accepted |  |  | Parent Task |  | 24 | 16 | 1 hr | 1 hr | 8 | 66.67% | V4.2 - EC1
TAP-124472_JACOBIANS | 55 | 54 |  | 01.10.01.01.00.00.00.00 | TAP-124472 | TAP-125802 | [TAP-124472_JACOBIANS] ¦ [JBO] Productization of Kinematic Pipeline SWI_TeleopController | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 24 | 16 | 24 | 28.8 | 8 | 66.67% | V4.2 - EC1
TAP-133812 | 56 |  |  | 01.10.02.00.00.00.00.00 |  | TAP-133812 | [TAP-133812] ¦ [JBO] Productization of SWI_JacobianBasedOptimization | Feature | Accepted |  |  | Parent Task |  | 27.5 | 0 | 1 hr | 1 hr | 27.5 | 0% | V4.2 - EC1
TAP-133812_JACOBIANS | 57 | 56 |  | 01.10.02.01.00.00.00.00 | TAP-133812 | TAP-134961 | [TAP-133812_JACOBIANS] ¦ [JBO] Productization of SWI_JacobianBasedOptimization | User Story | In progress | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 27.5 | 0 | 27.5 | 33 | 27.5 | 0% | V4.2 - EC1
TAP-137324 | 58 |  |  | 01.10.03.00.00.00.00.00 |  | TAP-137324 | [TAP-137324] ¦ [JBO] Requirement and cFMEA Workshops | Feature | Accepted |  |  | Parent Task |  | 14 | 6 | 1 hr | 1 hr | 8 | 42.86% | V4.2 - EC1
TAP-137324_JACOBIANS | 59 | 58 |  | 01.10.03.01.00.00.00.00 | TAP-137324 | TAP-136946 | [TAP-137324_JACOBIANS] ¦ [JBO] Requirement and cFMEA Workshops | User Story | Done | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 14 | 6 | 14 | 16.8 | 8 | 42.86% | V4.2 - EC1
TAP-133814 | 60 |  |  | 01.10.04.00.00.00.00.00 |  | TAP-133814 | [TAP-133814] ¦ [JBO] Productization of CameraControl Kinematic Pipeline and Jaw Pipeline | Feature | Accepted |  |  | Parent Task |  | 32 | 0 | 1 hr | 1 hr | 32 | 0% | V4.2 - EC2
TAP-133814_PUPPETEERS | 61 | 60 |  | 01.10.04.01.00.00.00.00 | TAP-133814 | TAP-134975 | [TAP-133814_PUPPETEERS] ¦ [JBO] Productization of CameraControl Kinematic Pipeline and Jaw Pipeline | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 32 | 0 | 32 | 38.4 | 32 | 0% | V4.2 - EC2
TAP-134602 | 62 |  |  | 01.10.05.00.00.00.00.00 |  | TAP-134602 | [TAP-134602] ¦ [JBO] Finalize JBO Prototype Algorithms for PI16 | Feature | Done |  |  | Parent Task |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-134602_JACOBIANS | 63 | 62 |  | 01.10.05.01.00.00.00.00 | TAP-134602 | TAP-132588 | [TAP-134602_JACOBIANS] ¦ [JBO] Finalize JBO Prototype Algorithms for PI16 | User Story | Done | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 8 | 8 | 8 | 9.6 | 0 | 100% | V4.2 - EC1
TAP-125255 | 64 | 252 |  | 02.01.00.00.00.00.00.00 |  | TAP-125255 | [TAP-125255] ¦ [IRR] Update/Automate Data Recorder V&V for IRR Interface Changes | Feature | Done |  |  | Parent Task |  | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-125255_BOOSTERS | 65 | 64 |  | 02.01.01.00.00.00.00.00 | TAP-125255 | TAP-124574 | [TAP-125255_BOOSTERS] ¦ [IRR] Update/Automate Data Recorder V&V for IRR Interface Changes | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task |  | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-136909 | 66 | 256 |  | 02.02.00.00.00.00.00.00 |  | TAP-136909 | [TAP-136909] ¦ [IRR] Tune Motor and Joint Controller | Feature | PROPOSED |  |  | Parent Task |  | 21 | 0 | 1 hr | 1 hr | 21 | 0% | V4.2 - EC2
TAP-136909_COREINSTRUMENTS | 67 | 66 |  | 02.02.01.00.00.00.00.00 | TAP-136909 | TAP-137036 | [TAP-136909_COREINSTRUMENTS] ¦ [IRR] Tune Motor and Joint Controller | User Story | Open | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 21 | 0 | 21 | 25.2 | 21 | 0% | V4.2 - EC2
TAP-136657 | 68 | 256 |  | 02.03.00.00.00.00.00.00 |  | TAP-136657 | [TAP-136657] ¦ [FSTR][IRR] Integration of the tool design documents into the code repository | Feature | Accepted |  |  | Parent Task |  | 2.5 | 0 | 1 hr | 1 hr | 2.5 | 0% | V4.2 - EC2
TAP-136657_EMBEDDED | 69 | 68 |  | 02.03.01.00.00.00.00.00 | TAP-136657 | TAP-133605 | [TAP-136657_EMBEDDED] ¦ [FSTR][IRR] Integration of the tool design documents into the code repository | User Story | In progress | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 2.5 | 0 | 2.5 | 3 | 2.5 | 0% | V4.2 - EC2
TAP-111749 | 70 | 193,256 |  | 02.04.01.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | Accepted |  |  | Parent Task |  | 12 | 0.5 | 1 hr | 1 hr | 11.5 | 4.167% | V4.2 - EC2
TAP-111749_COREINSTRUMENTS | 71 | 70 |  | 02.04.01.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 12 | 0.5 | 12 | 14.4 | 11.5 | 4.167% | V4.2 - EC2
TAP-111750 | 72 | 256 |  | 02.04.02.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  | Parent Task |  | 11.5 | 0 | 1 hr | 1 hr | 11.5 | 0% | V4.2 - EC2
TAP-111750_COREINSTRUMENTS | 73 | 72 |  | 02.04.02.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 11.5 | 0 | 11.5 | 13.8 | 11.5 | 0% | V4.2 - EC2
TAP-117678 | 74 | 256 |  | 02.04.03.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | Accepted |  |  | Parent Task |  | 28 | 0 | 1 hr | 1 hr | 28 | 0% | V4.2 - EC2
TAP-117678_COREINSTRUMENTS | 75 | 74 |  | 02.04.03.01.00.00.00.00 | TAP-117678 | TAP-127786 | [TAP-117678_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature Estimation | Open | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 28 | 0 | 28 | 33.6 | 28 | 0% | V4.2 - EC2
TAP-136410 | 76 | 256 |  | 02.04.04.00.00.00.00.00 |  | TAP-136410 | [TAP-136410] ¦ [IRR] Productize Kinematics for IRR Wristed Instruments | Feature | Accepted |  |  | Parent Task |  | 37 | 6 | 1 hr | 1 hr | 31 | 16.22% | V4.2 - EC2
TAP-136410_PUPPETEERS | 77 | 76 |  | 02.04.04.02.00.00.00.00 | TAP-136410 | TAP-125837 | [TAP-136410_PUPPETEERS] ¦ [IRR] Productize Kinematics for IRR Wristed Instruments | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 37 | 6 | 37 | 44.4 | 31 | 16.22% | V4.2 - EC2
TAP-132462 | 78 | 256 |  | 02.06.00.00.00.00.00.00 |  | TAP-132462 | [TAP-132462] ¦ [IRR] Finish IRR Merge to Develop and v4 Staging Branch | Feature | Accepted |  |  | Parent Task |  | 4 | 0 | 1 hr | 1 hr | 4 | 0% | V4.2 - EC2
TAP-132462_COREINSTRUMENTS | 79 | 78 |  | 02.06.01.00.00.00.00.00 | TAP-132462 | TAP-133364 | [TAP-132462_COREINSTRUMENTS] ¦ [IRR] Finish IRR Merge to Develop and v4 Staging Branch | User Story | Open | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 4 | 0 | 4 | 4.8 | 4 | 0% | V4.2 - EC2
TAP-137313 | 80 | 256 |  | 02.07.01.00.00.00.00.00 |  | TAP-137313 | [TAP-137313] ¦ [JBO] Support of External Contractors for PI16 | Feature | Accepted |  |  | Parent Task |  | 5 | 1 | 1 hr | 1 hr | 4 | 20% | V4.2 - EC2
TAP-137313_JACOBIANS | 81 | 80 |  | 02.07.01.01.00.00.00.00 | TAP-137313 | TAP-136391 | [TAP-137313_JACOBIANS] ¦ [JBO] Support of External Contractors for PI16 | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 5 | 1 | 5 | 6 | 4 | 20% | V4.2 - EC2
TAP-137334 | 82 | 256 |  | 02.07.02.00.00.00.00.00 |  | TAP-137334 | [TAP-137334] ¦ [JBO] Productize SWI-549 SraKinematicValidation | Feature | PROPOSED |  |  | Parent Task |  | 48 | 0 | 1 hr | 1 hr | 40 | 0% | V4.2 - EC2
TAP-137334_JACOBIANS | 83 | 82 |  | 02.07.02.01.00.00.00.00 | TAP-137334 | TAP-137335 | [TAP-137334_JACOBIANS] ¦ [JBO] Productize SWI-549 SraKinematicValidation | Feature Estimation | Done | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 40 | 60 | 40 | 0% | V4.2 - EC2
TAP-137337 | 84 | 256 |  | 02.07.03.00.00.00.00.00 |  | TAP-137337 | [TAP-137337] ¦ [JBO] Develop Force Feedback MIL Tests | Feature | Accepted |  |  | Parent Task |  | 10 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - EC2
TAP-137337_JACOBIANS | 85 | 84 |  | 02.07.03.01.00.00.00.00 | TAP-137337 | TAP-137338 | [TAP-137337_JACOBIANS] ¦ [JBO] Develop Force Feedback MIL Tests | Feature Estimation | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 10 | 0 | 10 | 12 | 10 | 0% | V4.2 - EC2
TAP-137339 | 86 | 256 |  | 02.07.04.00.00.00.00.00 |  | TAP-137339 | [TAP-137339] ¦ [JBO] Develop Design Documents for all JBO SWIs | Feature | PROPOSED |  |  | Parent Task |  | 9 | 0 | 1 hr | 1 hr | 12 | 0% | V4.2 - EC2
TAP-137339_JACOBIANS | 87 | 86 |  | 02.07.04.01.00.00.00.00 | TAP-137339 | TAP-137340 | [TAP-137339_JACOBIANS] ¦ [JBO] Develop Design Documents for all JBO SWIs | Feature Estimation | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 12 | 15 | 12 | 0% | V4.2 - EC2
TAP-136914 | 88 | 256 |  | 02.07.05.00.00.00.00.00 |  | TAP-136914 | [TAP-136914] ¦ [BH]JBO PI16 MIL Development and training | Feature | Accepted |  |  | Parent Task |  | 29 | 0 | 1 hr | 1 hr | 29 | 0% | V4.2 - EC2
TAP-136914_BUGHUNTERS | 89 | 88 |  | 02.07.05.01.00.00.00.00 | TAP-136914 | TAP-136840 | [TAP-136914_BUGHUNTERS] ¦ [BH]JBO PI16 MIL Development and training | User Story | Open | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task |  | 29 | 0 | 29 | 34.8 | 29 | 0% | V4.2 - EC2
TAP-133813 | 90 | 256 |  | 02.07.06.00.00.00.00.00 |  | TAP-133813 | [TAP-133813] ¦ [JBO] Productization of Force Feedback | Feature | Accepted |  |  | Parent Task |  | 36 | 0 | 1 hr | 1 hr | 36 | 0% | V4.2 - EC2
TAP-133813_JACOBIANS | 91 | 90 |  | 02.07.06.01.00.00.00.00 | TAP-133813 | TAP-134971 | [TAP-133813_JACOBIANS] ¦ [JBO] Productization of Force Feedback | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 36 | 0 | 36 | 43.2 | 36 | 0% | V4.2 - EC2
TAP-124475 | 92 | 256 |  | 02.07.07.00.00.00.00.00 |  | TAP-124475 | [TAP-124475] ¦ [JBO] Implement RCMs in MSO | Feature | Accepted |  |  | Parent Task |  | 14 | 10 | 1 hr | 1 hr | 4 | 71.43% | V4.2 - EC2
TAP-124475_JACOBIANS | 93 | 92 |  | 02.07.07.01.00.00.00.00 | TAP-124475 | TAP-115761 | [TAP-124475_JACOBIANS] ¦ [JBO] Implement RCMs in MSO | User Story | Done | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 14 | 10 | 14 | 16.8 | 4 | 71.43% | V4.2 - EC2
TAP-137265 | 94 | 256 |  | 02.07.08.00.00.00.00.00 |  | TAP-137265 | [TAP-137265] ¦ [JBO] Productization of SWI-69-MscKinematics and SWI-72-HandleFiltering | Feature | PROPOSED |  |  | Parent Task |  | 19 | 2 | 1 hr | 1 hr | 17 | 10.53% | V4.2 - EC2
TAP-137265_JACOBIANS | 95 | 94 |  | 02.07.08.01.00.00.00.00 | TAP-137265 | TAP-134987 | [TAP-137265_JACOBIANS] ¦ [JBO] Productization of SWI-69-MscKinematics and SWI-72-HandleFiltering | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 19 | 2 | 19 | 22.8 | 17 | 10.53% | V4.2 - EC2
TAP-133906 | 96 | 256 |  | 02.07.09.00.00.00.00.00 |  | TAP-133906 | [TAP-133906] ¦ [JBO] JBO PI16 MIL Development | Feature | Accepted |  |  | Parent Task |  | 41.75 | 13 | 1 hr | 1 hr | 28.75 | 31.14% | V4.2 - EC2
TAP-133906_JACOBIANS | 97 | 96 |  | 02.07.09.01.00.00.00.00 | TAP-133906 | TAP-125809 | [TAP-133906_JACOBIANS] ¦ [JBO] JBO PI16 MIL Development | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 14.75 | 2 | 14.75 | 17.7 | 12.75 | 13.56% | V4.2 - EC2
TAP-133906_PUPPETEERS | 98 | 96 |  | 02.07.09.02.00.00.00.00 | TAP-133906 | TAP-135487 | [TAP-133906_PUPPETEERS] ¦ [JBO] JBO PI16 MIL Development | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 27 | 11 | 27 | 32.4 | 16 | 40.74% | V4.2 - EC2
TAP-133906_COREINSTRUMENTS | 99 |  |  | 02.08.00.00.00.00.00.00 |  | TAP-131923 | [TAP-133906_COREINSTRUMENTS] ¦ [JBO] JBO PI16 MIL Development | User Story | In progress | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-134541 | 100 | 256 |  | 02.09.00.00.00.00.00.00 |  | TAP-134541 | [TAP-134541] ¦ [IRR] Test Development and Dry Run for pre-RC1 | Feature | Accepted |  |  | Parent Task |  | 84 | 12 | 1 hr | 1 hr | 72 | 14.29% | V4.2 - EC2
TAP-134541_COREINSTRUMENTS | 101 | 100 |  | 02.09.01.00.00.00.00.00 | TAP-134541 | TAP-132512 | [TAP-134541_COREINSTRUMENTS] ¦ [IRR] Test Development and Dry Run for pre-RC1 | User Story | Open | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 84 | 12 | 84 | 100.8 | 72 | 14.29% | V4.2 - EC2
TAP-131594 | 102 | 256 |  | 02.10.01.00.00.00.00.00 |  | TAP-131594 | [TAP-131594] ¦ [IRR] [Spike] Algorithm Development of Torque Loss Check De-risking [EC1 Flag] | Feature | Accepted |  |  | Parent Task |  | 11 | 0 | 1 hr | 1 hr | 11 | 0% | V4.2 - EC2
TAP-131594_COREINSTRUMENTS | 103 | 102 |  | 02.10.01.01.00.00.00.00 | TAP-131594 | TAP-126504 | [TAP-131594_COREINSTRUMENTS] ¦ [IRR] [Spike] Algorithm Development of Torque Loss Check De-risking [EC1 Flag] | User Story | Open | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 11 | 0 | 11 | 13.2 | 11 | 0% | V4.2 - EC2
TAP-111747 | 104 | 256 |  | 02.10.02.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 35 | 0% | V4.2 - EC2
TAP-111747_COREINSTRUMENTS | 105 | 104 |  | 02.10.02.01.00.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747_COREINSTRUMENTS] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 35 | 60 | 35 | 0% | V4.2 - EC2
TAP-113111 | 106 | 131 |  | 02.11.01.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Done |  |  | Parent Task |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-113111_PUPPETEERS | 107 | 106 |  | 02.11.01.01.01.00.00.00 | TAP-113111 | TAP-125828 | [TAP-113111_PUPPETEERS] ¦ [IRR][Spike] Plan Interfaces and Architecture for Instrument Usage Table | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 18 | 18 | 18 | 21.6 | 0 | 100% | V4.2 - EC2
TAP-113123 | 108 | 127,131 |  | 02.11.01.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | Done |  |  | Parent Task |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-113123_PIXELPOETS | 109 | 108 |  | 02.11.01.02.01.00.00.00 | TAP-113123 | TAP-124572 | [TAP-113123_PIXELPOETS] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 4 | 4 | 4 | 4.8 | 0 | 100% | V4.2 - EC2
TAP-114692 | 110 | 256 |  | 02.11.01.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | Done |  |  | Parent Task |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-114692_CASTLEBLACK | 111 | 110 |  | 02.11.01.03.01.00.00.00 | TAP-114692 | TAP-116170 | [TAP-114692_CASTLEBLACK] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 2 | 2 | 2 | 2.4 | 0 | 100% | V4.2 - EC2
TAP-114692_PUPPETEERS | 112 | 110 |  | 02.11.01.03.02.00.00.00 | TAP-114692 | TAP-116199 | [TAP-114692_PUPPETEERS] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 20 | 20 | 20 | 24 | 0 | 100% | V4.2 - EC2
TAP-114692_COREINSTRUMENTS | 113 | 110 |  | 02.11.01.03.07.00.00.00 | TAP-114692 | TAP-123143 | [TAP-114692_COREINSTRUMENTS] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | User Story | Done | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 2 | 2 | 2 | 2.4 | 0 | 100% | V4.2 - EC2
TAP-114689 | 114 | 127 |  | 02.11.01.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  | Parent Task |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-114689_PIXELPOETS | 115 | 114 |  | 02.11.01.04.01.00.00.00 | TAP-114689 | TAP-115102 | [TAP-114689_PIXELPOETS] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 13 | 13 | 13 | 15.6 | 0 | 100% | V4.2 - EC2
TAP-130664 | 116 | 256 |  | 02.11.01.05.00.00.00.00 |  | TAP-130664 | [TAP-130664] ¦ [IRR] Prototype UFSW Use Life Summary Screens | Feature | Accepted |  |  | Parent Task |  | 14 | 3 | 1 hr | 1 hr | 11 | 21.43% | V4.2 - EC2
TAP-130664_PUPPETEERS | 117 | 116 |  | 02.11.01.05.01.00.00.00 | TAP-130664 | TAP-135022 | [TAP-130664_PUPPETEERS] ¦ [IRR] Prototype UFSW Use Life Summary Screens | User Story | Groomed | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 14 | 3 | 14 | 16.8 | 11 | 21.43% | V4.2 - EC2
TAP-132912 | 118 | 256 |  | 02.11.01.06.00.00.00.00 |  | TAP-132912 | [TAP-132912] ¦ [IRR] Prototype Use Life Summary Screens | Feature | Accepted |  |  | Parent Task |  | 29 | 0 | 1 hr | 1 hr | 29 | 0% | V4.2 - EC2
TAP-132912_PIXELPOETS | 119 | 118 |  | 02.11.01.06.01.00.00.00 | TAP-132912 | TAP-132288 | [TAP-132912_PIXELPOETS] ¦ [IRR] Prototype Use Life Summary Screens | User Story | In progress | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 29 | 0 | 29 | 34.8 | 29 | 0% | V4.2 - EC2
TAP-90375 | 120 | 256 |  | 02.11.02.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  | Parent Task |  | 9 | 0 | 1 hr | 1 hr | 9 | 0% | V4.2 - EC2
TAP-90375_STELLARS | 121 | 120 |  | 02.11.02.01.01.00.00.00 | TAP-90375 | TAP-96606 | [TAP-90375_STELLARS] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task |  | 9 | 0 | 9 | 10.8 | 9 | 0% | V4.2 - EC2
TAP-111861 | 122 | 256,135 |  | 02.11.02.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | Done |  |  | Parent Task |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-111861_EMBEDDED | 123 | 122 |  | 02.11.02.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_EMBEDDED] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111861_USERFLOWSW | 124 | 122 |  | 02.11.02.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_USERFLOWSW] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111861_DRUSHTI | 125 | 122 |  | 02.11.02.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_DRUSHTI] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111861_PUPPETEERS | 126 | 122 |  | 02.11.02.02.04.00.00.00 | TAP-111861 | TAP-125548 | [TAP-111861_PUPPETEERS] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 32 | 32 | 32 | 38.4 | 0 | 100% | V4.2 - EC2
TAP-111687 | 127 | 256 | 108,114 | 02.11.02.03.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  | Parent Task |  | 2 | 0 | 1 hr | 1 hr | 33 | 0% | V4.2 - EC2
TAP-111687_PIXELPOETS | 128 | 127 |  | 02.11.02.03.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_PIXELPOETS] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 20 | 34 | 20 | 0% | V4.2 - EC2
TAP-111687_USERFLOWSW | 129 | 127 |  | 02.11.02.03.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_USERFLOWSW] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 8 | 12 | 8 | 0% | V4.2 - EC2
TAP-111687_EMBEDDED | 130 | 127 |  | 02.11.02.03.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_EMBEDDED] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | EMBEDDED | Child Task |  | 0 | 0 | 5 | 15 | 5 | 0% | V4.2 - EC2
TAP-111695 | 131 | 256 | 106,108 | 02.11.02.05.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 48 | 0% | V4.2 - EC2
TAP-111695_PIXELPOETS | 132 | 131 |  | 02.11.02.05.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_PIXELPOETS] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 11 | 26 | 11 | 0% | V4.2 - EC2
TAP-111695_USERFLOWSW | 133 | 131 |  | 02.11.02.05.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_USERFLOWSW] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 30 | 50 | 30 | 0% | V4.2 - EC2
TAP-111695_DRUSHTI | 134 | 131 |  | 02.11.02.05.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_DRUSHTI] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task |  | 0 | 0 | 7 | 8 | 7 | 0% | V4.2 - EC2
TAP-133272 | 135 | 256 | 122 | 02.11.02.07.00.00.00.00 |  | TAP-133272 | [TAP-133272] ¦ [IRR] Consolidate IRR Use Life Notification Strategy | Feature | Accepted |  |  | Parent Task |  | 27 | 0 | 1 hr | 1 hr | 27 | 0% | V4.2 - EC2
TAP-133272_PUPPETEERS | 136 | 135 |  | 02.11.02.07.01.00.00.00 | TAP-133272 | TAP-125553 | [TAP-133272_PUPPETEERS] ¦ [IRR] Consolidate IRR Use Life Notification Strategy | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 27 | 0 | 27 | 32.4 | 27 | 0% | V4.2 - EC2
TAP-139183 | 137 |  |  | 02.12.00.00.00.00.00.00 |  | TAP-139183 | [TAP-139183] ¦ [IRR] Update SW to Match Requirement Updates | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - EC2
TAP-111774 | 138 | 148,143,256 |  | 03.01.01.01.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | Done |  |  | Parent Task |  | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-111774_COREINSTRUMENTS | 139 | 138 |  | 03.01.01.01.01.00.00.00 | TAP-111774 | TAP-111970 | [TAP-111774_COREINSTRUMENTS] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111774_JACOBIANS | 140 | 138 |  | 03.01.01.01.02.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774_JACOBIANS] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111774_CASTLEBLACK | 141 | 138 |  | 03.01.01.01.03.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774_CASTLEBLACK] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111774_PUPPETEERS | 142 | 138 |  | 03.01.01.01.04.00.00.00 | TAP-111774 | TAP-116202 | [TAP-111774_PUPPETEERS] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-112080 | 143 | 148,260 | 138 | 03.01.01.02.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature | Accepted |  |  | Parent Task |  | 4 | 0 | 1 hr | 1 hr | 4 | 0% | V4.2 - EC2
TAP-112080_COREINSTRUMENTS | 144 | 143 |  | 03.01.01.02.01.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080_COREINSTRUMENTS] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-112080_JACOBIANS | 145 | 143 |  | 03.01.01.02.02.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_JACOBIANS] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 4 | 0 | 4 | 4.8 | 4 | 0% | V4.2 - EC2
TAP-112080_USERFLOWSW | 146 | 143 |  | 03.01.01.02.03.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_USERFLOWSW] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-112080_INBETWEENERS | 147 | 143 |  | 03.01.01.02.04.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_INBETWEENERS] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775 | 148 | 260 | 138,143 | 03.01.01.03.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature | PROPOSED |  |  | Parent Task |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | V4.2 - EC2
TAP-111775_COREINSTRUMENTS | 149 | 148 |  | 03.01.01.03.01.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775_COREINSTRUMENTS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775_JACOBIANS | 150 | 148 |  | 03.01.01.03.02.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_JACOBIANS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 13 | 0 | 13 | 15.6 | 13 | 0% | V4.2 - EC2
TAP-111775_USERFLOWSW | 151 | 148 |  | 03.01.01.03.03.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_USERFLOWSW] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775_INBETWEENERS | 152 | 148 |  | 03.01.01.03.04.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_INBETWEENERS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775_PUPPETEERS | 153 | 148 |  | 03.01.01.03.05.00.00.00 | TAP-111775 | TAP-121472 | [TAP-111775_PUPPETEERS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 1 | 0 | 1 | 1.2 | 1 | 0% | V4.2 - EC2
TAP-128530 | 154 | 260 |  | 03.01.02.01.00.00.00.00 |  | TAP-128530 | [TAP-128530] ¦ [IRR] Update GUI SW to show message text on full ACAD | Feature | Accepted |  |  | Parent Task |  | 15 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - EC2
TAP-128530_PIXELPOETS | 155 | 154 |  | 03.01.02.01.01.00.00.00 | TAP-128530 | TAP-132099 | [TAP-128530_PIXELPOETS] ¦ [IRR] Update GUI SW to show message text on full ACAD | User Story | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 10 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-128527 | 156 | 260 |  | 03.01.02.02.00.00.00.00 |  | TAP-128527 | [TAP-128527] ¦ [IRR] Update ACAD to No Longer Show Percentages | Feature | Accepted |  |  | Parent Task |  | 10 | 2 | 1 hr | 1 hr | 0 | 0% | V4.2 - EC2
TAP-128527_EMBEDDED | 157 | 156 |  | 03.01.02.02.01.00.00.00 | TAP-128527 | TAP-135543 | [TAP-128527_EMBEDDED] ¦ [IRR] Update ACAD to No Longer Show Percentages | User Story | Done | Foundation - Fred | EMBEDDED | Child Task |  | 2 | 2 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-133880 | 158 | 260,256 |  | 03.01.02.03.00.00.00.00 |  | TAP-133880 | [TAP-133880] ¦ [IRR] Update SRA SW To Not Calculate/Send Percentages | Feature | Accepted |  |  | Parent Task |  | 5 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - EC2
TAP-133880_PUPPETEERS | 159 | 158 |  | 03.01.02.03.01.00.00.00 | TAP-133880 | TAP-136346 | [TAP-133880_PUPPETEERS] ¦ [IRR] Update SRA SW To Not Calculate/Send Percentages | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 5 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-138442 | 160 | 256 |  | 03.01.03.01.00.00.00.00 |  | TAP-138442 | [TAP-138442] ¦ [IRR] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  | Parent Task |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | V4.2 - EC2
TAP-138442_EMBEDDED | 161 | 160 |  | 03.01.03.01.01.00.00.00 | TAP-138442 | TAP-138465 | [TAP-138442_EMBEDDED] ¦ [IRR] Reliability and Instrument Tool Consolidation | User Story | Open | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 3 | 0 | 3 | 3.6 | 3 | 0% | V4.2 - EC2
TAP-123862 | 162 | 256,170 |  | 03.01.04.01.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | Feature | Done |  |  | Parent Task |  | 22.5 | 22.5 | 1 hr | 1 hr | 0 | 100%
TAP-123862_EMBEDDED | 163 | 162 |  | 03.01.04.01.01.00.00.00 | TAP-123862 | TAP-124413 | [TAP-123862_EMBEDDED] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | User Story | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 18.5 | 18.5 | 18.5 | 22.2 | 0 | 100%
TAP-123862_ZENITH | 164 | 162 |  | 03.01.04.01.10.00.00.00 | TAP-123862 | TAP-126037 | [TAP-123862_ZENITH] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | User Story | Done | Advanced Instruments - Zenith | ZENITH | Child Task |  | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-123862_CASTLEBLACK | 165 | 162 |  | 03.01.04.01.11.00.00.00 | TAP-123862 | TAP-126145 | [TAP-123862_CASTLEBLACK] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-123863 | 166 | 256,170 |  | 03.01.04.02.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | Feature | Done |  |  | Parent Task |  | 29.5 | 29.5 | 1 hr | 1 hr | 0 | 100%
TAP-123863_EMBEDDED | 167 | 166 |  | 03.01.04.02.02.00.00.00 | TAP-123863 | TAP-124578 | [TAP-123863_EMBEDDED] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | User Story | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 25.5 | 25.5 | 25.5 | 30.6 | 0 | 100%
TAP-123863_CASTLEBLACK | 168 | 166 |  | 03.01.04.02.11.00.00.00 | TAP-123863 | TAP-126023 | [TAP-123863_CASTLEBLACK] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-123863_NEPTUNE | 169 | 166 |  | 03.01.04.02.16.00.00.00 | TAP-123863 | TAP-134546 | [TAP-123863_NEPTUNE] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | User Story | Done | Advanced Instruments - Neptune | NEPTUNE | Child Task |  | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-111656 | 170 | 260 | 166,162 | 03.01.04.05.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 70 | 0% | V4.2 - EC2
TAP-111656_CLASSY2 | 171 | 170 |  | 03.01.04.05.01.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_CLASSY2] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - EC2
TAP-111656_BOOSTERS | 172 | 170 |  | 03.01.04.05.02.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_BOOSTERS] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - EC2
TAP-111656_INBETWEENERS | 173 | 170 |  | 03.01.04.05.03.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_INBETWEENERS] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-111656_CASTLEBLACK | 174 | 170 |  | 03.01.04.05.04.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_CASTLEBLACK] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-111656_USERFLOWSW | 175 | 170 |  | 03.01.04.05.05.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_USERFLOWSW] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 5 | 10 | 5 | 0% | V4.2 - EC2
TAP-111656_EMBEDDED | 176 | 170 |  | 03.01.04.05.06.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_EMBEDDED] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-111656_COREINSTRUMENTS | 177 | 170 |  | 03.01.04.05.07.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656_COREINSTRUMENTS] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 5 | 15 | 5 | 0% | V4.2 - EC2
TAP-132913 | 178 | 260 |  | 03.01.04.06.00.00.00.00 |  | TAP-132913 | [TAP-132913] ¦ [IRR] Use Life Variant management in BSCM | Feature | Accepted |  |  | Parent Task |  | 5.5 | 0.5 | 1 hr | 1 hr | 5 | 9.091% | V4.2 - EC2
TAP-132913_EMBEDDED | 179 | 178 |  | 03.01.04.06.01.00.00.00 | TAP-132913 | TAP-137248 | [TAP-132913_EMBEDDED] ¦ [IRR] Use Life Variant management in BSCM | User Story | Open | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 5.5 | 0.5 | 5.5 | 6.6 | 5 | 9.091% | V4.2 - EC2
TAP-111838 | 180 | 184,260 |  | 03.01.05.01.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - EC2
TAP-111838_COREINSTRUMENTS | 181 | 180 |  | 03.01.05.01.01.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838_COREINSTRUMENTS] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - EC2
TAP-104213 | 182 | 184,260 |  | 03.01.05.02.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - EC2
TAP-104213_COREINSTRUMENTS | 183 | 182 |  | 03.01.05.02.01.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213_COREINSTRUMENTS] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 45 | 15 | 0% | V4.2 - EC2
TAP-111842 | 184 | 260 | 182,180 | 03.01.05.03.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 40 | 0% | V4.2 - EC2
TAP-111842_COREINSTRUMENTS | 185 | 184 |  | 03.01.05.03.01.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842_COREINSTRUMENTS] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-111842_USERFLOWSW | 186 | 184 |  | 03.01.05.03.02.00.00.00 | TAP-111842 | TAP-127787 | [TAP-111842_USERFLOWSW] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature Estimation | Open | Advanced Instruments - Remus | USERFLOWSW | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-112119 | 187 | 260 |  | 03.02.01.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - EC2
TAP-112119_COREINSTRUMENTS | 188 | 187 |  | 03.02.01.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119_COREINSTRUMENTS] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 10 | 20 | 10 | 0% | V4.2 - EC2
TAP-111925 | 189 | 260 |  | 03.03.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - EC2
TAP-111925_COREINSTRUMENTS | 190 | 189 |  | 03.03.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925_COREINSTRUMENTS] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 30 | 15 | 0% | V4.2 - EC2
TAP-111756 | 191 | 201,264,260 | 33 | 03.04.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Controller SWI | Feature | PROPOSED |  |  | Parent Task |  | 6 | 0 | 1 hr | 1 hr | 35 | 0% | V4.2 - EC2
TAP-111756_COREINSTRUMENTS | 192 | 191 |  | 03.04.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Controller SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 35 | 45 | 35 | 0% | V4.2 - EC2
TAP-111757 | 193 | 203,264,260 | 70 | 03.04.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 16 | 0% | V4.2 - EC2
TAP-111757_COREINSTRUMENTS | 194 | 193 |  | 03.04.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 16 | 30 | 16 | 0% | V4.2 - EC2
TAP-111724 | 195 | 260 |  | 03.05.00.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 27 | 0% | V4.2 - EC2
TAP-111724_COREINSTRUMENTS | 196 | 195 |  | 03.05.01.00.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724_COREINSTRUMENTS] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 27 | 30 | 27 | 0% | V4.2 - EC2
TAP-111761 | 197 | 264 |  | 04.01.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Internal Calibration Module | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 25 | 0% | V4.2 - RC1
TAP-111761_COREINSTRUMENTS | 198 | 197 |  | 04.01.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761_COREINSTRUMENTS] ¦ [IRR] Product SW Development Internal Calibration Module | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 25 | 30 | 25 | 0% | V4.2 - RC1
TAP-110382 | 199 | 264 |  | 04.01.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Module | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 5 | 0% | V4.2 - RC1
TAP-110382_COREINSTRUMENTS | 200 | 199 |  | 04.01.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382_COREINSTRUMENTS] ¦ [IRR] Product SW Development Motor Controller Module | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 5 | 8 | 5 | 0% | V4.2 - RC1
TAP-111762 | 201 | 264 | 191 | 04.01.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Joint Controller Module | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - RC1
TAP-111762_COREINSTRUMENTS | 202 | 201 |  | 04.01.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762_COREINSTRUMENTS] ¦ [IRR] Product SW Development Joint Controller Module | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 25 | 15 | 0% | V4.2 - RC1
TAP-111748 | 203 | 264 | 193 | 04.01.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 8 | 0% | V4.2 - RC1
TAP-111748_COREINSTRUMENTS | 204 | 203 |  | 04.01.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748_COREINSTRUMENTS] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 8 | 15 | 8 | 0% | V4.2 - RC1
TAP-111764 | 205 | 264 |  | 04.01.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development State Machine Module | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - RC1
TAP-111764_COREINSTRUMENTS | 206 | 205 |  | 04.01.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764_COREINSTRUMENTS] ¦ [IRR] Product SW Development State Machine Module | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - RC1
TAP-111766 | 207 | 264 |  | 04.01.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Preprocessor Module | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - RC1
TAP-111766_COREINSTRUMENTS | 208 | 207 |  | 04.01.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766_COREINSTRUMENTS] ¦ [IRR] Product SW Development Preprocessor Module | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 20 | 15 | 0% | V4.2 - RC1
TAP-112082 | 209 | 264 |  | 04.02.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 50 | 0% | V4.2 - RC1
TAP-112082_COREINSTRUMENTS | 210 | 209 |  | 04.02.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082_COREINSTRUMENTS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 60 | 15 | 0% | V4.2 - RC1
TAP-112082_EMBEDDED | 211 | 209 |  | 04.02.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_EMBEDDED] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - RC1
TAP-112082_USERFLOWSW | 212 | 209 |  | 04.02.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_USERFLOWSW] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 10 | 20 | 10 | 0% | V4.2 - RC1
TAP-112082_PIXELPOETS | 213 | 209 |  | 04.02.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 8 | 15 | 8 | 0% | V4.2 - RC1
TAP-112082_JACOBIANS | 214 | 209 |  | 04.02.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 7 | 15 | 7 | 0% | V4.2 - RC1
TAP-112093 | 215 | 264 |  | 04.02.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 135 | 0% | V4.2 - RC1
TAP-112093_COREINSTRUMENTS | 216 | 215 |  | 04.02.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093_COREINSTRUMENTS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 55 | 70 | 55 | 0% | V4.2 - RC1
TAP-112093_EMBEDDED | 217 | 215 |  | 04.02.02.02.00.00.00.00 | TAP-112093 | TAP-127793 | [TAP-112093_EMBEDDED] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112093_USERFLOWSW | 218 | 215 |  | 04.02.02.03.00.00.00.00 | TAP-112093 | TAP-127794 | [TAP-112093_USERFLOWSW] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Remus | USERFLOWSW | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112093_PIXELPOETS | 219 | 215 |  | 04.02.02.04.00.00.00.00 | TAP-112093 | TAP-127795 | [TAP-112093_PIXELPOETS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112093_JACOBIANS | 220 | 215 |  | 04.02.02.05.00.00.00.00 | TAP-112093 | TAP-127796 | [TAP-112093_JACOBIANS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112094 | 221 | 264 |  | 04.02.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 87 | 0% | V4.2 - RC1
TAP-112094_COREINSTRUMENTS | 222 | 221 |  | 04.02.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094_COREINSTRUMENTS] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 87 | 170 | 87 | 0% | V4.2 - RC1
TAP-113100 | 223 | 270 |  | 05.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 250 | 0% | V4.2 - RC2
TAP-113100_COREINSTRUMENTS | 224 | 223 |  | 05.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100_COREINSTRUMENTS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 200 | 400 | 200 | 0% | V4.2 - RC2
TAP-113100_JACOBIANS | 225 | 223 |  | 05.01.02.00.00.00.00.00 | TAP-113100 | TAP-127797 | [TAP-113100_JACOBIANS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 50 | 100 | 50 | 0% | V4.2 - RC2
TAP-111900 | 226 | 275 | 267 | 06.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 197 | 0% | V4.2 - DVR
TAP-111900_COREINSTRUMENTS | 227 | 226 |  | 06.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900_COREINSTRUMENTS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 30 | 60 | 30 | 0% | V4.2 - DVR
TAP-111900_BUGHUNTERS | 228 | 226 |  | 06.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_BUGHUNTERS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task |  | 0 | 0 | 0 | 1 | 0 | 0% | V4.2 - DVR
TAP-111900_JACOBIANS | 229 | 226 |  | 06.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_JACOBIANS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 15 | 20 | 15 | 0% | V4.2 - DVR
TAP-111900_USERFLOWSW | 230 | 226 |  | 06.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_USERFLOWSW] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Romulus | USERFLOWSW | Child Task |  | 0 | 0 | 30 | 40 | 30 | 0% | V4.2 - DVR
TAP-111900_PIXELPOETS | 231 | 226 |  | 06.01.06.00.00.00.00.00 | TAP-111900 | TAP-112682 | [TAP-111900_PIXELPOETS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - DVR
TAP-111900_SUNRISERS | 232 | 226 |  | 06.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_SUNRISERS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task |  | 0 | 0 | 3 | 9 | 3 | 0% | V4.2 - DVR
TAP-111900_TEAMBD | 233 | 226 |  | 06.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_TEAMBD] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task |  | 0 | 0 | 3 | 5 | 3 | 0% | V4.2 - DVR
TAP-111900_COSSACKS | 234 | 226 |  | 06.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_COSSACKS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS | Child Task |  | 0 | 0 | 8 | 13 | 8 | 0% | V4.2 - DVR
TAP-111900_EMBEDDED | 235 | 226 |  | 06.01.13.00.00.00.00.00 | TAP-111900 | TAP-137948 | [TAP-111900_EMBEDDED] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - DVR
TAP-111900_CLASSY | 236 | 226 |  | 06.01.14.00.00.00.00.00 | TAP-111900 | TAP-137949 | [TAP-111900_CLASSY] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Foundation - Classy | CLASSY | Child Task |  | 0 | 0 | 18 | 20 | 18 | 0% | V4.2 - DVR
TAP-111900_PUPPETEERS | 237 | 226 |  | 06.01.15.00.00.00.00.00 | TAP-111900 | TAP-137950 | [TAP-111900_PUPPETEERS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 0 | 0 | 70 | 80 | 70 | 0% | V4.2 - DVR
TAP-112042 | 238 | 275 |  | 06.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V4.2][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 22 | 0% | V4.2 - DVR
TAP-112042_BUILDERS | 239 | 238 |  | 06.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_BUILDERS] ¦ [V4.2][IRR] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS | Child Task |  | 0 | 0 | 22 | 30 | 22 | 0% | V4.2 - DVR
TAP-111692 | 240 | 275 |  | 06.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 130 | 0% | V4.2 - DVR
TAP-111692_ASTRANPSDEVELOPERS | 241 | 240 |  | 06.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_ASTRANPSDEVELOPERS] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task |  | 0 | 0 | 20 | 25 | 20 | 0% | V4.2 - DVR
TAP-111692_TOOLSRULES | 242 | 240 |  | 06.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_TOOLSRULES] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES | Child Task |  | 0 | 0 | 20 | 25 | 20 | 0% | V4.2 - DVR
TAP-111692_INBETWEENERS | 243 | 240 |  | 06.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_INBETWEENERS] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 50 | 65 | 50 | 0% | V4.2 - DVR
TAP-111692_TRIPLETEA | 244 | 240 |  | 06.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_TRIPLETEA] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task |  | 0 | 0 | 40 | 80 | 40 | 0% | V4.2 - DVR
TAP-112231 | 245 | 275 |  | 06.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 40 | 0% | V4.2 - DVR
TAP-112231_ASTRANPSVALIDATORS | 246 | 245 |  | 06.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task |  | 0 | 0 | 40 | 50 | 40 | 0% | V4.2 - DVR
TAP-112233 | 247 | 275 |  | 06.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - DVR
TAP-112233_ASTRANPSVALIDATORS | 248 | 247 |  | 06.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task |  | 0 | 0 | 10 | 20 | 10 | 0% | V4.2 - DVR
TAP-112234 | 249 | 275 |  | 06.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 20 | 0% | V4.2 - DVR
TAP-112234_TOOLSRULES | 250 | 249 |  | 06.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - DVR
TAP-113127 | 251 | 275 |  | 06.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - DVR
TAP-111760 | 252 | 253 | 1,41,30,35,7,13,15,26,11,28,23,33,17,5,52,9,64,54,56,37,62,60,39,47,45,58,21,19 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  | Parent Task | TAP-111721 | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 | TAP-133812 | TAP-130796 | TAP-134602 | TAP-133814 | TAP-129482 | TAP-135038 | TAP-134301 | TAP-132587 | TAP-137324 | TAP-111719 | TAP-124116
TAP-111763 | 253 | 256,255 | 252 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 1 | 0% | V4.2
TAP-111763_SEAMLESS | 254 | 253 |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 1 | 2 | 1 | 0% | V4.2
TAP-127945 | 255 |  | 253 | 07.03.00.00.00.00.00.00 |  | TAP-127945 | [TAP-127945] ¦ [Prochain][IRR] EC1 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2
TAP-113104 | 256 | 257 | 138,253,166,162,122,88,96,92,74,94,76,72,90,70,66,78,82,80,68,84,86,110,116,104,135,118,120,127,102,158,131,100,160 | 07.04.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  | Parent Task | TAP-111861 | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 | TAP-133813 | TAP-111749 | TAP-136909 | TAP-132462 | TAP-137334 | TAP-137313 | TAP-136657 | TAP-137337 | TAP-137339 | TAP-114692 | TAP-130664 | TAP-111747 | TAP-133272 | TAP-132912 | TAP-90375 | TAP-111687 | TAP-131594 | TAP-133880 | TAP-111695 | TAP-134541 | TAP-138442
TAP-113105 | 257 | 264,259 | 256 | 07.05.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2
TAP-113105_SEAMLESS | 258 | 257 |  | 07.05.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2
TAP-127946 | 259 |  | 257 | 07.06.00.00.00.00.00.00 |  | TAP-127946 | [TAP-127946] ¦ [Prochain][IRR] EC2 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2
TAP-137349 | 260 | 261 | 156,154,158,143,148,170,49,178,180,182,184,187,189,191,193,195 | 07.07.00.00.00.00.00.00 |  | TAP-137349 | [TAP-137349] ¦ [IRR][Milestone] EC3 Code Freeze (placeholder) | Feature | PROPOSED |  |  | Parent Task | TAP-111838 | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 | TAP-111757 | TAP-111758 | TAP-111759 | TAP-111724
TAP-137351 | 261 | 263 | 260 | 07.08.00.00.00.00.00.00 |  | TAP-137351 | [TAP-137351] ¦ [IRR][Milestone] EC3 Tagged and Released (Placeholder) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2
TAP-137351_SEAMLESS | 262 | 261 |  | 07.08.01.00.00.00.00.00 | TAP-137351 | TAP-137352 | [TAP-137351_SEAMLESS] ¦ [IRR][Milestone] EC3 Tagged and Released (Placeholder) | Feature Estimation | Open | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2
TAP-137353 | 263 |  | 261 | 07.09.00.00.00.00.00.00 |  | TAP-137353 | [TAP-137353] ¦ [Prochain][IRR] EC3 Prochain Endpoint (Placeholder) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2
TAP-111765 | 264 | 265 | 191,193,197,199,201,203,205,207,209,215,221,257,21 | 07.10.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  | Parent Task | TAP-111764 | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1 | TAP-122269 | TAP-125315 | TAP-127798 | TAP-111719
TAP-111768 | 265 | 266 | 264 | 07.11.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1
TAP-111769 | 266 | 267 | 265 | 07.12.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1
TAP-111767 | 267 | 226,269 | 266 | 07.13.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - RC1
TAP-111767_SEAMLESS | 268 | 267 |  | 07.13.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - RC1
TAP-127947 | 269 |  | 267 | 07.14.00.00.00.00.00.00 |  | TAP-127947 | [TAP-127947] ¦ [Prochain][IRR] RC1 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1
TAP-113101 | 270 | 271 | 223 | 07.15.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113102 | 271 | 272 | 270 | 07.16.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113103 | 272 | 275,274 | 271 | 07.17.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-113103_SEAMLESS | 273 | 272 |  | 07.17.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0%
TAP-127948 | 274 |  | 272 | 07.18.00.00.00.00.00.00 |  | TAP-127948 | [TAP-127948] ¦ [Prochain][IRR] RC2 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121104 | 275 |  | 226,238,240,245,247,249,251,272 | 07.19.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - DVR