## Summary
Resource Names | Sum FDR
COREINSTRUMENTS | 1494.5
EMBEDDED | 173
PUPPETEERS | 253
JACOBIANS | 322
CASTLEBLACK | 9
BOOSTERS | 22
BUGHUNTERS | 25
PIXELPOETS | 110
STELLARS | 9
USERFLOWSW | 123
DRUSHTI | 7
NEPTUNE | 36
ANIMATORS | 30
INBETWEENERS | 70
ZENITH | 1
CLASSY2 | 10
SUNRISERS | 3
TEAMBD | 3
COSSACKS | 8
CLASSY | 18
BUILDERS | 22
ASTRANPSDEVELOPERS | 20
TOOLSRULES | 40
TRIPLETEA | 40
ASTRANPSVALIDATORS | 50
SEAMLESS | 41
Total FDR: | 2939.5

## Log
DataTimeStamp | Selector | Event | Data
2024-12-06 11:20 | TAP-97668_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111730_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-94966_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111554_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111569_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-112077_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-112077_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-124116_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-124116_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111721_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111723_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111723_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-94125_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-94125_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-95800_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-95800_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111740_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111740_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111751_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-130796_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-135038_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-111834_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-132587_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-134301_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-123834_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-124472_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-133812_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-137324_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-133814_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC1
2024-12-06 11:20 | TAP-134602_JACOBIANS | Story Point with 0 Effort | Missing Sum Total SP
2024-12-06 11:20 | TAP-125255_BOOSTERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-136909_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-136657_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-136657_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111749_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111749_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111750_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-117678_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-112842 | Repeated Key | Previous Row: 253, Current: 354
2024-12-06 11:21 | TAP-136410_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-132462_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-137313_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-137334_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-137337_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-137339_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-136914_BUGHUNTERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-133813_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-124475_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-137265_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-133906_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-133906_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-113111_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-113111_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-113111_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-113123_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-114692_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-116170 | Repeated Key | Previous Row: 449, Current: 460
2024-12-06 11:21 | TAP-114689_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-130664_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-132912_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-90375_STELLARS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-90375_STELLARS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-90375_STELLARS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111861_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-128527_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-128530_PIXELPOETS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111687_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-132288 | Repeated Key | Previous Row: 468, Current: 513
2024-12-06 11:21 | TAP-132289 | Repeated Key | Previous Row: 469, Current: 514
2024-12-06 11:21 | TAP-133880_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111695_DRUSHTI | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-133272_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-103448_NEPTUNE | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-95983_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111774_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111774_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-112080_INBETWEENERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:21 | TAP-111775_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-134541_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111747_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-123863_NEPTUNE | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111656_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-130665_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-132913_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-132913_EMBEDDED | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111838_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111838_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-104213_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111842_USERFLOWSW | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-112119_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111925_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111925_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111925_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111753_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111753_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111753_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111754_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111754_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111754_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111756_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111756_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111756_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111757_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111757_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111757_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111758_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111758_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111758_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111759_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - EC2
2024-12-06 11:22 | TAP-111724_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111761_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-110382_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111762_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111748_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111764_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111766_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-112082_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-112093_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-112094_COREINSTRUMENTS | Duplicate Milestone (Key already in Successor List) | V4.2 - RC2
2024-12-06 11:22 | TAP-113100_JACOBIANS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 11:22 | TAP-111900_PUPPETEERS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 11:22 | TAP-112042_BUILDERS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 11:22 | TAP-111692_TRIPLETEA | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 11:22 | TAP-112231_ASTRANPSVALIDATORS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 11:22 | TAP-112233_ASTRANPSVALIDATORS | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 11:22 | TAP-112234_TOOLSRULES | Duplicate Milestone (Key already in Successor List) | V4.2 - DVR
2024-12-06 11:22 | TAP-113127 | Milestone not found in the dictionary | V4.2
2024-12-06 11:22 | TAP-137353 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111765 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111768 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111769 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:22 | TAP-111769 | Duplicate Milestone (Key already in Successor List) | V4.2 - RC1
2024-12-06 11:23 | TAP-120097 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-124062 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111554 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111569 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-112077 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-124116 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-124116 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111719 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111719 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111723 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-94125 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-94125 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-95800 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-95800 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111740 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111740 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111751 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111751 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-130796 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-135038 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-111834 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-132587 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-134301 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-123834 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-124472 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-133812 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-137324 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-133814 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-134602 | Missing Unique ID Successor | V4.2 - EC1
2024-12-06 11:23 | TAP-136909 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-136657 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111749 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111749 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111750 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111750 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-117678 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-136410 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-132462 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-137313 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-137334 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-137337 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-137339 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-136914 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-133813 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-124475 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-137265 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-133906 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-113111 | Missing Unique ID Successor | TAP-111689
2024-12-06 11:23 | TAP-113111 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-113111 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-113123 | Missing Unique ID Successor | TAP-111689
2024-12-06 11:23 | TAP-113123 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-113123 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-113123 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-114692 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-114689 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-130664 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-132912 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-90375 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111861 | Missing Unique ID Successor | TAP-133471
2024-12-06 11:23 | TAP-111861 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111861 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111861 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-128527 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-128530 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111687 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-133880 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111695 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-133272 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-103448 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-95983 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-123914 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-112080 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-112080 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111775 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-134541 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111747 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-131594 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111656 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-130665 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-132913 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111838 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111838 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-104213 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-104213 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111842 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-112119 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111925 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111753 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111753 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111753 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111754 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111754 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111754 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111756 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111756 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111756 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111757 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111757 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111757 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111758 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111758 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111758 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111759 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111759 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111759 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111724 | Missing Unique ID Successor | V4.2 - EC2
2024-12-06 11:23 | TAP-111761 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-110382 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111762 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111748 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111764 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111766 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-112082 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-112093 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-112094 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-113100 | Missing Unique ID Successor | V4.2 - RC2
2024-12-06 11:23 | TAP-111900 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 11:23 | TAP-112042 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 11:23 | TAP-111692 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 11:23 | TAP-112231 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 11:23 | TAP-112233 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 11:23 | TAP-112234 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 11:23 | TAP-113127 | Missing Unique ID Successor | V4.2 - DVR
2024-12-06 11:23 | TAP-111760 | Missing Unique ID Predecessor | TAP-129482
2024-12-06 11:23 | TAP-113104 | Missing Unique ID Predecessor | TAP-111772
2024-12-06 11:23 | TAP-113104 | Missing Unique ID Predecessor | TAP-111773
2024-12-06 11:23 | TAP-113104 | Missing Unique ID Predecessor | TAP-111642
2024-12-06 11:23 | TAP-113104 | Missing Unique ID Predecessor | TAP-112113
2024-12-06 11:23 | TAP-113104 | Missing Unique ID Predecessor | TAP-123818
2024-12-06 11:23 | TAP-113104 | Missing Unique ID Predecessor | TAP-111689
2024-12-06 11:23 | TAP-111765 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111765 | Missing Unique ID Predecessor | TAP-124484
2024-12-06 11:23 | TAP-111765 | Missing Unique ID Predecessor | TAP-109680
2024-12-06 11:23 | TAP-111765 | Missing Unique ID Predecessor | TAP-122269
2024-12-06 11:23 | TAP-111765 | Missing Unique ID Predecessor | TAP-125315
2024-12-06 11:23 | TAP-111765 | Missing Unique ID Predecessor | TAP-127798
2024-12-06 11:23 | TAP-111768 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111769 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111767 | Missing Unique ID Successor | V4.2 - RC1
2024-12-06 11:23 | TAP-111767 | Missing Unique ID Successor | V4.2 - RC1
Input Data File Path: | C:\Users\sapird3\Downloads\IRR_Medium_Term_NEW_241101_1345 (1).xls
Input Mapping File Path: | C:\Users\sapird3\Downloads\Team Mapping for Jira Project converter.xlsx
Creation Date: | 12/06/2024
Latest Update: | 12/06/2024
Script Execution Time (sec): | 185.13 seconds
Script Execution Time (min): | 3.09 minutes

## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete | Milestone
TAP-94739 | 1 | 3,267 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  | Parent Task |  | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-94739_COREINSTRUMENTS | 2 | 1 |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-94739_COREINSTRUMENTS] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-97668 | 3 | 5 | 1 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  | Parent Task |  | 32.5 | 32.5 | 1 hr | 1 hr | 0 | 100%
TAP-97668_COREINSTRUMENTS | 4 | 3 |  | 01.01.02.01.00.00.00.00 | TAP-97668 | TAP-111972 | [TAP-97668_COREINSTRUMENTS] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 32.5 | 32.5 | 32.5 | 39 | 0 | 100%
TAP-120097 | 5 | 267 | 3 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | Done |  |  | Parent Task |  | 46.5 | 46.5 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-120097_COREINSTRUMENTS | 6 | 5 |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-106674 | [TAP-120097_COREINSTRUMENTS] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 46.5 | 46.5 | 46.5 | 55.8 | 0 | 100% | V4.2 - EC1
TAP-111730 | 7 | 267,9 |  | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | Done |  |  | Parent Task |  | 20 | 20 | 1 hr | 1 hr | 0 | 100%
TAP-111730_COREINSTRUMENTS | 8 | 7 |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 | [TAP-111730_COREINSTRUMENTS] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 20 | 20 | 20 | 24 | 0 | 100%
TAP-124062 | 9 | 267 | 7 | 01.02.02.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | Done |  |  | Parent Task |  | 38 | 38 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-124062_COREINSTRUMENTS | 10 | 9 |  | 01.02.02.01.00.00.00.00 | TAP-124062 | TAP-116459 | [TAP-124062_COREINSTRUMENTS] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | User Story | Done | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 38 | 38 | 38 | 45.6 | 0 | 100% | V4.2 - EC1
TAP-94966 | 11 | 267 |  | 01.03.01.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | Done |  |  | Parent Task |  | 37 | 37 | 1 hr | 1 hr | 0 | 100%
TAP-94966_COREINSTRUMENTS | 12 | 11 |  | 01.03.01.01.00.00.00.00 | TAP-94966 | TAP-111781 | [TAP-94966_COREINSTRUMENTS] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 37 | 37 | 37 | 44.4 | 0 | 100%
TAP-111554 | 13 | 267 |  | 01.03.02.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness | Feature | Done |  |  | Parent Task |  | 35 | 35 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-111554_COREINSTRUMENTS | 14 | 13 |  | 01.03.02.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554_COREINSTRUMENTS] ¦ [IRR][Enhancement] Improve Cutting Control Robustness | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 35 | 35 | 35 | 42 | 0 | 100% | V4.2 - EC1
TAP-111569 | 15 | 267 |  | 01.03.04.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] P1/P1+ Instrument Integration, Testing, Tuning, EC1 Design Reviews | Feature | Accepted |  |  | Parent Task |  | 56 | 2 | 1 hr | 1 hr | 54 | 3.571% | V4.2 - EC1
TAP-111569_COREINSTRUMENTS | 16 | 15 |  | 01.03.04.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569_COREINSTRUMENTS] ¦ [IRR][Enabler] P1/P1+ Instrument Integration, Testing, Tuning, EC1 Design Reviews | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 56 | 2 | 56 | 67.2 | 54 | 3.571% | V4.2 - EC1
TAP-112077 | 17 | 267 |  | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Done |  |  | Parent Task |  | 34 | 34 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-112077_COREINSTRUMENTS | 18 | 17 |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077_COREINSTRUMENTS] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 34 | 34 | 34 | 40.8 | 0 | 100% | V4.2 - EC1
TAP-124116 | 19 | 21,267 |  | 01.05.02.00.00.00.00.00 |  | TAP-124116 | [TAP-124116] ¦ [IRR][Enabler] Setup of EtherCAT DAQ module for Synchronized Data Acquisition | Feature | In progress |  |  | Parent Task |  | 13 | 0 | 1 hr | 1 hr | 13 | 0% | V4.2 - EC1
TAP-124116_EMBEDDED | 20 | 19 |  | 01.05.02.01.00.00.00.00 | TAP-124116 | TAP-124075 | [TAP-124116_EMBEDDED] ¦ [IRR][Enabler] Setup of EtherCAT DAQ module for Synchronized Data Acquisition | User Story | In progress | Foundation - Fred | EMBEDDED | Child Task |  | 13 | 0 | 13 | 15.6 | 13 | 0% | V4.2 - EC1
TAP-111719 | 21 | 279,267 | 19 | 01.05.03.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  | Parent Task |  | 7 | 2 | 1 hr | 1 hr | 5 | 28.57% | V4.2 - EC1
TAP-111719_EMBEDDED | 22 | 21 |  | 01.05.03.02.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719_EMBEDDED] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 7 | 2 | 7 | 8.4 | 5 | 28.57% | V4.2 - EC1
TAP-111721 | 23 | 267 |  | 01.05.04.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | Done |  |  | Parent Task |  | 24.5 | 24.5 | 1 hr | 1 hr | 0 | 100%
TAP-111721_COREINSTRUMENTS | 24 | 23 |  | 01.05.04.01.00.00.00.00 | TAP-111721 | TAP-111917 | [TAP-111721_COREINSTRUMENTS] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 22.5 | 22.5 | 22.5 | 27 | 0 | 100%
TAP-111721_PUPPETEERS | 25 | 23 |  | 01.05.04.11.00.00.00.00 | TAP-111721 | TAP-123066 | [TAP-111721_PUPPETEERS] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-111723 | 26 | 267 |  | 01.05.05.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates RUFS lab ( no date continous lab) | Feature | Accepted |  |  | Parent Task |  | 5 | 0 | 1 hr | 1 hr | 5 | 0% | V4.2 - EC1
TAP-111723_COREINSTRUMENTS | 27 | 26 |  | 01.05.05.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723_COREINSTRUMENTS] ¦ [IRR][Enabler] Labs Support for Controller Updates RUFS lab ( no date continous lab) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 5 | 0 | 5 | 6 | 5 | 0% | V4.2 - EC1
TAP-94125 | 28 | 198,267 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | Accepted |  |  | Parent Task |  | 37 | 0 | 1 hr | 1 hr | 37 | 0% | V4.2 - EC1
TAP-94125_COREINSTRUMENTS | 29 | 28 |  | 01.06.01.02.00.00.00.00 | TAP-94125 | TAP-97748 | [TAP-94125_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | User Story | In progress | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 37 | 0 | 37 | 44.4 | 37 | 0% | V4.2 - EC1
TAP-95800 | 30 | 200,267 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | In progress |  |  | Parent Task |  | 46 | 46 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-95800_COREINSTRUMENTS | 31 | 30 |  | 01.06.02.02.00.00.00.00 | TAP-95800 | TAP-111779 | [TAP-95800_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 41 | 41 | 41 | 49.2 | 0 | 100% | V4.2 - EC1
TAP-95800_EMBEDDED | 32 | 30 |  | 01.06.02.21.00.00.00.00 | TAP-95800 | TAP-130566 | [TAP-95800_EMBEDDED] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | User Story | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 5 | 5 | 5 | 6 | 0 | 100% | V4.2 - EC1
TAP-111740 | 33 | 202,267 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | Done |  |  | Parent Task |  | 40.5 | 40.5 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-111740_COREINSTRUMENTS | 34 | 33 |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 40.5 | 40.5 | 40.5 | 48.6 | 0 | 100% | V4.2 - EC1
TAP-111751 | 35 | 208,267 |  | 01.06.04.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | Accepted |  |  | Parent Task |  | 22 | 0 | 1 hr | 1 hr | 22 | 0% | V4.2 - EC1
TAP-111751_COREINSTRUMENTS | 36 | 35 |  | 01.06.04.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 22 | 0 | 22 | 26.4 | 22 | 0% | V4.2 - EC1
TAP-130796 | 37 | 267 |  | 01.06.05.00.00.00.00.00 |  | TAP-130796 | [TAP-130796] ¦ [IRR][Phase 1b] Test Cleanup for IRR Controller Release | Feature | Done |  |  | Parent Task |  | 16 | 16 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-130796_COREINSTRUMENTS | 38 | 37 |  | 01.06.05.01.00.00.00.00 | TAP-130796 | TAP-129700 | [TAP-130796_COREINSTRUMENTS] ¦ [IRR][Phase 1b] Test Cleanup for IRR Controller Release | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 16 | 16 | 16 | 19.2 | 0 | 100% | V4.2 - EC1
TAP-135038 | 39 | 267 |  | 01.06.06.00.00.00.00.00 |  | TAP-135038 | [TAP-135038] ¦ [IRR] Finalize Joint Controller | Feature | Accepted |  |  | Parent Task |  | 8 | 0 | 1 hr | 1 hr | 8 | 0% | V4.2 - EC1
TAP-135038_COREINSTRUMENTS | 40 | 39 |  | 01.06.06.01.00.00.00.00 | TAP-135038 | TAP-126529 | [TAP-135038_COREINSTRUMENTS] ¦ [IRR] Finalize Joint Controller | User Story | Open | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 8 | 0 | 8 | 9.6 | 8 | 0% | V4.2 - EC1
TAP-111834 | 41 | 267 |  | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | Accepted |  |  | Parent Task |  | 17 | 7 | 1 hr | 1 hr | 10 | 41.18% | V4.2 - EC1
TAP-111834_JACOBIANS | 42 | 41 |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834_JACOBIANS] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC1
TAP-111834_CASTLEBLACK | 43 | 41 |  | 01.07.01.02.00.00.00.00 | TAP-111834 | TAP-126232 | [TAP-111834_CASTLEBLACK] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 1 | 0 | 1 | 1.2 | 1 | 0% | V4.2 - EC1
TAP-111834_COREINSTRUMENTS | 44 | 41 |  | 01.07.01.03.00.00.00.00 | TAP-111834 | TAP-126522 | [TAP-111834_COREINSTRUMENTS] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 16 | 7 | 16 | 19.2 | 9 | 43.75% | V4.2 - EC1
TAP-132587 | 45 | 267 |  | 01.07.02.00.00.00.00.00 |  | TAP-132587 | [TAP-132587] ¦ [IRR] Support Workflow Updates for IRR Shears | Feature | Accepted |  |  | Parent Task |  | 13 | 0 | 1 hr | 1 hr | 13 | 0% | V4.2 - EC1
TAP-132587_PUPPETEERS | 46 | 45 |  | 01.07.02.01.00.00.00.00 | TAP-132587 | TAP-136339 | [TAP-132587_PUPPETEERS] ¦ [IRR] Support Workflow Updates for IRR Shears | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 13 | 0 | 13 | 15.6 | 13 | 0% | V4.2 - EC1
TAP-134301 | 47 | 267 |  | 01.07.03.00.00.00.00.00 |  | TAP-134301 | [TAP-134301] ¦ [IRR][JBO] Assess LSI Shears and JBO for Reliability+Workspace Impact | Feature | Accepted |  |  | Parent Task |  | 3 | 0 | 1 hr | 1 hr | 3 | 0% | V4.2 - EC1
TAP-134301_JACOBIANS | 48 | 47 |  | 01.07.03.01.00.00.00.00 | TAP-134301 | TAP-136330 | [TAP-134301_JACOBIANS] ¦ [IRR][JBO] Assess LSI Shears and JBO for Reliability+Workspace Impact | User Story | In progress | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 3 | 0 | 3 | 3.6 | 3 | 0% | V4.2 - EC1
TAP-123834 | 49 | 267 |  | 01.08.00.00.00.00.00.00 |  | TAP-123834 | [TAP-123834] ¦ [IRR] Migrate IRR SW to Post-Cyber Branch | Feature | Done |  |  | Parent Task |  | 8 | 8 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC1
TAP-123834_COREINSTRUMENTS | 50 | 49 |  | 01.08.07.00.00.00.00.00 | TAP-123834 | TAP-126497 | [TAP-123834_COREINSTRUMENTS] ¦ [IRR] Migrate IRR SW to Post-Cyber Branch | User Story | Done | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 8 | 8 | 8 | 9.6 | 0 | 100% | V4.2 - EC1
TAP-124472 | 51 | 267 |  | 01.09.01.00.00.00.00.00 |  | TAP-124472 | [TAP-124472] ¦ [JBO] Productization of Kinematic Pipeline SWI_TeleopController | Feature | Accepted |  |  | Parent Task |  | 24 | 7 | 1 hr | 1 hr | 17 | 29.17% | V4.2 - EC1
TAP-124472_JACOBIANS | 52 | 51 |  | 01.09.01.01.00.00.00.00 | TAP-124472 | TAP-125802 | [TAP-124472_JACOBIANS] ¦ [JBO] Productization of Kinematic Pipeline SWI_TeleopController | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 24 | 7 | 24 | 28.8 | 17 | 29.17% | V4.2 - EC1
TAP-133812 | 53 | 267 |  | 01.09.02.00.00.00.00.00 |  | TAP-133812 | [TAP-133812] ¦ [JBO] Productization of SWI_JacobianBasedOptimization | Feature | Accepted |  |  | Parent Task |  | 28 | 0 | 1 hr | 1 hr | 28 | 0% | V4.2 - EC1
TAP-133812_JACOBIANS | 54 | 53 |  | 01.09.02.01.00.00.00.00 | TAP-133812 | TAP-134961 | [TAP-133812_JACOBIANS] ¦ [JBO] Productization of SWI_JacobianBasedOptimization | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 28 | 0 | 28 | 33.6 | 28 | 0% | V4.2 - EC1
TAP-137324 | 55 | 267 |  | 01.09.03.00.00.00.00.00 |  | TAP-137324 | [TAP-137324] ¦ [JBO] Requirement and cFMEA Workshops | Feature | Accepted |  |  | Parent Task |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | V4.2 - EC1
TAP-137324_JACOBIANS | 56 | 55 |  | 01.09.03.01.00.00.00.00 | TAP-137324 | TAP-136946 | [TAP-137324_JACOBIANS] ¦ [JBO] Requirement and cFMEA Workshops | User Story | In progress | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 12 | 0 | 12 | 14.4 | 12 | 0% | V4.2 - EC1
TAP-133814 | 57 | 267 |  | 01.09.04.00.00.00.00.00 |  | TAP-133814 | [TAP-133814] ¦ [JBO] Productization of CameraControl Kinematic Pipeline and Jaw Pipeline | Feature | Accepted |  |  | Parent Task |  | 32 | 0 | 1 hr | 1 hr | 32 | 0% | V4.2 - EC1
TAP-133814_PUPPETEERS | 58 | 57 |  | 01.09.04.01.00.00.00.00 | TAP-133814 | TAP-134975 | [TAP-133814_PUPPETEERS] ¦ [JBO] Productization of CameraControl Kinematic Pipeline and Jaw Pipeline | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 32 | 0 | 32 | 38.4 | 32 | 0% | V4.2 - EC1
TAP-134602 | 59 | 267 |  | 01.09.05.00.00.00.00.00 |  | TAP-134602 | [TAP-134602] ¦ [JBO] Finalize JBO Prototype Algorithms for PI16 | Feature | Accepted |  |  | Parent Task |  | 6 | 1 | 1 hr | 1 hr | 5 | 16.67% | V4.2 - EC1
TAP-134602_JACOBIANS | 60 | 59 |  | 01.09.05.01.00.00.00.00 | TAP-134602 | TAP-132588 | [TAP-134602_JACOBIANS] ¦ [JBO] Finalize JBO Prototype Algorithms for PI16 | User Story | In progress | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 6 | 1 | 6 | 7.2 | 5 | 16.67% | V4.2 - EC1
TAP-125255 | 61 | 267 |  | 02.01.00.00.00.00.00.00 |  | TAP-125255 | [TAP-125255] ¦ [IRR] Update/Automate Data Recorder V&V for IRR Interface Changes | Feature | Done |  |  | Parent Task |  | 12 | 12 | 1 hr | 1 hr | 0 | 100%
TAP-125255_BOOSTERS | 62 | 61 |  | 02.01.01.00.00.00.00.00 | TAP-125255 | TAP-124574 | [TAP-125255_BOOSTERS] ¦ [IRR] Update/Automate Data Recorder V&V for IRR Interface Changes | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task |  | 12 | 12 | 12 | 14.4 | 0 | 100%
TAP-136909 | 63 | 271 |  | 02.02.00.00.00.00.00.00 |  | TAP-136909 | [TAP-136909] ¦ [IRR] Tune Motor and Joint Controller | Feature | Accepted |  |  | Parent Task |  | 21 | 0 | 1 hr | 1 hr | 21 | 0% | V4.2 - EC2
TAP-136909_COREINSTRUMENTS | 64 | 63 |  | 02.02.01.00.00.00.00.00 | TAP-136909 | TAP-137036 | [TAP-136909_COREINSTRUMENTS] ¦ [IRR] Tune Motor and Joint Controller | User Story | Open | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 21 | 0 | 21 | 25.2 | 21 | 0% | V4.2 - EC2
TAP-136657 | 65 | 271 |  | 02.03.00.00.00.00.00.00 |  | TAP-136657 | [TAP-136657] ¦ [FSTR][IRR] Integration of the tool design documents into the code repository | Feature | Accepted |  |  | Parent Task |  | 2.5 | 0 | 1 hr | 1 hr | 2.5 | 0% | V4.2 - EC2
TAP-136657_EMBEDDED | 66 | 65 |  | 02.03.01.00.00.00.00.00 | TAP-136657 | TAP-133605 | [TAP-136657_EMBEDDED] ¦ [FSTR][IRR] Integration of the tool design documents into the code repository | User Story | Open | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 2.5 | 0 | 2.5 | 3 | 2.5 | 0% | V4.2 - EC2
TAP-111749 | 67 | 204,271 |  | 02.04.01.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | Accepted |  |  | Parent Task |  | 12 | 0 | 1 hr | 1 hr | 12 | 0% | V4.2 - EC2
TAP-111749_COREINSTRUMENTS | 68 | 67 |  | 02.04.01.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 12 | 0 | 12 | 14.4 | 12 | 0% | V4.2 - EC2
TAP-111750 | 69 | 206,271 |  | 02.04.02.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  | Parent Task |  | 11.5 | 0 | 1 hr | 1 hr | 11.5 | 0% | V4.2 - EC2
TAP-111750_COREINSTRUMENTS | 70 | 69 |  | 02.04.02.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 11.5 | 0 | 11.5 | 13.8 | 11.5 | 0% | V4.2 - EC2
TAP-117678 | 71 | 271 |  | 02.04.03.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | Accepted |  |  | Parent Task |  | 23 | 0 | 1 hr | 1 hr | 23 | 0% | V4.2 - EC2
TAP-117678_COREINSTRUMENTS | 72 | 71 |  | 02.04.03.01.00.00.00.00 | TAP-117678 | TAP-127786 | [TAP-117678_COREINSTRUMENTS] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature Estimation | Open | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 23 | 0 | 23 | 27.6 | 23 | 0% | V4.2 - EC2
TAP-136410 | 73 | 271 |  | 02.04.04.00.00.00.00.00 |  | TAP-136410 | [TAP-136410] ¦ [IRR] Productize Kinematics for IRR Wristed Instruments | Feature | Accepted |  |  | Parent Task |  | 37 | 6 | 1 hr | 1 hr | 31 | 16.22% | V4.2 - EC2
TAP-136410_PUPPETEERS | 74 | 73 |  | 02.04.04.02.00.00.00.00 | TAP-136410 | TAP-125837 | [TAP-136410_PUPPETEERS] ¦ [IRR] Productize Kinematics for IRR Wristed Instruments | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 37 | 6 | 37 | 44.4 | 31 | 16.22% | V4.2 - EC2
TAP-132462 | 75 | 271 |  | 02.06.00.00.00.00.00.00 |  | TAP-132462 | [TAP-132462] ¦ [IRR] Finish IRR Merge to Develop and v4 Staging Branch | Feature | Accepted |  |  | Parent Task |  | 4 | 0 | 1 hr | 1 hr | 4 | 0% | V4.2 - EC2
TAP-132462_COREINSTRUMENTS | 76 | 75 |  | 02.06.01.00.00.00.00.00 | TAP-132462 | TAP-133364 | [TAP-132462_COREINSTRUMENTS] ¦ [IRR] Finish IRR Merge to Develop and v4 Staging Branch | User Story | Open | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 4 | 0 | 4 | 4.8 | 4 | 0% | V4.2 - EC2
TAP-137313 | 77 | 271 |  | 02.07.01.00.00.00.00.00 |  | TAP-137313 | [TAP-137313] ¦ [JBO] Support of External Contractors for PI16 | Feature | Accepted |  |  | Parent Task |  | 5 | 0 | 1 hr | 1 hr | 5 | 0% | V4.2 - EC2
TAP-137313_JACOBIANS | 78 | 77 |  | 02.07.01.01.00.00.00.00 | TAP-137313 | TAP-136391 | [TAP-137313_JACOBIANS] ¦ [JBO] Support of External Contractors for PI16 | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 5 | 0 | 5 | 6 | 5 | 0% | V4.2 - EC2
TAP-137334 | 79 | 271 |  | 02.07.02.00.00.00.00.00 |  | TAP-137334 | [TAP-137334] ¦ [JBO] Productize SWI-549 SraKinematicValidation | Feature | PROPOSED |  |  | Parent Task |  | 46 | 0 | 1 hr | 1 hr | 40 | 0% | V4.2 - EC2
TAP-137334_JACOBIANS | 80 | 79 |  | 02.07.02.01.00.00.00.00 | TAP-137334 | TAP-137335 | [TAP-137334_JACOBIANS] ¦ [JBO] Productize SWI-549 SraKinematicValidation | Feature Estimation | Done | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 40 | 60 | 40 | 0% | V4.2 - EC2
TAP-137337 | 81 | 271 |  | 02.07.03.00.00.00.00.00 |  | TAP-137337 | [TAP-137337] ¦ [JBO] Develop Force Feedback MIL Tests | Feature | Accepted |  |  | Parent Task |  | 10 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - EC2
TAP-137337_JACOBIANS | 82 | 81 |  | 02.07.03.01.00.00.00.00 | TAP-137337 | TAP-137338 | [TAP-137337_JACOBIANS] ¦ [JBO] Develop Force Feedback MIL Tests | Feature Estimation | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 10 | 0 | 10 | 12 | 10 | 0% | V4.2 - EC2
TAP-137339 | 83 | 271 |  | 02.07.04.00.00.00.00.00 |  | TAP-137339 | [TAP-137339] ¦ [JBO] Develop Design Documents for all JBO SWIs | Feature | PROPOSED |  |  | Parent Task |  | 9 | 0 | 1 hr | 1 hr | 12 | 0% | V4.2 - EC2
TAP-137339_JACOBIANS | 84 | 83 |  | 02.07.04.01.00.00.00.00 | TAP-137339 | TAP-137340 | [TAP-137339_JACOBIANS] ¦ [JBO] Develop Design Documents for all JBO SWIs | Feature Estimation | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 12 | 15 | 12 | 0% | V4.2 - EC2
TAP-136914 | 85 | 271 |  | 02.07.05.00.00.00.00.00 |  | TAP-136914 | [TAP-136914] ¦ [BH]JBO PI16 MIL Development and training | Feature | Accepted |  |  | Parent Task |  | 25 | 0 | 1 hr | 1 hr | 25 | 0% | V4.2 - EC2
TAP-136914_BUGHUNTERS | 86 | 85 |  | 02.07.05.01.00.00.00.00 | TAP-136914 | TAP-136840 | [TAP-136914_BUGHUNTERS] ¦ [BH]JBO PI16 MIL Development and training | User Story | Open | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task |  | 25 | 0 | 25 | 30 | 25 | 0% | V4.2 - EC2
TAP-133813 | 87 | 271 |  | 02.07.06.00.00.00.00.00 |  | TAP-133813 | [TAP-133813] ¦ [JBO] Productization of Force Feedback | Feature | Accepted |  |  | Parent Task |  | 34 | 0 | 1 hr | 1 hr | 34 | 0% | V4.2 - EC2
TAP-133813_JACOBIANS | 88 | 87 |  | 02.07.06.01.00.00.00.00 | TAP-133813 | TAP-134971 | [TAP-133813_JACOBIANS] ¦ [JBO] Productization of Force Feedback | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 34 | 0 | 34 | 40.8 | 34 | 0% | V4.2 - EC2
TAP-124475 | 89 | 271 |  | 02.07.07.00.00.00.00.00 |  | TAP-124475 | [TAP-124475] ¦ [JBO] Implement RCMs in MSO | Feature | Accepted |  |  | Parent Task |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | V4.2 - EC2
TAP-124475_JACOBIANS | 90 | 89 |  | 02.07.07.01.00.00.00.00 | TAP-124475 | TAP-115761 | [TAP-124475_JACOBIANS] ¦ [JBO] Implement RCMs in MSO | User Story | In progress | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 14 | 0 | 14 | 16.8 | 14 | 0% | V4.2 - EC2
TAP-137265 | 91 | 271 |  | 02.07.08.00.00.00.00.00 |  | TAP-137265 | [TAP-137265] ¦ [JBO] Productization of SWI-69-MscKinematics and SWI-72-HandleFiltering | Feature | PROPOSED |  |  | Parent Task |  | 11 | 0 | 1 hr | 1 hr | 11 | 0% | V4.2 - EC2
TAP-137265_JACOBIANS | 92 | 91 |  | 02.07.08.01.00.00.00.00 | TAP-137265 | TAP-134987 | [TAP-137265_JACOBIANS] ¦ [JBO] Productization of SWI-69-MscKinematics and SWI-72-HandleFiltering | User Story | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 11 | 0 | 11 | 13.2 | 11 | 0% | V4.2 - EC2
TAP-133906 | 93 | 271 |  | 02.07.09.00.00.00.00.00 |  | TAP-133906 | [TAP-133906] ¦ [JBO] JBO PI16 MIL Development | Feature | Accepted |  |  | Parent Task |  | 41 | 0 | 1 hr | 1 hr | 41 | 0% | V4.2 - EC2
TAP-133906_JACOBIANS | 94 | 93 |  | 02.07.09.01.00.00.00.00 | TAP-133906 | TAP-125809 | [TAP-133906_JACOBIANS] ¦ [JBO] JBO PI16 MIL Development | User Story | Open | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 14 | 0 | 14 | 16.8 | 14 | 0% | V4.2 - EC2
TAP-133906_PUPPETEERS | 95 | 93 |  | 02.07.09.02.00.00.00.00 | TAP-133906 | TAP-135487 | [TAP-133906_PUPPETEERS] ¦ [JBO] JBO PI16 MIL Development | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 27 | 0 | 27 | 32.4 | 27 | 0% | V4.2 - EC2
TAP-133906_COREINSTRUMENTS | 96 |  |  | 02.08.00.00.00.00.00.00 |  | TAP-131923 | [TAP-133906_COREINSTRUMENTS] ¦ [JBO] JBO PI16 MIL Development | User Story | In progress | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-113111 | 97 | 128 |  | 03.01.01.01.01.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Done |  |  | Parent Task |  | 18 | 18 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-113111_PUPPETEERS | 98 | 97 |  | 03.01.01.01.01.01.00.00 | TAP-113111 | TAP-125828 | [TAP-113111_PUPPETEERS] ¦ [IRR][Spike] Plan Interfaces and Architecture for Instrument Usage Table | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 18 | 18 | 18 | 21.6 | 0 | 100% | V4.2 - EC2
TAP-113123 | 99 | 122,128 |  | 03.01.01.01.02.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | Done |  |  | Parent Task |  | 4 | 4 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-113123_PIXELPOETS | 100 | 99 |  | 03.01.01.01.02.01.00.00 | TAP-113123 | TAP-124572 | [TAP-113123_PIXELPOETS] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 4 | 4 | 4 | 4.8 | 0 | 100% | V4.2 - EC2
TAP-114692 | 101 | 271 |  | 03.01.01.01.03.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | Done |  |  | Parent Task |  | 24 | 24 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-114692_CASTLEBLACK | 102 | 101 |  | 03.01.01.01.03.01.00.00 | TAP-114692 | TAP-116170 | [TAP-114692_CASTLEBLACK] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 2 | 2 | 2 | 2.4 | 0 | 100% | V4.2 - EC2
TAP-114692_PUPPETEERS | 103 | 101 |  | 03.01.01.01.03.02.00.00 | TAP-114692 | TAP-116199 | [TAP-114692_PUPPETEERS] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 20 | 20 | 20 | 24 | 0 | 100% | V4.2 - EC2
TAP-114692_COREINSTRUMENTS | 104 | 101 |  | 03.01.01.01.03.07.00.00 | TAP-114692 | TAP-123143 | [TAP-114692_COREINSTRUMENTS] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | User Story | Done | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 2 | 2 | 2 | 2.4 | 0 | 100% | V4.2 - EC2
TAP-114689 | 105 | 122 |  | 03.01.01.01.04.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  | Parent Task |  | 15 | 15 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-114689_PIXELPOETS | 106 | 105 |  | 03.01.01.01.04.01.00.00 | TAP-114689 | TAP-115102 | [TAP-114689_PIXELPOETS] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 13 | 13 | 13 | 15.6 | 0 | 100% | V4.2 - EC2
TAP-130664 | 107 | 275 |  | 03.01.01.01.05.00.00.00 |  | TAP-130664 | [TAP-130664] ¦ [IRR][Spike] Prototype UFSW Use Life Summary Screens | Feature | Accepted |  |  | Parent Task |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | V4.2 - EC2
TAP-130664_PUPPETEERS | 108 | 107 |  | 03.01.01.01.05.01.00.00 | TAP-130664 | TAP-135022 | [TAP-130664_PUPPETEERS] ¦ [IRR][Spike] Prototype UFSW Use Life Summary Screens | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 14 | 0 | 14 | 16.8 | 14 | 0% | V4.2 - EC2
TAP-132912 | 109 | 275 |  | 03.01.01.01.06.00.00.00 |  | TAP-132912 | [TAP-132912] ¦ [IRR] Prototype Use Life Summary Screens | Feature | Accepted |  |  | Parent Task |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | V4.2 - EC2
TAP-132912_PIXELPOETS | 110 | 109 |  | 03.01.01.01.06.01.00.00 | TAP-132912 | TAP-132288 | [TAP-132912_PIXELPOETS] ¦ [IRR] Prototype Use Life Summary Screens | User Story | In progress | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 14 | 0 | 14 | 16.8 | 14 | 0% | V4.2 - EC2
TAP-90375 | 111 | 275 |  | 03.01.01.02.01.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  | Parent Task |  | 9 | 0 | 1 hr | 1 hr | 9 | 0% | V4.2 - EC2
TAP-90375_STELLARS | 112 | 111 |  | 03.01.01.02.01.01.00.00 | TAP-90375 | TAP-96606 | [TAP-90375_STELLARS] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task |  | 9 | 0 | 9 | 10.8 | 9 | 0% | V4.2 - EC2
TAP-111861 | 113 | 271,132 |  | 03.01.01.02.02.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | Done |  |  | Parent Task |  | 32 | 32 | 1 hr | 1 hr | 0 | 100% | V4.2 - EC2
TAP-111861_EMBEDDED | 114 | 113 |  | 03.01.01.02.02.01.00.00 | TAP-111861 | TAP-112869 | [TAP-111861_EMBEDDED] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111861_USERFLOWSW | 115 | 113 |  | 03.01.01.02.02.02.00.00 | TAP-111861 | TAP-112870 | [TAP-111861_USERFLOWSW] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111861_DRUSHTI | 116 | 113 |  | 03.01.01.02.02.03.00.00 | TAP-111861 | TAP-112871 | [TAP-111861_DRUSHTI] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111861_PUPPETEERS | 117 | 113 |  | 03.01.01.02.02.04.00.00 | TAP-111861 | TAP-125548 | [TAP-111861_PUPPETEERS] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 32 | 32 | 32 | 38.4 | 0 | 100% | V4.2 - EC2
TAP-128527 | 118 | 275 |  | 03.01.01.02.03.00.00.00 |  | TAP-128527 | [TAP-128527] ¦ [IRR] Update ACAD to No Longer Show Percentages | Feature | Accepted |  |  | Parent Task |  | 10 | 2 | 1 hr | 1 hr | 0 | 0% | V4.2 - EC2
TAP-128527_EMBEDDED | 119 | 118 |  | 03.01.01.02.03.01.00.00 | TAP-128527 | TAP-135543 | [TAP-128527_EMBEDDED] ¦ [IRR] Update ACAD to No Longer Show Percentages | User Story | Done | Foundation - Fred | EMBEDDED | Child Task |  | 2 | 2 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-128530 | 120 | 275 |  | 03.01.01.02.04.00.00.00 |  | TAP-128530 | [TAP-128530] ¦ [IRR] Update GUI SW to show message text on full ACAD | Feature | Accepted |  |  | Parent Task |  | 15 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - EC2
TAP-128530_PIXELPOETS | 121 | 120 |  | 03.01.01.02.04.01.00.00 | TAP-128530 | TAP-132099 | [TAP-128530_PIXELPOETS] ¦ [IRR] Update GUI SW to show message text on full ACAD | User Story | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 10 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-111687 | 122 | 275 | 99,105 | 03.01.01.02.05.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  | Parent Task |  | 2 | 0 | 1 hr | 1 hr | 33 | 0% | V4.2 - EC2
TAP-111687_PIXELPOETS | 123 | 122 |  | 03.01.01.02.05.01.00.00 | TAP-111687 | TAP-111903 | [TAP-111687_PIXELPOETS] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 20 | 34 | 20 | 0% | V4.2 - EC2
TAP-111687_USERFLOWSW | 124 | 122 |  | 03.01.01.02.05.02.00.00 | TAP-111687 | TAP-112872 | [TAP-111687_USERFLOWSW] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 8 | 12 | 8 | 0% | V4.2 - EC2
TAP-111687_EMBEDDED | 125 | 122 |  | 03.01.01.02.05.03.00.00 | TAP-111687 | TAP-112873 | [TAP-111687_EMBEDDED] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | EMBEDDED | Child Task |  | 0 | 0 | 5 | 15 | 5 | 0% | V4.2 - EC2
TAP-133880 | 126 | 275 |  | 03.01.01.02.06.00.00.00 |  | TAP-133880 | [TAP-133880] ¦ [IRR] Update SRA SW To Not Calculate/Send Percentages | Feature | Accepted |  |  | Parent Task |  | 5 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - EC2
TAP-133880_PUPPETEERS | 127 | 126 |  | 03.01.01.02.06.01.00.00 | TAP-133880 | TAP-136346 | [TAP-133880_PUPPETEERS] ¦ [IRR] Update SRA SW To Not Calculate/Send Percentages | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 5 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-111695 | 128 | 275 | 97,99 | 03.01.01.02.08.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 48 | 0% | V4.2 - EC2
TAP-111695_PIXELPOETS | 129 | 128 |  | 03.01.01.02.08.01.00.00 | TAP-111695 | TAP-111905 | [TAP-111695_PIXELPOETS] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 11 | 26 | 11 | 0% | V4.2 - EC2
TAP-111695_USERFLOWSW | 130 | 128 |  | 03.01.01.02.08.02.00.00 | TAP-111695 | TAP-112876 | [TAP-111695_USERFLOWSW] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 30 | 50 | 30 | 0% | V4.2 - EC2
TAP-111695_DRUSHTI | 131 | 128 |  | 03.01.01.02.08.03.00.00 | TAP-111695 | TAP-112877 | [TAP-111695_DRUSHTI] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task |  | 0 | 0 | 7 | 8 | 7 | 0% | V4.2 - EC2
TAP-133272 | 132 | 275 | 113 | 03.01.01.02.10.00.00.00 |  | TAP-133272 | [TAP-133272] ¦ [IRR] Consolidate IRR Use Life Notification Strategy | Feature | Accepted |  |  | Parent Task |  | 27 | 0 | 1 hr | 1 hr | 27 | 0% | V4.2 - EC2
TAP-133272_PUPPETEERS | 133 | 132 |  | 03.01.01.02.10.01.00.00 | TAP-133272 | TAP-125553 | [TAP-133272_PUPPETEERS] ¦ [IRR] Consolidate IRR Use Life Notification Strategy | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 27 | 0 | 27 | 32.4 | 27 | 0% | V4.2 - EC2
TAP-103448 | 134 | 275 |  | 03.01.02.01.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [Newton] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  | Parent Task |  | 40 | 5 | 1 hr | 1 hr | 35 | 12.5% | V4.2 - EC2
TAP-103448_EMBEDDED | 135 | 134 |  | 03.01.02.01.01.00.00.00 | TAP-103448 | TAP-99022 | [TAP-103448_EMBEDDED] ¦ [Newton] Reliability and Instrument Tool Consolidation | User Story | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 5 | 5 | 5 | 6 | 0 | 100% | V4.2 - EC2
TAP-103448_NEPTUNE | 136 | 134 |  | 03.01.02.01.02.00.00.00 | TAP-103448 | TAP-114885 | [TAP-103448_NEPTUNE] ¦ [Newton] Reliability and Instrument Tool Consolidation | User Story | Groomed | Advanced Instruments - Neptune | NEPTUNE | Child Task |  | 35 | 0 | 35 | 42 | 35 | 0% | V4.2 - EC2
TAP-95983 | 137 | 275 |  | 03.01.02.02.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  | Parent Task |  | 80 | 40 | 1 hr | 1 hr | 40 | 50% | V4.2 - EC2
TAP-95983_COREINSTRUMENTS | 138 | 137 |  | 03.01.02.02.01.00.00.00 | TAP-95983 | TAP-88491 | [TAP-95983_COREINSTRUMENTS] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | User Story | Done | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 37 | 20 | 37 | 44.4 | 17 | 54.05% | V4.2 - EC2
TAP-95983_ANIMATORS | 139 | 137 |  | 03.01.02.02.07.00.00.00 | TAP-95983 | TAP-115103 | [TAP-95983_ANIMATORS] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | User Story | Open | Shared Services - Animators | ANIMATORS | Child Task |  | 30 | 20 | 30 | 36 | 10 | 66.67% | V4.2 - EC2
TAP-95983_EMBEDDED | 140 | 137 |  | 03.01.02.02.12.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_EMBEDDED] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature Estimation | Open | Foundation - Fred | EMBEDDED | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-95983_PUPPETEERS | 141 | 137 |  | 03.01.02.02.13.00.00.00 | TAP-95983 | TAP-116408 | [TAP-95983_PUPPETEERS] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 13 | 0 | 13 | 15.6 | 13 | 0% | V4.2 - EC2
TAP-123914 | 142 | 275 |  | 03.01.02.03.00.00.00.00 |  | TAP-123914 | [TAP-123914] ¦ [IRR] Create standardized test tools for data collection and analysis | Feature | Accepted |  |  | Parent Task |  | 46 | 0 | 1 hr | 1 hr | 46 | 0% | V4.2 - EC2
TAP-123914_COREINSTRUMENTS | 143 | 142 |  | 03.01.02.03.01.00.00.00 | TAP-123914 | TAP-116494 | [TAP-123914_COREINSTRUMENTS] ¦ [IRR] Create standardized test tools for data collection and analysis | User Story | Open | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 46 | 0 | 46 | 55.2 | 46 | 0% | V4.2 - EC2
TAP-111774 | 144 | 154,149,271 |  | 03.01.03.01.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | Done |  |  | Parent Task |  | 9 | 9 | 1 hr | 1 hr | 0 | 100%
TAP-111774_COREINSTRUMENTS | 145 | 144 |  | 03.01.03.01.01.00.00.00 | TAP-111774 | TAP-111970 | [TAP-111774_COREINSTRUMENTS] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111774_JACOBIANS | 146 | 144 |  | 03.01.03.01.02.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774_JACOBIANS] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111774_CASTLEBLACK | 147 | 144 |  | 03.01.03.01.03.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774_CASTLEBLACK] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111774_PUPPETEERS | 148 | 144 |  | 03.01.03.01.04.00.00.00 | TAP-111774 | TAP-116202 | [TAP-111774_PUPPETEERS] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 9 | 9 | 9 | 10.8 | 0 | 100%
TAP-112080 | 149 | 154,275 | 144 | 03.01.03.02.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature | Accepted |  |  | Parent Task |  | 4 | 0 | 1 hr | 1 hr | 4 | 0% | V4.2 - EC2
TAP-112080_COREINSTRUMENTS | 150 | 149 |  | 03.01.03.02.01.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080_COREINSTRUMENTS] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-112080_JACOBIANS | 151 | 149 |  | 03.01.03.02.02.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080_JACOBIANS] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 4 | 0 | 4 | 4.8 | 4 | 0% | V4.2 - EC2
TAP-112080_USERFLOWSW | 152 | 149 |  | 03.01.03.02.03.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080_USERFLOWSW] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-112080_INBETWEENERS | 153 | 149 |  | 03.01.03.02.04.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080_INBETWEENERS] ¦ [IRR][Spike] Plan for Removal of MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775 | 154 | 275 | 144,149 | 03.01.03.03.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature | PROPOSED |  |  | Parent Task |  | 14 | 0 | 1 hr | 1 hr | 14 | 0% | V4.2 - EC2
TAP-111775_COREINSTRUMENTS | 155 | 154 |  | 03.01.03.03.01.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775_COREINSTRUMENTS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775_JACOBIANS | 156 | 154 |  | 03.01.03.03.02.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775_JACOBIANS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 13 | 0 | 13 | 15.6 | 13 | 0% | V4.2 - EC2
TAP-111775_USERFLOWSW | 157 | 154 |  | 03.01.03.03.03.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775_USERFLOWSW] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775_INBETWEENERS | 158 | 154 |  | 03.01.03.03.04.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775_INBETWEENERS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 100% | V4.2 - EC2
TAP-111775_PUPPETEERS | 159 | 154 |  | 03.01.03.03.05.00.00.00 | TAP-111775 | TAP-121472 | [TAP-111775_PUPPETEERS] ¦ [IRR] Development of Replacement/Removal of Joint Tracking Check for IRR | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 1 | 0 | 1 | 1.2 | 1 | 0% | V4.2 - EC2
TAP-134541 | 160 | 275 |  | 03.01.04.00.00.00.00.00 |  | TAP-134541 | [TAP-134541] ¦ [IRR] Test Development and Dry Run for pre-RC1 | Feature | Accepted |  |  | Parent Task |  | 57 | 0 | 1 hr | 1 hr | 57 | 0% | V4.2 - EC2
TAP-134541_COREINSTRUMENTS | 161 | 160 |  | 03.01.04.01.00.00.00.00 | TAP-134541 | TAP-132512 | [TAP-134541_COREINSTRUMENTS] ¦ [IRR] Test Development and Dry Run for pre-RC1 | User Story | Open | Core Instruments - Happy Jaws | COREINSTRUMENTS | Child Task |  | 57 | 0 | 57 | 68.4 | 57 | 0% | V4.2 - EC2
TAP-111747 | 162 | 275 |  | 03.01.05.01.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 50 | 0% | V4.2 - EC2
TAP-111747_COREINSTRUMENTS | 163 | 162 |  | 03.01.05.01.01.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747_COREINSTRUMENTS] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 50 | 100 | 50 | 0% | V4.2 - EC2
TAP-131594 | 164 | 275 |  | 03.01.05.02.00.00.00.00 |  | TAP-131594 | [TAP-131594] ¦ [IRR] [Spike] Algorithm Development of Torque Loss Check De-risking [EC1 Flag] | Feature | Accepted |  |  | Parent Task |  | 11 | 0 | 1 hr | 1 hr | 11 | 0% | V4.2 - EC2
TAP-131594_COREINSTRUMENTS | 165 | 164 |  | 03.01.05.02.01.00.00.00 | TAP-131594 | TAP-126504 | [TAP-131594_COREINSTRUMENTS] ¦ [IRR] [Spike] Algorithm Development of Torque Loss Check De-risking [EC1 Flag] | User Story | Open | Core Instruments - Sirius | COREINSTRUMENTS | Child Task |  | 11 | 0 | 11 | 13.2 | 11 | 0% | V4.2 - EC2
TAP-123862 | 166 | 271,174 |  | 03.01.06.01.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | Feature | Done |  |  | Parent Task |  | 22.5 | 22.5 | 1 hr | 1 hr | 0 | 100%
TAP-123862_EMBEDDED | 167 | 166 |  | 03.01.06.01.01.00.00.00 | TAP-123862 | TAP-124413 | [TAP-123862_EMBEDDED] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | User Story | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 18.5 | 18.5 | 18.5 | 22.2 | 0 | 100%
TAP-123862_ZENITH | 168 | 166 |  | 03.01.06.01.10.00.00.00 | TAP-123862 | TAP-126037 | [TAP-123862_ZENITH] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | User Story | Done | Advanced Instruments - Zenith | ZENITH | Child Task |  | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-123862_CASTLEBLACK | 169 | 166 |  | 03.01.06.01.11.00.00.00 | TAP-123862 | TAP-126145 | [TAP-123862_CASTLEBLACK] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-123863 | 170 | 271,174 |  | 03.01.06.02.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | Feature | Done |  |  | Parent Task |  | 29.5 | 29.5 | 1 hr | 1 hr | 0 | 100%
TAP-123863_EMBEDDED | 171 | 170 |  | 03.01.06.02.02.00.00.00 | TAP-123863 | TAP-124578 | [TAP-123863_EMBEDDED] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | User Story | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 25.5 | 25.5 | 25.5 | 30.6 | 0 | 100%
TAP-123863_CASTLEBLACK | 172 | 170 |  | 03.01.06.02.11.00.00.00 | TAP-123863 | TAP-126023 | [TAP-123863_CASTLEBLACK] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-123863_NEPTUNE | 173 | 170 |  | 03.01.06.02.16.00.00.00 | TAP-123863 | TAP-134546 | [TAP-123863_NEPTUNE] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | User Story | Done | Advanced Instruments - Neptune | NEPTUNE | Child Task |  | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-111656 | 174 | 275 | 170,166 | 03.01.06.05.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 70 | 0% | V4.2 - EC2
TAP-111656_CLASSY2 | 175 | 174 |  | 03.01.06.05.01.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656_CLASSY2] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - EC2
TAP-111656_BOOSTERS | 176 | 174 |  | 03.01.06.05.02.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656_BOOSTERS] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - EC2
TAP-111656_INBETWEENERS | 177 | 174 |  | 03.01.06.05.03.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656_INBETWEENERS] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-111656_CASTLEBLACK | 178 | 174 |  | 03.01.06.05.04.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656_CASTLEBLACK] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - EC2
TAP-111656_USERFLOWSW | 179 | 174 |  | 03.01.06.05.05.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656_USERFLOWSW] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 5 | 10 | 5 | 0% | V4.2 - EC2
TAP-111656_EMBEDDED | 180 | 174 |  | 03.01.06.05.06.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656_EMBEDDED] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-111656_COREINSTRUMENTS | 181 | 174 |  | 03.01.06.05.07.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656_COREINSTRUMENTS] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 5 | 15 | 5 | 0% | V4.2 - EC2
TAP-130665 | 182 | 275 |  | 03.01.06.06.00.00.00.00 |  | TAP-130665 | [TAP-130665] ¦ [IRR] Kinematic Variant Management in Mini-Bedside Configuration Manager | Feature | Accepted |  |  | Parent Task |  | 44 | 2 | 1 hr | 1 hr | 42 | 4.545% | V4.2 - EC2
TAP-130665_EMBEDDED | 183 | 182 |  | 03.01.06.06.01.00.00.00 | TAP-130665 | TAP-129688 | [TAP-130665_EMBEDDED] ¦ [IRR] Kinematic Variant Management in Mini-Bedside Configuration Manager | User Story | Groomed | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 36 | 2 | 36 | 43.2 | 34 | 5.556% | V4.2 - EC2
TAP-130665_PUPPETEERS | 184 | 182 |  | 03.01.06.06.14.00.00.00 | TAP-130665 | TAP-136589 | [TAP-130665_PUPPETEERS] ¦ [IRR] Kinematic Variant Management in Mini-Bedside Configuration Manager | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 8 | 0 | 8 | 9.6 | 8 | 0% | V4.2 - EC2
TAP-132913 | 185 | 275 |  | 03.01.06.07.00.00.00.00 |  | TAP-132913 | [TAP-132913] ¦ [IRR] Use Life Variant management in BSCM | Feature | Accepted |  |  | Parent Task |  | 5.5 | 0 | 1 hr | 1 hr | 5.5 | 0% | V4.2 - EC2
TAP-132913_EMBEDDED | 186 | 185 |  | 03.01.06.07.01.00.00.00 | TAP-132913 | TAP-137248 | [TAP-132913_EMBEDDED] ¦ [IRR] Use Life Variant management in BSCM | User Story | Open | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 5.5 | 0 | 5.5 | 6.6 | 5.5 | 0% | V4.2 - EC2
TAP-111838 | 187 | 191,275 |  | 03.01.07.01.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - EC2
TAP-111838_COREINSTRUMENTS | 188 | 187 |  | 03.01.07.01.01.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838_COREINSTRUMENTS] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - EC2
TAP-104213 | 189 | 191,275 |  | 03.01.07.02.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - EC2
TAP-104213_COREINSTRUMENTS | 190 | 189 |  | 03.01.07.02.01.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213_COREINSTRUMENTS] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 45 | 15 | 0% | V4.2 - EC2
TAP-111842 | 191 | 275 | 189,187 | 03.01.07.03.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 40 | 0% | V4.2 - EC2
TAP-111842_COREINSTRUMENTS | 192 | 191 |  | 03.01.07.03.01.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842_COREINSTRUMENTS] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-111842_USERFLOWSW | 193 | 191 |  | 03.01.07.03.02.00.00.00 | TAP-111842 | TAP-127787 | [TAP-111842_USERFLOWSW] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature Estimation | Open | Advanced Instruments - Remus | USERFLOWSW | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-112119 | 194 | 275 |  | 03.02.01.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - EC2
TAP-112119_COREINSTRUMENTS | 195 | 194 |  | 03.02.01.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119_COREINSTRUMENTS] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 10 | 20 | 10 | 0% | V4.2 - EC2
TAP-111925 | 196 | 275 |  | 03.03.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - EC2
TAP-111925_COREINSTRUMENTS | 197 | 196 |  | 03.03.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925_COREINSTRUMENTS] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 30 | 15 | 0% | V4.2 - EC2
TAP-111753 | 198 | 212,279,275 | 28 | 03.04.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 30 | 0% | V4.2 - EC2
TAP-111753_COREINSTRUMENTS | 199 | 198 |  | 03.04.01.01.00.00.00.00 | TAP-111753 | TAP-111954 | [TAP-111753_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 30 | 50 | 30 | 0% | V4.2 - EC2
TAP-111754 | 200 | 214,279,275 | 30 | 03.04.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  | Parent Task |  | 3 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - EC2
TAP-111754_COREINSTRUMENTS | 201 | 200 |  | 03.04.02.01.00.00.00.00 | TAP-111754 | TAP-111955 | [TAP-111754_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - EC2
TAP-111756 | 202 | 216,279,275 | 33 | 03.04.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  | Parent Task |  | 6 | 0 | 1 hr | 1 hr | 35 | 0% | V4.2 - EC2
TAP-111756_COREINSTRUMENTS | 203 | 202 |  | 03.04.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 35 | 45 | 35 | 0% | V4.2 - EC2
TAP-111757 | 204 | 218,279,275 | 67 | 03.04.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 16 | 0% | V4.2 - EC2
TAP-111757_COREINSTRUMENTS | 205 | 204 |  | 03.04.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 16 | 30 | 16 | 0% | V4.2 - EC2
TAP-111758 | 206 | 220,279,275 | 69 | 03.04.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - EC2
TAP-111758_COREINSTRUMENTS | 207 | 206 |  | 03.04.05.01.00.00.00.00 | TAP-111758 | TAP-111958 | [TAP-111758_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 30 | 15 | 0% | V4.2 - EC2
TAP-111759 | 208 | 222,279,275 | 35 | 03.04.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 20 | 0% | V4.2 - EC2
TAP-111759_COREINSTRUMENTS | 209 | 208 |  | 03.04.06.01.00.00.00.00 | TAP-111759 | TAP-111959 | [TAP-111759_COREINSTRUMENTS] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - EC2
TAP-111724 | 210 | 275 |  | 03.05.00.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 27 | 0% | V4.2 - EC2
TAP-111724_COREINSTRUMENTS | 211 | 210 |  | 03.05.01.00.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724_COREINSTRUMENTS] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 27 | 30 | 27 | 0% | V4.2 - EC2
TAP-111761 | 212 | 279 | 198 | 04.01.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 25 | 0% | V4.2 - RC1
TAP-111761_COREINSTRUMENTS | 213 | 212 |  | 04.01.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761_COREINSTRUMENTS] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 25 | 30 | 25 | 0% | V4.2 - RC1
TAP-110382 | 214 | 279 | 200 | 04.01.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 5 | 0% | V4.2 - RC1
TAP-110382_COREINSTRUMENTS | 215 | 214 |  | 04.01.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382_COREINSTRUMENTS] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 5 | 8 | 5 | 0% | V4.2 - RC1
TAP-111762 | 216 | 279 | 202 | 04.01.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - RC1
TAP-111762_COREINSTRUMENTS | 217 | 216 |  | 04.01.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762_COREINSTRUMENTS] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 25 | 15 | 0% | V4.2 - RC1
TAP-111748 | 218 | 279 | 204 | 04.01.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 8 | 0% | V4.2 - RC1
TAP-111748_COREINSTRUMENTS | 219 | 218 |  | 04.01.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748_COREINSTRUMENTS] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 8 | 15 | 8 | 0% | V4.2 - RC1
TAP-111764 | 220 | 279 | 206 | 04.01.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - RC1
TAP-111764_COREINSTRUMENTS | 221 | 220 |  | 04.01.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764_COREINSTRUMENTS] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - RC1
TAP-111766 | 222 | 279 | 208 | 04.01.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 15 | 0% | V4.2 - RC1
TAP-111766_COREINSTRUMENTS | 223 | 222 |  | 04.01.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766_COREINSTRUMENTS] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 20 | 15 | 0% | V4.2 - RC1
TAP-112082 | 224 | 279 |  | 04.02.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 50 | 0% | V4.2 - RC1
TAP-112082_COREINSTRUMENTS | 225 | 224 |  | 04.02.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082_COREINSTRUMENTS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 15 | 60 | 15 | 0% | V4.2 - RC1
TAP-112082_EMBEDDED | 226 | 224 |  | 04.02.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082_EMBEDDED] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - RC1
TAP-112082_USERFLOWSW | 227 | 224 |  | 04.02.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082_USERFLOWSW] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles | USERFLOWSW | Child Task |  | 0 | 0 | 10 | 20 | 10 | 0% | V4.2 - RC1
TAP-112082_PIXELPOETS | 228 | 224 |  | 04.02.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082_PIXELPOETS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 8 | 15 | 8 | 0% | V4.2 - RC1
TAP-112082_JACOBIANS | 229 | 224 |  | 04.02.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082_JACOBIANS] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 7 | 15 | 7 | 0% | V4.2 - RC1
TAP-112093 | 230 | 279 |  | 04.02.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 135 | 0% | V4.2 - RC1
TAP-112093_COREINSTRUMENTS | 231 | 230 |  | 04.02.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093_COREINSTRUMENTS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 55 | 70 | 55 | 0% | V4.2 - RC1
TAP-112093_EMBEDDED | 232 | 230 |  | 04.02.02.02.00.00.00.00 | TAP-112093 | TAP-127793 | [TAP-112093_EMBEDDED] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - I2E | EMBEDDED | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112093_USERFLOWSW | 233 | 230 |  | 04.02.02.03.00.00.00.00 | TAP-112093 | TAP-127794 | [TAP-112093_USERFLOWSW] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Remus | USERFLOWSW | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112093_PIXELPOETS | 234 | 230 |  | 04.02.02.04.00.00.00.00 | TAP-112093 | TAP-127795 | [TAP-112093_PIXELPOETS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112093_JACOBIANS | 235 | 230 |  | 04.02.02.05.00.00.00.00 | TAP-112093 | TAP-127796 | [TAP-112093_JACOBIANS] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - RC1
TAP-112094 | 236 | 279 |  | 04.02.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 87 | 0% | V4.2 - RC1
TAP-112094_COREINSTRUMENTS | 237 | 236 |  | 04.02.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094_COREINSTRUMENTS] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 87 | 170 | 87 | 0% | V4.2 - RC1
TAP-113100 | 238 | 285 |  | 05.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 250 | 0% | V4.2 - RC2
TAP-113100_COREINSTRUMENTS | 239 | 238 |  | 05.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100_COREINSTRUMENTS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 200 | 400 | 200 | 0% | V4.2 - RC2
TAP-113100_JACOBIANS | 240 | 238 |  | 05.01.02.00.00.00.00.00 | TAP-113100 | TAP-127797 | [TAP-113100_JACOBIANS] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 50 | 100 | 50 | 0% | V4.2 - RC2
TAP-111900 | 241 | 290 | 282 | 06.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 127 | 0% | V4.2 - DVR
TAP-111900_COREINSTRUMENTS | 242 | 241 |  | 06.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900_COREINSTRUMENTS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task |  | 0 | 0 | 30 | 60 | 30 | 0% | V4.2 - DVR
TAP-111900_BUGHUNTERS | 243 | 241 |  | 06.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900_BUGHUNTERS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task |  | 0 | 0 | 0 | 1 | 0 | 0% | V4.2 - DVR
TAP-111900_JACOBIANS | 244 | 241 |  | 06.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900_JACOBIANS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Core Instruments - Jacobians | JACOBIANS | Child Task |  | 0 | 0 | 15 | 20 | 15 | 0% | V4.2 - DVR
TAP-111900_USERFLOWSW | 245 | 241 |  | 06.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900_USERFLOWSW] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Romulus | USERFLOWSW | Child Task |  | 0 | 0 | 30 | 40 | 30 | 0% | V4.2 - DVR
TAP-111900_PIXELPOETS | 246 | 241 |  | 06.01.06.00.00.00.00.00 | TAP-111900 | TAP-112682 | [TAP-111900_PIXELPOETS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task |  | 0 | 0 | 20 | 30 | 20 | 0% | V4.2 - DVR
TAP-111900_SUNRISERS | 247 | 241 |  | 06.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900_SUNRISERS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task |  | 0 | 0 | 3 | 9 | 3 | 0% | V4.2 - DVR
TAP-111900_TEAMBD | 248 | 241 |  | 06.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900_TEAMBD] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task |  | 0 | 0 | 3 | 5 | 3 | 0% | V4.2 - DVR
TAP-111900_COSSACKS | 249 | 241 |  | 06.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900_COSSACKS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS | Child Task |  | 0 | 0 | 8 | 13 | 8 | 0% | V4.2 - DVR
TAP-111900_EMBEDDED | 250 | 241 |  | 06.01.13.00.00.00.00.00 | TAP-111900 | TAP-137948 | [TAP-111900_EMBEDDED] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Core Instruments - NotMySegFault | EMBEDDED | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - DVR
TAP-111900_CLASSY | 251 | 241 |  | 06.01.14.00.00.00.00.00 | TAP-111900 | TAP-137949 | [TAP-111900_CLASSY] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Foundation - Classy | CLASSY | Child Task |  | 0 | 0 | 18 | 20 | 18 | 0% | V4.2 - DVR
TAP-111900_PUPPETEERS | 252 | 241 |  | 06.01.15.00.00.00.00.00 | TAP-111900 | TAP-137950 | [TAP-111900_PUPPETEERS] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task |  | 0 | 0 | 0 | 0 | 0 | 0% | V4.2 - DVR
TAP-112042 | 253 | 290 |  | 06.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V4.2][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 22 | 0% | V4.2 - DVR
TAP-112042_BUILDERS | 254 | 253 |  | 06.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042_BUILDERS] ¦ [V4.2][IRR] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS | Child Task |  | 0 | 0 | 22 | 30 | 22 | 0% | V4.2 - DVR
TAP-111692 | 255 | 290 |  | 06.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 130 | 0% | V4.2 - DVR
TAP-111692_ASTRANPSDEVELOPERS | 256 | 255 |  | 06.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692_ASTRANPSDEVELOPERS] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task |  | 0 | 0 | 20 | 25 | 20 | 0% | V4.2 - DVR
TAP-111692_TOOLSRULES | 257 | 255 |  | 06.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692_TOOLSRULES] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES | Child Task |  | 0 | 0 | 20 | 25 | 20 | 0% | V4.2 - DVR
TAP-111692_INBETWEENERS | 258 | 255 |  | 06.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692_INBETWEENERS] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task |  | 0 | 0 | 50 | 65 | 50 | 0% | V4.2 - DVR
TAP-111692_TRIPLETEA | 259 | 255 |  | 06.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692_TRIPLETEA] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task |  | 0 | 0 | 40 | 80 | 40 | 0% | V4.2 - DVR
TAP-112231 | 260 | 290 |  | 06.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 40 | 0% | V4.2 - DVR
TAP-112231_ASTRANPSVALIDATORS | 261 | 260 |  | 06.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task |  | 0 | 0 | 40 | 50 | 40 | 0% | V4.2 - DVR
TAP-112233 | 262 | 290 |  | 06.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - DVR
TAP-112233_ASTRANPSVALIDATORS | 263 | 262 |  | 06.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233_ASTRANPSVALIDATORS] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task |  | 0 | 0 | 10 | 20 | 10 | 0% | V4.2 - DVR
TAP-112234 | 264 | 290 |  | 06.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 20 | 0% | V4.2 - DVR
TAP-112234_TOOLSRULES | 265 | 264 |  | 06.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234_TOOLSRULES] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES | Child Task |  | 0 | 0 | 20 | 40 | 20 | 0% | V4.2 - DVR
TAP-113127 | 266 | 290 |  | 06.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - DVR
TAP-111760 | 267 | 268 | 1,41,30,35,7,13,15,26,11,28,23,33,17,5,49,9,61,51,53,37,59,57,39,47,45,55,21,19 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  | Parent Task | TAP-111721 | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 | TAP-133812 | TAP-130796 | TAP-134602 | TAP-133814 | TAP-129482 | TAP-135038 | TAP-134301 | TAP-132587 | TAP-137324 | TAP-111719 | TAP-124116
TAP-111763 | 268 | 271,270 | 267 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-111763_SEAMLESS | 269 | 268 |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763_SEAMLESS] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 1 | 2 | 1 | 0%
TAP-127945 | 270 |  | 268 | 07.03.00.00.00.00.00.00 |  | TAP-127945 | [TAP-127945] ¦ [Prochain][IRR] EC1 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113104 | 271 | 272 | 144,268,170,166,113,85,93,89,71,91,73,69,87,67,63,75,79,77,65,81,83,101 | 07.04.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  | Parent Task | TAP-111861 | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  | TAP-133813 | TAP-111749 | TAP-136909 | TAP-132462 | TAP-137334 | TAP-137313 | TAP-136657 | TAP-137337 | TAP-137339 | TAP-114692
TAP-113105 | 272 | 279,274 | 271 | 07.05.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-113105_SEAMLESS | 273 | 272 |  | 07.05.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105_SEAMLESS] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0%
TAP-127946 | 274 |  | 272 | 07.06.00.00.00.00.00.00 |  | TAP-127946 | [TAP-127946] ¦ [Prochain][IRR] EC2 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-137349 | 275 | 276 | 107,109,111,118,120,122,126,128,132,134,137,142,149,154,160,162,164,174,182,185,187,189,191,194,196,198,200,202,204,206,208,210 | 07.07.00.00.00.00.00.00 |  | TAP-137349 | [TAP-137349] ¦ [IRR][Milestone] EC3 Code Freeze (placeholder) | Feature | PROPOSED |  |  | Parent Task | TAP-95983 | 0 | 0 | 1 hr | 1 hr | 0 | 0% |  | TAP-130665 | TAP-132913 | TAP-111838 | TAP-104213 | TAP-111842 | TAP-112119 | TAP-111925 | TAP-111753 | TAP-111754 | TAP-111756 | TAP-111757 | TAP-111758 | TAP-111759 | TAP-111724
TAP-137351 | 276 | 278 | 275 | 07.08.00.00.00.00.00.00 |  | TAP-137351 | [TAP-137351] ¦ [IRR][Milestone] EC3 Tagged and Released (Placeholder) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-137351_SEAMLESS | 277 | 276 |  | 07.08.01.00.00.00.00.00 | TAP-137351 | TAP-137352 | [TAP-137351_SEAMLESS] ¦ [IRR][Milestone] EC3 Tagged and Released (Placeholder) | Feature Estimation | Open | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0%
TAP-137353 | 278 |  | 276 | 07.09.00.00.00.00.00.00 |  | TAP-137353 | [TAP-137353] ¦ [Prochain][IRR] EC3 Prochain Endpoint (Placeholder) | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111765 | 279 | 280 | 198,200,202,204,206,208,212,214,216,218,220,222,224,230,236,272,21 | 07.10.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  | Parent Task | TAP-111764 | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1 | TAP-122269 | TAP-125315 | TAP-127798 | TAP-111719
TAP-111768 | 280 | 281 | 279 | 07.11.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1
TAP-111769 | 281 | 282 | 280 | 07.12.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1
TAP-111767 | 282 | 241,284 | 281 | 07.13.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0% | V4.2 - RC1
TAP-111767_SEAMLESS | 283 | 282 |  | 07.13.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767_SEAMLESS] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0% | V4.2 - RC1
TAP-127947 | 284 |  | 282 | 07.14.00.00.00.00.00.00 |  | TAP-127947 | [TAP-127947] ¦ [Prochain][IRR] RC1 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - RC1
TAP-113101 | 285 | 286 | 238 | 07.15.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113102 | 286 | 287 | 285 | 07.16.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113103 | 287 | 290,289 | 286 | 07.17.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-113103_SEAMLESS | 288 | 287 |  | 07.17.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103_SEAMLESS] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task |  | 0 | 0 | 10 | 15 | 10 | 0%
TAP-127948 | 289 |  | 287 | 07.18.00.00.00.00.00.00 |  | TAP-127948 | [TAP-127948] ¦ [Prochain][IRR] RC2 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121104 | 290 |  | 241,253,255,260,262,264,266,287 | 07.19.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  | Parent Task |  | 0 | 0 | 1 hr | 1 hr | 0 | 0% | V4.2 - DVR