## IRR Medium Term - NEW!
Key | Isuue Type | Summary | Refinement Level | Art Scrum Team | Status | Σ Realistic Estimate | Σ Worst-Case Estimate | Σ Story Points | Parent Feature
01.00.00.00.00.00.00.00 |  | EC1- Reliability Only | 0 |  |  | 0 | 0 | 0
01.01.00.00.00.00.00.00 |  | Re-architecting wristed instruments controller - Lok Man | 0 |  |  | 0 | 0 | 0
01.01.01.00.00.00.00.00 | TAP-94739 | [IRR] Develop Consolidated SW Architecture Design for Medium IRR | 0 |  | Done | 0 | 0 | 0
01.01.01.01.00.00.00.00 | TAP-96814 | [Architecture] Document Software Concept Architecture for IRR | 0 | Core Instruments - Happy Jaws | Cancelled | 0 | 0 | 0 | TAP-94739
01.01.01.02.00.00.00.00 | TAP-97584 | [IRR][Arch] Describe wristed controller system functional architecture | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-94739
01.01.01.03.00.00.00.00 | TAP-99738 | [IRR][SW] Prepare for Planning Discussion on IDU Actuator Plug-and-Play Architecture | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-94739
01.01.01.04.00.00.00.00 | TAP-97602 | [IRR][Arch] Analyze requirement impact | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-94739
01.01.01.05.00.00.00.00 | TAP-106673 | [IRR][Arch] Analyze WS5 prototype functions and architecture | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-94739
01.01.01.06.00.00.00.00 | TAP-111973 | [IRR][Core Instruments] Develop Consolidated SW Architecture Design for Medium IRR | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-94739
01.01.02.00.00.00.00.00 | TAP-97668 | [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | 0 |  | Groomed | 0 | 0 | 0
01.01.02.01.00.00.00.00 | TAP-111972 | [IRR][Core Instruments] Introduce Consolidated Wristed Architecture into Medium IRR SW | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-97668
01.01.02.02.00.00.00.00 | TAP-105494 | [IRR][Arch] Create consolidated wristed architecture prototype | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.03.00.00.00.00 | TAP-106674 | [IRR][Arch] Validate consolidated wristed architecture prototype | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.04.00.00.00.00 | TAP-97689 | [IRR][Arch] Update instrument data model for wristed instruments | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.05.00.00.00.00 | TAP-97600 | [IRR][Arch] Identify impacts and opportunities on testing strategy | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-97668
01.01.02.06.00.00.00.00 | TAP-97598 | [IRR][Arch] Finalize external interfaces of wristed controller SWI | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.07.00.00.00.00 | TAP-97595 | [IRR][Arch] Review and refine state logic and state machines | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-97668
01.01.02.08.00.00.00.00 | TAP-97586 | [IRR][Arch] Migration and branch sync considerations | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-97668
01.01.02.09.00.00.00.00 | TAP-97581 | [IRR][Arch] Define internal structure and interfaces for wristed instrument controller | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.10.00.00.00.00 | TAP-97568 | [IRR][Arch] Select architecture concept for wristed controller family | 0 | Core Instruments - Happy Jaws | In progress | 0 | 0 | 0 | TAP-97668
01.01.02.11.00.00.00.00 | TAP-114763 | [IRR][Arch] Refine design inputs to wristed instrument architecture | 0 | Core Instruments - Happy Jaws | Cancelled | 0 | 0 | 0 | TAP-97668
01.01.02.12.00.00.00.00 | TAP-114765 | [IRR][Arch] Update functional decomposition documents | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-97668
01.01.02.13.00.00.00.00 | TAP-114792 | [IRR][Arch] Decide on controller design with impact on software architecture | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-97668
01.01.02.14.00.00.00.00 | TAP-114794 | [IRR][Arch] Requirements workshop | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-97668
01.01.02.15.00.00.00.00 | TAP-114803 | [IRR][Arch] Migrate IRR branch to new arch and validate | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.16.00.00.00.00 | TAP-115970 | [IRR][Arch] Complete V&V Impact Analysis and Initial V&V Strategy | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.17.00.00.00.00 | TAP-116501 | [IRR][Arch] Reserve time for requirement updates | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.02.18.00.00.00.00 | TAP-117147 | [IRR][Arch] Simulink design guidelines and patterns within IRR controller | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-97668
01.01.03.00.00.00.00.00 | TAP-120097 | [IRR][Enhancement] Finalize IRR Wristed Architecture | 0 |  | PROPOSED | 0 | 0 | 0
01.02.00.00.00.00.00.00 |  | IRR Clamping Controller Development (1a) - Stefan | 0 |  |  | 0 | 0 | 0
01.02.01.00.00.00.00.00 | TAP-111730 | [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | 0 |  | Accepted | 0 | 0 | 0
01.02.01.01.00.00.00.00 | TAP-111898 | [IRR][Core Instruments] Fix force generation at clamp initiation | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111730
01.02.01.02.00.00.00.00 | TAP-116458 | [IRR][Clamping] Update switching logic in jaw torque estimator | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-111730
01.02.01.03.00.00.00.00 | TAP-116459 | [IRR][Clamping] Improve force estimator | 0 | Core Instruments - Happy Jaws | In progress | 0 | 0 | 0 | TAP-111730
01.02.01.04.00.00.00.00 | TAP-116460 | [IRR][Clamping] Investigate jaw torque buildup issue | 0 | Core Instruments - Happy Jaws | Cancelled | 0 | 0 | 0 | TAP-111730
01.02.01.05.00.00.00.00 | TAP-116461 | [IRR][Clamping] Technical design review | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-111730
01.02.01.06.00.00.00.00 | TAP-116462 | [IRR][Clamping] Adjust clamping parameters post June ORSI | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-111730
01.02.01.07.00.00.00.00 | TAP-116463 | [IRR][Clamping] Collect clamp data on previously identified low clamp force instrument | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-111730
01.02.01.08.00.00.00.00 | TAP-121692 | [IRR][Clamping] Prototype clamping hysteresis model | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-111730
01.02.02.00.00.00.00.00 | TAP-111731 | [IRR][Enhancement] Reduce force variation when articulating during clamp | 0 |  | PROPOSED | 0 | 0 | 0
01.02.02.01.00.00.00.00 | TAP-111906 | [IRR][Core Instruments] Reduce force variation when articulating during clamp | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111731
01.02.02.02.00.00.00.00 | TAP-112037 | [Animators] Reduce Force Variation when articulating during clamp | 0 | Shared Services - Animators | Open | 0 | 0 | 0 | TAP-111731
01.03.00.00.00.00.00.00 |  | IRR Articulation Controller Development (1a) - Bryn | 0 |  |  | 0 | 0 | 0
01.03.01.00.00.00.00.00 | TAP-112077 | [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | 0 |  | Accepted | 0 | 0 | 0
01.03.01.01.00.00.00.00 | TAP-112079 | [IRR][Core Instruments] Articulation KPI generation and evaluation | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-112077
01.03.01.02.00.00.00.00 | TAP-115017 | [IRR][Articulation] Finalize KPI/Simulation Script | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-112077
01.03.01.03.00.00.00.00 | TAP-116519 | [IRR][Articulation/Actuation] Setup Tracking Fixture in Boston | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-112077
01.03.01.04.00.00.00.00 | TAP-116520 | [IRR][Articulation/Actuation] Setup Tracking Fixture in NoHa | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-112077
01.03.01.05.00.00.00.00 | TAP-116521 | [IRR][Articulation/Actuation] Setup Tracking Fixture in Wessling | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-112077
01.03.01.06.00.00.00.00 | TAP-116522 | [IRR][Articulation/Actuation] Tracking Fixture and Elmo Interface Finalization | 0 | Core Instruments - Sirius | In progress | 0 | 0 | 0 | TAP-112077
01.03.01.07.00.00.00.00 | TAP-116523 | [IRR][Articulation/Actuation] Setup Engineering Test Script | 0 | Core Instruments - Sirius | In progress | 0 | 0 | 0 | TAP-112077
01.03.01.08.00.00.00.00 | TAP-116524 | [IRR][Articulation/Actuation] Run Engineering Test with Tracking Fixture | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-112077
01.03.01.09.00.00.00.00 | TAP-116525 | [IRR][Articulation/Actuation] Compare Engineering Test Results with SR Tests | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-112077
01.03.01.10.00.00.00.00 | TAP-116526 | [IRR][Articulation/Actuation] Jaw Actuation Hysteresis and Jaw Scaling Analysis Script | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-112077
01.03.01.11.00.00.00.00 | TAP-116527 | [IRR][Articulation/Actuation] Investigate Jaw Actuation Issues with Engineering Test | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-112077
01.03.01.12.00.00.00.00 | TAP-116528 | [IRR][Articulation/Actuation] Articulation Under Load in Simulation | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-112077
01.03.01.13.00.00.00.00 | TAP-116529 | [IRR][Articulation/Actuation] Investigate Instrument Shaking when J6 Moving | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-112077
01.03.01.14.00.00.00.00 | TAP-116530 | [IRR][Articulation/Actuation] Get Clinical Feedback | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-112077
01.03.01.15.00.00.00.00 | TAP-116586 | [IRR][Articulation/Actuation] Evaluate/Implement Other KPIs given Engineering Test Results | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-112077
01.03.01.16.00.00.00.00 | TAP-118635 | [IRR][Articulation] Investigate delay-compensation tracking error KPI | 0 | Core Instruments - Sirius | In progress | 0 | 0 | 0 | TAP-112077
01.03.02.00.00.00.00.00 |  | IRR Cutting Controller Development (1a) - Lok Man | 0 |  |  | 0 | 0 | 0
01.03.02.01.00.00.00.00 | TAP-112076 | [IRR][Enabler] Damage Modeling Documentation | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.01.01.00.00.00 | TAP-112078 | [IRR][Core Instruments] Damage Modeling Documentation | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-112076
01.03.02.02.00.00.00.00 | TAP-94966 | [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | 0 |  | Accepted | 0 | 0 | 0
01.03.02.02.01.00.00.00 | TAP-111781 | [IRR][Core Instruments] Develop a Jaw Estimator for Shears | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-94966
01.03.02.02.02.00.00.00 | TAP-111786 | [IRR][Core Instruments] Enable Tuning of Use-Life to Cutting Performance Trade-offs | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-94966
01.03.02.02.03.00.00.00 | TAP-115109 | [IRR][PlantModels] Support evaluation of the controller estimator in the plant model | 0 | Shared Services - Animators | Open | 0 | 0 | 0 | TAP-94966
01.03.02.02.04.00.00.00 | TAP-115111 | [IRR][PlantModel] Integrate a cable damage model in the plant model simulation | 0 | Shared Services - Animators | Open | 0 | 0 | 0 | TAP-94966
01.03.02.02.05.00.00.00 | TAP-116502 | [IRR][Cutting] Reproduce position estimation failures & Investigate | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-94966
01.03.02.02.06.00.00.00 | TAP-116503 | [IRR][Cutting] Develop hard-stop detection for robust closing | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-94966
01.03.02.02.07.00.00.00 | TAP-116504 | [IRR][Cutting] Develop calibration for robust position estimation | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-94966
01.03.02.02.08.00.00.00 | TAP-116505 | [IRR][Cutting] Update cutting KPIs for capturing reliable performance / HW variation | 0 | Core Instruments - Happy Jaws | In progress | 0 | 0 | 0 | TAP-94966
01.03.02.02.09.00.00.00 | TAP-116506 | [IRR][Cutting] Support Tissue Cutting investigation with Systems | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-94966
01.03.02.02.10.00.00.00 | TAP-116507 | [IRR][Cutting] Get feedback from clinical team | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-94966
01.03.02.02.11.00.00.00 | TAP-116508 | [IRR][Use-life] Document use-life model | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-94966
01.03.02.02.12.00.00.00 | TAP-116509 | [IRR][Use-life] Identify dependent use-life parameters | 0 | Core Instruments - Sirius | In progress | 0 | 0 | 0 | TAP-94966
01.03.02.02.13.00.00.00 | TAP-116510 | [IRR][Use-life] Investigate methods to improve use-life trade-off | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94966
01.03.02.02.14.00.00.00 | TAP-116511 | [IRR][Use-life] Create trade-off curves 1 | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94966
01.03.02.02.15.00.00.00 | TAP-116512 | [IRR][Use-life] Create trade-off curves 2 | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94966
01.03.02.03.00.00.00.00 | TAP-111554 | [IRR][Enhancement] Improve Cutting Control Robustness I1 | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.03.01.00.00.00 | TAP-111782 | [IRR][Core Instruments] Improve Cutting Control Robustness I1 | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111554
01.03.02.04.00.00.00.00 | TAP-111555 | [IRR][Enhancement] Improve Cutting Control Robustness I2 | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.04.01.00.00.00 | TAP-111783 | [IRR][Core Instruments] Improve Cutting Control Robustness I2 | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111555
01.03.02.05.00.00.00.00 | TAP-112012 | [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.05.01.00.00.00 | TAP-112015 | [IRR][Enhancement] Cutting Control Enhancements | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-112012
01.03.02.06.00.00.00.00 | TAP-111560 | [IRR][Feature] Enable Tuning of Use-Life to Cutting Performance Trade-offs | 0 |  | Cancelled | 0 | 0 | 0
01.03.02.07.00.00.00.00 | TAP-111569 | [IRR][Enabler] Integration, Testing, Demo, Design Review | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.07.01.00.00.00 | TAP-111797 | [IRR][Core Instruments] Integration, Testing, Demo, Design Review | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111569
01.03.02.08.00.00.00.00 | TAP-111565 | [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.08.01.00.00.00 | TAP-111793 | [IRR][Core Instruments] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111565
01.03.02.08.02.00.00.00 | TAP-111794 | [IRR][Animators] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | 0 | Shared Services - Animators | Cancelled | 0 | 0 | 0 | TAP-111565
01.03.02.09.00.00.00.00 | TAP-111556 | [IRR][Enhancement] Reduce use-life impact from cutting I1 | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.09.01.00.00.00 | TAP-111784 | [IRR][Core Instruments] Reduce use-life impact from cutting I1 | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111556
01.03.02.10.00.00.00.00 | TAP-111559 | [IRR][Enhancement] Reduce use-life impact from cutting I2 | 0 |  | PROPOSED | 0 | 0 | 0
01.03.02.10.01.00.00.00 | TAP-111785 | [IRR][Core Instruments] Reduce use-life impact from cutting I2 | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111559
01.03.03.00.00.00.00.00 | TAP-120096 | [IRR][Enabler] Formalize Articulation KPI's | 0 |  | PROPOSED | 0 | 0 | 0
01.04.00.00.00.00.00.00 |  | Controller tuning and testing (phase 1a/2a) - Stefan | 0 |  |  | 0 | 0 | 0
01.04.01.00.00.00.00.00 | TAP-103448 | [IRR] Reliability and Instrument Tool Consolidation | 0 |  | Accepted | 0 | 0 | 0
01.04.01.01.00.00.00.00 | TAP-99022 | [v3.1][IRR][IDU CMD][I2E] Add Shears functionality to M-IRR's tool within Discrete Control Command | 0 | Advanced Instruments - I2E | Done | 0 | 0 | 0 | TAP-103448
01.04.01.02.00.00.00.00 | TAP-114885 | [Newton][I2E][IDU CMD][IDU Fix Ctl] Port LED Capability to IDU CMD / Common | 0 | Advanced Instruments - I2E | Open | 0 | 0 | 0 | TAP-103448
01.04.01.03.00.00.00.00 | TAP-114886 | [Newton][I2E][IDU CMD][IDU Fix Ctl] Port Automatic Data Recorder Triggering on Errors | 0 | Advanced Instruments - I2E | Open | 0 | 0 | 0 | TAP-103448
01.04.01.04.00.00.00.00 | TAP-114887 | [Newton][I2E][IDU CMD][IDU Fix Ctl] Port automatically running IDU CMD on 2X fixtures | 0 | Advanced Instruments - I2E | Open | 0 | 0 | 0 | TAP-103448
01.04.01.05.00.00.00.00 | TAP-114892 | [Newton][I2E][IDU CMD][IDU Fix Ctl] Port tmp file logging when parsing/running trajectory files to IDU CMD | 0 | Advanced Instruments - I2E | Open | 0 | 0 | 0 | TAP-103448
01.04.02.00.00.00.00.00 | TAP-111562 | [IRR][Enabler] Set up fixtures and processing scripts for IRR HW Testing | 0 |  | Cancelled | 0 | 0 | 0
01.04.03.00.00.00.00.00 | TAP-116286 | [IRR] Analysis of Key Behaviors in Presence of Reprocessing | 0 |  | Accepted | 0 | 0 | 0
01.04.03.01.00.00.00.00 | TAP-116513 | [IRR][Analysis] Collect clamp data on previously identified low clamp force instrument | 0 | Core Instruments - Happy Jaws | Cancelled | 0 | 0 | 0 | TAP-116286
01.04.03.02.00.00.00.00 | TAP-116514 | [IRR][Analysis] Obtain brand new needle drivers | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-116286
01.04.03.03.00.00.00.00 | TAP-116515 | [IRR][Analysis] Collect KPI data on a set of brand new instruments | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-116286
01.04.03.04.00.00.00.00 | TAP-116516 | [IRR][Analysis] Reprocess instruments | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-116286
01.04.03.05.00.00.00.00 | TAP-116517 | [IRR][Analysis] Collect KPI data on a set of reprocessed instruments | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-116286
01.04.03.06.00.00.00.00 | TAP-116518 | [IRR][Analysis] Investigate instrument aging effects on KPIs | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-116286
01.04.04.00.00.00.00.00 | TAP-95983 | [IRR][Enabler] Develop Framework for Wristed Control Testing | 0 |  | Accepted | 0 | 0 | 0
01.04.04.01.00.00.00.00 | TAP-88491 | [IRR][PlantSim][Happy Jaws] Introduce IDU Standalones to Modeling Team | 0 | Core Instruments - Happy Jaws | Done | 0 | 0 | 0 | TAP-95983
01.04.04.02.00.00.00.00 | TAP-87610 | [IRR][PlantSim][Sirius] Setup VM with Docker and git on Server in Mounds View | 0 | Core Instruments - Sirius | In progress | 0 | 0 | 0 | TAP-95983
01.04.04.03.00.00.00.00 | TAP-111914 | [IRR][Core Instruments] Support for Simulation of Wristed Instruments for Control | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-95983
01.04.04.04.00.00.00.00 | TAP-112038 | [Animators] Reduce Force Variation when articulating during clamp | 0 | Shared Services - Animators | Cancelled | 0 | 0 | 0 | TAP-95983
01.04.04.05.00.00.00.00 | TAP-111921 | [IRR][Core Instruments] Playback harnesses for debugging / testing | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-95983
01.04.04.06.00.00.00.00 | TAP-111725 | [IRR][Enabler][Playback] Implement SW or tool updates to enable playback simulation | 0 | Core Instruments - Sirius | In progress | 0 | 0 | 0 | TAP-95983
01.04.04.07.00.00.00.00 | TAP-115103 | [IRR][PlantModels] Wristed Instrument Model Credibility and Risk Assessment (Validation) | 0 | Shared Services - Animators | Open | 0 | 0 | 0 | TAP-95983
01.04.04.08.00.00.00.00 | TAP-115108 | [IRR][PlantModels] Document model stability and variability over the supported parameter space | 0 | Shared Services - Animators | Open | 0 | 0 | 0 | TAP-95983
01.04.04.09.00.00.00.00 | TAP-111915 | [IRR][Core Instruments] Test Development for Closed Loop Control Evaluation (Includes Fixturing) | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-95983
01.04.04.10.00.00.00.00 | TAP-111790 | [IRR][Core Instruments] Set Up Suture and Tissue Feeder for Cutting Tests | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-95983
01.04.04.11.00.00.00.00 | TAP-111788 | [IRR][Core Instruments] Set Up Camera Pose Measurement Fixture for Shears | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-95983
01.04.04.12.00.00.00.00 | TAP-111789 | [IRR][Fred] Set Up Camera Pose Measurement Fixture for Shears | 0 | Foundation - Fred | Open | 0 | 0 | 0 | TAP-95983
01.04.04.13.00.00.00.00 | TAP-114540 | [IRR][Sirius] Update Reliability Logging for Failure Detection Log Collection | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95983
01.04.04.14.00.00.00.00 | TAP-116408 | [IRR][Puppeteers] Support for framework for wristed testing | 0 | Core Instruments - Puppeteers | Open | 0 | 0 | 0 | TAP-95983
01.04.04.15.00.00.00.00 | TAP-116440 | [IRR][PlantModels] Provide an interface for external loads on the instrument | 0 | Shared Services - Animators | Done | 0 | 0 | 0 | TAP-95983
01.04.04.16.00.00.00.00 | TAP-116441 | [IRR][PlantModels] Provide a mask summarizing the plant model parameters | 0 | Shared Services - Animators | Open | 0 | 0 | 0 | TAP-95983
01.04.04.17.00.00.00.00 | TAP-116442 | [IRR][PlantModels] Request/Coordinate support for the ein_ng build process on the HPC cluster | 0 | Shared Services - Animators | In progress | 0 | 0 | 0 | TAP-95983
01.04.04.18.00.00.00.00 | TAP-116456 | [IRR][PlantModels] Setup an evaluation framework for parameter scan simulations | 0 | Shared Services - Animators | Open | 0 | 0 | 0 | TAP-95983
01.04.04.19.00.00.00.00 | TAP-116457 | [IRR][PlantModels] Familiarize with the IDU standalone tester | 0 | Shared Services - Animators | Done | 0 | 0 | 0 | TAP-95983
01.04.04.20.00.00.00.00 | TAP-116491 | [IRR][Playback][Happy Jaws] Evaluate Playback tools and Use Cases | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-95983
01.04.04.21.00.00.00.00 | TAP-116492 | [IRR][HW Testing][Happy Jaws] Investigate Engineering Test Infrastructure Improvements | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-95983
01.04.04.22.00.00.00.00 | TAP-116493 | [IRR][HW Testing][Happy Jaws] Implement Standardized Engineering Test Scripts | 0 | Core Instruments - Happy Jaws | Open | 0 | 0 | 0 | TAP-95983
01.04.04.23.00.00.00.00 | TAP-116494 | [IRR][Playback][Sirius] Create script for running playback simulation | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95983
01.04.04.24.00.00.00.00 | TAP-116495 | [IRR][Spike][Equivalency][Sirius] Develop Equivalency Test for IRR Controller | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95983
01.04.04.25.00.00.00.00 | TAP-116496 | [IRR][HW Testing][Sirius] Documentation of HW Test Fixturing and Setup | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95983
01.04.04.26.00.00.00.00 | TAP-116497 | [IRR][HW Testing][Sirius] Implement Standardized Engineering Test Reports | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95983
01.04.04.27.00.00.00.00 | TAP-116498 | [IRR][Sirius] Derating Tool Documentation | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-95983
01.04.04.28.00.00.00.00 | TAP-116499 | [IRR][Sirius] Continuous Shmio Logging Documentation | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-95983
01.04.04.29.00.00.00.00 | TAP-116500 | [IRR][Sirius] Single signal logging Documentation | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95983
01.04.04.30.00.00.00.00 | TAP-118633 | [IRR][Enabler][Tools] Replace calibration_override to replace with state machine variant subsystem | 0 | Core Instruments - Sirius | In progress | 0 | 0 | 0 | TAP-95983
01.04.04.31.00.00.00.00 | TAP-121182 | [IRR][Enabler] Tools to analyze motor position controller | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95983
01.04.05.00.00.00.00.00 | TAP-111719 | [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | 0 |  | Accepted | 0 | 0 | 0
01.04.05.01.00.00.00.00 | TAP-111916 | [IRR][Core Instruments] EtherCAT interface module for real-time I/O on IDU fixture | 0 | Core Instruments | Open | 0 | 0 | 0 | TAP-111719
01.04.05.02.00.00.00.00 | TAP-112039 | [IRR][Fred] EtherCAT interface module for real-time I/O on IDU fixture | 0 | Foundation - Fred | Open | 0 | 0 | 0 | TAP-111719
01.04.05.03.00.00.00.00 | TAP-112040 | [IRR][I2E] EtherCAT interface module for real-time I/O on IDU fixture | 0 | Advanced Instruments - I2E | Done | 0 | 0 | 0 | TAP-111719
01.04.05.04.00.00.00.00 | TAP-114445 | [MIRR][I2E][Spike] Support Sebastian in testing/configuring Galil | 0 | Advanced Instruments - I2E | In progress | 0 | 0 | 0 | TAP-111719
01.04.05.05.00.00.00.00 | TAP-114446 | [MIRR][I2E] Add Ethercat Master/shmios to Diagnostic Folder and rc.startup | 0 | Advanced Instruments - I2E | Open | 0 | 0 | 0 | TAP-111719
01.04.06.00.00.00.00.00 | TAP-111721 | [IRR][Enabler] Summer 2024 IRR Lab Support | 0 |  | In progress | 0 | 0 | 0
01.04.06.01.00.00.00.00 | TAP-111917 | [IRR][Core Instruments] Labs Support for Controller Updates (PI14) | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111721
01.04.06.02.00.00.00.00 | TAP-115880 | [IRR][ORSI] Update Lab SW for Hard Stop recovery | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-111721
01.04.06.03.00.00.00.00 | TAP-116068 | [IRR] Generate Controller Prototype for "tipped pulley" HW Design | 0 | Core Instruments - Sirius | Cancelled | 0 | 0 | 0 | TAP-111721
01.04.06.04.00.00.00.00 | TAP-116464 | [IRR][ORSI] Decide on parameters to derate with clinical | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-111721
01.04.06.05.00.00.00.00 | TAP-116465 | [IRR][ORSI] Attend ORSI | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-111721
01.04.06.06.00.00.00.00 | TAP-116466 | [IRR][ORSI] Reserve time for protocol development and ORSI related controller development | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-111721
01.04.06.07.00.00.00.00 | TAP-116467 | [IRR][RUFS] Prepare lab branch | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-111721
01.04.06.08.00.00.00.00 | TAP-121702 | [IRR] Update IRR SW With Detachment Detection | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-111721
01.04.07.00.00.00.00.00 | TAP-111722 | [IRR][Enabler] Labs Support for Controller Updates (PI15) | 0 |  | PROPOSED | 0 | 0 | 0
01.04.07.01.00.00.00.00 | TAP-111918 | [IRR][Core Instruments] Labs Support for Controller Updates (PI15) | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111722
01.04.08.00.00.00.00.00 | TAP-111723 | [IRR][Enabler] Labs Support for Controller Updates (PI16) | 0 |  | PROPOSED | 0 | 0 | 0
01.04.08.01.00.00.00.00 | TAP-111919 | [IRR][Core Instruments] Labs Support for Controller Updates (PI16) | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111723
01.04.09.00.00.00.00.00 | TAP-111724 | [IRR][Enabler] Labs Support for Controller Updates (PI17) | 0 |  | PROPOSED | 0 | 0 | 0
01.04.09.01.00.00.00.00 | TAP-111920 | [IRR][Core Instruments] Labs Support for Controller Updates (PI17) | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-111724
01.04.10.00.00.00.00.00 | TAP-112119 | [IRR] Final Regression of performance with Finalized HW (Phase 2a) | 0 |  | PROPOSED | 0 | 0 | 0
01.04.10.01.00.00.00.00 | TAP-112120 | [IRR] Final Regression of performance with Finalized HW (Phase 2a) | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-112119
01.05.00.00.00.00.00.00 |  | First Phase SW Development on IRR Controller (Phase 1b) - Rashid/Lok Man | 0 |  |  | 0 | 0 | 0
01.05.01.00.00.00.00.00 | TAP-94125 | [IRR][Phase 1b] First Phase SW Development for Instrument Homing Compatible with WS5 Structure | 0 |  | Accepted | 0 | 0 | 0
01.05.01.01.00.00.00.00 | TAP-97747 | [WS5][Homing][Sirius] Evaluate Homing Controller Architecture and Identify Improvements | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.02.00.00.00.00 | TAP-97748 | [WS5][Homing][Sirius] Update DD for Homing Controller | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.03.00.00.00.00 | TAP-97749 | [WS5][Homing][Sirius] Run and fix Static Analysis on Homing Controller | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.04.00.00.00.00 | TAP-97750 | [WS5][Homing][Sirius] Create/Update Unit tests for Homing Controller | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.05.00.00.00.00 | TAP-97751 | [WS5][Homing][Sirius] cFMEA Risk analysis for Homing Controller | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.06.00.00.00.00 | TAP-97752 | [WS5][Homing][Sirius] Reserve for RCM creation | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.07.00.00.00.00 | TAP-97753 | [WS5][Homing][Sirius] Develop requirements for homing controller (Part 1) | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.08.00.00.00.00 | TAP-97754 | [WS5][Homing][Sirius] Create MIL tests for homing controller: ENGAGE_COUPLERS | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.09.00.00.00.00 | TAP-97755 | [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_JAW | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.10.00.00.00.00 | TAP-97756 | [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_TENSION | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.11.00.00.00.00 | TAP-97757 | [WS5][Homing][Sirius] Create MIL tests for homing controller: HOME_YAW/HOME_PITCH | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.12.00.00.00.00 | TAP-97758 | [WS5][Homing][Sirius] Develop requirements for homing controller (Part 2) | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-94125
01.05.01.13.00.00.00.00 | TAP-97910 | [WS5][Homing][Sirius] Homing Controller Implementation Sync | 0 | Core Instruments - Sirius | Cancelled | 0 | 0 | 0 | TAP-94125
01.05.01.14.00.00.00.00 | TAP-111778 | [IRR][Core Instruments] First Phase SW Development for Instrument Homing Compatible with WS5 Structure | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-94125
01.05.02.00.00.00.00.00 | TAP-95800 | [IRR][Phase 1b] First Phase SW Development Motor Controller Compatible with WS5 Structure | 0 |  | Accepted | 0 | 0 | 0
01.05.02.01.00.00.00.00 | TAP-91185 | [IRG][SW][WS5] Investigate alternative IDU motor position control approaches | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95800
01.05.02.02.00.00.00.00 | TAP-111779 | [IRR][Core Instruments] First Phase SW Development Motor Controller Compatible with WS5 Structure | 0 | Core Instruments | Done | 0 | 0 | 0 | TAP-95800
01.05.02.03.00.00.00.00 | TAP-116475 | [IRR][Phase 1b][Motor Controller] Informal design review | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95800
01.05.02.04.00.00.00.00 | TAP-116476 | [IRR][Phase 1b][Motor Controller] Decide on testing strategy | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95800
01.05.02.05.00.00.00.00 | TAP-116477 | [IRR][Phase 1b][Motor Controller] Create MIL/Unit tests for motor controller | 0 | Core Instruments - Sirius | Open | 0 | 0 | 0 | TAP-95800
01.05.02.06.00.00.00.00 | TAP-116478 | [IRR][Phase 1b][Motor Controller] Update and fix Static Analysis issues | 0 | Core Instruments - Sirius | Done | 0 | 0 | 0 | TAP-95800