## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete
TAP-121866 | 1 |  | 9,41,39,3,78,76,74,80,5,33 | 01.01.01.00.00.00.00.00 |  | TAP-121866 | [TAP-121866] ¦ [PnP][UFSW] Integration of Instrument Workflow Managers after removing build flag in develop | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121866 | 2 |  |  | 01.01.01.01.00.00.00.00 | TAP-121866 | TAP-121879 | [TAP-121866] ¦ [PnP][UFSW] Integration of Instrument Workflow Managers after removing build flag in develop | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121861 | 3 | 1 |  | 01.02.01.00.00.00.00.00 |  | TAP-121861 | [TAP-121861] ¦ [PnP][UFSW] Endoscope Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121861 | 4 |  |  | 01.02.01.01.00.00.00.00 | TAP-121861 | TAP-121877 | [TAP-121861] ¦ [PnP][UFSW] Endoscope Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121857 | 5 | 1 | 23 | 01.02.02.00.00.00.00.00 |  | TAP-121857 | [TAP-121857] ¦ [PnP][UFSW] Croc Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121857 | 6 |  |  | 01.02.02.01.00.00.00.00 | TAP-121857 | TAP-121874 | [TAP-121857] ¦ [PnP][UFSW] Croc Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 30 | 0 | 0 | 0 | 30 | 0%
TAP-121937 | 7 | 53,55 | 25 | 01.02.03.00.00.00.00.00 |  | TAP-121937 | [TAP-121937] ¦ [PnP][GUI] Isolate Language-related files for modularization | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
_GUI | 8 |  |  | 01.02.03.01.00.00.00.00 | TAP-121937 | TAP-114836 | [_GUI] ¦ [PnP] GUI - SWI Updates: Language | User Story | Open | GUI | GUI | Child Task | User Stories | 30 | 0 | 0 | 0 | 30 | 0%
TAP-121858 | 9 | 1 |  | 01.02.04.00.00.00.00.00 |  | TAP-121858 | [TAP-121858] ¦ [PnP][UFSW] Single Use Instrument Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121858 | 10 |  |  | 01.02.04.01.00.00.00.00 | TAP-121858 | TAP-121875 | [TAP-121858] ¦ [PnP][UFSW] Single Use Instrument Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 30 | 0 | 5 | 10 | 30 | 0%
TAP-121886 | 11 |  | 25,53,55 | 01.02.05.00.00.00.00.00 |  | TAP-121886 | [TAP-121886] ¦ [PnP][GUI] Isolate Instrument Indicator components to prepare for phase 2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
_GUI | 12 |  |  | 01.02.05.01.00.00.00.00 | TAP-121886 | TAP-114824 | [_GUI] ¦ [PnP] [GUI] - SWI Updates: Surgery Header | User Story | Groomed | GUI | GUI | Child Task | User Stories | 30 | 0 | 5 | 10 | 30 | 0%
TAP-114819 | 13 | 31 | 23 | 01.03.01.00.00.00.00.00 |  | TAP-114819 | [TAP-114819] ¦ [PnP] GUI - Pre Planning PnP Interface | Feature | Done |  |  | Parent Task | User Stories | 33 | 0 | 1 hr | 1 hr | 33 | 100%
_GUI | 14 |  |  | 01.03.01.01.00.00.00.00 | TAP-114819 | TAP-112001 | [_GUI] ¦ [Spike][v5.0][GUI][PnP] Investigate adding new instruments on runtime part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 33 | 0 | 1 hr | 1 hr | 33 | 100%
TAP-113463 | 15 | 31 | 23 | 01.03.02.00.00.00.00.00 |  | TAP-113463 | [TAP-113463] ¦ [PnP] GUI Testing Framework Improvements | Feature | Done |  |  | Parent Task | User Stories | 38 | 0 | 1 hr | 1 hr | 38 | 100%
_GUI | 16 |  |  | 01.03.02.01.00.00.00.00 | TAP-113463 | TAP-114721 | [_GUI] ¦ [PnP][GUI][Test][Must] Plan new test framework architecture | User Story | Done | GUI | GUI | Child Task | User Stories | 38 | 0 | 1 hr | 1 hr | 38 | 100%
TAP-113896 | 17 | 31 | 25 | 01.03.03.00.00.00.00.00 |  | TAP-113896 | [TAP-113896] ¦ [PnP] GUI - SWI Updates Part 1 | Feature | Done |  |  | Parent Task | User Stories | 64 | 0 | 1 hr | 1 hr | 64 | 100%
_GUI | 18 |  |  | 01.03.03.01.00.00.00.00 | TAP-113896 | TAP-114462 | [_GUI] ¦ [PnP][zenith] GUI - SWI Updates: Common SWI | User Story | Done | GUI | GUI | Child Task | User Stories | 64 | 0 | 1 hr | 1 hr | 64 | 100%
TAP-115384 | 19 | 72 |  | 01.03.04.00.00.00.00.00 |  | TAP-115384 | [TAP-115384] ¦ [PnP][UFSW] Migrate to the DR Arch - Containers | Feature | Done |  |  | Parent Task | User Stories | 83 | 0 | 1 hr | 1 hr | 83 | 100%
_UFSW | 20 |  |  | 01.03.04.01.00.00.00.00 | TAP-115384 | TAP-115874 | [_UFSW] ¦ [SPIKE] [zenith] Prototype container strategy for PnP vs Dont reboot | User Story | Done | UFSW | UFSW | Child Task | User Stories | 83 | 0 | 1 hr | 1 hr | 83 | 100%
TAP-114464 | 21 | 31 | 25 | 01.03.05.00.00.00.00.00 |  | TAP-114464 | [TAP-114464] ¦ [PnP] GUI - SWI Updates Part 2 | Feature | Done |  |  | Parent Task | User Stories | 87 | 0 | 1 hr | 1 hr | 87 | 100%
_GUI | 22 |  |  | 01.03.05.01.00.00.00.00 | TAP-114464 | TAP-113881 | [_GUI] ¦ [PnP] [GUI] - SWI Updates: System Configuration | User Story | Done | GUI | GUI | Child Task | User Stories | 87 | 0 | 1 hr | 1 hr | 87 | 100%
TAP-114992 | 23 | 13,31,33,15,5,74,76,78,80,25,57,90 | 19 | 01.03.06.00.00.00.00.00 |  | TAP-114992 | [TAP-114992] ¦ [PnP][UFSW] Migrate to the DR ACA Assembly Workflow Manager | Feature | Done |  |  | Parent Task | User Stories | 101 | 0 | 1 hr | 1 hr | 101 | 100%
_UFSW | 24 |  |  | 01.03.06.01.00.00.00.00 | TAP-114992 | TAP-115128 | [_UFSW] ¦ [PnP][UFSW] Prototype Design/Translators/Interface for SRA Teleop ACA Assembly Workflow Manager Re-Factor | User Story | Done | UFSW | UFSW | Child Task | User Stories | 101 | 0 | 1 hr | 1 hr | 101 | 100%
TAP-103900 | 25 | 17,35,37,53,45,11,7,55,43,49,47,51 | 23 | 01.03.07.00.00.00.00.00 |  | TAP-103900 | [TAP-103900] ¦ [Arch][PnP] GUI - Migration of SWIs to MVC - Prep and Initial Candidates | Feature | Done |  |  | Parent Task | User Stories | 126 | 0 | 1 hr | 1 hr | 126 | 100%
_GUI | 26 |  |  | 01.03.07.02.00.00.00.00 | TAP-103900 | TAP-104269 | [_GUI] ¦ [Enabler][v5.0][PnP][PixelPoets] How will refactoring impact the translation tool | User Story | Done | GUI | GUI | Child Task | User Stories | 126 | 0 | 1 hr | 1 hr | 126 | 100%
TAP-114890 | 27 |  | 19 | 01.03.08.00.00.00.00.00 |  | TAP-114890 | [TAP-114890] ¦ [PnP][UFSW] Migrate the Manual Mode STM to the Don't Reboot architecture | Feature | Done |  |  | Parent Task | User Stories | 159 | 0 | 1 hr | 1 hr | 159 | 100%
_UFSW | 28 |  |  | 01.03.08.01.00.00.00.00 | TAP-114890 | TAP-115076 | [_UFSW] ¦ [PnP][UFSW] Implement the Column, Insertion Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 159 | 0 | 1 hr | 1 hr | 159 | 100%
TAP-115011 | 29 |  | 19 | 01.03.09.00.00.00.00.00 |  | TAP-115011 | [TAP-115011] ¦ [PnP][UFSW] Migrate to the DR Bedside User Commands and Registration Workflow Managers | Feature | Done |  |  | Parent Task | User Stories | 183 | 0 | 1 hr | 1 hr | 183 | 100%
_UFSW | 30 |  |  | 01.03.09.01.00.00.00.00 | TAP-115011 | TAP-115382 | [_UFSW] ¦ [zenith] Complete Initial Design for the Bedside Registration Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 183 | 0 | 1 hr | 1 hr | 183 | 100%
TAP-125001 | 31 |  | 23,13,15,17,21 | 01.04.01.00.00.00.00.00 |  | TAP-125001 | [TAP-125001] ¦ [PnP][GUI] Rollover for PI14 PnP GUI work | Feature | Accepted |  |  | Parent Task | User Stories | 198 | 0 | 1 hr | 1 hr | 198 | 0%
_GUI | 32 |  |  | 01.04.01.01.00.00.00.00 | TAP-125001 | TAP-125185 | [_GUI] ¦ [PnP][GUI][Fusion] Technical Design Review for Staging Branch Changes and Merge Strategy Approval | User Story | In progress | GUI | GUI | Child Task | User Stories | 198 | 0 | 1 hr | 1 hr | 198 | 0%
TAP-124981 | 33 | 1 | 23 | 01.04.02.00.00.00.00.00 |  | TAP-124981 | [TAP-124981] ¦ [PnP][UFSW] PnP Set up For Don't Reboot SRA Refactor | Feature | Accepted |  |  | Parent Task | User Stories | 222 | 0 | 1 hr | 1 hr | 222 | 0%
_UFSW | 34 |  |  | 01.04.02.01.00.00.00.00 | TAP-124981 | TAP-125666 | [_UFSW] ¦ Initial design for the Local Power Constraints Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 222 | 0 | 1 hr | 1 hr | 222 | 100%
TAP-121911 | 35 | 53,55 | 25 | 01.04.03.00.00.00.00.00 |  | TAP-121911 | [TAP-121911] ¦ [PnP][GUI] Isolate Notification Indicator | Feature | Accepted |  |  | Parent Task | User Stories | 227 | 0 | 1 hr | 1 hr | 227 | 0%
_GUI | 36 |  |  | 01.04.03.01.00.00.00.00 | TAP-121911 | TAP-114830 | [_GUI] ¦ [PnP] [GUI] - SWI Updates: Notification Indicator Part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 227 | 0 | 1 hr | 1 hr | 227 | 100%
TAP-121904 | 37 | 53,55 | 25 | 01.04.04.00.00.00.00.00 |  | TAP-121904 | [TAP-121904] ¦ [PnP][GUI] Isolate vision system components | Feature | Accepted |  |  | Parent Task | User Stories | 237 | 0 | 1 hr | 1 hr | 237 | 0%
_GUI | 38 |  |  | 01.04.04.01.00.00.00.00 | TAP-121904 | TAP-113893 | [_GUI] ¦ [PnP][GUI][Fusion] SWI Updates: Video Data | User Story | Groomed | GUI | GUI | Child Task | User Stories | 237 | 0 | 1 hr | 1 hr | 237 | 0%
TAP-121856 | 39 |  |  | 01.04.05.00.00.00.00.00 |  | TAP-121856 | [TAP-121856] ¦ [PnP][UFSW] LigaSure Workflow Manager Migration | Feature | In progress |  |  | Parent Task | User Stories | 257.5 | 0 | 1 hr | 1 hr | 257.5 | 0%
TAP-121856 | 40 |  |  | 01.04.05.01.00.00.00.00 | TAP-121856 | TAP-121872 | [TAP-121856] ¦ [PnP][UFSW] LigaSure Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 257.5 | 0 | 1 hr | 1 hr | 257.5 | 0%
TAP-121860 | 41 | 1 |  | 01.04.06.00.00.00.00.00 |  | TAP-121860 | [TAP-121860] ¦ [PnP][UFSW] Core Wristed Instruments Workflow Manager Migration | Feature | Accepted |  |  | Parent Task | User Stories | 321.5 | 0 | 1 hr | 1 hr | 321.5 | 0%
TAP-121860 | 42 |  |  | 01.04.06.01.00.00.00.00 | TAP-121860 | TAP-121876 | [TAP-121860] ¦ [PnP][UFSW] Core Wristed Instruments Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 321.5 | 0 | 1 hr | 1 hr | 321.5 | 0%
TAP-121901 | 43 | 53,55 | 25 | 01.05.01.00.00.00.00.00 |  | TAP-121901 | [TAP-121901] ¦ [PnP][GUI] Isolate instrument and ergonomic settings | Feature | PROPOSED |  |  | Parent Task | User Stories | 362.5 | 0 | 1 hr | 1 hr | 362.5 | 0%
_GUI | 44 |  |  | 01.05.01.01.00.00.00.00 | TAP-121901 | TAP-114838 | [_GUI] ¦ [PnP] GUI - SWI Updates: Instrument Settings | User Story | Open | GUI | GUI | Child Task | User Stories | 362.5 | 0 | 249 | 331 | 362.5 | 0%
TAP-121891 | 45 | 53,55 | 25 | 01.05.02.00.00.00.00.00 |  | TAP-121891 | [TAP-121891] ¦ [PnP][GUI] Isolate startup and calibration components | Feature | PROPOSED |  |  | Parent Task | User Stories | 367.5 | 0 | 1 hr | 1 hr | 367.5 | 0%
_GUI | 46 |  |  | 01.05.02.01.00.00.00.00 | TAP-121891 | TAP-114835 | [_GUI] ¦ [PnP] [GUI] - SWI Updates: System Component | User Story | Open | GUI | GUI | Child Task | User Stories | 367.5 | 0 | 274 | 391 | 367.5 | 0%
TAP-121921 | 47 | 53,55 | 25 | 01.05.03.00.00.00.00.00 |  | TAP-121921 | [TAP-121921] ¦ [PnP][GUI] Isolate ORTI process and display manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 372.5 | 0 | 1 hr | 1 hr | 372.5 | 0%
_GUI | 48 |  |  | 01.05.03.01.00.00.00.00 | TAP-121921 | TAP-114850 | [_GUI] ¦ [PnP] GUI - SWI Updates: ORTI Display | User Story | Open | GUI | GUI | Child Task | User Stories | 372.5 | 0 | 299 | 431 | 372.5 | 0%
TAP-121927 | 49 | 53,55 | 25 | 01.05.04.00.00.00.00.00 |  | TAP-121927 | [TAP-121927] ¦ [PnP][GUI] Isolate S3D and STS process and display manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 372.5 | 0 | 1 hr | 1 hr | 372.5 | 0%
_GUI | 50 |  |  | 01.05.04.01.00.00.00.00 | TAP-121927 | TAP-114846 | [_GUI] ¦ [PnP] GUI - SWI Updates: SID Screen Components | User Story | Open | GUI | GUI | Child Task | User Stories | 372.5 | 0 | 319 | 471 | 372.5 | 0%
TAP-121873 | 51 | 53,55 | 25 | 01.05.05.00.00.00.00.00 |  | TAP-121873 | [TAP-121873] ¦ [PnP][GUI][Test] Implement Semi Automated SSR Coverage | Feature | PROPOSED |  |  | Parent Task | User Stories | 372.5 | 0 | 1 hr | 1 hr | 372.5 | 0%
TAP-121873 | 52 |  |  | 01.05.05.01.00.00.00.00 | TAP-121873 | TAP-121884 | [TAP-121873] ¦ [PnP][GUI][Test] Implement Semi Automated SSR Coverage | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 372.5 | 0 | 349 | 521 | 372.5 | 0%
TAP-121871 | 53 | 11 | 25,35,37,45,43,47,7,49,51 | 01.05.06.00.00.00.00.00 |  | TAP-121871 | [TAP-121871] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 1 | Feature | Accepted |  |  | Parent Task | User Stories | 372.5 | 0 | 1 hr | 1 hr | 372.5 | 0%
TAP-121871 | 54 |  |  | 01.05.06.01.00.00.00.00 | TAP-121871 | TAP-121883 | [TAP-121871] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 1 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 372.5 | 0 | 349 | 521 | 372.5 | 0%
TAP-121885 | 55 | 11 | 25,35,37,45,43,47,7,49,51 | 01.05.07.00.00.00.00.00 |  | TAP-121885 | [TAP-121885] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 402.5 | 0 | 1 hr | 1 hr | 402.5 | 0%
TAP-121885 | 56 |  |  | 01.05.07.01.00.00.00.00 | TAP-121885 | TAP-121887 | [TAP-121885] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 2 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 402.5 | 0 | 349 | 521 | 402.5 | 0%
TAP-125200 | 57 |  | 23 | 01.05.08.00.00.00.00.00 |  | TAP-125200 | [TAP-125200] ¦ [PnP][GUI] Create Product Architecture with Interface Specifications for Modularized Instrument Software Development | Feature | Accepted |  |  | Parent Task | User Stories | 432.5 | 0 | 1 hr | 1 hr | 432.5 | 0%
_GUI | 58 |  |  | 01.05.08.01.00.00.00.00 | TAP-125200 | TAP-125351 | [_GUI] ¦ [PnP] GUI - Draft the Product Architecture for GUI | User Story | Groomed | GUI | GUI | Child Task | User Stories | 432.5 | 0 | 349 | 521 | 432.5 | 0%
TAP-129535 | 59 |  | 60,68 | 02.01.01.00.00.00.00.00 |  | TAP-129535 | [TAP-129535] ¦ [PnP][v4.2] Migrate embedded PnP updates to v4.2 - Adv Instrument ART | Feature | PROPOSED |  |  | Parent Task | User Stories | 437.5 | 0 | 1 hr | 1 hr | 437.5 | 0%
TAP-126357 | 60 | 59 | 66 | 02.01.02.00.00.00.00.00 |  | TAP-126357 | [TAP-126357] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Desired Data Pipeline | Feature | PROPOSED |  |  | Parent Task | User Stories | 437.5 | 0 | 1 hr | 1 hr | 437.5 | 0%
_EMBEDDED | 61 |  |  | 02.01.02.01.00.00.00.00 | TAP-126357 | TAP-126108 | [_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] Dry run all IDU Primary TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 437.5 | 0 | 357 | 533 | 437.5 | 0%
TAP-130040 | 62 |  |  | 02.01.03.00.00.00.00.00 |  | TAP-130040 | [TAP-130040] ¦ [PnP][Zenith][Embedded] SRA HAL TC Updates Due to Data Pipeline Refactor | Feature | PROPOSED |  |  | Parent Task | User Stories | 471.5 | 0 | 1 hr | 1 hr | 471.5 | 0%
TAP-130040 | 63 |  |  | 02.01.03.01.00.00.00.00 | TAP-130040 | TAP-130041 | [TAP-130040] ¦ [PnP][Zenith][Embedded] SRA HAL TC Updates Due to Data Pipeline Refactor | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 471.5 | 0 | 386 | 573 | 471.5 | 0%
TAP-85741 | 64 | 66,124,68,128 |  | 02.02.01.00.00.00.00.00 |  | TAP-85741 | [TAP-85741] ¦ [PnP][Zenith][Embedded] Actual Transport and Application Layer Implementation and Memory Manager IDU Refactor | Feature | Done |  |  | Parent Task | User Stories | 471.5 | 0 | 1 hr | 1 hr | 471.5 | 100%
_EMBEDDED | 65 |  |  | 02.02.01.01.00.00.00.00 | TAP-85741 | TAP-96951 | [_EMBEDDED] ¦ [Plug n Play][I2E][IDU Primary][Enabler] Design Memory Manager for IDU Primary Instrument Parameter Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 471.5 | 0 | 1 hr | 1 hr | 471.5 | 100%
TAP-121915 | 66 | 82,118,116,60,122 | 64 | 02.03.01.00.00.00.00.00 |  | TAP-121915 | [TAP-121915] ¦ [PnP][Zenith][Embedded] Desired Parameter Pipeline from SRA HAL to Instrumentation | Feature | Accepted |  |  | Parent Task | User Stories | 561.5 | 0 | 1 hr | 1 hr | 561.5 | 0%
TAP-121915 | 67 |  |  | 02.03.01.01.00.00.00.00 | TAP-121915 | TAP-121955 | [TAP-121915] ¦ [PnP][Zenith][Embedded] Desired Parameter Pipeline from SRA HAL to Instrumentation | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 561.5 | 0 | 1 hr | 1 hr | 561.5 | 0%
TAP-126005 | 68 | 59 | 64 | 02.03.02.00.00.00.00.00 |  | TAP-126005 | [TAP-126005] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Actual Data Pipeline | Feature | Accepted |  |  | Parent Task | User Stories | 614.5 | 0 | 1 hr | 1 hr | 614.5 | 0%
_EMBEDDED | 69 |  |  | 02.03.02.01.00.00.00.00 | TAP-126005 | TAP-125098 | [_EMBEDDED] ¦ [PnP][zenith][Embedded] Integration Testing for Actual Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 614.5 | 0 | 1 hr | 1 hr | 614.5 | 100%
TAP-99224 | 70 |  | 90 | 03.01.01.00.00.00.00.00 |  | TAP-99224 | [TAP-99224] ¦ [PnP] [Architecture] [Enabler][Controls] EIN-SWI-176 Croc Controller Refactor | Feature | PROPOSED |  |  | Parent Task | User Stories | 654.5 | 0 | 1 hr | 1 hr | 654.5 | 0%
TAP-99224 | 71 |  |  | 03.01.01.01.00.00.00.00 | TAP-99224 | TAP-121522 | [TAP-99224] ¦ [PnP] [Architecture] [Enabler][Controls] EIN-SWI-176 Croc Controller Refactor | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 654.5 | 0 | 527 | 726 | 654.5 | 0%
TAP-103935 | 72 |  | 19 | 04.01.01.00.00.00.00.00 |  | TAP-103935 | [TAP-103935] ¦ [PnP][Arch][UFSW] MSC - Migrate Energy STM to Aux Fn Manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 654.5 | 0 | 1 hr | 1 hr | 654.5 | 0%
_UFSW | 73 |  |  | 04.01.01.01.00.00.00.00 | TAP-103935 | TAP-97705 | [_UFSW] ¦ [Scrumbledores] MSC plug and play concept architecture and prototyping | User Story | Done | UFSW | UFSW | Child Task | User Stories | 654.5 | 0 | 527 | 726 | 654.5 | 100%
TAP-121902 | 74 | 1 | 23 | 04.02.01.00.00.00.00.00 |  | TAP-121902 | [TAP-121902] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Core Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 686.5 | 0 | 1 hr | 1 hr | 686.5 | 0%
TAP-121902 | 75 |  |  | 04.02.01.01.00.00.00.00 | TAP-121902 | TAP-121944 | [TAP-121902] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Core Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 686.5 | 0 | 564 | 776 | 686.5 | 0%
TAP-121900 | 76 | 1 | 23 | 04.02.02.00.00.00.00.00 |  | TAP-121900 | [TAP-121900] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Croc Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 686.5 | 0 | 1 hr | 1 hr | 686.5 | 0%
TAP-121900 | 77 |  |  | 04.02.02.01.00.00.00.00 | TAP-121900 | TAP-121942 | [TAP-121900] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Croc Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 686.5 | 0 | 564 | 776 | 686.5 | 0%
TAP-121898 | 78 | 1 | 23 | 04.02.03.00.00.00.00.00 |  | TAP-121898 | [TAP-121898] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Ligasure Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 686.5 | 0 | 1 hr | 1 hr | 686.5 | 0%
TAP-121898 | 79 |  |  | 04.02.03.01.00.00.00.00 | TAP-121898 | TAP-121941 | [TAP-121898] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Ligasure Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 686.5 | 0 | 564 | 776 | 686.5 | 0%
TAP-121905 | 80 | 1 | 23 | 04.02.04.00.00.00.00.00 |  | TAP-121905 | [TAP-121905] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Single Use Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 689.5 | 0 | 1 hr | 1 hr | 689.5 | 0%
TAP-121905 | 81 |  |  | 04.02.04.01.00.00.00.00 | TAP-121905 | TAP-121946 | [TAP-121905] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Single Use Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 689.5 | 0 | 564 | 776 | 689.5 | 0%
TAP-121922 | 82 | 110 | 66 | 04.03.01.00.00.00.00.00 |  | TAP-121922 | [TAP-121922] ¦ [PnP][Zenith][Embedded] Implement Instrumentation Latching within the SRA HAL/BSCM | Feature | PROPOSED |  |  | Parent Task | User Stories | 689.5 | 0 | 1 hr | 1 hr | 689.5 | 0%
TAP-121922 | 83 |  |  | 04.03.01.01.00.00.00.00 | TAP-121922 | TAP-121961 | [TAP-121922] ¦ [PnP][Zenith][Embedded] Implement Instrumentation Latching within the SRA HAL/BSCM | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 689.5 | 0 | 564 | 776 | 689.5 | 0%
TAP-103932 | 84 |  |  | 04.04.01.00.00.00.00.00 |  | TAP-103932 | [TAP-103932] ¦ [PnP][Arch][UFSW] Migrate IX STM Instrument Attachment to PnP SWIs | Feature | Done |  |  | Parent Task | User Stories | 689.5 | 0 | 1 hr | 1 hr | 689.5 | 100%
_UFSW | 85 |  |  | 04.04.01.01.00.00.00.00 | TAP-103932 | TAP-105843 | [_UFSW] ¦ [UFSW][Newton][PnP] Initial design and requirements set up/review | User Story | Done | UFSW | UFSW | Child Task | User Stories | 689.5 | 0 | 1 hr | 1 hr | 689.5 | 100%
TAP-103933 | 86 |  |  | 04.04.02.00.00.00.00.00 |  | TAP-103933 | [TAP-103933] ¦ [PnP][Arch][UFSW] Migrate IX STM Internal/External Calibration to PnP SWIs | Feature | Done |  |  | Parent Task | User Stories | 730.5 | 0 | 1 hr | 1 hr | 730.5 | 100%
_UFSW | 87 |  |  | 04.04.02.02.00.00.00.00 | TAP-103933 | TAP-106142 | [_UFSW] ¦ [Organelles][PnP][Spike] Draft Implementation plan for IX STM Internal/External Calibration migration | User Story | Done | UFSW | UFSW | Child Task | User Stories | 730.5 | 0 | 1 hr | 1 hr | 730.5 | 100%
TAP-114308 | 88 | 118,116 | 90 | 04.04.03.00.00.00.00.00 |  | TAP-114308 | [TAP-114308] ¦ [PnP][Controls] Migration of IDU Controller SWIs | Feature | Done |  |  | Parent Task | User Stories | 743.5 | 0 | 1 hr | 1 hr | 743.5 | 100%
_CONTROLS | 89 |  |  | 04.04.03.03.00.00.00.00 | TAP-114308 | TAP-114494 | [_CONTROLS] ¦ [zenith] Data Corruption RCMs - Get Buy-In from Quality for Update | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 743.5 | 0 | 1 hr | 1 hr | 743.5 | 100%
TAP-114299 | 90 | 88,98,100,70 | 23 | 04.04.04.00.00.00.00.00 |  | TAP-114299 | [TAP-114299] ¦ [PnP][Controls] Setup IDU Controller Container | Feature | Done |  |  | Parent Task | User Stories | 753.5 | 0 | 1 hr | 1 hr | 753.5 | 100%
_CONTROLS | 91 |  |  | 04.04.04.01.00.00.00.00 | TAP-114299 | TAP-114400 | [_CONTROLS] ¦ [zenith] Identify SWIs to Migrate, wrangle their signals inside container, 1/2 | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 753.5 | 0 | 1 hr | 1 hr | 753.5 | 100%
TAP-121913 | 92 | 96,118,116 | 98,100 | 04.05.01.00.00.00.00.00 |  | TAP-121913 | [TAP-121913] ¦ [PnP][Controls] IDU Actuator Controller - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 760.5 | 0 | 1 hr | 1 hr | 760.5 | 0%
TAP-121913 | 93 |  |  | 04.05.01.01.00.00.00.00 | TAP-121913 | TAP-121954 | [TAP-121913] ¦ [PnP][Controls] IDU Actuator Controller - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 760.5 | 0 | 658 | 870 | 760.5 | 0%
TAP-121912 | 94 | 96,118,116 | 98,100 | 04.05.02.00.00.00.00.00 |  | TAP-121912 | [TAP-121912] ¦ [PnP][Controls] IDU Actuator Monitor - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 761.5 | 0 | 1 hr | 1 hr | 761.5 | 0%
TAP-121912 | 95 |  |  | 04.05.02.01.00.00.00.00 | TAP-121912 | TAP-121953 | [TAP-121912] ¦ [PnP][Controls] IDU Actuator Monitor - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 761.5 | 0 | 658 | 870 | 761.5 | 0%
TAP-121925 | 96 | 116,118 | 102,114,92,94,104,106,112 | 04.05.03.00.00.00.00.00 |  | TAP-121925 | [TAP-121925] ¦ [PnP][Controls] IDU Controller SysIL Verification - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 800.5 | 0 | 1 hr | 1 hr | 800.5 | 0%
TAP-121925 | 97 |  |  | 04.05.03.01.00.00.00.00 | TAP-121925 | TAP-121963 | [TAP-121925] ¦ [PnP][Controls] IDU Controller SysIL Verification - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 800.5 | 0 | 658 | 870 | 800.5 | 0%
TAP-121923 | 98 | 102,114,92,94,104,106,118,116,112 | 90 | 04.05.04.00.00.00.00.00 |  | TAP-121923 | [TAP-121923] ¦ [PnP][Controls] IDU Controller Debug Logging - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 821.5 | 0 | 1 hr | 1 hr | 821.5 | 0%
TAP-121923 | 99 |  |  | 04.05.04.01.00.00.00.00 | TAP-121923 | TAP-121962 | [TAP-121923] ¦ [PnP][Controls] IDU Controller Debug Logging - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 821.5 | 0 | 658 | 870 | 821.5 | 0%
TAP-121920 | 100 | 102,114,92,94,104,106,118,116,112 | 90 | 04.05.05.00.00.00.00.00 |  | TAP-121920 | [TAP-121920] ¦ [PnP][Controls] IDU Controller Error Handler - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 826.5 | 0 | 1 hr | 1 hr | 826.5 | 0%
TAP-121920 | 101 |  |  | 04.05.05.01.00.00.00.00 | TAP-121920 | TAP-121959 | [TAP-121920] ¦ [PnP][Controls] IDU Controller Error Handler - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 826.5 | 0 | 658 | 870 | 826.5 | 0%
TAP-121919 | 102 | 96,118,116 | 98,100 | 04.05.06.00.00.00.00.00 |  | TAP-121919 | [TAP-121919] ¦ [PnP][Controls] IDU Controller "Workflow Manager" - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 839.5 | 0 | 1 hr | 1 hr | 839.5 | 0%
TAP-121919 | 103 |  |  | 04.05.06.01.00.00.00.00 | TAP-121919 | TAP-121958 | [TAP-121919] ¦ [PnP][Controls] IDU Controller "Workflow Manager" - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 839.5 | 0 | 658 | 870 | 839.5 | 0%
TAP-121910 | 104 | 96,118,116 | 98,100 | 04.05.07.00.00.00.00.00 |  | TAP-121910 | [TAP-121910] ¦ [PnP][Controls] IDU Actuator Output Processing - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 841.5 | 0 | 1 hr | 1 hr | 841.5 | 0%
TAP-121910 | 105 |  |  | 04.05.07.01.00.00.00.00 | TAP-121910 | TAP-121951 | [TAP-121910] ¦ [PnP][Controls] IDU Actuator Output Processing - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 841.5 | 0 | 658 | 870 | 841.5 | 0%
TAP-121908 | 106 | 96,118,116 | 98,100 | 04.05.08.00.00.00.00.00 |  | TAP-121908 | [TAP-121908] ¦ [PnP][Controls] IDU Actuator Input Processing - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 841.5 | 0 | 1 hr | 1 hr | 841.5 | 0%
TAP-121908 | 107 |  |  | 04.05.08.01.00.00.00.00 | TAP-121908 | TAP-121949 | [TAP-121908] ¦ [PnP][Controls] IDU Actuator Input Processing - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 841.5 | 0 | 658 | 870 | 841.5 | 0%
TAP-121906 | 108 | 126 | 110 | 04.05.09.00.00.00.00.00 |  | TAP-121906 | [TAP-121906] ¦ [PnP][Arch][Enabler][Embedded] Integrate BSCM with Subsystems | Feature | PROPOSED |  |  | Parent Task | User Stories | 846.5 | 0 | 1 hr | 1 hr | 846.5 | 0%
TAP-121906 | 109 |  |  | 04.05.09.01.00.00.00.00 | TAP-121906 | TAP-121947 | [TAP-121906] ¦ [PnP][Arch][Enabler][Embedded] Integrate BSCM with Subsystems | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 846.5 | 0 | 658 | 870 | 846.5 | 0%
TAP-97909 | 110 | 108,120 | 82 | 04.05.10.00.00.00.00.00 |  | TAP-97909 | [TAP-97909] ¦ [PnP][Zenith][Embedded] Implement Bedside Config Manager | Feature | Accepted |  |  | Parent Task | User Stories | 846.5 | 0 | 1 hr | 1 hr | 846.5 | 0%
_EMBEDDED | 111 |  |  | 04.05.10.01.00.00.00.00 | TAP-97909 | TAP-97616 | [_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Enabler] Cyclic EtherCAT SRA HAL Framework Update | User Story | Groomed | Embedded | EMBEDDED | Child Task | User Stories | 846.5 | 0 | 658 | 870 | 846.5 | 0%
TAP-126766 | 112 | 96,118,116 | 98,100,114 | 04.05.11.00.00.00.00.00 |  | TAP-126766 | [TAP-126766] ¦ [PnP][Controls] Instrument Controller - Migration - Test Work | Feature | PROPOSED |  |  | Parent Task | User Stories | 857.5 | 0 | 1 hr | 1 hr | 857.5 | 0%
TAP-126766 | 113 |  |  | 04.05.11.01.00.00.00.00 | TAP-126766 | TAP-121956 | [TAP-126766] ¦ [PnP][Controls] Instrument Controller - Migration - Test Work | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 857.5 | 0 | 701 | 935 | 857.5 | 0%
TAP-121916 | 114 | 96,118,116,112 | 98,100 | 04.05.12.00.00.00.00.00 |  | TAP-121916 | [TAP-121916] ¦ [PnP][Controls] Instrument Controller - Migration - Dev Work | Feature | Accepted |  |  | Parent Task | User Stories | 876.5 | 0 | 1 hr | 1 hr | 876.5 | 0%
TAP-121916 | 115 |  |  | 04.05.12.01.00.00.00.00 | TAP-121916 | TAP-121956 | [TAP-121916] ¦ [PnP][Controls] Instrument Controller - Migration - Dev Work | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 876.5 | 0 | 1 hr | 1 hr | 876.5 | 0%
TAP-121926 | 116 |  | 118,96,88,106,104,94,92,66,114,102,100,98,112 | 04.05.13.00.00.00.00.00 |  | TAP-121926 | [TAP-121926] ¦ [PnP][IDU][Controls] Merge to Develop Behind Build Flag | Feature | PROPOSED |  |  | Parent Task | User Stories | 896.5 | 0 | 1 hr | 1 hr | 896.5 | 0%
TAP-121926 | 117 |  |  | 04.05.13.01.00.00.00.00 | TAP-121926 | TAP-121964 | [TAP-121926] ¦ [PnP][IDU][Controls] Merge to Develop Behind Build Flag | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 896.5 | 0 | 701 | 935 | 896.5 | 0%
TAP-121917 | 118 | 116 | 88,106,104,94,92,66,114,102,100,98,96,112 | 04.05.14.00.00.00.00.00 |  | TAP-121917 | [TAP-121917] ¦ [PnP][IDU][Controls] Preliminary Integration of M-IRR and Newton | Feature | PROPOSED |  |  | Parent Task | User Stories | 896.5 | 0 | 1 hr | 1 hr | 896.5 | 0%
TAP-121917 | 119 |  |  | 04.05.14.01.00.00.00.00 | TAP-121917 | TAP-121957 | [TAP-121917] ¦ [PnP][IDU][Controls] Preliminary Integration of M-IRR and Newton | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 896.5 | 0 | 701 | 935 | 896.5 | 0%
TAP-94827 | 120 |  | 110 | 04.05.15.00.00.00.00.00 |  | TAP-94827 | [TAP-94827] ¦ [PnP][Architecture][Embedded] Update Tools to new Instrument Interfaces | Feature | PROPOSED |  |  | Parent Task | User Stories | 896.5 | 0 | 1 hr | 1 hr | 896.5 | 0%
TAP-94827 | 121 |  |  | 04.05.15.01.00.00.00.00 | TAP-94827 | TAP-121503 | [TAP-94827] ¦ [PnP][Architecture][Embedded] Update Tools to new Instrument Interfaces | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 896.5 | 0 | 701 | 935 | 896.5 | 0%
TAP-122018 | 122 |  | 66 | 04.05.16.00.00.00.00.00 |  | TAP-122018 | [TAP-122018] ¦ [PnP][Arch][Test]HIL Testing for Embedded IDU Testing | Feature | PROPOSED |  |  | Parent Task | User Stories | 896.5 | 0 | 1 hr | 1 hr | 896.5 | 0%
TAP-122018 | 123 |  |  | 04.05.16.01.00.00.00.00 | TAP-122018 | TAP-122041 | [TAP-122018] ¦ [PnP][Arch][Test]HIL Testing for Embedded IDU Testing | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 896.5 | 0 | 701 | 935 | 896.5 | 0%
TAP-84434 | 124 |  | 64 | 04.05.17.00.00.00.00.00 |  | TAP-84434 | [TAP-84434] ¦ [PnP][Arch][Enabler][Embedded] Create Infrastructure - Data Aggregator Interfaces | Feature | PROPOSED |  |  | Parent Task | User Stories | 896.5 | 0 | 1 hr | 1 hr | 896.5 | 0%
_EMBEDDED | 125 |  |  | 04.05.17.01.00.00.00.00 | TAP-84434 | TAP-85298 | [_EMBEDDED] ¦ [Newton][Enabler][Sunrisers] Config Data Manager and Instr. Data Interface Prototype | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 896.5 | 0 | 701 | 935 | 896.5 | 0%
TAP-121929 | 126 |  | 108 | 04.05.18.00.00.00.00.00 |  | TAP-121929 | [TAP-121929] ¦ [PnP][Zenith][Embedded] System Integration Testing for Controllers, IDU Primary, SRA HAL/BSCM | Feature | PROPOSED |  |  | Parent Task | User Stories | 896.5 | 0 | 1 hr | 1 hr | 896.5 | 0%
TAP-121929 | 127 |  |  | 04.05.18.01.00.00.00.00 | TAP-121929 | TAP-121967 | [TAP-121929] ¦ [PnP][Zenith][Embedded] System Integration Testing for Controllers, IDU Primary, SRA HAL/BSCM | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 896.5 | 0 | 831 | 1025 | 896.5 | 0%
TAP-97775 | 128 |  | 64 | 04.05.19.00.00.00.00.00 |  | TAP-97775 | [TAP-97775] ¦ [PnP][V5.0][Embedded] GECAT for Instruments Data Transportation: S-function interfaces - Foundation Support | Feature | Accepted |  |  | Parent Task | User Stories | 896.5 | 0 | 1 hr | 1 hr | 896.5 | 0%
_EMBEDDED | 129 |  |  | 04.05.19.01.00.00.00.00 | TAP-97775 | TAP-85764 | [_EMBEDDED] ¦ Support S-function development for Initial Attachment data usage | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 896.5 | 0 | 831 | 1025 | 896.5 | 0%

## Log
DataTimeStamp | Event | Data | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
2024-09-13 11:18 | Start: | DANSAP Formatter, v1.6 | _EMBEDDED
2024-09-13 11:18 | Input File: | PnP_Categorized_240904_1601 (discipline+refinement level updated).xls | _EMBEDDED |  | TAP-121864
2024-09-13 11:18 | Output File: | Project_Import_DS_.xlsx | _EMBEDDED
2024-09-13 11:18 | Info |  | _EMBEDDED
2024-09-13 11:18 | Processing: | Jira Data: Rows: 497, Cols: 16 | _EMBEDDED
2024-09-13 11:18 | Result: | Project Data: Rows: 129, Cols: 20 | _EMBEDDED |  | TAP-121864
2024-09-13 11:18 | Processing Complete: | 22.502346992492676 seconds | _EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
|  |  | _EMBEDDED | TAP-121864
_EMBEDDED
_EMBEDDED
|  |  | _EMBEDDED | TAP-121864
_EMBEDDED
|  |  | _EMBEDDED | TAP-114818
|  |  | _EMBEDDED | TAP-113642
|  |  | _EMBEDDED | TAP-121864
_EMBEDDED
|  |  | _EMBEDDED | TAP-121864
_EMBEDDED
_EMBEDDED
_EMBEDDED
|  |  | _EMBEDDED | TAP-115465
|  |  | _EMBEDDED |  | TAP-125195
_EMBEDDED
|  |  | _EMBEDDED | TAP-103479
|  |  | _EMBEDDED |  | TAP-121864
_EMBEDDED
|  |  | _EMBEDDED |  | TAP-121864
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
|  |  | _EMBEDDED | TAP-94814
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
|  |  | _EMBEDDED | TAP-106649
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED
_EMBEDDED

## Summary
Resource Names | Sum FDR
UFSW | 2788
GUI | 2542
EMBEDDED | 6388
CONTROLS | 7894
Total FDR: | 100164