## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete
TAP-94739 | 1 | 5,284 |  | 01.01.01.00.00.00.00.00 |  | TAP-94739 | [TAP-94739] ¦ [IRR] Develop Consolidated SW Architecture Design for Medium IRR | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-94739_HAPPYJAWS | 2 | 1 |  | 01.01.01.02.00.00.00.00 | TAP-94739 | TAP-97584 | [TAP-94739_HAPPYJAWS] ¦ [IRR][Arch] Describe wristed controller system functional architecture | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 219.5 | 92.5 | 5 | 6 | 0 | 100%
TAP-94739_SIRIUS | 3 | 1 |  | 01.01.01.04.00.00.00.00 | TAP-94739 | TAP-97602 | [TAP-94739_SIRIUS] ¦ [IRR][Arch] Analyze requirement impact | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 316 | 110 | 3 | 3.6 | 0 | 100%
TAP-94739_SIRIUS | 4 | 1 |  | 01.01.01.06.00.00.00.00 | TAP-94739 | TAP-111973 | [TAP-94739_SIRIUS] ¦ [IRR][Arch] Analyze requirement impact | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-97668 | 5 | 9 | 1 | 01.01.02.00.00.00.00.00 |  | TAP-97668 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-97668 | 6 | 5 |  | 01.01.02.01.00.00.00.00 | TAP-97668 | TAP-111972 | [TAP-97668] ¦ [IRR] Introduce Consolidated Wristed Architecture into Medium IRR SW | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-97668_HAPPYJAWS | 7 | 5 |  | 01.01.02.02.00.00.00.00 | TAP-97668 | TAP-97600 | [TAP-97668_HAPPYJAWS] ¦ [IRR][Arch] Identify impacts and opportunities on testing strategy | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 3.5 | 3.5 | 3.5 | 4.2 | 0 | 100%
TAP-97668_SIRIUS | 8 | 5 |  | 01.01.02.04.00.00.00.00 | TAP-97668 | TAP-97586 | [TAP-97668_SIRIUS] ¦ [IRR][Arch] Migration and branch sync considerations | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-120097 | 9 | 284 | 5 | 01.01.03.00.00.00.00.00 |  | TAP-120097 | [TAP-120097] ¦ [IRR][Enhancement] Finalize IRR Wristed Architecture and Interfaces in SW | Feature | In progress |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-120097_HAPPYJAWS | 10 | 9 |  | 01.01.03.01.00.00.00.00 | TAP-120097 | TAP-97689 | [TAP-120097_HAPPYJAWS] ¦ [IRR][Arch] Update instrument data model for wristed instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-120097_SIRIUS | 11 | 9 |  | 01.01.03.08.00.00.00.00 | TAP-120097 | TAP-126505 | [TAP-120097_SIRIUS] ¦ [IRR][Arch][Sirius] Finalize input side SWI's architecture including interfaces (Pending PR) | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 5 | 5 | 5 | 6 | 0 | 100%
TAP-111730 | 12 | 284,15 |  | 01.02.01.00.00.00.00.00 |  | TAP-111730 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature | Done |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-111730 | 13 | 12 |  | 01.02.01.01.00.00.00.00 | TAP-111730 | TAP-111898 | [TAP-111730] ¦ [IRR][Enhancement] Adjust Clamping Performance for Functional Acceptability | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111730_HAPPYJAWS | 14 | 12 |  | 01.02.01.02.00.00.00.00 | TAP-111730 | TAP-116458 | [TAP-111730_HAPPYJAWS] ¦ [IRR][Clamping] Update switching logic in jaw torque estimator | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 6 | 6 | 6 | 7.2 | 0 | 100%
TAP-124062 | 15 | 284 | 12 | 01.02.02.00.00.00.00.00 |  | TAP-124062 | [TAP-124062] ¦ [IRR] Actuation and Clamping Performance Update Including Slow Close | Feature | In progress |  |  | Parent Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-124062_SIRIUS | 16 | 15 |  | 01.02.02.01.00.00.00.00 | TAP-124062 | TAP-116459 | [TAP-124062_SIRIUS] ¦ [IRR][Clamping] Continue Investigating Improvements to force estimator | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-124062_HAPPYJAWS | 17 | 15 |  | 01.02.02.02.00.00.00.00 | TAP-124062 | TAP-125695 | [TAP-124062_HAPPYJAWS] ¦ [IRR][Clamping] Evaluate Clamping Performance for Low-Force Graspers | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-94966 | 18 | 284 |  | 01.03.01.00.00.00.00.00 |  | TAP-94966 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature | Done |  |  | Parent Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 100%
TAP-94966 | 19 | 18 |  | 01.03.01.01.00.00.00.00 | TAP-94966 | TAP-111781 | [TAP-94966] ¦ [IRR][Enhancement] Update Shears Estimators/Controller for Use-Life and Performance Characteristics (phase 1a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-94966_HAPPYJAWS | 20 | 18 |  | 01.03.01.03.00.00.00.00 | TAP-94966 | TAP-116502 | [TAP-94966_HAPPYJAWS] ¦ [IRR][Cutting] Reproduce position estimation failures & Investigate | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 4 | 4 | 4 | 4.8 | 0 | 100%
TAP-94966_SIRIUS | 21 | 18 |  | 01.03.01.08.00.00.00.00 | TAP-94966 | TAP-116509 | [TAP-94966_SIRIUS] ¦ [IRR][Use-life] Identify dependent use-life parameters | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 8 | 8 | 8 | 9.6 | 0 | 100%
TAP-111554 | 22 | 284 |  | 01.03.02.00.00.00.00.00 |  | TAP-111554 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness | Feature | In progress |  |  | Parent Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-111554 | 23 | 22 |  | 01.03.02.01.00.00.00.00 | TAP-111554 | TAP-111782 | [TAP-111554] ¦ [IRR][Enhancement] Improve Cutting Control Robustness | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111554_SIRIUS | 24 | 22 |  | 01.03.02.03.00.00.00.00 | TAP-111554 | TAP-116507 | [TAP-111554_SIRIUS] ¦ [IRR][Cutting][Sirius] Get feedback from clinical team | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-111554_HAPPYJAWS | 25 | 22 |  | 01.03.02.05.00.00.00.00 | TAP-111554 | TAP-126637 | [TAP-111554_HAPPYJAWS] ¦ [IRR][Cutting] Migrate cutting Changes to IRR V4 Branch | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-111569 | 26 | 284 |  | 01.03.04.00.00.00.00.00 |  | TAP-111569 | [TAP-111569] ¦ [IRR][Enabler] P1 Integration, Testing, Tuning, EC1 Design Reviews | Feature | PROPOSED |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-111569 | 27 | 26 |  | 01.03.04.01.00.00.00.00 | TAP-111569 | TAP-111797 | [TAP-111569] ¦ [IRR][Enabler] P1 Integration, Testing, Tuning, EC1 Design Reviews | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 8 | 12 | 0 | 100%
TAP-112077 | 28 | 284 |  | 01.04.01.00.00.00.00.00 |  | TAP-112077 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112077 | 29 | 28 |  | 01.04.01.01.00.00.00.00 | TAP-112077 | TAP-112079 | [TAP-112077] ¦ [IRR][Enabler] Articulation/Free Space Actuation KPI generation and evaluation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-112077_SIRIUS | 30 | 28 |  | 01.04.01.02.00.00.00.00 | TAP-112077 | TAP-115017 | [TAP-112077_SIRIUS] ¦ [IRR][Articulation] Finalize KPI/Simulation Script | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 7 | 7 | 7 | 8.4 | 0 | 100%
TAP-112077_HAPPYJAWS | 31 | 28 |  | 01.04.01.04.00.00.00.00 | TAP-112077 | TAP-116520 | [TAP-112077_HAPPYJAWS] ¦ [IRR][Articulation/Actuation] Setup Tracking Fixture in NoHa | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-103448 | 32 | 284 |  | 01.05.01.00.00.00.00.00 |  | TAP-103448 | [TAP-103448] ¦ [Newton] Reliability and Instrument Tool Consolidation | Feature | Accepted |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-103448_I2E | 33 | 32 |  | 01.05.01.01.00.00.00.00 | TAP-103448 | TAP-99022 | [TAP-103448_I2E] ¦ [v3.1][IRR][IDU CMD][I2E] Add Shears functionality to M-IRR's tool within Discrete Control Command | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 67 | 23 | 5 | 6 | 0 | 100%
TAP-95983 | 34 | 284 |  | 01.05.03.00.00.00.00.00 |  | TAP-95983 | [TAP-95983] ¦ [IRR][Enabler] Develop Framework for Wristed Control Testing | Feature | Accepted |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-95983_HAPPYJAWS | 35 | 34 |  | 01.05.03.01.00.00.00.00 | TAP-95983 | TAP-88491 | [TAP-95983_HAPPYJAWS] ¦ [IRR][PlantSim][Happy Jaws] Introduce IDU Standalones to Modeling Team | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-95983_SIRIUS | 36 | 34 |  | 01.05.03.02.00.00.00.00 | TAP-95983 | TAP-87610 | [TAP-95983_SIRIUS] ¦ [IRR][PlantSim][Sirius] Setup VM with Docker and git on Server in Mounds View | User Story | In progress | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 4 | 0 | 4 | 4.8 | 4 | 0%
TAP-95983_SIRIUS | 37 | 34 |  | 01.05.03.03.00.00.00.00 | TAP-95983 | TAP-111914 | [TAP-95983_SIRIUS] ¦ [IRR][PlantSim][Sirius] Setup VM with Docker and git on Server in Mounds View | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-95983_ANIMATORS | 38 | 34 |  | 01.05.03.07.00.00.00.00 | TAP-95983 | TAP-115103 | [TAP-95983_ANIMATORS] ¦ [IRR][PlantModels] Wristed Instrument Model Credibility and Risk Assessment (Validation) | User Story | Open | Shared Services - Animators | ANIMATORS | Child Task | User Stories | 30 | 20 | 0 | 0 | 0 | 0%
TAP-95983_ANIMATORS | 39 | 34 |  | 01.05.03.12.00.00.00.00 | TAP-95983 | TAP-111789 | [TAP-95983_ANIMATORS] ¦ [IRR][PlantModels] Wristed Instrument Model Credibility and Risk Assessment (Validation) | Feature Estimation | Open | Foundation - Fred | FRED | Child Task | User Stories | 1 | 0 | 0 | 0 | 0 | 0%
TAP-95983_PUPPETEERS | 40 | 34 |  | 01.05.03.13.00.00.00.00 | TAP-95983 | TAP-116408 | [TAP-95983_PUPPETEERS] ¦ [IRR][Puppeteers] Support for framework for wristed testing | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 116 | 51 | 13 | 15.6 | 13 | 0%
TAP-124116 | 41 | 43 |  | 01.05.04.00.00.00.00.00 |  | TAP-124116 | [TAP-124116] ¦ [IRR][Enabler] Setup of EtherCAT DAQ module for Synchronized Data Acquisition | Feature | Accepted |  |  | Parent Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-124116_FRED | 42 | 41 |  | 01.05.04.01.00.00.00.00 | TAP-124116 | TAP-124075 | [TAP-124116_FRED] ¦ [IRR][Fred][Spike] Investigate Ethercat Slave Issues with Galil | User Story | Open | Foundation - Fred | FRED | Child Task | User Stories | 13 | 0 | 13 | 15.6 | 13 | 0%
TAP-111719 | 43 | 284 | 41 | 01.05.05.00.00.00.00.00 |  | TAP-111719 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature | Accepted |  |  | Parent Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-111719 | 44 | 43 |  | 01.05.05.02.00.00.00.00 | TAP-111719 | TAP-112040 | [TAP-111719] ¦ [IRR][Enabler] EtherCAT interface module for real-time I/O on IDU fixture | Feature Estimation | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 0 | 0 | 14 | 20 | 0 | 100%
TAP-111721 | 45 | 284 |  | 01.05.06.00.00.00.00.00 |  | TAP-111721 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-111721 | 46 | 45 |  | 01.05.06.01.00.00.00.00 | TAP-111721 | TAP-111917 | [TAP-111721] ¦ [IRR][Enabler] Summer 2024 IRR Lab Support | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111721_SIRIUS | 47 | 45 |  | 01.05.06.03.00.00.00.00 | TAP-111721 | TAP-116464 | [TAP-111721_SIRIUS] ¦ [IRR][ORSI] Decide on parameters to derate with clinical | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 0.5 | 0.5 | 0.5 | 0.6 | 0 | 100%
TAP-111721_HAPPYJAWS | 48 | 45 |  | 01.05.06.08.00.00.00.00 | TAP-111721 | TAP-122340 | [TAP-111721_HAPPYJAWS] ¦ [IRR] Update Lab SW with Protection Against Slow Close | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-111721_PUPPETEERS | 49 | 45 |  | 01.05.06.11.00.00.00.00 | TAP-111721 | TAP-123066 | [TAP-111721_PUPPETEERS] ¦ [IRR][Puppeteers] Merge latest JBO updates to IRR staging branch for ORSI lab | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-111723 | 50 | 284 |  | 01.05.07.00.00.00.00.00 |  | TAP-111723 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature | PROPOSED |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-111723 | 51 | 50 |  | 01.05.07.01.00.00.00.00 | TAP-111723 | TAP-111919 | [TAP-111723] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI16) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 27 | 30 | 0 | 100%
TAP-111723_SIRIUS | 52 | 50 |  | 01.05.07.02.00.00.00.00 | TAP-111723 | TAP-115880 | [TAP-111723_SIRIUS] ¦ [IRR][ORSI] Update Lab SW for Hard Stop recovery | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-129482 | 53 |  |  | 01.05.08.00.00.00.00.00 |  | TAP-129482 | [TAP-129482] ¦ [IRR] P1 HW Integration Testing | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-123914 | 54 | 284 |  | 01.05.09.00.00.00.00.00 |  | TAP-123914 | [TAP-123914] ¦ [IRR] Create standardized test tools for data collection and analysis | Feature | Accepted |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-123914_SIRIUS | 55 | 54 |  | 01.05.09.01.00.00.00.00 | TAP-123914 | TAP-116494 | [TAP-123914_SIRIUS] ¦ [Playback] [Sirius] Create script for running playback simulation | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-123914_HAPPYJAWS | 56 | 54 |  | 01.05.09.02.00.00.00.00 | TAP-123914 | TAP-116491 | [TAP-123914_HAPPYJAWS] ¦ [Playback][Happy Jaws] Extend the useability of playback simulation to log data which excludes calibration | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 6 | 0 | 6 | 7.2 | 6 | 0%
TAP-94125 | 57 | 187,284 |  | 01.06.01.00.00.00.00.00 |  | TAP-94125 | [TAP-94125] ¦ [IRR][Phase 1b] First Phase SW Development for Calibration and Homing | Feature | PROPOSED |  |  | Parent Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 0%
TAP-94125_SIRIUS | 58 | 57 |  | 01.06.01.01.00.00.00.00 | TAP-94125 | TAP-97747 | [TAP-94125_SIRIUS] ¦ [WS5][Homing][Sirius] Evaluate Homing Controller Architecture and Identify Improvements | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 5 | 0 | 5 | 6 | 5 | 0%
TAP-94125_SIRIUS | 59 | 57 |  | 01.06.01.14.00.00.00.00 | TAP-94125 | TAP-111778 | [TAP-94125_SIRIUS] ¦ [WS5][Homing][Sirius] Evaluate Homing Controller Architecture and Identify Improvements | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-95800 | 60 | 189,284 |  | 01.06.02.00.00.00.00.00 |  | TAP-95800 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature | In progress |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-95800 | 61 | 60 |  | 01.06.02.02.00.00.00.00 | TAP-95800 | TAP-111779 | [TAP-95800] ¦ [IRR][Phase 1b] First Phase SW Development of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-95800_HAPPYJAWS | 62 | 60 |  | 01.06.02.03.00.00.00.00 | TAP-95800 | TAP-116475 | [TAP-95800_HAPPYJAWS] ¦ [IRR][Phase 1b][Motor Controller] Informal design review | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-95800_SIRIUS | 63 | 60 |  | 01.06.02.04.00.00.00.00 | TAP-95800 | TAP-116476 | [TAP-95800_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller][Sirius] Decide on testing strategy and unit breakdown | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-95800_I2E | 64 | 60 |  | 01.06.02.21.00.00.00.00 | TAP-95800 | TAP-130566 | [TAP-95800_I2E] ¦ [IRR][I2E][IDU CMD] IRR Improvements to Discrete Control - J6 Commands | User Story | Open | Advanced Instruments - I2E | I2E | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-111740 | 65 | 192,284 |  | 01.06.03.00.00.00.00.00 |  | TAP-111740 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature | In progress |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-111740 | 66 | 65 |  | 01.06.03.01.00.00.00.00 | TAP-111740 | TAP-111950 | [TAP-111740] ¦ [IRR][Phase 1b] First Phase SW Development of Joint Trajectory Manager + Joint Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111740_HAPPYJAWS | 67 | 65 |  | 01.06.03.02.00.00.00.00 | TAP-111740 | TAP-115106 | [TAP-111740_HAPPYJAWS] ¦ [IRR][Phase 1b][Happy Jaws] Refactor teleoperation SWI to consolidate IK and improve architecture | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-111740_SIRIUS | 68 | 65 |  | 01.06.03.04.00.00.00.00 | TAP-111740 | TAP-116484 | [TAP-111740_SIRIUS] ¦ [IRR][Phase 1b][Joint Controller] Decide on testing strategy and unit breakdown | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-111749 | 69 | 196,284 |  | 01.06.04.00.00.00.00.00 |  | TAP-111749 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-111749 | 70 | 69 |  | 01.06.04.01.00.00.00.00 | TAP-111749 | TAP-111951 | [TAP-111749] ¦ [IRR][Phase 1b] First Phase SW Development of Output-side SWI's for IRR Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 16 | 30 | 0 | 100%
TAP-111749_SIRIUS | 71 | 69 |  | 01.06.04.02.00.00.00.00 | TAP-111749 | TAP-112328 | [TAP-111749_SIRIUS] ¦ [IRR] Evaluate risk rank of alternate instrument hardware failure modes | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111750 | 72 | 198,284 |  | 01.06.05.00.00.00.00.00 |  | TAP-111750 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111750 | 73 | 72 |  | 01.06.05.01.00.00.00.00 | TAP-111750 | TAP-111952 | [TAP-111750] ¦ [IRR][Phase 1b] First Phase SW Development of Wristed Instrument state machine | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 35 | 0 | 100%
TAP-111751 | 74 | 200,284 |  | 01.06.06.00.00.00.00.00 |  | TAP-111751 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111751 | 75 | 74 |  | 01.06.06.01.00.00.00.00 | TAP-111751 | TAP-111953 | [TAP-111751] ¦ [IRR][Phase 1b] First Phase SW Development of Input-Side SWI's for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 28 | 45 | 0 | 100%
TAP-117678 | 76 | 284 |  | 01.06.07.00.00.00.00.00 |  | TAP-117678 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-117678 | 77 | 76 |  | 01.06.07.01.00.00.00.00 | TAP-117678 | TAP-127786 | [TAP-117678] ¦ [IRR][Phase 1b] First Phase SW Development for Overall IDUSW Updates | Feature Estimation | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 0 | 0 | 20 | 35 | 0 | 0%
TAP-130796 | 78 |  |  | 01.06.08.00.00.00.00.00 |  | TAP-130796 | [TAP-130796] ¦ [IRR][Phase 1b] Test Cleanup for IRR Controller Release | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-130796_HAPPYJAWS | 79 | 78 |  | 01.06.08.01.00.00.00.00 | TAP-130796 | TAP-129700 | [TAP-130796_HAPPYJAWS] ¦ [Happy Jaws][SWIV] Investigate cause of MIL EIN-TC_SW-3723 hanging | User Story | Done | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 5 | 5 | 0 | 0 | 0 | 100%
TAP-130796_SIRIUS | 80 | 78 |  | 01.06.08.02.00.00.00.00 | TAP-130796 | TAP-129697 | [TAP-130796_SIRIUS] ¦ [Sirius][SWIV] Update EIN-TC_SW-2535 to reduce runtime | User Story | In progress | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 6 | 0 | 0 | 0 | 6 | 0%
TAP-111834 | 81 | 284 |  | 01.07.01.00.00.00.00.00 |  | TAP-111834 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature | In progress |  |  | Parent Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 0%
TAP-111834 | 82 | 81 |  | 01.07.01.01.00.00.00.00 | TAP-111834 | TAP-112842 | [TAP-111834] ¦ [IRR] Support Kinematic/HW Updates for IRR Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 85 | 56 | 0 | 0 | 0 | 100%
TAP-111834_PUPPETEERS | 83 | 81 |  | 01.07.01.02.00.00.00.00 | TAP-111834 | TAP-125837 | [TAP-111834_PUPPETEERS] ¦ [IRR][Puppeteers] Update Kinematics to Support IRR Instrument Parameters | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 13 | 0 | 13 | 15.6 | 13 | 0%
TAP-111834_CASTLEBLACK | 84 | 81 |  | 01.07.01.06.00.00.00.00 | TAP-111834 | TAP-126232 | [TAP-111834_CASTLEBLACK] ¦ [Architecture][IRR] Update Instrument Kinematic Data Interface | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-111834_HAPPYJAWS | 85 | 81 |  | 01.07.01.09.00.00.00.00 | TAP-111834 | TAP-126522 | [TAP-111834_HAPPYJAWS] ¦ [IRR][Kinematics][Happy Jaws] Update instrument kinematics matrix to accomodate new twisted yoke in MCS and update pulley radius | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-111834_SIRIUS | 86 | 81 |  | 01.07.01.10.00.00.00.00 | TAP-111834 | TAP-126523 | [TAP-111834_SIRIUS] ¦ [IRR][Kinematics] Work with Lupine to update camera algorithm for new twisted shears | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-125255 | 87 | 284 |  | 01.08.00.00.00.00.00.00 |  | TAP-125255 | [TAP-125255] ¦ [IRR] Update/Automate Data Recorder V&V for IRR Interface Changes | Feature | Accepted |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-125255_BOOSTERS | 88 | 87 |  | 01.08.01.00.00.00.00.00 | TAP-125255 | TAP-124574 | [TAP-125255_BOOSTERS] ¦ [IRR][Boosters] Run data recorder auto gen script with new interfaces | User Story | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 12 | 6 | 3 | 3.6 | 0 | 100%
TAP-123834 | 89 | 284 |  | 01.09.00.00.00.00.00.00 |  | TAP-123834 | [TAP-123834] ¦ [IRR] Migrate IRR SW to Post-Cyber Branch | Feature | In progress |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-123834_PUPPETEERS | 90 | 89 |  | 01.09.02.00.00.00.00.00 | TAP-123834 | TAP-125551 | [TAP-123834_PUPPETEERS] ¦ [IRR][Puppeteers] Migrate code for JBO SW to Post-Cyber Branch | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 5 | 0 | 5 | 6 | 5 | 0%
TAP-123834_SIRIUS | 91 | 89 |  | 01.09.07.00.00.00.00.00 | TAP-123834 | TAP-126497 | [TAP-123834_SIRIUS] ¦ [IRR] Migrate Baseline Controller to IRR V4 Branch | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-111724 | 92 | 288 |  | 02.01.00.00.00.00.00.00 |  | TAP-111724 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-111724 | 93 | 92 |  | 02.01.01.00.00.00.00.00 | TAP-111724 | TAP-111920 | [TAP-111724] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI17) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 27 | 30 | 0 | 100%
TAP-112119 | 94 | 284 |  | 02.03.01.00.00.00.00.00 |  | TAP-112119 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112119 | 95 | 94 |  | 02.03.01.01.00.00.00.00 | TAP-112119 | TAP-112120 | [TAP-112119] ¦ [IRR] Final Regression of performance with Finalized HW (Phase 2a) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 20 | 0 | 100%
TAP-111747 | 96 | 288 |  | 02.04.01.00.00.00.00.00 |  | TAP-111747 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111747 | 97 | 96 |  | 02.04.01.01.00.00.00.00 | TAP-111747 | TAP-111913 | [TAP-111747] ¦ [IRR] Algorithm Development and Risk Analysis of Detachment Detection for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 50 | 100 | 0 | 100%
TAP-131594 | 98 |  |  | 02.04.02.00.00.00.00.00 |  | TAP-131594 | [TAP-131594] ¦ [IRR] Algorithm Development of Torque Loss Check | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111772 | 99 | 288 |  | 02.05.01.00.00.00.00.00 |  | TAP-111772 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111772 | 100 | 99 |  | 02.05.01.01.00.00.00.00 | TAP-111772 | TAP-111965 | [TAP-111772] ¦ [IRR] Algorithm Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 20 | 0 | 100%
TAP-111773 | 101 | 288 |  | 02.05.02.00.00.00.00.00 |  | TAP-111773 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111773 | 102 | 101 |  | 02.05.02.01.00.00.00.00 | TAP-111773 | TAP-111966 | [TAP-111773] ¦ [IRR] SW + Test Development for Broken Instrument Detection during Calibration | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 100%
TAP-111838 | 103 | 107,288 |  | 02.06.01.00.00.00.00.00 |  | TAP-111838 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111838 | 104 | 103 |  | 02.06.01.01.00.00.00.00 | TAP-111838 | TAP-111967 | [TAP-111838] ¦ [IRR] Investigate HALT Prevention and Recovery for IDU Errors | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-104213 | 105 | 107,288 |  | 02.06.02.00.00.00.00.00 |  | TAP-104213 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature | In progress |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-104213 | 106 | 105 |  | 02.06.02.01.00.00.00.00 | TAP-104213 | TAP-111968 | [TAP-104213] ¦ [IRR] Easy Exchange Prototyping for Quick Recovery | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 45 | 0 | 100%
TAP-111842 | 107 | 288 | 105,103 | 02.06.03.00.00.00.00.00 |  | TAP-111842 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111842 | 108 | 107 |  | 02.06.03.01.00.00.00.00 | TAP-111842 | TAP-111969 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 100%
TAP-111842 | 109 | 107 |  | 02.06.03.02.00.00.00.00 | TAP-111842 | TAP-127787 | [TAP-111842] ¦ [IRR] SW Development of HALT Recovery/Prevention | Feature Estimation | Open | Advanced Instruments - Remus | REMUS | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 0%
TAP-111774 | 110 | 121,115,288 |  | 02.07.01.00.00.00.00.00 |  | TAP-111774 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-111774 | 111 | 110 |  | 02.07.01.01.00.00.00.00 | TAP-111774 | TAP-111970 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111774 | 112 | 110 |  | 02.07.01.02.00.00.00.00 | TAP-111774 | TAP-112183 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 100%
TAP-111774 | 113 | 110 |  | 02.07.01.03.00.00.00.00 | TAP-111774 | TAP-112184 | [TAP-111774] ¦ [IRR][Advanced] Analysis of Need for MSO Joint Tracking Check | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111774_PUPPETEERS | 114 | 110 |  | 02.07.01.04.00.00.00.00 | TAP-111774 | TAP-116202 | [TAP-111774_PUPPETEERS] ¦ [IRR][Puppeteers] Create cFMEA draft in Excel Sheet for MSO Joint Tracking Check | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-112080 | 115 | 121,288 | 110 | 02.07.02.00.00.00.00.00 |  | TAP-112080 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-112080 | 116 | 115 |  | 02.07.02.01.00.00.00.00 | TAP-112080 | TAP-112081 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 13 | 22 | 0 | 100%
TAP-112080 | 117 | 115 |  | 02.07.02.02.00.00.00.00 | TAP-112080 | TAP-112185 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-112080 | 118 | 115 |  | 02.07.02.03.00.00.00.00 | TAP-112080 | TAP-112186 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 4 | 6 | 0 | 100%
TAP-112080 | 119 | 115 |  | 02.07.02.04.00.00.00.00 | TAP-112080 | TAP-112187 | [TAP-112080] ¦ [IRR] Prototype Removal/Replacement of MSO Joint Tracking Check | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 0 | 0 | 10 | 20 | 0 | 100%
TAP-112080_PUPPETEERS | 120 | 115 |  | 02.07.02.05.00.00.00.00 | TAP-112080 | TAP-116414 | [TAP-112080_PUPPETEERS] ¦ [IRR][Puppeteers] Kinematics prototype for MSO joint check replacement | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 13 | 0 | 0 | 0 | 13 | 0%
TAP-111775 | 121 | 288 | 110,115 | 02.07.03.00.00.00.00.00 |  | TAP-111775 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-111775 | 122 | 121 |  | 02.07.03.01.00.00.00.00 | TAP-111775 | TAP-111971 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 16 | 24 | 0 | 100%
TAP-111775 | 123 | 121 |  | 02.07.03.02.00.00.00.00 | TAP-111775 | TAP-112188 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 0 | 0 | 15 | 25 | 0 | 100%
TAP-111775 | 124 | 121 |  | 02.07.03.03.00.00.00.00 | TAP-111775 | TAP-112189 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 4 | 6 | 0 | 100%
TAP-111775 | 125 | 121 |  | 02.07.03.04.00.00.00.00 | TAP-111775 | TAP-112190 | [TAP-111775] ¦ [IRR] Development of Replacement Joint Tracking Check for IRR | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 0 | 0 | 10 | 20 | 0 | 100%
TAP-111775_PUPPETEERS | 126 | 121 |  | 02.07.03.05.00.00.00.00 | TAP-111775 | TAP-121472 | [TAP-111775_PUPPETEERS] ¦ [IRR][Puppeteers] Update Polarion | User Story | Open | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 1 | 0 | 0 | 0 | 1 | 0%
TAP-123862 | 127 | 288 |  | 02.08.01.00.00.00.00.00 |  | TAP-123862 | [TAP-123862] ¦ [IRR] Prototype Updated Wristed Programming for M-IRR Instrument Variants and Expiration | Feature | Accepted |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-123862_I2E | 128 | 127 |  | 02.08.01.01.00.00.00.00 | TAP-123862 | TAP-124413 | [TAP-123862_I2E] ¦ [I2E][IRR][Enabler] Determine instrument memory mapping for DSV 2 | User Story | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 3 | 3 | 3 | 3.6 | 0 | 100%
TAP-123862_ZENITH | 129 | 127 |  | 02.08.01.11.00.00.00.00 | TAP-123862 | TAP-126037 | [TAP-123862_ZENITH] ¦ [Zenith] Sync-up to prevent/addess merge conflicts 1 | User Story | Open | Advanced Instruments - Zenith | ZENITH | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-123862_CASTLEBLACK | 130 | 127 |  | 02.08.01.12.00.00.00.00 | TAP-123862 | TAP-126145 | [TAP-123862_CASTLEBLACK] ¦ [Architecture][IRR] Memory Map Architecture | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-123863 | 131 | 288 |  | 02.08.02.00.00.00.00.00 |  | TAP-123863 | [TAP-123863] ¦ [IRR] Instr Ctr Variant Selection Architecture Design With Data Consolidation | Feature | Accepted |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-123863_I2E | 132 | 131 |  | 02.08.02.02.00.00.00.00 | TAP-123863 | TAP-124578 | [TAP-123863_I2E] ¦ [IRR][I2E][SRA HAL] Mapping of instrument id + DSV to controller version json: Implementation & Unit Test | User Story | In progress | Advanced Instruments - I2E | I2E | Child Task | User Stories | 8 | 0 | 8 | 9.6 | 8 | 0%
TAP-123863_CASTLEBLACK | 133 | 131 |  | 02.08.02.14.00.00.00.00 | TAP-123863 | TAP-126023 | [TAP-123863_CASTLEBLACK] ¦ [Architecture] Instrument Data Interfaces for MIRR | User Story | In progress | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-123863_ZENITH | 134 | 131 |  | 02.08.02.15.00.00.00.00 | TAP-123863 | TAP-126042 | [TAP-123863_ZENITH] ¦ [Zenith] Sync-up to prevent/address merge conflicts 2 | User Story | Open | Advanced Instruments - Zenith | ZENITH | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-111642 | 135 | 288 |  | 02.08.03.00.00.00.00.00 |  | TAP-111642 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature | PROPOSED |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-111642 | 136 | 135 |  | 02.08.03.01.00.00.00.00 | TAP-111642 | TAP-111941 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111642 | 137 | 135 |  | 02.08.03.02.00.00.00.00 | TAP-111642 | TAP-111942 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 100%
TAP-111642 | 138 | 135 |  | 02.08.03.03.00.00.00.00 | TAP-111642 | TAP-111943 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 3 | 5 | 0 | 100%
TAP-111642 | 139 | 135 |  | 02.08.03.04.00.00.00.00 | TAP-111642 | TAP-111944 | [TAP-111642] ¦ [IRR] Controller Versioning: Solution Concept and Prototype | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111656 | 140 | 288 |  | 02.08.04.00.00.00.00.00 |  | TAP-111656 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111656 | 141 | 140 |  | 02.08.04.01.00.00.00.00 | TAP-111656 | TAP-111933 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Classy 2 | CLASSY2 | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111656 | 142 | 140 |  | 02.08.04.02.00.00.00.00 | TAP-111656 | TAP-111935 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111656 | 143 | 140 |  | 02.08.04.03.00.00.00.00 | TAP-111656 | TAP-111936 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 100%
TAP-111656 | 144 | 140 |  | 02.08.04.04.00.00.00.00 | TAP-111656 | TAP-111937 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Open | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111656 | 145 | 140 |  | 02.08.04.05.00.00.00.00 | TAP-111656 | TAP-111938 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 5 | 10 | 0 | 100%
TAP-111656 | 146 | 140 |  | 02.08.04.06.00.00.00.00 | TAP-111656 | TAP-111939 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 100%
TAP-111656 | 147 | 140 |  | 02.08.04.07.00.00.00.00 | TAP-111656 | TAP-111940 | [TAP-111656] ¦ [IRR] Controller Versioning: Productization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 5 | 15 | 0 | 100%
TAP-130665 | 148 |  |  | 02.08.05.00.00.00.00.00 |  | TAP-130665 | [TAP-130665] ¦ [IRR] Non-controller Variant Management in Bedside Configuration Manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111925 | 149 | 288 |  | 02.09.01.00.00.00.00.00 |  | TAP-111925 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111925 | 150 | 149 |  | 02.09.01.01.00.00.00.00 | TAP-111925 | TAP-111945 | [TAP-111925] ¦ [IRR] Simulation for Verification Regression on Particular Instruments | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 30 | 0 | 100%
TAP-113111 | 151 | 176,181 |  | 02.10.01.01.00.00.00.00 |  | TAP-113111 | [TAP-113111] ¦ [IRR][Spike] Plan Interfaces and Architecture for Instrument Usage Table | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113111_PUPPETEERS | 152 | 151 |  | 02.10.01.01.01.00.00.00 | TAP-113111 | TAP-125828 | [TAP-113111_PUPPETEERS] ¦ [IRR][Puppeteers][SPIKE] Investigate SRA Updates to Support Usage Tables | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-113123 | 153 | 171,176,181 |  | 02.10.01.02.00.00.00.00 |  | TAP-113123 | [TAP-113123] ¦ [IRR][Spike][Advanced] Plan Interfaces, Architecture, GUI Layout for Instrument Usage Table | Feature | Accepted |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-113123_PIXELPOETS | 154 | 153 |  | 02.10.01.02.01.00.00.00 | TAP-113123 | TAP-124572 | [TAP-113123_PIXELPOETS] ¦ [Pixel Poets][MIRR] Determine DDS Strategy with UFSW/Architecture | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 16 | 15 | 3 | 3.6 | 0 | 100%
TAP-114692 | 155 |  |  | 02.10.01.03.00.00.00.00 |  | TAP-114692 | [TAP-114692] ¦ [IRR][Spike] Prototype Use Life Messaging and Countdown Interfaces | Feature | Done |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-114692_CASTLEBLACK | 156 | 155 |  | 02.10.01.03.01.00.00.00 | TAP-114692 | TAP-116170 | [TAP-114692_CASTLEBLACK] ¦ [Architecture] Display remaining Instrument Use-Life | User Story | Done | Shared Services - Castle Black | CASTLEBLACK | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-114692_PUPPETEERS | 157 | 155 |  | 02.10.01.03.02.00.00.00 | TAP-114692 | TAP-116199 | [TAP-114692_PUPPETEERS] ¦ [IRR][Puppeteers] Sree session | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-114692_SIRIUS | 158 | 155 |  | 02.10.01.03.07.00.00.00 | TAP-114692 | TAP-123143 | [TAP-114692_SIRIUS] ¦ [IRR][Sirius] Manually update use life notcodes for staging/IRR-v3-control-development | User Story | Done | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 2 | 2 | 2 | 2.4 | 0 | 100%
TAP-114689 | 159 | 171 |  | 02.10.01.04.00.00.00.00 |  | TAP-114689 | [TAP-114689] ¦ [IRR][Spike] Prototype Use Life Count-Down Display | Feature | Done |  |  | Parent Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-114689_PIXELPOETS | 160 | 159 |  | 02.10.01.04.01.00.00.00 | TAP-114689 | TAP-115102 | [TAP-114689_PIXELPOETS] ¦ [MIRR][Pixel Poets] Finalize Design for Use Life Indicator | User Story | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 1 | 1 | 1 | 1.2 | 0 | 100%
TAP-130664 | 161 |  |  | 02.10.01.05.00.00.00.00 |  | TAP-130664 | [TAP-130664] ¦ [IRR][Spike] Prototype Use Life Summary Screens | Feature | PROPOSED |  |  | Parent Task | User Stories | 1 | 1 | 1 hr | 1 hr | 0 | 100%
TAP-90375 | 162 | 288 |  | 02.10.02.01.00.00.00.00 |  | TAP-90375 | [TAP-90375] ¦ (CAPA2023-019111) Disabled Instrument Workflow Messaging Updates | Feature | Groomed |  |  | Parent Task | User Stories | 1 | 1 | 1 hr | 1 hr | 0 | 100%
TAP-90375_STELLARS | 163 | 162 |  | 02.10.02.01.01.00.00.00 | TAP-90375 | TAP-96606 | [TAP-90375_STELLARS] ¦ [Stellars] [TAP-90375] [Enabler] Identify Jama linking to be updated | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 103 | 32 | 1 | 1.2 | 1 | 0%
TAP-111861 | 164 | 288 |  | 02.10.02.02.00.00.00.00 |  | TAP-111861 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-111861 | 165 | 164 |  | 02.10.02.02.01.00.00.00 | TAP-111861 | TAP-112869 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 0 | 0 | 12 | 18 | 0 | 100%
TAP-111861 | 166 | 164 |  | 02.10.02.02.02.00.00.00 | TAP-111861 | TAP-112870 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 15 | 20 | 0 | 100%
TAP-111861 | 167 | 164 |  | 02.10.02.02.03.00.00.00 | TAP-111861 | TAP-112871 | [TAP-111861] ¦ [IRR] Update Expiration Calculations and Notifications for Wristed Instruments | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 0 | 0 | 7 | 8 | 0 | 100%
TAP-111861_PUPPETEERS | 168 | 164 |  | 02.10.02.02.04.00.00.00 | TAP-111861 | TAP-125548 | [TAP-111861_PUPPETEERS] ¦ [IRR][Puppeteers] Migrate Code for Use Life SW to Post-Cyber Branch | User Story | Done | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 5 | 5 | 0 | 0 | 0 | 100%
TAP-128527 | 169 |  |  | 02.10.02.03.00.00.00.00 |  | TAP-128527 | [TAP-128527] ¦ [IRR] Update ACAD to No Longer Show Percentages | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-128530 | 170 |  |  | 02.10.02.04.00.00.00.00 |  | TAP-128530 | [TAP-128530] ¦ [IRR] Update GUI SW to show message text on full ACAD | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-111687 | 171 | 288 | 153,159 | 02.10.02.05.00.00.00.00 |  | TAP-111687 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-111687 | 172 | 171 |  | 02.10.02.05.01.00.00.00 | TAP-111687 | TAP-111903 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 0 | 0 | 20 | 34 | 0 | 100%
TAP-111687 | 173 | 171 |  | 02.10.02.05.02.00.00.00 | TAP-111687 | TAP-112872 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 8 | 12 | 0 | 100%
TAP-111687 | 174 | 171 |  | 02.10.02.05.03.00.00.00 | TAP-111687 | TAP-112873 | [TAP-111687] ¦ [IRR] Instrument Use Life Count-Down Display | Feature Estimation | Open | Foundation - Fred | FRED | Child Task | User Stories | 0 | 0 | 5 | 15 | 0 | 0%
TAP-111687_PUPPETEERS | 175 | 171 |  | 02.10.02.05.04.00.00.00 | TAP-111687 | TAP-115871 | [TAP-111687_PUPPETEERS] ¦ [IRR][Puppeteers] Increment Use count when instrument is expired | User Story | Groomed | Core Instruments - Puppeteers | PUPPETEERS | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-111689 | 176 | 288 | 151,153 | 02.10.02.06.00.00.00.00 |  | TAP-111689 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-111689 | 177 | 176 |  | 02.10.02.06.01.00.00.00 | TAP-111689 | TAP-111904 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 0 | 0 | 17 | 28 | 0 | 100%
TAP-111689 | 178 | 176 |  | 02.10.02.06.02.00.00.00 | TAP-111689 | TAP-112874 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 15 | 20 | 0 | 100%
TAP-111689 | 179 | 176 |  | 02.10.02.06.03.00.00.00 | TAP-111689 | TAP-112875 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 0 | 0 | 7 | 8 | 0 | 100%
TAP-111689 | 180 | 176 |  | 02.10.02.06.04.00.00.00 | TAP-111689 | TAP-127789 | [TAP-111689] ¦ [IRR] End of Procedure Instrument Usage Splash Screen | Feature Estimation | Open | Foundation - Boosters | BOOSTERS | Child Task | User Stories | 0 | 0 | 15 | 45 | 0 | 0%
TAP-111695 | 181 | 288 | 151,153 | 02.10.02.07.00.00.00.00 |  | TAP-111695 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111695 | 182 | 181 |  | 02.10.02.07.01.00.00.00 | TAP-111695 | TAP-111905 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 0 | 0 | 11 | 26 | 0 | 100%
TAP-111695 | 183 | 181 |  | 02.10.02.07.02.00.00.00 | TAP-111695 | TAP-112876 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 30 | 50 | 0 | 100%
TAP-111695 | 184 | 181 |  | 02.10.02.07.03.00.00.00 | TAP-111695 | TAP-112877 | [TAP-111695] ¦ [IRR] Mid-Procedure Instrument Usage Splash Screen | Feature Estimation | Done | Released Product Engineering - Drushti | DRUSHTI | Child Task | User Stories | 0 | 0 | 7 | 8 | 0 | 100%
TAP-130765 | 185 |  |  | 02.10.02.08.00.00.00.00 |  | TAP-130765 | [TAP-130765] ¦ [IRR] 4.2 Translation Tool Updates | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-130765_HAPPYJAWS | 186 | 185 |  | 02.12.00.00.00.00.00.00 |  | TAP-131923 | [TAP-130765_HAPPYJAWS] ¦ Update IRR Architecture Markdown for Project Summary | User Story | In progress | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111753 | 187 | 202,292 | 57 | 03.01.01.00.00.00.00.00 |  | TAP-111753 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111753 | 188 | 187 |  | 03.01.01.01.00.00.00.00 | TAP-111753 | TAP-111954 | [TAP-111753] ¦ [IRR] Requirements and SW Verification of IRR Homing Manager | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 30 | 50 | 0 | 100%
TAP-111754 | 189 | 204,292 | 60 | 03.01.02.00.00.00.00.00 |  | TAP-111754 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111754 | 190 | 189 |  | 03.01.02.01.00.00.00.00 | TAP-111754 | TAP-111955 | [TAP-111754] ¦ [IRR] Requirements and SW Verification of IRR Motor Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111754_SIRIUS | 191 | 189 |  | 03.01.02.02.00.00.00.00 | TAP-111754 | TAP-116481 | [TAP-111754_SIRIUS] ¦ [IRR][Phase 1b][Motor Controller] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-111756 | 192 | 206,292 | 65 | 03.01.03.00.00.00.00.00 |  | TAP-111756 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-111756 | 193 | 192 |  | 03.01.03.01.00.00.00.00 | TAP-111756 | TAP-111956 | [TAP-111756] ¦ [IRR] Requirements and SW Verification of IRR Teleoperation Controller | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 35 | 45 | 0 | 100%
TAP-111756_HAPPYJAWS | 194 | 192 |  | 03.01.03.02.00.00.00.00 | TAP-111756 | TAP-116489 | [TAP-111756_HAPPYJAWS] ¦ [IRR][Phase 1b][Teleoperation] Create RCMs found in cFMEA | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-111756_SIRIUS | 195 | 192 |  | 03.01.03.03.00.00.00.00 | TAP-111756 | TAP-131009 | [TAP-111756_SIRIUS] ¦ [SWIV] Update test analysis for EIN-TC_SW-2563 | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-111757 | 196 | 208,292 | 69 | 03.01.04.00.00.00.00.00 |  | TAP-111757 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-111757 | 197 | 196 |  | 03.01.04.01.00.00.00.00 | TAP-111757 | TAP-111957 | [TAP-111757] ¦ [IRR] Requirements and SW Verification of IRR Monitor SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 16 | 30 | 0 | 100%
TAP-111758 | 198 | 210,292 | 72 | 03.01.05.00.00.00.00.00 |  | TAP-111758 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111758 | 199 | 198 |  | 03.01.05.01.00.00.00.00 | TAP-111758 | TAP-111958 | [TAP-111758] ¦ [IRR] Requirements and SW Verification of IRR Procedure Manager SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 30 | 0 | 100%
TAP-111759 | 200 | 212,292 | 74 | 03.01.06.00.00.00.00.00 |  | TAP-111759 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111759 | 201 | 200 |  | 03.01.06.01.00.00.00.00 | TAP-111759 | TAP-111959 | [TAP-111759] ¦ [IRR] Requirements and SW Verification of IRR Estimator SWI | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 100%
TAP-111761 | 202 | 292 | 187 | 03.02.01.00.00.00.00.00 |  | TAP-111761 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111761 | 203 | 202 |  | 03.02.01.01.00.00.00.00 | TAP-111761 | TAP-111961 | [TAP-111761] ¦ [IRR] Product SW Development Homing Manager Sub-SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 25 | 30 | 0 | 100%
TAP-110382 | 204 | 292 | 189 | 03.02.02.00.00.00.00.00 |  | TAP-110382 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-110382 | 205 | 204 |  | 03.02.02.01.00.00.00.00 | TAP-110382 | TAP-111780 | [TAP-110382] ¦ [IRR] Product SW Development Motor Controller Compatible with WS5 Structure | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 5 | 8 | 0 | 100%
TAP-111762 | 206 | 292 | 192 | 03.02.03.00.00.00.00.00 |  | TAP-111762 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111762 | 207 | 206 |  | 03.02.03.01.00.00.00.00 | TAP-111762 | TAP-111962 | [TAP-111762] ¦ [IRR] Product SW Development Teleoperation Controller for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 25 | 0 | 100%
TAP-111748 | 208 | 292 | 196 | 03.02.04.00.00.00.00.00 |  | TAP-111748 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111748 | 209 | 208 |  | 03.02.04.01.00.00.00.00 | TAP-111748 | TAP-111960 | [TAP-111748] ¦ [IRR] Product SW Development Monitor SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 8 | 15 | 0 | 100%
TAP-111764 | 210 | 292 | 198 | 03.02.05.00.00.00.00.00 |  | TAP-111764 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111764 | 211 | 210 |  | 03.02.05.01.00.00.00.00 | TAP-111764 | TAP-111963 | [TAP-111764] ¦ [IRR] Product SW Development Procedure Manager for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111766 | 212 | 292 | 200 | 03.02.06.00.00.00.00.00 |  | TAP-111766 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111766 | 213 | 212 |  | 03.02.06.01.00.00.00.00 | TAP-111766 | TAP-111964 | [TAP-111766] ¦ [IRR] Product SW Development Estimator SWI for IRR | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 20 | 0 | 100%
TAP-112082 | 214 | 292 |  | 03.03.01.00.00.00.00.00 |  | TAP-112082 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112082 | 215 | 214 |  | 03.03.01.01.00.00.00.00 | TAP-112082 | TAP-112083 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 60 | 0 | 100%
TAP-112082 | 216 | 214 |  | 03.03.01.02.00.00.00.00 | TAP-112082 | TAP-113209 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-112082 | 217 | 214 |  | 03.03.01.03.00.00.00.00 | TAP-112082 | TAP-113210 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Organelles | ORGANELLES | Child Task | User Stories | 0 | 0 | 10 | 20 | 0 | 100%
TAP-112082 | 218 | 214 |  | 03.03.01.04.00.00.00.00 | TAP-112082 | TAP-113211 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 0 | 0 | 8 | 15 | 0 | 100%
TAP-112082 | 219 | 214 |  | 03.03.01.05.00.00.00.00 | TAP-112082 | TAP-113212 | [TAP-112082] ¦ [IRR] Achieve stability for integration testing, MTBI and TBOE required for RC1 | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 0 | 0 | 7 | 15 | 0 | 100%
TAP-112093 | 220 | 292 |  | 03.03.02.00.00.00.00.00 |  | TAP-112093 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112093 | 221 | 220 |  | 03.03.02.01.00.00.00.00 | TAP-112093 | TAP-112097 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 55 | 70 | 0 | 100%
TAP-112093 | 222 | 220 |  | 03.03.02.02.00.00.00.00 | TAP-112093 | TAP-127793 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - I2E | I2E | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 0%
TAP-112093 | 223 | 220 |  | 03.03.02.03.00.00.00.00 | TAP-112093 | TAP-127794 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Remus | REMUS | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 0%
TAP-112093 | 224 | 220 |  | 03.03.02.04.00.00.00.00 | TAP-112093 | TAP-127795 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 0%
TAP-112093 | 225 | 220 |  | 03.03.02.05.00.00.00.00 | TAP-112093 | TAP-127796 | [TAP-112093] ¦ [IRR] BRR prep and finalization | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 0%
TAP-112094 | 226 | 292 |  | 03.03.03.00.00.00.00.00 |  | TAP-112094 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112094 | 227 | 226 |  | 03.03.03.01.00.00.00.00 | TAP-112094 | TAP-112096 | [TAP-112094] ¦ [IRR] TRR prep and finalization | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 87 | 170 | 0 | 100%
TAP-113100 | 228 | 298 |  | 04.01.00.00.00.00.00.00 |  | TAP-113100 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113100 | 229 | 228 |  | 04.01.01.00.00.00.00.00 | TAP-113100 | TAP-113108 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 200 | 400 | 0 | 100%
TAP-113100 | 230 | 228 |  | 04.01.02.00.00.00.00.00 | TAP-113100 | TAP-127797 | [TAP-113100] ¦ [IRR][Milestone] RC2 Code Freeze | Feature Estimation | Open | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 0 | 0 | 50 | 100 | 0 | 0%
TAP-111900 | 231 | 303 | 295 | 05.01.00.00.00.00.00.00 |  | TAP-111900 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111900 | 232 | 231 |  | 05.01.01.00.00.00.00.00 | TAP-111900 | TAP-112677 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 30 | 60 | 0 | 100%
TAP-111900 | 233 | 231 |  | 05.01.02.00.00.00.00.00 | TAP-111900 | TAP-112678 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Bug Hunters | BUGHUNTERS | Child Task | User Stories | 0 | 0 | 0 | 1 | 0 | 100%
TAP-111900 | 234 | 231 |  | 05.01.03.00.00.00.00.00 | TAP-111900 | TAP-112679 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - I2E | I2E | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111900 | 235 | 231 |  | 05.01.04.00.00.00.00.00 | TAP-111900 | TAP-112680 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 0 | 0 | 15 | 20 | 0 | 100%
TAP-111900 | 236 | 231 |  | 05.01.05.00.00.00.00.00 | TAP-111900 | TAP-112681 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Romulus | ROMULUS | Child Task | User Stories | 0 | 0 | 15 | 20 | 0 | 100%
TAP-111900 | 237 | 231 |  | 05.01.06.00.00.00.00.00 | TAP-111900 | TAP-112682 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Open | Advanced Instruments - Pixel Poets | PIXELPOETS | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 0%
TAP-111900 | 238 | 231 |  | 05.01.07.00.00.00.00.00 | TAP-111900 | TAP-112683 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Remus | REMUS | Child Task | User Stories | 0 | 0 | 15 | 20 | 0 | 100%
TAP-111900 | 239 | 231 |  | 05.01.08.00.00.00.00.00 | TAP-111900 | TAP-112684 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - Sunrisers | SUNRISERS | Child Task | User Stories | 3 | 3 | 3 | 9 | 0 | 100%
TAP-111900 | 240 | 231 |  | 05.01.09.00.00.00.00.00 | TAP-111900 | TAP-112685 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Advanced Instruments - TeamBD | TEAMBD | Child Task | User Stories | 0 | 0 | 3 | 5 | 0 | 100%
TAP-111900 | 241 | 231 |  | 05.01.11.00.00.00.00.00 | TAP-111900 | TAP-112688 | [TAP-111900] ¦ [IRR] Formal Software Verification activities | Feature Estimation | Done | Shared Services - Cossacks | COSSACKS | Child Task | User Stories | 0 | 0 | 5 | 8 | 0 | 100%
TAP-112042 | 242 | 303 |  | 05.02.00.00.00.00.00.00 |  | TAP-112042 | [TAP-112042] ¦ [V4.2][IRR] Field Script Readiness Evaluation | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112042 | 243 | 242 |  | 05.02.01.00.00.00.00.00 | TAP-112042 | TAP-112222 | [TAP-112042] ¦ [V4.2][IRR] Field Script Readiness Evaluation | Feature Estimation | Done | Shared Services - Builders | BUILDERS | Child Task | User Stories | 0 | 0 | 22 | 30 | 0 | 100%
TAP-111692 | 244 | 303 |  | 05.03.00.00.00.00.00.00 |  | TAP-111692 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111692 | 245 | 244 |  | 05.03.01.00.00.00.00.00 | TAP-111692 | TAP-112223 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Astra NPS Developers | ASTRANPSDEVELOPERS | Child Task | User Stories | 0 | 0 | 20 | 25 | 0 | 100%
TAP-111692 | 246 | 244 |  | 05.03.02.00.00.00.00.00 | TAP-111692 | TAP-112224 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 0 | 0 | 20 | 25 | 0 | 100%
TAP-111692 | 247 | 244 |  | 05.03.03.00.00.00.00.00 | TAP-111692 | TAP-112226 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Inbetweeners | INBETWEENERS | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 100%
TAP-111692 | 248 | 244 |  | 05.03.04.00.00.00.00.00 | TAP-111692 | TAP-112227 | [TAP-111692] ¦ [IRR] Software Tool Development as needed for M-IRR Release | Feature Estimation | Done | Shared Services - Triple Tea | TRIPLETEA | Child Task | User Stories | 0 | 0 | 40 | 80 | 0 | 100%
TAP-112231 | 249 | 303 |  | 05.04.00.00.00.00.00.00 |  | TAP-112231 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112231 | 250 | 249 |  | 05.04.01.00.00.00.00.00 | TAP-112231 | TAP-112236 | [TAP-112231] ¦ [IRR][v3.1] NPS validation for BRR/TRR | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task | User Stories | 0 | 0 | 40 | 50 | 0 | 100%
TAP-112233 | 251 | 303 |  | 05.05.00.00.00.00.00.00 |  | TAP-112233 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112233 | 252 | 251 |  | 05.05.01.00.00.00.00.00 | TAP-112233 | TAP-112237 | [TAP-112233] ¦ [IRR][v3.1] NPS validation for Field service/ PLXS | Feature Estimation | Done | Shared Services - Astra NPS Validators | ASTRANPSVALIDATORS | Child Task | User Stories | 0 | 0 | 10 | 20 | 0 | 100%
TAP-112234 | 253 | 303 |  | 05.06.00.00.00.00.00.00 |  | TAP-112234 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112234 | 254 | 253 |  | 05.06.01.00.00.00.00.00 | TAP-112234 | TAP-112240 | [TAP-112234] ¦ [IRR] ESAT Changes M-IRR | Feature Estimation | Done | Foundation - Tools Rules | TOOLSRULES | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 100%
TAP-113127 | 255 | 303 |  | 05.07.00.00.00.00.00.00 |  | TAP-113127 | [TAP-113127] ¦ [IRR][V4.1] SOUP Impact (for additional scope - EOL, CAPA, Patch Release, RAS Defects) | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-115187 | 256 |  |  | 06.01.01.01.00.00.00.00 |  | TAP-115187 | [TAP-115187] ¦ {CAPA2023-019237} update Z-slide brake check test | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-115187_STELLARS | 257 | 256 |  | 06.01.01.01.01.00.00.00 | TAP-115187 | TAP-115835 | [TAP-115187_STELLARS] ¦ [Stellars] [RAS-7203] [Enabler] Identify and draft Test Changes - Part 1 | User Story | Done | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 5 | 5 | 0 | 0 | 0 | 100%
TAP-115187_SUNRISERS | 258 | 256 |  | 06.01.01.01.07.00.00.00 | TAP-115187 | TAP-116278 | [TAP-115187_SUNRISERS] ¦ [Sunrisers] [RAS-7203] [Enabler] Implementation changes review - SP2 | User Story | Done | Released Product Engineering - Sunrisers | SUNRISERS | Child Task | User Stories | 1 | 1 | 0 | 0 | 0 | 100%
TAP-122269 | 259 | 292 |  | 06.01.01.02.00.00.00.00 |  | TAP-122269 | [TAP-122269] ¦ [CAPA2023-019237] update Z-slide brake check test - Develop | Feature | Accepted |  |  | Parent Task | User Stories | 1 | 1 | 1 hr | 1 hr | 0 | 100%
TAP-122269_STELLARS | 260 | 259 |  | 06.01.01.02.01.00.00.00 | TAP-122269 | TAP-117467 | [TAP-122269_STELLARS] ¦ [Stellars] [RAS-7203] Attend CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 1 | 0 | 1 | 1.2 | 1 | 0%
TAP-64314 | 261 |  |  | 06.01.02.01.00.00.00.00 |  | TAP-64314 | [TAP-64314] ¦ [CAPA][SPIKE] Complete CAPA Investigation Phase of Roll Jump Discontinuity | Feature | Done |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 100%
TAP-64314_JACOBIANS | 262 | 261 |  | 06.01.02.01.01.00.00.00 | TAP-64314 | TAP-60617 | [TAP-64314_JACOBIANS] ¦ [MBTI][Spike] Investigate Potential Causes of Roll Jump Discontinuity (RAS-7532) | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 6.25 | 6.25 | 0 | 0 | 0 | 100%
TAP-64315 | 263 |  |  | 06.01.02.02.00.00.00.00 |  | TAP-64315 | [TAP-64315] ¦ [CAPA] Kinematics SW CAPAs: Investigation & Implementation | Feature | Done |  |  | Parent Task | User Stories | 6.25 | 6.25 | 1 hr | 1 hr | 0 | 100%
TAP-64315_JACOBIANS | 264 | 263 |  | 06.01.02.02.01.00.00.00 | TAP-64315 | TAP-72807 | [TAP-64315_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians][SPIKE] Investigate Solutions for Technical Root Cause | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 8 | 8 | 0 | 0 | 0 | 100%
TAP-64315_REFLECT | 265 | 263 |  | 06.01.02.02.08.00.00.00 | TAP-64315 | TAP-76433 | [TAP-64315_REFLECT] ¦ [CAPA][UNWRAP][Reflect][Spike] Investigate Technical Fix | User Story | Done | Advanced Instruments - Reflect | REFLECT | Child Task | User Stories | 7 | 7 | 0 | 0 | 0 | 100%
TAP-83712 | 266 |  |  | 06.01.02.04.00.00.00.00 |  | TAP-83712 | [TAP-83712] ¦ [Newton][CAPA] Kinematics SW CAPAs: Implementation Phase | Feature | Done |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-83712_JACOBIANS | 267 | 266 |  | 06.01.02.04.01.00.00.00 | TAP-83712 | TAP-86373 | [TAP-83712_JACOBIANS] ¦ [CAPA][SWEEP][Jacobians] Support User study | User Story | Done | Advanced Instruments - Jacobians | JACOBIANS | Child Task | User Stories | 2 | 2 | 0 | 0 | 0 | 100%
TAP-83712_VISUAL | 268 | 266 |  | 06.01.04.01.00.00.00.00 |  | TAP-86405 | [TAP-83712_VISUAL] ¦ [CAPA] Storz Controller crash on second storz power cycle with endoscope connected | User Story | Done | Foundation - Visual | VISUAL | Child Task | User Stories | 11 | 11 | 0 | 0 | 0 | 100%
TAP-125315 | 269 | 292 |  | 06.04.01.03.01.00.00.00 |  | TAP-125315 | [TAP-125315] ¦ [Spike] [RAS-7177] Investigate Instrument Insertion without Internal Calibration | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-125315_STELLARS | 270 | 269 |  | 06.04.01.03.01.01.00.00 | TAP-125315 | TAP-125859 | [TAP-125315_STELLARS] ¦ [Stellars] [Spike] [RAS-7177] Review the existing logs from RAS ticket | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-127798 | 271 | 292 |  | 06.04.01.04.00.00.00.00 |  | TAP-127798 | [TAP-127798] ¦ Attachment workflow fix for use count updates | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-127798 | 272 | 271 |  | 06.04.01.04.01.00.00.00 | TAP-127798 | TAP-127799 | [TAP-127798] ¦ Attachment workflow fix for use count updates | Feature Estimation | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 0 | 0 | 15 | 30 | 0 | 0%
TAP-127798 | 273 | 271 |  | 06.04.01.04.02.00.00.00 | TAP-127798 | TAP-127800 | [TAP-127798] ¦ Attachment workflow fix for use count updates | Feature Estimation | Open | Advanced Instruments - Remus | REMUS | Child Task | User Stories | 0 | 0 | 30 | 50 | 0 | 0%
TAP-127878 | 274 |  |  | 06.04.01.05.00.00.00.00 |  | TAP-127878 | [TAP-127878] ¦ [IRR] HALT workflow improvements | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-127878 | 275 | 274 |  | 06.04.01.05.01.00.00.00 | TAP-127878 | TAP-127879 | [TAP-127878] ¦ [IRR] HALT workflow improvements | Feature Estimation | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 0 | 0 | 5 | 15 | 0 | 0%
TAP-127878 | 276 | 274 |  | 06.04.01.05.02.00.00.00 | TAP-127878 | TAP-127880 | [TAP-127878] ¦ [IRR] HALT workflow improvements | Feature Estimation | Open | Advanced Instruments - Remus | REMUS | Child Task | User Stories | 0 | 0 | 10 | 20 | 0 | 0%
TAP-128479 | 277 |  |  | 06.04.02.01.02.00.00.00 |  | TAP-128479 | [TAP-128479] ¦ [IRR] Clean Up Unknown Instrument Response | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-94573 | 278 |  |  | 06.04.03.02.01.00.00.00 |  | TAP-94573 | [TAP-94573] ¦ [RAS-10357] [Spike] Incorrect instrument use count increase | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-94573_STELLARS | 279 | 278 |  | 06.04.03.02.01.01.00.00 | TAP-94573 | TAP-96622 | [TAP-94573_STELLARS] ¦ [Stellars] [RAS-10357] [Spike] Reproduce issue in SW 4.x | User Story | Done | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 1 | 1 | 0 | 0 | 0 | 100%
TAP-109680 | 280 | 292 |  | 06.04.03.02.03.00.00.00 |  | TAP-109680 | [TAP-109680] ¦ [RAS-10357] Incorrect instrument use count increase - Implementation | Feature | PROPOSED |  |  | Parent Task | User Stories | 1 | 1 | 1 hr | 1 hr | 0 | 100%
TAP-109680_STELLARS | 281 | 280 |  | 06.04.03.02.03.01.00.00 | TAP-109680 | TAP-114754 | [TAP-109680_STELLARS] ¦ [Stellars] [RAS-10357] CCB Review | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-124484 | 282 | 292 |  | 06.04.03.03.01.00.00.00 |  | TAP-124484 | [TAP-124484] ¦ [RAS-4536] [Stellars] Undefined response to SIM/Instrument Memory Error | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-124484_STELLARS | 283 | 282 |  | 06.04.03.03.01.01.00.00 | TAP-124484 | TAP-125567 | [TAP-124484_STELLARS] ¦ [Stellars] [RAS-4536] SW Implementation - Undefined response to SIM/Instrument Memory Error | User Story | Open | Released Product Engineering - Stellars | STELLARS | Child Task | User Stories | 8 | 0 | 8 | 9.6 | 8 | 0%
TAP-111760 | 284 | 285 | 1,81,60,43,76,34,74,12,22,72,69,94,26,32,50,18,57,45,65,28,9,89,15,54,87 | 07.01.00.00.00.00.00.00 |  | TAP-111760 | [TAP-111760] ¦ [IRR][Milestone] EC1 Code Freeze | Feature | PROPOSED |  |  | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-111763 | 285 | 288,287 | 284 | 07.02.00.00.00.00.00.00 |  | TAP-111763 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature | PROPOSED |  |  | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-111763 | 286 | 285 |  | 07.02.01.00.00.00.00.00 | TAP-111763 | TAP-111770 | [TAP-111763] ¦ [IRR][Milestone] EC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-127945 | 287 |  | 285 | 07.03.00.00.00.00.00.00 |  | TAP-127945 | [TAP-127945] ¦ [Prochain][IRR] EC1 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113104 | 288 | 289 | 92,176,162,131,171,127,164,181 | 07.04.00.00.00.00.00.00 |  | TAP-113104 | [TAP-113104] ¦ [IRR][Milestone] EC2 Code Freeze | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113105 | 289 | 292,291 | 288 | 07.05.00.00.00.00.00.00 |  | TAP-113105 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113105 | 290 | 289 |  | 07.05.01.00.00.00.00.00 | TAP-113105 | TAP-113106 | [TAP-113105] ¦ [IRR][Milestone] EC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-127946 | 291 |  | 289 | 07.06.00.00.00.00.00.00 |  | TAP-127946 | [TAP-127946] ¦ [Prochain][IRR] EC2 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111765 | 292 | 293 | 187,189,192,196,198,200,202,204,206,208,210,212,214,220,226,289,282,280,259,269,271 | 07.07.00.00.00.00.00.00 |  | TAP-111765 | [TAP-111765] ¦ [IRR][Milestone] RC1 Code Freeze | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111768 | 293 | 294 | 292 | 07.08.00.00.00.00.00.00 |  | TAP-111768 | [TAP-111768] ¦ [IRR][Milestone] BRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111769 | 294 | 295 | 293 | 07.09.00.00.00.00.00.00 |  | TAP-111769 | [TAP-111769] ¦ [IRR][Milestone] TRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111767 | 295 | 231,297 | 294 | 07.10.00.00.00.00.00.00 |  | TAP-111767 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111767 | 296 | 295 |  | 07.10.01.00.00.00.00.00 | TAP-111767 | TAP-111771 | [TAP-111767] ¦ [IRR][Milestone] RC1 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-127947 | 297 |  | 295 | 07.11.00.00.00.00.00.00 |  | TAP-127947 | [TAP-127947] ¦ [Prochain][IRR] RC1 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113101 | 298 | 299 | 228 | 07.12.00.00.00.00.00.00 |  | TAP-113101 | [TAP-113101] ¦ [IRR][Milestone] RC2 BRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113102 | 299 | 300 | 298 | 07.13.00.00.00.00.00.00 |  | TAP-113102 | [TAP-113102] ¦ [IRR][Milestone] RC2 TRR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113103 | 300 | 303,302 | 299 | 07.14.00.00.00.00.00.00 |  | TAP-113103 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-113103 | 301 | 300 |  | 07.14.01.00.00.00.00.00 | TAP-113103 | TAP-113107 | [TAP-113103] ¦ [IRR][Milestone] RC2 Tagged and Released | Feature Estimation | Done | Shared Services - Seamless | SEAMLESS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-127948 | 302 |  | 300 | 07.15.00.00.00.00.00.00 |  | TAP-127948 | [TAP-127948] ¦ [Prochain][IRR] RC2 Prochain Endpoint | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121104 | 303 |  | 231,242,244,249,251,253,255,300 | 07.16.00.00.00.00.00.00 |  | TAP-121104 | [TAP-121104] ¦ [IRR][Milestone] DVR | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-94968 | 304 |  |  | 08.03.01.00.00.00.00.00 |  | TAP-94968 | [TAP-94968] ¦ [IRR][Investigation] Develop and document an instrument use life model | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111726 | 305 |  |  | 08.03.02.00.00.00.00.00 |  | TAP-111726 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111726 | 306 | 305 |  | 08.03.02.01.00.00.00.00 | TAP-111726 | TAP-111947 | [TAP-111726] ¦ [IRR][Enabler] Wristed Damage Modelling: Bending radius | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 100%
TAP-111727 | 307 |  |  | 08.03.03.00.00.00.00.00 |  | TAP-111727 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111727 | 308 | 307 |  | 08.03.03.01.00.00.00.00 | TAP-111727 | TAP-111948 | [TAP-111727] ¦ [IRR][Enabler] Wristed Damage Modelling: Validation | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111729 | 309 |  |  | 08.03.04.00.00.00.00.00 |  | TAP-111729 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111729 | 310 | 309 |  | 08.03.04.01.00.00.00.00 | TAP-111729 | TAP-111949 | [TAP-111729] ¦ [IRR][Enhancement] Use-life count using damage model | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-94967 | 311 |  |  | 08.03.05.00.00.00.00.00 |  | TAP-94967 | [TAP-94967] ¦ [IRR][Prototype] Develop a Use Life Model that is Compatible With Instrument Programming | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111733 | 312 |  |  | 08.04.00.00.00.00.00.00 |  | TAP-111733 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111733 | 313 | 312 |  | 08.04.01.00.00.00.00.00 | TAP-111733 | TAP-111908 | [TAP-111733] ¦ [IRR][Enhancement][L-IRR] Explore user clamp force setting | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111734 | 314 |  |  | 08.05.00.00.00.00.00.00 |  | TAP-111734 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111734 | 315 | 314 |  | 08.05.01.00.00.00.00.00 | TAP-111734 | TAP-111911 | [TAP-111734] ¦ [[IRR][Enhancement][L-IRR] Explore haptic force regulation / feedback for clamp force | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111735 | 316 |  |  | 08.06.00.00.00.00.00.00 |  | TAP-111735 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111735 | 317 | 316 |  | 08.06.01.00.00.00.00.00 | TAP-111735 | TAP-111912 | [TAP-111735] ¦ [IRR][Enhancement][L-IRR] Explore clamp+cut control for Needle Cutting Grasper | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-111570 | 318 |  |  | 08.07.00.00.00.00.00.00 |  | TAP-111570 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111570 | 319 | 318 |  | 08.07.01.00.00.00.00.00 | TAP-111570 | TAP-111798 | [TAP-111570] ¦ [IRR][Feature][L-IRR] UX Update for Paddle to Cut Command Mapping | Feature Estimation | Open | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-112107 | 320 |  |  | 09.01.03.00.00.00.00.00 |  | TAP-112107 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112107 | 321 | 320 |  | 09.01.03.01.00.00.00.00 | TAP-112107 | TAP-112114 | [TAP-112107] ¦ [IRR][HW-SW Dependency] Grasper SKU Characterization at Frictional Max/Min | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 15 | 30 | 0 | 100%
TAP-111934 | 322 |  |  | 09.01.04.00.00.00.00.00 |  | TAP-111934 | [TAP-111934] ¦ [IRR] Requirement and Verification Expansion to Cover all Gofirst Graspers | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112085 | 323 |  |  | 09.01.05.00.00.00.00.00 |  | TAP-112085 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112085 | 324 | 323 |  | 09.01.05.01.00.00.00.00 | TAP-112085 | TAP-112090 | [TAP-112085] ¦ [IRR] Regress Clamping KPI's for Graspers vis-a-vis Clamp Force | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 10 | 0 | 100%
TAP-112084 | 325 |  |  | 09.01.06.00.00.00.00.00 |  | TAP-112084 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112084 | 326 | 325 |  | 09.01.06.01.00.00.00.00 | TAP-112084 | TAP-112088 | [TAP-112084] ¦ [IRR] Regress Articulation KPI's on Graspers vis-a-vis Pretension | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 10 | 0 | 100%
TAP-112101 | 327 |  |  | 09.01.07.00.00.00.00.00 |  | TAP-112101 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112101 | 328 | 327 |  | 09.01.07.01.00.00.00.00 | TAP-112101 | TAP-112103 | [TAP-112101] ¦ [IRR] Additional controls feature(s) to compensate for hardware variability | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 160 | 320 | 0 | 100%
TAP-112086 | 329 |  |  | 09.01.08.00.00.00.00.00 |  | TAP-112086 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112086 | 330 | 329 |  | 09.01.08.01.00.00.00.00 | TAP-112086 | TAP-112091 | [TAP-112086] ¦ [IRR] Requirement and Verification Engineering for Multi-SKU Release | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 25 | 50 | 0 | 100%
TAP-112087 | 331 |  |  | 09.01.09.00.00.00.00.00 |  | TAP-112087 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112087 | 332 | 331 |  | 09.01.09.01.00.00.00.00 | TAP-112087 | TAP-112092 | [TAP-112087] ¦ [IRR] Product SW Development for Rest of Graspers | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 50 | 100 | 0 | 100%
TAP-112095 | 333 |  |  | 09.02.01.00.00.00.00.00 |  | TAP-112095 | [TAP-112095] ¦ [IRR][Roe/RoW] Update IRR Controller Structure for 3-Cabled Instrument Compatibility | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112095_HAPPYJAWS | 334 | 333 |  | 09.02.01.01.00.00.00.00 | TAP-112095 | TAP-124573 | [TAP-112095_HAPPYJAWS] ¦ [IRR] Prototype 3-cable support for staging/irr-v3 | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-112076 | 335 |  |  | 09.03.01.00.00.00.00.00 |  | TAP-112076 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112076 | 336 | 335 |  | 09.03.01.01.00.00.00.00 | TAP-112076 | TAP-112078 | [TAP-112076] ¦ [IRR][Enabler] Damage Modeling Documentation | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 10 | 0 | 100%
TAP-111555 | 337 |  |  | 09.03.02.00.00.00.00.00 |  | TAP-111555 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111555 | 338 | 337 |  | 09.03.02.01.00.00.00.00 | TAP-111555 | TAP-111783 | [TAP-111555] ¦ [IRR][Enhancement] Improve Cutting Control Robustness I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 12 | 18 | 0 | 100%
TAP-112012 | 339 |  |  | 09.03.03.00.00.00.00.00 |  | TAP-112012 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-112012 | 340 | 339 |  | 09.03.03.01.00.00.00.00 | TAP-112012 | TAP-112015 | [TAP-112012] ¦ [IRR][Enhancement] Cutting Control Enhancements Focused on Cable Slack | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 12 | 18 | 0 | 100%
TAP-111565 | 341 |  |  | 09.03.04.00.00.00.00.00 |  | TAP-111565 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111565 | 342 | 341 |  | 09.03.04.01.00.00.00.00 | TAP-111565 | TAP-111793 | [TAP-111565] ¦ [IRR][Enabler] Control-oriented Mathematical Modelling for Shears Actuation and Cutting | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 5 | 20 | 0 | 100%
TAP-111556 | 343 |  |  | 09.03.05.00.00.00.00.00 |  | TAP-111556 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111556 | 344 | 343 |  | 09.03.05.01.00.00.00.00 | TAP-111556 | TAP-111784 | [TAP-111556] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I1 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111559 | 345 |  |  | 09.03.06.00.00.00.00.00 |  | TAP-111559 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111559 | 346 | 345 |  | 09.03.06.01.00.00.00.00 | TAP-111559 | TAP-111785 | [TAP-111559] ¦ [IRR][Enhancement] Reduce use-life impact from cutting I2 | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 100%
TAP-111731 | 347 |  |  | 09.03.07.00.00.00.00.00 |  | TAP-111731 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-111731 | 348 | 347 |  | 09.03.07.01.00.00.00.00 | TAP-111731 | TAP-111906 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 50 | 50 | 0 | 100%
TAP-111731 | 349 | 347 |  | 09.03.07.02.00.00.00.00 | TAP-111731 | TAP-112037 | [TAP-111731] ¦ [IRR][Enhancement] Reduce force variation when articulating during clamp | Feature Estimation | Open | Shared Services - Animators | ANIMATORS | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-120096 | 350 |  |  | 09.03.08.00.00.00.00.00 |  | TAP-120096 | [TAP-120096] ¦ [IRR][Enabler] Formalize Articulation KPI's | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-116286 | 351 |  |  | 09.03.09.00.00.00.00.00 |  | TAP-116286 | [TAP-116286] ¦ [IRR] Analysis of Key Behaviors in Presence of Reprocessing | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-116286_SIRIUS | 352 | 351 |  | 09.03.09.02.00.00.00.00 | TAP-116286 | TAP-116514 | [TAP-116286_SIRIUS] ¦ [IRR][Analysis] Obtain brand new needle drivers | User Story | Open | Core Instruments - Sirius | SIRIUS | Child Task | User Stories | 2 | 0 | 2 | 2.4 | 2 | 0%
TAP-116286_HAPPYJAWS | 353 | 351 |  | 09.03.09.03.00.00.00.00 | TAP-116286 | TAP-116515 | [TAP-116286_HAPPYJAWS] ¦ [IRR][Analysis] Collect KPI data on a set of brand new instruments | User Story | Open | Core Instruments - Happy Jaws | HAPPYJAWS | Child Task | User Stories | 3 | 0 | 3 | 3.6 | 3 | 0%
TAP-111722 | 354 |  |  | 09.03.10.00.00.00.00.00 |  | TAP-111722 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-111722 | 355 | 354 |  | 09.03.10.01.00.00.00.00 | TAP-111722 | TAP-111918 | [TAP-111722] ¦ [IRR][Enabler] Labs Support for Controller Updates (PI15) | Feature Estimation | Done | Core Instruments | COREINSTRUMENTS | Child Task | User Stories | 0 | 0 | 27 | 30 | 0 | 100%
TAP-111865 | 356 |  |  | 09.03.11.00.00.00.00.00 |  | TAP-111865 | [TAP-111865] ¦ [IRR][Not Confirmed Scope]Update Use Life Definition to Count While in POSITION_CONTROL instead of INSERTED | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%

## Log
DataTimeStamp | Event | Data | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
2024-09-16 12:13 | Start: | DANSAP Formatter, v1.6 | TAP-111865 |  | TAP-112113
2024-09-16 12:13 | Input File: | IRR_Medium_Term_NEW_240913_1413.xls | TAP-111865 |  | TAP-123818
2024-09-16 12:13 | Output File: | Project_Import_DS_14.xlsx
2024-09-16 12:13 | Info
2024-09-16 12:13 | Processing: | Jira Data: Rows: 787, Cols: 16
2024-09-16 12:15 | Result: | Project Data: Rows: 356, Cols: 20
2024-09-16 12:15 | Processing Complete: | 85.85776042938232 seconds

## Summary
Resource Names | Sum FDR
HAPPYJAWS | 87.5
SIRIUS | 64.5
COREINSTRUMENTS | 1367
I2E | 125
ANIMATORS | 0
FRED | 18
PUPPETEERS | 39
JACOBIANS | 117
CASTLEBLACK | 9
BOOSTERS | 28
REMUS | 95
ORGANELLES | 94
INBETWEENERS | 90
ZENITH | 2
CLASSY2 | 10
PIXELPOETS | 100
STELLARS | 16
DRUSHTI | 21
BUGHUNTERS | 0
ROMULUS | 15
SUNRISERS | 3
TEAMBD | 3
COSSACKS | 5
BUILDERS | 22
ASTRANPSDEVELOPERS | 20
TOOLSRULES | 40
TRIPLETEA | 40
ASTRANPSVALIDATORS | 50
REFLECT | 0
VISUAL | 0
SEAMLESS | 40
Total FDR: | 42352.5