## Project
Text10 | Unique ID | UniqueIDSuccessors | UniqueIDPredecessors | Text11 | Text12 | Text13 | Name | Text14 | Text15 | Text16 | Resource Names | Text17 | Text18 | Text19 | Text20 | Duration | Duration1 | Text21 | % Complete
TAP-121866 | 1 |  | 17,143,125,4,292,290,288,295,12,107 | 01.01.01.00.00.00.00.00 |  | TAP-121866 | [TAP-121866] ¦ [PnP][UFSW] Integration of Instrument Workflow Managers after removing build flag in develop | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121866 | 2 | 1 |  | 01.01.01.01.00.00.00.00 | TAP-121866 | TAP-121879 | [TAP-121866] ¦ [PnP][UFSW] Integration of Instrument Workflow Managers after removing build flag in develop | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 40 | 70 | 0 | 0%
TAP-121866_UFSW | 3 | 1 |  | 01.01.01.02.00.00.00.00 | TAP-121866 | TAP-118851 | [TAP-121866_UFSW] ¦ [PnP] User Study for Auto Stop behavior change | User Story | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 40 | 70 | 0 | 0%
TAP-121861 | 4 | 1 |  | 01.02.01.00.00.00.00.00 |  | TAP-121861 | [TAP-121861] ¦ [PnP][UFSW] Endoscope Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121861 | 5 | 4 |  | 01.02.01.01.00.00.00.00 | TAP-121861 | TAP-121877 | [TAP-121861] ¦ [PnP][UFSW] Endoscope Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 0%
TAP-121861_UFSW | 6 | 4 |  | 01.02.01.02.00.00.00.00 | TAP-121861 | TAP-125629 | [TAP-121861_UFSW] ¦ [UFSW] Initial design for Endoscope Workflow Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 7 | 0 | 20 | 40 | 7 | 0%
TAP-121861_UFSW | 7 | 4 |  | 01.02.01.03.00.00.00.00 | TAP-121861 | TAP-125632 | [TAP-121861_UFSW] ¦ [UFSW] Implement the Endosocope Workflow Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 12 | 0 | 20 | 40 | 12 | 0%
TAP-121861_UFSW | 8 | 4 |  | 01.02.01.04.00.00.00.00 | TAP-121861 | TAP-125643 | [TAP-121861_UFSW] ¦ Integrate the Endoscope Workflow Manager with the SRA Controller | User Story | Open | UFSW | UFSW | Child Task | User Stories | 17 | 0 | 20 | 40 | 17 | 0%
TAP-121861_UFSW | 9 | 4 |  | 01.02.01.05.00.00.00.00 | TAP-121861 | TAP-125645 | [TAP-121861_UFSW] ¦ Complete documentation for the endoscope workflow manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 23 | 0 | 20 | 40 | 23 | 0%
TAP-121861_UFSW | 10 | 4 |  | 01.02.01.06.00.00.00.00 | TAP-121861 | TAP-125724 | [TAP-121861_UFSW] ¦ Implement SWI level behavioral MIL test for the Endoscope Workflow Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 28 | 0 | 20 | 40 | 28 | 0%
TAP-121861_UFSW | 11 | 4 |  | 01.02.01.07.00.00.00.00 | TAP-121861 | TAP-125732 | [TAP-121861_UFSW] ¦ [PnP][UFSW] Develop Smoke test for Endoscope Workflow Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 30 | 0 | 20 | 40 | 30 | 0%
TAP-121857 | 12 | 1 | 63 | 01.02.02.00.00.00.00.00 |  | TAP-121857 | [TAP-121857] ¦ [PnP][UFSW] Croc Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121857 | 13 | 12 |  | 01.02.02.01.00.00.00.00 | TAP-121857 | TAP-121874 | [TAP-121857] ¦ [PnP][UFSW] Croc Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 40 | 100 | 0 | 0%
TAP-121937 | 14 | 179,188 | 71 | 01.02.03.00.00.00.00.00 |  | TAP-121937 | [TAP-121937] ¦ [PnP][GUI] Isolate Language-related files for modularization | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121937_GUI | 15 | 14 |  | 01.02.03.01.00.00.00.00 | TAP-121937 | TAP-114836 | [TAP-121937_GUI] ¦ [PnP] GUI - SWI Updates: Language | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121937_GUI | 16 | 14 |  | 01.02.03.02.00.00.00.00 | TAP-121937 | TAP-121970 | [TAP-121937_GUI] ¦ [PnP] GUI - SWI Updates: Language | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 5 | 10 | 0 | 0%
TAP-121858 | 17 | 1 |  | 01.02.04.00.00.00.00.00 |  | TAP-121858 | [TAP-121858] ¦ [PnP][UFSW] Single Use Instrument Workflow Manager Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121858 | 18 | 17 |  | 01.02.04.01.00.00.00.00 | TAP-121858 | TAP-121875 | [TAP-121858] ¦ [PnP][UFSW] Single Use Instrument Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 40 | 70 | 0 | 0%
TAP-121886 | 19 |  | 71,179,188 | 01.02.05.00.00.00.00.00 |  | TAP-121886 | [TAP-121886] ¦ [PnP][GUI] Isolate Instrument Indicator components to prepare for phase 2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121886_GUI | 20 | 19 |  | 01.02.05.01.00.00.00.00 | TAP-121886 | TAP-114824 | [TAP-121886_GUI] ¦ [PnP] [GUI] - SWI Updates: Surgery Header | User Story | Groomed | GUI | GUI | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-121886_GUI | 21 | 19 |  | 01.02.05.02.00.00.00.00 | TAP-121886 | TAP-114460 | [TAP-121886_GUI] ¦ [PnP] GUI - SWI Updates: Arm Status | User Story | Open | GUI | GUI | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-121886_GUI | 22 | 19 |  | 01.02.05.03.00.00.00.00 | TAP-121886 | TAP-114832 | [TAP-121886_GUI] ¦ [PnP][Spike] GUI - Investigate Instrument and Endoscope Indicator | User Story | Done | GUI | GUI | Child Task | User Stories | 6 | 0 | 0 | 0 | 6 | 100%
TAP-121886_GUI | 23 | 19 |  | 01.02.05.04.00.00.00.00 | TAP-121886 | TAP-121938 | [TAP-121886_GUI] ¦ [PnP][Spike] GUI - Investigate Instrument and Endoscope Indicator | Feature Estimation | Done | GUI | GUI | Child Task | User Stories | 6 | 0 | 30 | 60 | 6 | 100%
TAP-114819 | 24 | 95 | 63 | 01.03.01.00.00.00.00.00 |  | TAP-114819 | [TAP-114819] ¦ [PnP] GUI - Pre Planning PnP Interface | Feature | Done |  |  | Parent Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 100%
TAP-114819_GUI | 25 | 24 |  | 01.03.01.01.00.00.00.00 | TAP-114819 | TAP-112001 | [TAP-114819_GUI] ¦ [Spike][v5.0][GUI][PnP] Investigate adding new instruments on runtime part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-114819_GUI | 26 | 24 |  | 01.03.01.02.00.00.00.00 | TAP-114819 | TAP-114871 | [TAP-114819_GUI] ¦ [Spike][v5.0][PnP] Investigate adding new instruments on runtime part 2 | User Story | Done | GUI | GUI | Child Task | User Stories | 10 | 5 | 1 hr | 1 hr | 5 | 100%
TAP-114819_GUI | 27 | 24 |  | 01.03.01.04.00.00.00.00 | TAP-114819 | TAP-121518 | [TAP-114819_GUI] ¦ [Spike][v5.0][PnP] Investigate adding new instruments on runtime part 2 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 10 | 5 | 1 hr | 1 hr | 5 | 50%
TAP-113463 | 28 | 95 | 63 | 01.03.02.00.00.00.00.00 |  | TAP-113463 | [TAP-113463] ¦ [PnP] GUI Testing Framework Improvements | Feature | Done |  |  | Parent Task | User Stories | 10 | 5 | 1 hr | 1 hr | 5 | 100%
TAP-113463_GUI | 29 | 28 |  | 01.03.02.01.00.00.00.00 | TAP-113463 | TAP-114721 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Must] Plan new test framework architecture | User Story | Done | GUI | GUI | Child Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-113463_GUI | 30 | 28 |  | 01.03.02.09.00.00.00.00 | TAP-113463 | TAP-114740 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Must] Implement test case template | User Story | Done | GUI | GUI | Child Task | User Stories | 7 | 5 | 1 hr | 1 hr | 2 | 100%
TAP-113463_GUI | 31 | 28 |  | 01.03.02.10.00.00.00.00 | TAP-113463 | TAP-114741 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Must] Implement local test runner | User Story | Done | GUI | GUI | Child Task | User Stories | 9 | 5 | 1 hr | 1 hr | 4 | 100%
TAP-113463_GUI | 32 | 28 |  | 01.03.02.11.00.00.00.00 | TAP-113463 | TAP-114742 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Must] Implement remote test runner | User Story | Done | GUI | GUI | Child Task | User Stories | 14 | 5 | 1 hr | 1 hr | 9 | 100%
TAP-113463_GUI | 33 | 28 |  | 01.03.02.12.00.00.00.00 | TAP-113463 | TAP-111100 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Should] Implement process to use autoflake, isort and yapf for python test code | User Story | Done | GUI | GUI | Child Task | User Stories | 15 | 5 | 1 hr | 1 hr | 10 | 100%
TAP-113463_GUI | 34 | 28 |  | 01.03.02.14.00.00.00.00 | TAP-113463 | TAP-111112 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Should] Implement strict type checking using mypy for python test code | User Story | Done | GUI | GUI | Child Task | User Stories | 17 | 5 | 1 hr | 1 hr | 12 | 100%
TAP-113463_GUI | 35 | 28 |  | 01.03.02.15.00.00.00.00 | TAP-113463 | TAP-111219 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Could] Investigate upgrading python version for test code base | User Story | Done | GUI | GUI | Child Task | User Stories | 19 | 5 | 1 hr | 1 hr | 14 | 100%
TAP-113463_GUI | 36 | 28 |  | 01.03.02.16.00.00.00.00 | TAP-113463 | TAP-111059 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Should] Implement logging strategy for test code using python.logging | User Story | Done | GUI | GUI | Child Task | User Stories | 20 | 5 | 1 hr | 1 hr | 15 | 100%
TAP-113463_GUI | 37 | 28 |  | 01.03.02.17.00.00.00.00 | TAP-113463 | TAP-114876 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Must] Implement barebones framework | User Story | Done | GUI | GUI | Child Task | User Stories | 24 | 5 | 1 hr | 1 hr | 19 | 100%
TAP-113463_GUI | 38 | 28 |  | 01.03.02.18.00.00.00.00 | TAP-113463 | TAP-111170 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Should] Create README.md for python test code | User Story | Done | GUI | GUI | Child Task | User Stories | 25 | 5 | 1 hr | 1 hr | 20 | 100%
TAP-113463_GUI | 39 | 28 |  | 01.03.02.20.00.00.00.00 | TAP-113463 | TAP-117701 | [TAP-113463_GUI] ¦ [PnP][GUI][Fusion][Test] Implement barebones framework tracker | User Story | Done | GUI | GUI | Child Task | User Stories | 29 | 5 | 1 hr | 1 hr | 24 | 100%
TAP-113463_GUI | 40 | 28 |  | 01.03.02.21.00.00.00.00 | TAP-113463 | TAP-118550 | [TAP-113463_GUI] ¦ [PnP][GUI][Test][Must][Spike] Request validation of pytest | User Story | Done | GUI | GUI | Child Task | User Stories | 31 | 5 | 1 hr | 1 hr | 26 | 100%
TAP-113896 | 41 | 95 | 71 | 01.03.03.00.00.00.00.00 |  | TAP-113896 | [TAP-113896] ¦ [PnP] GUI - SWI Updates Part 1 | Feature | Done |  |  | Parent Task | User Stories | 31 | 5 | 1 hr | 1 hr | 26 | 100%
TAP-113896_GUI | 42 | 41 |  | 01.03.03.01.00.00.00.00 | TAP-113896 | TAP-114462 | [TAP-113896_GUI] ¦ [PnP][zenith] GUI - SWI Updates: Common SWI | User Story | Done | GUI | GUI | Child Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-113896_GUI | 43 | 41 |  | 01.03.03.02.00.00.00.00 | TAP-113896 | TAP-113885 | [TAP-113896_GUI] ¦ [PnP] [GUI] - SWI Updates: Logging | User Story | Done | GUI | GUI | Child Task | User Stories | 8 | 5 | 1 hr | 1 hr | 3 | 100%
TAP-113896_GUI | 44 | 41 |  | 01.03.03.03.00.00.00.00 | TAP-113896 | TAP-113891 | [TAP-113896_GUI] ¦ [PnP] [GUI] - SWI Updates: Common Components | User Story | Done | GUI | GUI | Child Task | User Stories | 13 | 5 | 1 hr | 1 hr | 8 | 100%
TAP-113896_GUI | 45 | 41 |  | 01.03.03.04.00.00.00.00 | TAP-113896 | TAP-113880 | [TAP-113896_GUI] ¦ [PnP] GUI - SWI Updates: Screen | User Story | Done | GUI | GUI | Child Task | User Stories | 17 | 5 | 1 hr | 1 hr | 12 | 100%
TAP-113896_GUI | 46 | 41 |  | 01.03.03.05.00.00.00.00 | TAP-113896 | TAP-114820 | [TAP-113896_GUI] ¦ [PnP] [GUI] - SWI Updates: Theme | User Story | Done | GUI | GUI | Child Task | User Stories | 22 | 5 | 1 hr | 1 hr | 17 | 100%
TAP-113896_GUI | 47 | 41 |  | 01.03.03.06.00.00.00.00 | TAP-113896 | TAP-114085 | [TAP-113896_GUI] ¦ [Pixel Poets][PnP] Support GUI PnP Part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 22.5 | 5 | 1 hr | 1 hr | 17.5 | 100%
TAP-113896_GUI | 48 | 41 |  | 01.03.03.07.00.00.00.00 | TAP-113896 | TAP-114087 | [TAP-113896_GUI] ¦ [Pixel Poets][PnP] Support GUI PnP Part 2 | User Story | Done | GUI | GUI | Child Task | User Stories | 23 | 5 | 1 hr | 1 hr | 18 | 100%
TAP-113896_GUI | 49 | 41 |  | 01.03.03.08.00.00.00.00 | TAP-113896 | TAP-114088 | [TAP-113896_GUI] ¦ [Pixel Poets][PnP] Support GUI PnP Part 3 | User Story | Done | GUI | GUI | Child Task | User Stories | 23.5 | 5 | 1 hr | 1 hr | 18.5 | 100%
TAP-113896_GUI | 50 | 41 |  | 01.03.03.09.00.00.00.00 | TAP-113896 | TAP-114089 | [TAP-113896_GUI] ¦ [Pixel Poets][PnP] Support GUI PnP Part 4 | User Story | Done | GUI | GUI | Child Task | User Stories | 24 | 5 | 1 hr | 1 hr | 19 | 100%
TAP-113896_GUI | 51 | 41 |  | 01.03.03.11.00.00.00.00 | TAP-113896 | TAP-121517 | [TAP-113896_GUI] ¦ [Pixel Poets][PnP] Support GUI PnP Part 4 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 24 | 5 | 1 hr | 1 hr | 19 | 20.83%
TAP-115384 | 52 | 278 |  | 01.03.04.00.00.00.00.00 |  | TAP-115384 | [TAP-115384] ¦ [PnP][UFSW] Migrate to the DR Arch - Containers | Feature | Done |  |  | Parent Task | User Stories | 24 | 5 | 1 hr | 1 hr | 19 | 100%
TAP-115384_UFSW | 53 | 52 |  | 01.03.04.01.00.00.00.00 | TAP-115384 | TAP-115874 | [TAP-115384_UFSW] ¦ [SPIKE] [zenith] Prototype container strategy for PnP vs Dont reboot | User Story | Done | UFSW | UFSW | Child Task | User Stories | 4 | 4 | 1 hr | 1 hr | 0 | 100%
TAP-115384_UFSW | 54 | 52 |  | 01.03.04.03.00.00.00.00 | TAP-115384 | TAP-115921 | [TAP-115384_UFSW] ¦ [SPIKE] Prototype container strategy for PnP vs Dont reboot | User Story | Done | UFSW | UFSW | Child Task | User Stories | 8 | 4 | 1 hr | 1 hr | 4 | 100%
TAP-115384_UFSW | 55 | 52 |  | 01.03.04.04.00.00.00.00 | TAP-115384 | TAP-128285 | [TAP-115384_UFSW] ¦ [SPIKE] Prototype container strategy for PnP vs Dont reboot | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 8 | 4 | 1 hr | 1 hr | 4 | 50%
TAP-114464 | 56 | 95 | 71 | 01.03.05.00.00.00.00.00 |  | TAP-114464 | [TAP-114464] ¦ [PnP] GUI - SWI Updates Part 2 | Feature | Done |  |  | Parent Task | User Stories | 8 | 4 | 1 hr | 1 hr | 4 | 100%
TAP-114464_GUI | 57 | 56 |  | 01.03.05.01.00.00.00.00 | TAP-114464 | TAP-113881 | [TAP-114464_GUI] ¦ [PnP] [GUI] - SWI Updates: System Configuration | User Story | Done | GUI | GUI | Child Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-114464_GUI | 58 | 56 |  | 01.03.05.02.00.00.00.00 | TAP-114464 | TAP-114832 | [TAP-114464_GUI] ¦ [PnP][Spike] GUI - Investigate Instrument and Endoscope Indicator | User Story | Done | GUI | GUI | Child Task | User Stories | 6 | 3 | 1 hr | 1 hr | 3 | 100%
TAP-114464_GUI | 59 | 56 |  | 01.03.05.03.00.00.00.00 | TAP-114464 | TAP-114822 | [TAP-114464_GUI] ¦ [PnP] GUI - SWI Updates: Legal Part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 11 | 3 | 1 hr | 1 hr | 8 | 100%
TAP-114464_GUI | 60 | 56 |  | 01.03.05.04.00.00.00.00 | TAP-114464 | TAP-115466 | [TAP-114464_GUI] ¦ [PnP] GUI - SWI Updates: Legal Part 2 | User Story | Done | GUI | GUI | Child Task | User Stories | 15 | 3 | 1 hr | 1 hr | 12 | 100%
TAP-114464_GUI | 61 | 56 |  | 01.03.05.05.00.00.00.00 | TAP-114464 | TAP-114831 | [TAP-114464_GUI] ¦ [PnP][Machete] GUI - SWI Updates: Bedmap | User Story | Done | GUI | GUI | Child Task | User Stories | 17 | 3 | 1 hr | 1 hr | 14 | 100%
TAP-114464_GUI | 62 | 56 |  | 01.03.05.06.00.00.00.00 | TAP-114464 | TAP-121519 | [TAP-114464_GUI] ¦ [PnP][Machete] GUI - SWI Updates: Bedmap | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 17 | 3 | 1 hr | 1 hr | 14 | 17.65%
TAP-114992 | 63 | 24,95,107,28,12,288,290,292,295,71,196,319 | 52 | 01.03.06.00.00.00.00.00 |  | TAP-114992 | [TAP-114992] ¦ [PnP][UFSW] Migrate to the DR ACA Assembly Workflow Manager | Feature | Done |  |  | Parent Task | User Stories | 17 | 3 | 1 hr | 1 hr | 14 | 100%
TAP-114992_UFSW | 64 | 63 |  | 01.03.06.01.00.00.00.00 | TAP-114992 | TAP-115128 | [TAP-114992_UFSW] ¦ [PnP][UFSW] Prototype Design/Translators/Interface for SRA Teleop ACA Assembly Workflow Manager Re-Factor | User Story | Done | UFSW | UFSW | Child Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-114992_UFSW | 65 | 63 |  | 01.03.06.02.00.00.00.00 | TAP-114992 | TAP-115133 | [TAP-114992_UFSW] ¦ [PnP][UFSW] Implement the Calibration portion of Bedside/ACA Assembly Workflow Manager Re-Factor | User Story | Done | UFSW | UFSW | Child Task | User Stories | 10 | 3 | 1 hr | 1 hr | 7 | 100%
TAP-114992_UFSW | 66 | 63 |  | 01.03.06.03.00.00.00.00 | TAP-114992 | TAP-115139 | [TAP-114992_UFSW] ¦ [PnP][UFSW] Implement the Teleop portion of Bedside/ACA Assembly Workflow Manager Re-Factor | User Story | Done | UFSW | UFSW | Child Task | User Stories | 17 | 3 | 1 hr | 1 hr | 14 | 100%
TAP-114992_UFSW | 67 | 63 |  | 01.03.06.04.00.00.00.00 | TAP-114992 | TAP-115174 | [TAP-114992_UFSW] ¦ [PnP][UFSW] Create Idu Actuator Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 22 | 3 | 1 hr | 1 hr | 19 | 100%
TAP-114992_UFSW | 68 | 63 |  | 01.03.06.05.00.00.00.00 | TAP-114992 | TAP-116631 | [TAP-114992_UFSW] ¦ [PnP][UFSW] Prototype Design/Translators/Interface for Calibration ACA Assembly Workflow Manager Re-Factor | User Story | Done | UFSW | UFSW | Child Task | User Stories | 25 | 3 | 1 hr | 1 hr | 22 | 100%
TAP-114992_UFSW | 69 | 63 |  | 01.03.06.06.00.00.00.00 | TAP-114992 | TAP-117851 | [TAP-114992_UFSW] ¦ [Spike][PnP][UFSW] Initial Design of SRA Re-Factor for other units (IDU Actuator) | User Story | Done | UFSW | UFSW | Child Task | User Stories | 28 | 3 | 1 hr | 1 hr | 25 | 100%
TAP-114992_UFSW | 70 | 63 |  | 01.03.06.08.00.00.00.00 | TAP-114992 | TAP-121511 | [TAP-114992_UFSW] ¦ [Spike][PnP][UFSW] Initial Design of SRA Re-Factor for other units (IDU Actuator) | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 28 | 3 | 1 hr | 1 hr | 25 | 10.71%
TAP-103900 | 71 | 41,112,118,179,159,19,14,188,154,170,165,177 | 63 | 01.03.07.00.00.00.00.00 |  | TAP-103900 | [TAP-103900] ¦ [Arch][PnP] GUI - Migration of SWIs to MVC - Prep and Initial Candidates | Feature | Done |  |  | Parent Task | User Stories | 28 | 3 | 1 hr | 1 hr | 25 | 100%
TAP-103900_GUI | 72 | 100,71 |  | 01.03.07.02.00.00.00.00 | TAP-103900 | TAP-104269 | [TAP-103900_GUI] ¦ [Enabler][v5.0][PnP][PixelPoets] How will refactoring impact the translation tool | User Story | Done | GUI | GUI | Child Task | User Stories | 6 | 6 | 1 hr | 1 hr | 0 | 100%
TAP-103900_GUI | 73 | 71 | 75 | 01.03.07.03.00.00.00.00 | TAP-103900 | TAP-104794 | [TAP-103900_GUI] ¦ [v5.0][PnP][PixelPoets] Investigate path for updating modules / Determine SWI breakdown | User Story | Done | GUI | GUI | Child Task | User Stories | 24 | 6 | 1 hr | 1 hr | 18 | 100%
TAP-103900_GUI | 74 | 71 |  | 01.03.07.04.00.00.00.00 | TAP-103900 | TAP-110267 | [TAP-103900_GUI] ¦ [Enabler][v5.0][PnP][PixelPoets] Brainstorm Sessions => data model | User Story | Done | GUI | GUI | Child Task | User Stories | 29 | 6 | 1 hr | 1 hr | 23 | 100%
TAP-103900_GUI | 75 | 73,71 |  | 01.03.07.05.00.00.00.00 | TAP-103900 | TAP-110269 | [TAP-103900_GUI] ¦ [v5.0][PnP][PixelPoets] Prototype the best data model idea(s) from the Brainstorm meeting | User Story | Done | GUI | GUI | Child Task | User Stories | 37 | 6 | 1 hr | 1 hr | 31 | 100%
TAP-103900_GUI | 76 | 71 |  | 01.03.07.07.00.00.00.00 | TAP-103900 | TAP-96613 | [TAP-103900_GUI] ¦ Plug and Play Arch Defined | User Story | Done | GUI | GUI | Child Task | User Stories | 39 | 6 | 1 hr | 1 hr | 33 | 100%
TAP-103900_GUI | 77 | 71 |  | 01.03.07.08.00.00.00.00 | TAP-103900 | TAP-128287 | [TAP-103900_GUI] ¦ Plug and Play Arch Defined | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 39 | 6 | 1 hr | 1 hr | 33 | 15.38%
TAP-114890 | 78 |  | 52 | 01.03.08.00.00.00.00.00 |  | TAP-114890 | [TAP-114890] ¦ [PnP][UFSW] Migrate the Manual Mode STM to the Don't Reboot architecture | Feature | Done |  |  | Parent Task | User Stories | 39 | 6 | 1 hr | 1 hr | 33 | 100%
TAP-114890_UFSW | 79 | 78 |  | 01.03.08.01.00.00.00.00 | TAP-114890 | TAP-115076 | [TAP-114890_UFSW] ¦ [PnP][UFSW] Implement the Column, Insertion Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-114890_UFSW | 80 | 78 |  | 01.03.08.02.00.00.00.00 | TAP-114890 | TAP-115097 | [TAP-114890_UFSW] ¦ Implement the Orientation and Rotation Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 10 | 5 | 1 hr | 1 hr | 5 | 100%
TAP-114890_UFSW | 81 | 78 |  | 01.03.08.03.00.00.00.00 | TAP-114890 | TAP-115123 | [TAP-114890_UFSW] ¦ Implement the Pitch and Plane Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 15 | 5 | 1 hr | 1 hr | 10 | 100%
TAP-114890_UFSW | 82 | 78 |  | 01.03.08.04.00.00.00.00 | TAP-114890 | TAP-115147 | [TAP-114890_UFSW] ¦ Complete Initial Design for the Pitch and Plane Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 18 | 5 | 1 hr | 1 hr | 13 | 100%
TAP-114890_UFSW | 83 | 78 |  | 01.03.08.05.00.00.00.00 | TAP-114890 | TAP-115148 | [TAP-114890_UFSW] ¦ [PnP][UFSW] Complete Initial Design for the Column, Insertion Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 21 | 5 | 1 hr | 1 hr | 16 | 100%
TAP-114890_UFSW | 84 | 78 |  | 01.03.08.06.00.00.00.00 | TAP-114890 | TAP-115150 | [TAP-114890_UFSW] ¦ Complete Initial Design for the Orientation and Rotation Workflow Managers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 24 | 5 | 1 hr | 1 hr | 19 | 100%
TAP-114890_UFSW | 85 | 78 |  | 01.03.08.08.00.00.00.00 | TAP-114890 | TAP-118836 | [TAP-114890_UFSW] ¦ [PnP][UFSW] Migrate Notcodes to Bedside Setup Monitor | User Story | Done | UFSW | UFSW | Child Task | User Stories | 29 | 5 | 1 hr | 1 hr | 24 | 100%
TAP-115011 | 86 |  | 52 | 01.03.09.00.00.00.00.00 |  | TAP-115011 | [TAP-115011] ¦ [PnP][UFSW] Migrate to the DR Bedside User Commands and Registration Workflow Managers | Feature | Done |  |  | Parent Task | User Stories | 29 | 5 | 1 hr | 1 hr | 24 | 100%
TAP-115011_UFSW | 87 | 86 |  | 01.03.09.01.00.00.00.00 | TAP-115011 | TAP-115382 | [TAP-115011_UFSW] ¦ [zenith] Complete Initial Design for the Bedside Registration Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 2 | 2 | 1 hr | 1 hr | 0 | 100%
TAP-115011_UFSW | 88 | 86 |  | 01.03.09.02.00.00.00.00 | TAP-115011 | TAP-115386 | [TAP-115011_UFSW] ¦ [PnP][zenith] Implement the Bedside Registration Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 5 | 2 | 1 hr | 1 hr | 3 | 100%
TAP-115011_UFSW | 89 | 86 |  | 01.03.09.03.00.00.00.00 | TAP-115011 | TAP-115428 | [TAP-115011_UFSW] ¦ [zenith] Implement the Bedside User Command SWI | User Story | Done | UFSW | UFSW | Child Task | User Stories | 10 | 2 | 1 hr | 1 hr | 8 | 100%
TAP-115011_UFSW | 90 | 86 |  | 01.03.09.04.00.00.00.00 | TAP-115011 | TAP-115437 | [TAP-115011_UFSW] ¦ [zenith] Complete Initial Design for the Bedside User Command SWI | User Story | Done | UFSW | UFSW | Child Task | User Stories | 13 | 2 | 1 hr | 1 hr | 11 | 100%
TAP-115011_UFSW | 91 | 86 |  | 01.03.09.05.00.00.00.00 | TAP-115011 | TAP-116622 | [TAP-115011_UFSW] ¦ [PnP] [BH] MIL peer review in verification of Bedside User Command SWI | User Story | Done | UFSW | UFSW | Child Task | User Stories | 14 | 2 | 1 hr | 1 hr | 12 | 100%
TAP-115011_UFSW | 92 | 86 |  | 01.03.09.06.00.00.00.00 | TAP-115011 | TAP-116624 | [TAP-115011_UFSW] ¦ [PnP][BH] Review MIL tests for the Bedside Registration Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 15 | 2 | 1 hr | 1 hr | 13 | 100%
TAP-115011_UFSW | 93 | 86 |  | 01.03.09.07.00.00.00.00 | TAP-115011 | TAP-121513 | [TAP-115011_UFSW] ¦ [PnP][BH] Review MIL tests for the Bedside Registration Workflow Manager | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 15 | 2 | 1 hr | 1 hr | 13 | 13.33%
TAP-115011_UFSW | 94 | 86 |  | 01.03.09.08.00.00.00.00 | TAP-115011 | TAP-121999 | [TAP-115011_UFSW] ¦ [PnP][zenith] Implement SWI level behavioral MIL test for the Bedside Registration Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 17 | 2 | 1 hr | 1 hr | 15 | 100%
TAP-125001 | 95 |  | 63,24,28,41,56 | 01.04.01.00.00.00.00.00 |  | TAP-125001 | [TAP-125001] ¦ [PnP][GUI] Rollover for PI14 PnP GUI work | Feature | Accepted |  |  | Parent Task | User Stories | 17 | 2 | 1 hr | 1 hr | 15 | 11.76%
TAP-125001_GUI | 96 | 95 |  | 01.04.01.01.00.00.00.00 | TAP-125001 | TAP-125185 | [TAP-125001_GUI] ¦ [PnP][GUI][Fusion] Technical Design Review for Staging Branch Changes and Merge Strategy Approval | User Story | In progress | GUI | GUI | Child Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-125001_GUI | 97 | 95 |  | 01.04.01.02.00.00.00.00 | TAP-125001 | TAP-125578 | [TAP-125001_GUI] ¦ [PnP][GUI][ATF][Fusion] Generate ATF report on HW | User Story | Groomed | GUI | GUI | Child Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 0%
TAP-125001_GUI | 98 | 95 |  | 01.04.01.03.00.00.00.00 | TAP-125001 | TAP-114826 | [TAP-125001_GUI] ¦ [PnP][GUI][Fusion] SWI Updates: Shutdown | User Story | In progress | GUI | GUI | Child Task | User Stories | 9.5 | 0 | 1 hr | 1 hr | 9.5 | 0%
TAP-125001_GUI | 99 | 95 |  | 01.04.01.04.00.00.00.00 | TAP-125001 | TAP-113886 | [TAP-125001_GUI] ¦ [PnP][GUI][Fusion] GUI - SWI Updates: Communication | User Story | In progress | GUI | GUI | Child Task | User Stories | 15 | 0 | 1 hr | 1 hr | 15 | 0%
TAP-125001_GUI | 100 | 95 | 72 | 01.04.01.05.00.00.00.00 | TAP-125001 | TAP-113642 | [TAP-125001_GUI] ¦ [v5.0][PnP][zenith] Remove duplicated files for translation tool | User Story | Done | GUI | GUI | Child Task | User Stories | 18 | 0 | 1 hr | 1 hr | 18 | 100%
TAP-125001_GUI | 101 | 95 |  | 01.04.01.06.00.00.00.00 | TAP-125001 | TAP-121478 | [TAP-125001_GUI] ¦ [PnP][GUI][Fusion] Update requirement tracing in Jama and Polarion | User Story | Done | GUI | GUI | Child Task | User Stories | 22 | 0 | 1 hr | 1 hr | 22 | 100%
TAP-125001_GUI | 102 | 95 |  | 01.04.01.07.00.00.00.00 | TAP-125001 | TAP-119258 | [TAP-125001_GUI] ¦ [PnP][GUI][Fusion] SWI Update: Extract children SWI of common SWI library | User Story | Done | GUI | GUI | Child Task | User Stories | 25 | 0 | 1 hr | 1 hr | 25 | 100%
TAP-125001_GUI | 103 | 95 |  | 01.04.01.08.00.00.00.00 | TAP-125001 | TAP-126015 | [TAP-125001_GUI] ¦ [SPIKE][GUI][PnP] Investigate what manual tests should be run (if any) based on impacted SSRs | User Story | Done | GUI | GUI | Child Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 100%
TAP-125001_GUI | 104 | 95 |  | 01.04.01.09.00.00.00.00 | TAP-125001 | TAP-128283 | [TAP-125001_GUI] ¦ [SPIKE][GUI][PnP] Investigate what manual tests should be run (if any) based on impacted SSRs | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 0%
TAP-125001_GUI | 105 | 95 |  | 01.04.01.10.00.00.00.00 | TAP-125001 | TAP-126021 | [TAP-125001_GUI] ¦ [PnP][GUI][Fusion] Merge staging branch into develop | User Story | Groomed | GUI | GUI | Child Task | User Stories | 27 | 0 | 1 hr | 1 hr | 27 | 0%
TAP-125001_GUI | 106 | 95 |  | 01.04.01.11.00.00.00.00 | TAP-125001 | TAP-130351 | [TAP-125001_GUI] ¦ [PnP][GUI] Update Design Documents | User Story | Open | GUI | GUI | Child Task | User Stories | 29 | 0 | 1 hr | 1 hr | 29 | 0%
TAP-124981 | 107 | 1 | 63 | 01.04.02.00.00.00.00.00 |  | TAP-124981 | [TAP-124981] ¦ [PnP][UFSW] PnP Set up For Don't Reboot SRA Refactor | Feature | Accepted |  |  | Parent Task | User Stories | 29 | 0 | 1 hr | 1 hr | 29 | 0%
TAP-124981_UFSW | 108 | 107 |  | 01.04.02.01.00.00.00.00 | TAP-124981 | TAP-125666 | [TAP-124981_UFSW] ¦ Initial design for the Local Power Constraints Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-124981_UFSW | 109 | 107 |  | 01.04.02.02.00.00.00.00 | TAP-124981 | TAP-125668 | [TAP-124981_UFSW] ¦ Implement the Local Power Constraints Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 7 | 3 | 1 hr | 1 hr | 4 | 100%
TAP-124981_UFSW | 110 | 107 |  | 01.04.02.03.00.00.00.00 | TAP-124981 | TAP-128284 | [TAP-124981_UFSW] ¦ Implement the Local Power Constraints Manager | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 7 | 3 | 1 hr | 1 hr | 4 | 42.86%
TAP-124981_UFSW | 111 | 107 |  | 01.04.02.04.00.00.00.00 | TAP-124981 | TAP-128537 | [TAP-124981_UFSW] ¦ [UFSW] [SRA] Cherry Pick Local Power Constraints Manager into DR post-cyber staging branch | User Story | Done | UFSW | UFSW | Child Task | User Stories | 8 | 3 | 1 hr | 1 hr | 5 | 100%
TAP-121911 | 112 | 179,188 | 71 | 01.04.03.00.00.00.00.00 |  | TAP-121911 | [TAP-121911] ¦ [PnP][GUI] Isolate Notification Indicator | Feature | Accepted |  |  | Parent Task | User Stories | 8 | 3 | 1 hr | 1 hr | 5 | 37.5%
TAP-121911_GUI | 113 | 114,112 | 116 | 01.04.03.01.00.00.00.00 | TAP-121911 | TAP-114830 | [TAP-121911_GUI] ¦ [PnP] [GUI] - SWI Updates: Notification Indicator Part 1 | User Story | Done | GUI | GUI | Child Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-121911_GUI | 114 | 112 | 116,113 | 01.04.03.02.00.00.00.00 | TAP-121911 | TAP-115465 | [TAP-121911_GUI] ¦ [PnP] [GUI] - SWI Updates: Notification Indicator Part 2 | User Story | In progress | GUI | GUI | Child Task | User Stories | 14 | 8 | 1 hr | 1 hr | 6 | 57.14%
TAP-121911_GUI | 115 | 112 |  | 01.04.03.03.00.00.00.00 | TAP-121911 | TAP-121952 | [TAP-121911_GUI] ¦ [PnP] [GUI] - SWI Updates: Notification Indicator Part 2 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 14 | 8 | 1 hr | 1 hr | 6 | 57.14%
TAP-121911_GUI | 116 | 113,114,112 |  | 01.04.03.04.00.00.00.00 | TAP-121911 | TAP-125195 | [TAP-121911_GUI] ¦ [PnP] GUI - Complete Initial Design for the Notification Indicator SWI | User Story | Done | GUI | GUI | Child Task | User Stories | 17 | 8 | 1 hr | 1 hr | 9 | 100%
TAP-121911_GUI | 117 | 112 |  | 01.04.03.05.00.00.00.00 | TAP-121911 | TAP-125579 | [TAP-121911_GUI] ¦ [PnP][ATF] GUI - Generate ATF report on HW | User Story | Groomed | GUI | GUI | Child Task | User Stories | 18 | 8 | 1 hr | 1 hr | 10 | 44.44%
TAP-121904 | 118 | 179,188 | 71 | 01.04.04.00.00.00.00.00 |  | TAP-121904 | [TAP-121904] ¦ [PnP][GUI] Isolate vision system components | Feature | Accepted |  |  | Parent Task | User Stories | 18 | 8 | 1 hr | 1 hr | 10 | 44.44%
TAP-121904_GUI | 119 | 118 |  | 01.04.04.01.00.00.00.00 | TAP-121904 | TAP-113893 | [TAP-121904_GUI] ¦ [PnP][GUI][Fusion] SWI Updates: Video Data | User Story | Groomed | GUI | GUI | Child Task | User Stories | 5.5 | 0 | 1 hr | 1 hr | 5.5 | 0%
TAP-121904_GUI | 120 | 118 |  | 01.04.04.02.00.00.00.00 | TAP-121904 | TAP-114834 | [TAP-121904_GUI] ¦ [PnP][GUI][Fusion] SWI Updates: STech Filter Control | User Story | Groomed | GUI | GUI | Child Task | User Stories | 11 | 0 | 1 hr | 1 hr | 11 | 0%
TAP-121904_GUI | 121 | 118 |  | 01.04.04.03.00.00.00.00 | TAP-121904 | TAP-113892 | [TAP-121904_GUI] ¦ [PnP][GUI][Fusion] SWI Updates: Endoscope Control | User Story | Groomed | GUI | GUI | Child Task | User Stories | 16.5 | 0 | 1 hr | 1 hr | 16.5 | 0%
TAP-121904_GUI | 122 | 118 |  | 01.04.04.04.00.00.00.00 | TAP-121904 | TAP-114463 | [TAP-121904_GUI] ¦ [PnP] GUI - SWI Updates: ICG Control | User Story | Groomed | GUI | GUI | Child Task | User Stories | 25 | 0 | 1 hr | 1 hr | 25 | 0%
TAP-121904_GUI | 123 | 118 |  | 01.04.04.05.00.00.00.00 | TAP-121904 | TAP-121945 | [TAP-121904_GUI] ¦ [PnP] GUI - SWI Updates: ICG Control | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 25 | 0 | 1 hr | 1 hr | 25 | 0%
TAP-121904_GUI | 124 | 118 |  | 01.04.04.06.00.00.00.00 | TAP-121904 | TAP-125580 | [TAP-121904_GUI] ¦ [PnP][ATF] GUI - Generate ATF report on HW | User Story | Groomed | GUI | GUI | Child Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 0%
TAP-121856 | 125 |  |  | 01.04.05.00.00.00.00.00 |  | TAP-121856 | [TAP-121856] ¦ [PnP][UFSW] LigaSure Workflow Manager Migration | Feature | In progress |  |  | Parent Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 0%
TAP-121856 | 126 | 125 |  | 01.04.05.01.00.00.00.00 | TAP-121856 | TAP-121872 | [TAP-121856] ¦ [PnP][UFSW] LigaSure Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121856_UFSW | 127 | 125 |  | 01.04.05.06.00.00.00.00 | TAP-121856 | TAP-125698 | [TAP-121856_UFSW] ¦ [SPIKE][PnP][UFSW][IDU] Solidify interface pattern between Workflow Managers and Controllers | User Story | Done | UFSW | UFSW | Child Task | User Stories | 6 | 0 | 1 hr | 1 hr | 6 | 100%
TAP-121856_UFSW | 128 | 131,125 |  | 01.04.05.07.00.00.00.00 | TAP-121856 | TAP-125701 | [TAP-121856_UFSW] ¦ [PnP][UFSW] Develop Smoke test for LigaSure Workflow Manager | User Story | In progress | UFSW | UFSW | Child Task | User Stories | 10 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-121856_UFSW | 129 | 125 |  | 01.04.05.08.00.00.00.00 | TAP-121856 | TAP-125703 | [TAP-121856_UFSW] ¦ Initial design - pull Marystein functionality in to the Newton WFM to create combined Ligasure WFM | User Story | Done | UFSW | UFSW | Child Task | User Stories | 15 | 0 | 1 hr | 1 hr | 15 | 100%
TAP-121856_UFSW | 130 | 125 |  | 01.04.05.09.00.00.00.00 | TAP-121856 | TAP-125729 | [TAP-121856_UFSW] ¦ [PnP][UFSW][spike] prototype set design Ligasure Workflow Manager and Marystein controller | User Story | Done | UFSW | UFSW | Child Task | User Stories | 19 | 0 | 1 hr | 1 hr | 19 | 100%
TAP-121856_UFSW | 131 | 125 | 128 | 01.04.05.10.00.00.00.00 | TAP-121856 | TAP-125741 | [TAP-121856_UFSW] ¦ [PnP][Zenith] Implement SWI level behavioral MIL test for the Ligasure Workflow Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 24 | 0 | 1 hr | 1 hr | 24 | 0%
TAP-121856_UFSW | 132 | 125 |  | 01.04.05.11.00.00.00.00 | TAP-121856 | TAP-125742 | [TAP-121856_UFSW] ¦ [UFSW] Complete documentation for the Ligasure Workflow Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121856_UFSW | 133 | 125 |  | 01.04.05.12.00.00.00.00 | TAP-121856 | TAP-126097 | [TAP-121856_UFSW] ¦ [PnP] Add Newton Capability to SRA tools | User Story | Open | UFSW | UFSW | Child Task | User Stories | 33 | 0 | 1 hr | 1 hr | 33 | 0%
TAP-121856_UFSW | 134 | 125 |  | 01.04.05.13.00.00.00.00 | TAP-121856 | TAP-126334 | [TAP-121856_UFSW] ¦ Dry Run impacted IX Ligasure test cases (and update as needed) | User Story | Open | UFSW | UFSW | Child Task | User Stories | 37 | 0 | 1 hr | 1 hr | 37 | 0%
TAP-121856_UFSW | 135 | 125 |  | 01.04.05.14.00.00.00.00 | TAP-121856 | TAP-126337 | [TAP-121856_UFSW] ¦ [PnP] Update and dry run test case subset | User Story | Open | UFSW | UFSW | Child Task | User Stories | 40 | 0 | 1 hr | 1 hr | 40 | 0%
TAP-121856_UFSW | 136 | 125 |  | 01.04.05.15.00.00.00.00 | TAP-121856 | TAP-126339 | [TAP-121856_UFSW] ¦ [PnP][Zenith] Update TCs for Newton | User Story | In progress | UFSW | UFSW | Child Task | User Stories | 43 | 0 | 1 hr | 1 hr | 43 | 0%
TAP-121856_UFSW | 137 | 125 |  | 01.04.05.16.00.00.00.00 | TAP-121856 | TAP-126350 | [TAP-121856_UFSW] ¦ Detailed interface design review for Ligasure/Newton WFM with Domain | User Story | Done | UFSW | UFSW | Child Task | User Stories | 45 | 0 | 1 hr | 1 hr | 45 | 100%
TAP-121856_UFSW | 138 | 125 |  | 01.04.05.17.00.00.00.00 | TAP-121856 | TAP-125682 | [TAP-121856_UFSW] ¦ Cherry pick workflow managers and IX estimator in to post-cyber staging branch | User Story | Open | UFSW | UFSW | Child Task | User Stories | 50 | 0 | 1 hr | 1 hr | 50 | 0%
TAP-121856_UFSW | 139 | 125 |  | 01.04.05.18.00.00.00.00 | TAP-121856 | TAP-128536 | [TAP-121856_UFSW] ¦ Implementation: pull Marystein functionality in to Newton WFM to create Ligasure WFM | User Story | In progress | UFSW | UFSW | Child Task | User Stories | 56 | 0 | 1 hr | 1 hr | 56 | 0%
TAP-121856_UFSW | 140 | 125 |  | 01.04.05.19.00.00.00.00 | TAP-121856 | TAP-128168 | [TAP-121856_UFSW] ¦ Independent review Newton Domain Instrument Exchange | User Story | Done | UFSW | UFSW | Child Task | User Stories | 59 | 0 | 1 hr | 1 hr | 59 | 100%
TAP-121856_UFSW | 141 | 125 |  | 01.04.05.20.00.00.00.00 | TAP-121856 | TAP-128167 | [TAP-121856_UFSW] ¦ Independent review Newton Domain External Calibration | User Story | Done | UFSW | UFSW | Child Task | User Stories | 62 | 0 | 1 hr | 1 hr | 62 | 100%
TAP-121856_UFSW | 142 | 125 |  | 01.04.05.21.00.00.00.00 | TAP-121856 | TAP-130685 | [TAP-121856_UFSW] ¦ [PnP][Zenith] Behavioral MIL test for the Ligasure Workflow Manager for calibration functionality | User Story | In progress | UFSW | UFSW | Child Task | User Stories | 64 | 0 | 1 hr | 1 hr | 64 | 0%
TAP-121860 | 143 | 1 |  | 01.04.06.00.00.00.00.00 |  | TAP-121860 | [TAP-121860] ¦ [PnP][UFSW] Core Wristed Instruments Workflow Manager Migration | Feature | Accepted |  |  | Parent Task | User Stories | 64 | 0 | 1 hr | 1 hr | 64 | 0%
TAP-121860 | 144 | 143 |  | 01.04.06.01.00.00.00.00 | TAP-121860 | TAP-121876 | [TAP-121860] ¦ [PnP][UFSW] Core Wristed Instruments Workflow Manager Migration | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121860_UFSW | 145 | 143 |  | 01.04.06.02.00.00.00.00 | TAP-121860 | TAP-123389 | [TAP-121860_UFSW] ¦ [PnP][UFSW] SPIKE - Initial Prototype Design for Core Wristed Instruments | User Story | Done | UFSW | UFSW | Child Task | User Stories | 7 | 0 | 1 hr | 1 hr | 7 | 100%
TAP-121860_UFSW | 146 | 143 |  | 01.04.06.03.00.00.00.00 | TAP-121860 | TAP-125630 | [TAP-121860_UFSW] ¦ [USFW] Implementation of Core Wristed Workflow Manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 12 | 0 | 1 hr | 1 hr | 12 | 100%
TAP-121860_UFSW | 147 | 143 |  | 01.04.06.04.00.00.00.00 | TAP-121860 | TAP-125662 | [TAP-121860_UFSW] ¦ [SPIKE] Investigate if we need a separate workflow manager for MJ Shears | User Story | Done | UFSW | UFSW | Child Task | User Stories | 15 | 0 | 1 hr | 1 hr | 15 | 100%
TAP-121860_UFSW | 148 | 143 |  | 01.04.06.05.00.00.00.00 | TAP-121860 | TAP-125650 | [TAP-121860_UFSW] ¦ [UFSW] Complete documentation for the core wristed workflow manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 21 | 0 | 1 hr | 1 hr | 21 | 0%
TAP-121860_UFSW | 149 | 143 |  | 01.04.06.06.00.00.00.00 | TAP-121860 | TAP-125726 | [TAP-121860_UFSW] ¦ [UFSW] Integration of Core Wristed Workflow Manager with SRA Controller | User Story | In progress | UFSW | UFSW | Child Task | User Stories | 26 | 0 | 1 hr | 1 hr | 26 | 0%
TAP-121860_UFSW | 150 | 143 |  | 01.04.06.07.00.00.00.00 | TAP-121860 | TAP-125728 | [TAP-121860_UFSW] ¦ [UFSW] Implement SWI level behavioral MIL test for the Core Wristed Workflow Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 35 | 0 | 1 hr | 1 hr | 35 | 0%
TAP-121860_UFSW | 151 | 143 |  | 01.04.06.08.00.00.00.00 | TAP-121860 | TAP-125740 | [TAP-121860_UFSW] ¦ [SPIKE][PnP][UFSW] Develop Smoke test Workflow | User Story | Done | UFSW | UFSW | Child Task | User Stories | 38 | 0 | 1 hr | 1 hr | 38 | 100%
TAP-121860_UFSW | 152 | 143 |  | 01.04.06.09.00.00.00.00 | TAP-121860 | TAP-126331 | [TAP-121860_UFSW] ¦ Dry Run subset of impacted Test cases | User Story | Open | UFSW | UFSW | Child Task | User Stories | 39 | 0 | 1 hr | 1 hr | 39 | 0%
TAP-121860_UFSW | 153 | 143 |  | 01.04.06.10.00.00.00.00 | TAP-121860 | TAP-126348 | [TAP-121860_UFSW] ¦ [PnP][IDU][UFSW] Define Wristed Workflow Manager - Wristed Domain Detailed Interface | User Story | Done | UFSW | UFSW | Child Task | User Stories | 41 | 0 | 1 hr | 1 hr | 41 | 100%
TAP-121901 | 154 | 179,188 | 71 | 01.05.01.00.00.00.00.00 |  | TAP-121901 | [TAP-121901] ¦ [PnP][GUI] Isolate instrument and ergonomic settings | Feature | PROPOSED |  |  | Parent Task | User Stories | 41 | 0 | 1 hr | 1 hr | 41 | 0%
TAP-121901_GUI | 155 | 154 |  | 01.05.01.01.00.00.00.00 | TAP-121901 | TAP-114838 | [TAP-121901_GUI] ¦ [PnP] GUI - SWI Updates: Instrument Settings | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121901_GUI | 156 | 154 |  | 01.05.01.02.00.00.00.00 | TAP-121901 | TAP-114841 | [TAP-121901_GUI] ¦ [PnP] GUI - SWI Updates: Arm Configuration | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121901_GUI | 157 | 154 |  | 01.05.01.03.00.00.00.00 | TAP-121901 | TAP-114461 | [TAP-121901_GUI] ¦ [PnP] GUI - SWI Updates: Ergonomic Settings | User Story | Groomed | GUI | GUI | Child Task | User Stories | 5 | 0 | 0 | 0 | 5 | 0%
TAP-121901_GUI | 158 | 154 |  | 01.05.01.04.00.00.00.00 | TAP-121901 | TAP-121943 | [TAP-121901_GUI] ¦ [PnP] GUI - SWI Updates: Ergonomic Settings | Feature Estimation | Done | GUI | GUI | Child Task | User Stories | 5 | 0 | 25 | 60 | 5 | 100%
TAP-121891 | 159 | 179,188 | 71 | 01.05.02.00.00.00.00.00 |  | TAP-121891 | [TAP-121891] ¦ [PnP][GUI] Isolate startup and calibration components | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121891_GUI | 160 | 159 |  | 01.05.02.01.00.00.00.00 | TAP-121891 | TAP-114835 | [TAP-121891_GUI] ¦ [PnP] [GUI] - SWI Updates: System Component | User Story | Open | GUI | GUI | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-121891_GUI | 161 | 159 |  | 01.05.02.02.00.00.00.00 | TAP-121891 | TAP-114837 | [TAP-121891_GUI] ¦ [PnP] GUI - SWI Updates: Startup | User Story | Groomed | GUI | GUI | Child Task | User Stories | 8 | 0 | 0 | 0 | 8 | 0%
TAP-121891_GUI | 162 | 159 |  | 01.05.02.03.00.00.00.00 | TAP-121891 | TAP-114840 | [TAP-121891_GUI] ¦ [PnP] GUI - SWI Updates: Console Calibration | User Story | Open | GUI | GUI | Child Task | User Stories | 8 | 0 | 0 | 0 | 8 | 0%
TAP-121891_GUI | 163 | 159 |  | 01.05.02.04.00.00.00.00 | TAP-121891 | TAP-114844 | [TAP-121891_GUI] ¦ [PnP] GUI - SWI Updates: Arm Setup | User Story | Open | GUI | GUI | Child Task | User Stories | 8 | 0 | 0 | 0 | 8 | 0%
TAP-121891_GUI | 164 | 159 |  | 01.05.02.05.00.00.00.00 | TAP-121891 | TAP-121940 | [TAP-121891_GUI] ¦ [PnP] GUI - SWI Updates: Arm Setup | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 8 | 0 | 25 | 40 | 8 | 0%
TAP-121921 | 165 | 179,188 | 71 | 01.05.03.00.00.00.00.00 |  | TAP-121921 | [TAP-121921] ¦ [PnP][GUI] Isolate ORTI process and display manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-121921_GUI | 166 | 165 |  | 01.05.03.01.00.00.00.00 | TAP-121921 | TAP-114850 | [TAP-121921_GUI] ¦ [PnP] GUI - SWI Updates: ORTI Display | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121921_GUI | 167 | 165 |  | 01.05.03.02.00.00.00.00 | TAP-121921 | TAP-114851 | [TAP-121921_GUI] ¦ [PnP] GUI - SWI Updates: ORTI Screen Components | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121921_GUI | 168 | 165 |  | 01.05.03.03.00.00.00.00 | TAP-121921 | TAP-114852 | [TAP-121921_GUI] ¦ [PnP] GUI - SWI Updates: ORTI Display Manager | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121921_GUI | 169 | 165 |  | 01.05.03.04.00.00.00.00 | TAP-121921 | TAP-121960 | [TAP-121921_GUI] ¦ [PnP] GUI - SWI Updates: ORTI Display Manager | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 20 | 40 | 0 | 0%
TAP-121927 | 170 | 179,188 | 71 | 01.05.04.00.00.00.00.00 |  | TAP-121927 | [TAP-121927] ¦ [PnP][GUI] Isolate S3D and STS process and display manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121927_GUI | 171 | 170 |  | 01.05.04.01.00.00.00.00 | TAP-121927 | TAP-114846 | [TAP-121927_GUI] ¦ [PnP] GUI - SWI Updates: SID Screen Components | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121927_GUI | 172 | 170 |  | 01.05.04.02.00.00.00.00 | TAP-121927 | TAP-114847 | [TAP-121927_GUI] ¦ [PnP] GUI - SWI Updates: SID Display Manager | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121927_GUI | 173 | 170 |  | 01.05.04.03.00.00.00.00 | TAP-121927 | TAP-114848 | [TAP-121927_GUI] ¦ [PnP] GUI - SWI Updates: S3D Display Manager | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121927_GUI | 174 | 170 |  | 01.05.04.04.00.00.00.00 | TAP-121927 | TAP-114849 | [TAP-121927_GUI] ¦ [PnP] GUI - SWI Updates: S3D Screen Component | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121927_GUI | 175 | 170 |  | 01.05.04.05.00.00.00.00 | TAP-121927 | TAP-114845 | [TAP-121927_GUI] ¦ [PnP] GUI - SWI Updates: Surgeon Console Display | User Story | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-121927_GUI | 176 | 170 |  | 01.05.04.06.00.00.00.00 | TAP-121927 | TAP-121965 | [TAP-121927_GUI] ¦ [PnP] GUI - SWI Updates: Surgeon Console Display | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 30 | 50 | 0 | 0%
TAP-121873 | 177 | 179,188 | 71 | 01.05.05.00.00.00.00.00 |  | TAP-121873 | [TAP-121873] ¦ [PnP][GUI][Test] Implement Semi Automated SSR Coverage | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121873 | 178 | 177 |  | 01.05.05.01.00.00.00.00 | TAP-121873 | TAP-121884 | [TAP-121873] ¦ [PnP][GUI][Test] Implement Semi Automated SSR Coverage | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 24 | 40 | 0 | 0%
TAP-121871 | 179 | 19 | 71,112,118,159,154,165,14,170,177 | 01.05.06.00.00.00.00.00 |  | TAP-121871 | [TAP-121871] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 1 | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121871 | 180 | 179 |  | 01.05.06.01.00.00.00.00 | TAP-121871 | TAP-121883 | [TAP-121871] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 1 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 48 | 70 | 0 | 0%
TAP-121871_GUI | 181 | 179 |  | 01.05.06.02.00.00.00.00 | TAP-121871 | TAP-121896 | [TAP-121871_GUI] ¦ [PnP][GUI] Cover General GUI and Arm Cart Assy Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 5 | 0 | 48 | 70 | 5 | 0%
TAP-121871_GUI | 182 | 179 |  | 01.05.06.03.00.00.00.00 | TAP-121871 | TAP-121897 | [TAP-121871_GUI] ¦ [PnP][GUI] Cover Surgeon Ergonomics Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 10 | 0 | 48 | 70 | 10 | 0%
TAP-121871_GUI | 183 | 179 |  | 01.05.06.04.00.00.00.00 | TAP-121871 | TAP-121899 | [TAP-121871_GUI] ¦ [PnP][GUI] Cover Notifications and Safety Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 15 | 0 | 48 | 70 | 15 | 0%
TAP-121871_GUI | 184 | 179 |  | 01.05.06.05.00.00.00.00 | TAP-121871 | TAP-121903 | [TAP-121871_GUI] ¦ [PnP][GUI] Cover Endoscope Controls and other Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 20 | 0 | 48 | 70 | 20 | 0%
TAP-121871_GUI | 185 | 179 |  | 01.05.06.06.00.00.00.00 | TAP-121871 | TAP-121914 | [TAP-121871_GUI] ¦ [PnP][GUI] Cover Camera Control and other Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 25 | 0 | 48 | 70 | 25 | 0%
TAP-121871_GUI | 186 | 179 |  | 01.05.06.07.00.00.00.00 | TAP-121871 | TAP-121918 | [TAP-121871_GUI] ¦ [PnP][GUI] Cover System Activation Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 30 | 0 | 48 | 70 | 30 | 0%
TAP-121871_GUI | 187 | 179 |  | 01.05.06.08.00.00.00.00 | TAP-121871 | TAP-114744 | [TAP-121871_GUI] ¦ [PnP][GUI][Test][Must] Implement test report generator | User Story | Open | GUI | GUI | Child Task | User Stories | 30 | 0 | 48 | 70 | 30 | 0%
TAP-121885 | 188 | 19 | 71,112,118,159,154,165,14,170,177 | 01.05.07.00.00.00.00.00 |  | TAP-121885 | [TAP-121885] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 2 | Feature | PROPOSED |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121885 | 189 | 188 |  | 01.05.07.01.00.00.00.00 | TAP-121885 | TAP-121887 | [TAP-121885] ¦ [PnP][GUI][Test] Implement Fully Automated SSR Coverage Pt 2 | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 0 | 0 | 48 | 70 | 0 | 0%
TAP-121885_GUI | 190 | 188 |  | 01.05.07.02.00.00.00.00 | TAP-121885 | TAP-121930 | [TAP-121885_GUI] ¦ [PnP][GUI] Cover Storz Features Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 5 | 0 | 48 | 70 | 5 | 0%
TAP-121885_GUI | 191 | 188 |  | 01.05.07.03.00.00.00.00 | TAP-121885 | TAP-121933 | [TAP-121885_GUI] ¦ [PnP][GUI] Cover Splash Screen and Instrument Adjustment Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 10 | 0 | 48 | 70 | 10 | 0%
TAP-121885_GUI | 192 | 188 |  | 01.05.07.04.00.00.00.00 | TAP-121885 | TAP-121934 | [TAP-121885_GUI] ¦ [PnP][GUI] Cover Arm and Surgeon Console Calibration Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 15 | 0 | 48 | 70 | 15 | 0%
TAP-121885_GUI | 193 | 188 |  | 01.05.07.05.00.00.00.00 | TAP-121885 | TAP-121935 | [TAP-121885_GUI] ¦ [PnP][GUI] Cover Ancillary Functions and other Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 20 | 0 | 48 | 70 | 20 | 0%
TAP-121885_GUI | 194 | 188 |  | 01.05.07.06.00.00.00.00 | TAP-121885 | TAP-121936 | [TAP-121885_GUI] ¦ [PnP][GUI] Cover ACA and Instrumentation Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 25 | 0 | 48 | 70 | 25 | 0%
TAP-121885_GUI | 195 | 188 |  | 01.05.07.07.00.00.00.00 | TAP-121885 | TAP-121924 | [TAP-121885_GUI] ¦ [PnP][GUI] Cover Energy Delivery Requirements | User Story | Open | GUI | GUI | Child Task | User Stories | 30 | 0 | 48 | 70 | 30 | 0%
TAP-125200 | 196 |  | 63 | 01.05.08.00.00.00.00.00 |  | TAP-125200 | [TAP-125200] ¦ [PnP][GUI] Create Product Architecture with Interface Specifications for Modularized Instrument Software Development | Feature | Accepted |  |  | Parent Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-125200_GUI | 197 | 196 |  | 01.05.08.01.00.00.00.00 | TAP-125200 | TAP-125351 | [TAP-125200_GUI] ¦ [PnP] GUI - Draft the Product Architecture for GUI | User Story | Groomed | GUI | GUI | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-125200_GUI | 198 | 196 |  | 01.05.08.02.00.00.00.00 | TAP-125200 | TAP-125352 | [TAP-125200_GUI] ¦ [PnP] GUI - Create detailed Interface Specifications | User Story | Groomed | GUI | GUI | Child Task | User Stories | 6 | 0 | 0 | 0 | 6 | 0%
TAP-125200_GUI | 199 | 196 |  | 01.05.08.03.00.00.00.00 | TAP-125200 | TAP-116168 | [TAP-125200_GUI] ¦ [Architecture] GUI PnP Interfaces | User Story | Open | GUI | GUI | Child Task | User Stories | 8 | 0 | 0 | 0 | 8 | 0%
TAP-125200_GUI | 200 | 196 |  | 01.05.08.04.00.00.00.00 | TAP-125200 | TAP-128289 | [TAP-125200_GUI] ¦ [Architecture] GUI PnP Interfaces | Feature Estimation | Open | GUI | GUI | Child Task | User Stories | 8 | 0 | 8 | 12 | 8 | 0%
TAP-129535 | 201 |  | 202,262 | 02.01.01.00.00.00.00.00 |  | TAP-129535 | [TAP-129535] ¦ [PnP][v4.2] Migrate embedded PnP updates to v4.2 - Adv Instrument ART | Feature | PROPOSED |  |  | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-126357 | 202 | 201 | 245 | 02.01.02.00.00.00.00.00 |  | TAP-126357 | [TAP-126357] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Desired Data Pipeline | Feature | PROPOSED |  |  | Parent Task | User Stories | 8 | 0 | 1 hr | 1 hr | 8 | 0%
TAP-126357_EMBEDDED | 203 | 202 |  | 02.01.02.01.00.00.00.00 | TAP-126357 | TAP-126108 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] Dry run all IDU Primary TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-126357_EMBEDDED | 204 | 202 |  | 02.01.02.02.00.00.00.00 | TAP-126357 | TAP-126091 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Spike][zenith] IDU Primary Smoke Testing - Load, performance, etc. | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-126357_EMBEDDED | 205 | 202 |  | 02.01.02.03.00.00.00.00 | TAP-126357 | TAP-126078 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Interface Spec testing - Desired Negative TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-126357_EMBEDDED | 206 | 202 |  | 02.01.02.04.00.00.00.00 | TAP-126357 | TAP-126030 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Interface Spec testing - Actual Negative TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-126357_EMBEDDED | 207 | 202 |  | 02.01.02.05.00.00.00.00 | TAP-126357 | TAP-126081 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Interface Spec testing - Desired Positive TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 3 | 0 | 0 | 0 | 3 | 0%
TAP-126357_EMBEDDED | 208 | 202 |  | 02.01.02.06.00.00.00.00 | TAP-126357 | TAP-126071 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Interface Spec testing - Actual Positive TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 8 | 0 | 0 | 0 | 8 | 0%
TAP-126357_EMBEDDED | 209 | 202 |  | 02.01.02.07.00.00.00.00 | TAP-126357 | TAP-126089 | [TAP-126357_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Interface Spec testing - Application TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 13 | 0 | 0 | 0 | 13 | 0%
TAP-126357_EMBEDDED | 210 | 202 |  | 02.01.02.08.00.00.00.00 | TAP-126357 | TAP-126767 | [TAP-126357_EMBEDDED] ¦ [PnP][zenith][Embedded] Application Layer - Interface Spec Doc | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 0 | 0 | 16 | 0%
TAP-126357_EMBEDDED | 211 | 202 |  | 02.01.02.09.00.00.00.00 | TAP-126357 | TAP-124860 | [TAP-126357_EMBEDDED] ¦ [PnP][zenith][Embedded] IDU Primary - Design Document updates | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 19 | 0 | 0 | 0 | 19 | 0%
TAP-126357_EMBEDDED | 212 | 202 |  | 02.01.02.10.00.00.00.00 | TAP-126357 | TAP-126082 | [TAP-126357_EMBEDDED] ¦ [PnP][zenith][Embedded] SRA HAL - Updates to DD | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 22 | 0 | 0 | 0 | 22 | 0%
TAP-126357_EMBEDDED | 213 | 202 |  | 02.01.02.11.00.00.00.00 | TAP-126357 | TAP-104866 | [TAP-126357_EMBEDDED] ¦ [PnP][Zenith][Enabler] IDU Primary Update Unit Tests for RemovableDeviceSensor Class | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 27 | 0 | 0 | 0 | 27 | 0%
TAP-126357_EMBEDDED | 214 | 202 |  | 02.01.02.12.00.00.00.00 | TAP-126357 | TAP-126110 | [TAP-126357_EMBEDDED] ¦ [PnP][Zenith][Controls V&V] Discuss and Execute controls V&V Test Plan for Desired Pipeline Changes | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 29 | 0 | 0 | 0 | 29 | 0%
TAP-126357_EMBEDDED | 215 | 202 |  | 02.01.02.13.00.00.00.00 | TAP-126357 | TAP-128291 | [TAP-126357_EMBEDDED] ¦ [PnP][Zenith][Controls V&V] Discuss and Execute controls V&V Test Plan for Desired Pipeline Changes | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 29 | 0 | 29 | 40 | 29 | 0%
TAP-126357_EMBEDDED | 216 | 202 |  | 02.01.02.14.00.00.00.00 | TAP-126357 | TAP-129392 | [TAP-126357_EMBEDDED] ¦ [PnP][Zenith][Enabler] IDU Primary Update Unit Tests for RemovableDevice Class | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 34 | 0 | 29 | 40 | 34 | 0%
TAP-130040 | 217 |  |  | 02.01.03.00.00.00.00.00 |  | TAP-130040 | [TAP-130040] ¦ [PnP][Zenith][Embedded] SRA HAL TC Updates Due to Data Pipeline Refactor | Feature | PROPOSED |  |  | Parent Task | User Stories | 34 | 0 | 1 hr | 1 hr | 34 | 0%
TAP-130040 | 218 | 217 |  | 02.01.03.01.00.00.00.00 | TAP-130040 | TAP-130041 | [TAP-130040] ¦ [PnP][Zenith][Embedded] SRA HAL TC Updates Due to Data Pipeline Refactor | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-85741 | 219 | 245,430,262,435 |  | 02.02.01.00.00.00.00.00 |  | TAP-85741 | [TAP-85741] ¦ [PnP][Zenith][Embedded] Actual Transport and Application Layer Implementation and Memory Manager IDU Refactor | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-85741_EMBEDDED | 220 | 219 |  | 02.02.01.01.00.00.00.00 | TAP-85741 | TAP-96951 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][I2E][IDU Primary][Enabler] Design Memory Manager for IDU Primary Instrument Parameter Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-85741_EMBEDDED | 221 | 219 |  | 02.02.01.02.00.00.00.00 | TAP-85741 | TAP-96960 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][zenith][IDU Primary] Implement Cyclic EtherCAT Architecture | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 16 | 8 | 1 hr | 1 hr | 8 | 100%
TAP-85741_EMBEDDED | 222 | 219 |  | 02.02.01.03.00.00.00.00 | TAP-85741 | TAP-97641 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][Architecture][Spike][I2E] Impact Assessment and Test Analysis for IDU Primary Updates and SRA HAL | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 19 | 8 | 1 hr | 1 hr | 11 | 100%
TAP-85741_EMBEDDED | 223 | 219 |  | 02.02.01.04.00.00.00.00 | TAP-85741 | TAP-97699 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][I2E][IDU Primary][Spike] Propose a design for blobbing the one wire representation of the instrument data | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 24 | 8 | 1 hr | 1 hr | 16 | 100%
TAP-85741_EMBEDDED | 224 | 219 |  | 02.02.01.05.00.00.00.00 | TAP-85741 | TAP-100814 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][I2E][IDU Primary][Enabler] Cyclic EtherCAT Design Proposal | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 29 | 8 | 1 hr | 1 hr | 21 | 100%
TAP-85741_EMBEDDED | 225 | 219 |  | 02.02.01.06.00.00.00.00 | TAP-85741 | TAP-104014 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][I2E][Enabler][IDU Primary][SRA HAL] Design a proposal for the application layer of the instrument parameters | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 34 | 8 | 1 hr | 1 hr | 26 | 100%
TAP-85741_EMBEDDED | 226 | 219 |  | 02.02.01.07.00.00.00.00 | TAP-85741 | TAP-105168 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][zenith][IDU Primary] Finalize Memory Manager for IDU Primary | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 42 | 8 | 1 hr | 1 hr | 34 | 100%
TAP-85741_EMBEDDED | 227 | 219 |  | 02.02.01.08.00.00.00.00 | TAP-85741 | TAP-105357 | [TAP-85741_EMBEDDED] ¦ [PnP][zenith] IDU Primary - Actual Instrumentation Ethercat App Layer | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 47 | 8 | 1 hr | 1 hr | 39 | 100%
TAP-85741_EMBEDDED | 228 | 219 |  | 02.02.01.09.00.00.00.00 | TAP-85741 | TAP-102496 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][I2E][Spike] Create Reqs and Interface Spec for SRA HAL<->IDU Primary Instrument Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 52 | 8 | 1 hr | 1 hr | 44 | 100%
TAP-85741_EMBEDDED | 229 | 219 |  | 02.02.01.10.00.00.00.00 | TAP-85741 | TAP-105495 | [TAP-85741_EMBEDDED] ¦ [Zenith][PnP][Embedded] SRA HAL - Actual App Layer Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 57 | 8 | 1 hr | 1 hr | 49 | 100%
TAP-85741_EMBEDDED | 230 | 219 |  | 02.02.01.11.00.00.00.00 | TAP-85741 | TAP-106131 | [TAP-85741_EMBEDDED] ¦ [PnP][I2E][INST HIL] Enabler - Finalize HIL Framework Updates | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 62 | 8 | 1 hr | 1 hr | 54 | 100%
TAP-85741_EMBEDDED | 231 | 219 |  | 02.02.01.12.00.00.00.00 | TAP-85741 | TAP-106747 | [TAP-85741_EMBEDDED] ¦ [PnP][I2E][Enabler] Investigate SRA HAL Performance Requirement Adhoc Testing | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 67 | 8 | 1 hr | 1 hr | 59 | 100%
TAP-85741_EMBEDDED | 232 | 219 |  | 02.02.01.13.00.00.00.00 | TAP-85741 | TAP-106752 | [TAP-85741_EMBEDDED] ¦ [PnP][Arch][I2E][Enabler] Prepare for PnP Requirements Work | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 67.5 | 8 | 1 hr | 1 hr | 59.5 | 100%
TAP-85741_EMBEDDED | 233 | 219 |  | 02.02.01.14.00.00.00.00 | TAP-85741 | TAP-98109 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Enabler] Cyclic EtherCAT IDU Primary Framework Update | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 72.5 | 8 | 1 hr | 1 hr | 64.5 | 100%
TAP-85741_EMBEDDED | 234 | 219 |  | 02.02.01.15.00.00.00.00 | TAP-85741 | TAP-112105 | [TAP-85741_EMBEDDED] ¦ [PnP][I2E] Update unit tests to run on linux | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 75.5 | 8 | 1 hr | 1 hr | 67.5 | 100%
TAP-85741_EMBEDDED | 235 | 219 |  | 02.02.01.16.00.00.00.00 | TAP-85741 | TAP-112314 | [TAP-85741_EMBEDDED] ¦ [Newton] Investigate Reqs/TCs that could be automated from controls manual tests | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 76 | 8 | 1 hr | 1 hr | 68 | 100%
TAP-85741_EMBEDDED | 236 | 219 |  | 02.02.01.17.00.00.00.00 | TAP-85741 | TAP-113536 | [TAP-85741_EMBEDDED] ¦ [PnP][Spike] Continue Reading and Writing PnP Reqs for Data Pipeline & Data Manager | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 76 | 8 | 1 hr | 1 hr | 68 | 100%
TAP-85741_EMBEDDED | 237 | 219 |  | 02.02.01.18.00.00.00.00 | TAP-85741 | TAP-113538 | [TAP-85741_EMBEDDED] ¦ [PnP][zenith][Enabler] Benchmark Instrument Data Pipeline (Cont.) | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 81 | 8 | 1 hr | 1 hr | 73 | 100%
TAP-85741_EMBEDDED | 238 | 219 |  | 02.02.01.19.00.00.00.00 | TAP-85741 | TAP-115405 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Spike] Review and Plan adoption of EtherCAT cyclic updates for test framework | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 84 | 8 | 1 hr | 1 hr | 76 | 100%
TAP-85741_EMBEDDED | 239 | 219 |  | 02.02.01.20.00.00.00.00 | TAP-85741 | TAP-115424 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Spike] Impact assessment on IDU Primary TCs based on move to more general data | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 86 | 8 | 1 hr | 1 hr | 78 | 100%
TAP-85741_EMBEDDED | 240 | 219 |  | 02.02.01.21.00.00.00.00 | TAP-85741 | TAP-115982 | [TAP-85741_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Enabler] IDU Primary Test Framework Updates for EtherCAT Transport | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 89 | 8 | 1 hr | 1 hr | 81 | 100%
TAP-85741_EMBEDDED | 241 | 219 |  | 02.02.01.22.00.00.00.00 | TAP-85741 | TAP-115961 | [TAP-85741_EMBEDDED] ¦ [PnP][Zenith][Embedded]Write Integration Testing Plan (INST->SHMIO) | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 94 | 8 | 1 hr | 1 hr | 86 | 100%
TAP-85741_EMBEDDED | 242 | 219 |  | 02.02.01.23.00.00.00.00 | TAP-85741 | TAP-115467 | [TAP-85741_EMBEDDED] ¦ [PnP][zenith][Enabler] Discuss App Layer between IDU<->SRA Over Transport Layer | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 95 | 8 | 1 hr | 1 hr | 87 | 100%
TAP-85741_EMBEDDED | 243 | 219 |  | 02.02.01.25.00.00.00.00 | TAP-85741 | TAP-119582 | [TAP-85741_EMBEDDED] ¦ [PnP][Zenith][IDU Primary] Finalize SIM and IDU MemoryManager and Data Transportation | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 98 | 8 | 1 hr | 1 hr | 90 | 100%
TAP-85741_EMBEDDED | 244 | 219 |  | 02.02.01.26.00.00.00.00 | TAP-85741 | TAP-121514 | [TAP-85741_EMBEDDED] ¦ [PnP][Zenith][IDU Primary] Finalize SIM and IDU MemoryManager and Data Transportation | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 98 | 8 | 1 hr | 1 hr | 90 | 8.163%
TAP-121915 | 245 | 297,424,422,202,428 | 219 | 02.03.01.00.00.00.00.00 |  | TAP-121915 | [TAP-121915] ¦ [PnP][Zenith][Embedded] Desired Parameter Pipeline from SRA HAL to Instrumentation | Feature | Accepted |  |  | Parent Task | User Stories | 98 | 8 | 1 hr | 1 hr | 90 | 8.163%
TAP-121915 | 246 | 245 |  | 02.03.01.01.00.00.00.00 | TAP-121915 | TAP-121955 | [TAP-121915] ¦ [PnP][Zenith][Embedded] Desired Parameter Pipeline from SRA HAL to Instrumentation | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121915_EMBEDDED | 247 | 245 |  | 02.03.01.02.00.00.00.00 | TAP-121915 | TAP-97590 | [TAP-121915_EMBEDDED] ¦ [PnP][zenith][Embedded] SRA HAL - Desired Parameter Pipeline: Application Layer | User Story | Groomed | Embedded | EMBEDDED | Child Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121915_EMBEDDED | 248 | 245 |  | 02.03.01.03.00.00.00.00 | TAP-121915 | TAP-124856 | [TAP-121915_EMBEDDED] ¦ [PnP][zenith][Embedded] SRA HAL - Desired Application Layer Pipeline Unit Tests | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 10 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-121915_EMBEDDED | 249 | 245 |  | 02.03.01.04.00.00.00.00 | TAP-121915 | TAP-97659 | [TAP-121915_EMBEDDED] ¦ [PnP][zenith][Embedded] IDU Primary - Desired Instrumentation Ethercat App Layer | User Story | In progress | Embedded | EMBEDDED | Child Task | User Stories | 15 | 0 | 1 hr | 1 hr | 15 | 0%
TAP-121915_EMBEDDED | 250 | 245 |  | 02.03.01.05.00.00.00.00 | TAP-121915 | TAP-125100 | [TAP-121915_EMBEDDED] ¦ [PnP][zenith][Embedded] IDU Primary - Desired Instrumentation Memory Manager write to 1-Wire | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 20 | 0 | 1 hr | 1 hr | 20 | 0%
TAP-121915_EMBEDDED | 251 | 245 |  | 02.03.01.06.00.00.00.00 | TAP-121915 | TAP-125735 | [TAP-121915_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Desired TC-812 Updates | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 23 | 0 | 1 hr | 1 hr | 23 | 0%
TAP-121915_EMBEDDED | 252 | 245 |  | 02.03.01.07.00.00.00.00 | TAP-121915 | TAP-125743 | [TAP-121915_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Desired TC-3760 Updates | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 25 | 0 | 1 hr | 1 hr | 25 | 0%
TAP-121915_EMBEDDED | 253 | 245 |  | 02.03.01.08.00.00.00.00 | TAP-121915 | TAP-125745 | [TAP-121915_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Desired TC-3778 Updates | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 28 | 0 | 1 hr | 1 hr | 28 | 0%
TAP-121915_EMBEDDED | 254 | 245 |  | 02.03.01.09.00.00.00.00 | TAP-121915 | TAP-125748 | [TAP-121915_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Desired TC-3796 Updates | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 30 | 0 | 1 hr | 1 hr | 30 | 0%
TAP-121915_EMBEDDED | 255 | 245 |  | 02.03.01.10.00.00.00.00 | TAP-121915 | TAP-125993 | [TAP-121915_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary New USE_LIFE TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 33 | 0 | 1 hr | 1 hr | 33 | 0%
TAP-121915_EMBEDDED | 256 | 245 |  | 02.03.01.11.00.00.00.00 | TAP-121915 | TAP-126011 | [TAP-121915_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary New Instrument ID TC | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 36 | 0 | 1 hr | 1 hr | 36 | 0%
TAP-121915_EMBEDDED | 257 | 245 |  | 02.03.01.12.00.00.00.00 | TAP-121915 | TAP-126017 | [TAP-121915_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary New ROM ID TC | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 39 | 0 | 1 hr | 1 hr | 39 | 0%
TAP-121915_EMBEDDED | 258 | 245 |  | 02.03.01.13.00.00.00.00 | TAP-121915 | TAP-104865 | [TAP-121915_EMBEDDED] ¦ [PnP][Zenith][Enabler] Investigate changes to Reqs and RCMs for IDU<->OneWire Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 44 | 0 | 1 hr | 1 hr | 44 | 100%
TAP-121915_EMBEDDED | 259 | 245 |  | 02.03.01.14.00.00.00.00 | TAP-121915 | TAP-126086 | [TAP-121915_EMBEDDED] ¦ [PnP][zenith][Embedded] SRA HAL - Desired Parameter Pipeline: Parameter Translators | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 49 | 0 | 1 hr | 1 hr | 49 | 0%
TAP-121915_EMBEDDED | 260 | 245 |  | 02.03.01.15.00.00.00.00 | TAP-121915 | TAP-126003 | [TAP-121915_EMBEDDED] ¦ [PnP][zenith][Embedded] SRA HAL - Requirement updates | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 52 | 0 | 1 hr | 1 hr | 52 | 100%
TAP-121915_EMBEDDED | 261 | 245 |  | 02.03.01.16.00.00.00.00 | TAP-121915 | TAP-126140 | [TAP-121915_EMBEDDED] ¦ [PnP][zenith][Embedded] Application Layer - Interface Spec Diagram Creation | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 53 | 0 | 1 hr | 1 hr | 53 | 0%
TAP-126005 | 262 | 201 | 219 | 02.03.02.00.00.00.00.00 |  | TAP-126005 | [TAP-126005] ¦ [PnP][Zenith][Embedded] Dry Run Verification and Integration of Actual Data Pipeline | Feature | Accepted |  |  | Parent Task | User Stories | 53 | 0 | 1 hr | 1 hr | 53 | 0%
TAP-126005_EMBEDDED | 263 | 262 |  | 02.03.02.01.00.00.00.00 | TAP-126005 | TAP-125098 | [TAP-126005_EMBEDDED] ¦ [PnP][zenith][Embedded] Integration Testing for Actual Pipeline | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 8 | 8 | 1 hr | 1 hr | 0 | 100%
TAP-126005_EMBEDDED | 264 | 262 |  | 02.03.02.02.00.00.00.00 | TAP-126005 | TAP-126016 | [TAP-126005_EMBEDDED] ¦ [PnP][zenith][Embedded] IDU Primary - Resolve Bug Fixes found during dry runs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 13 | 8 | 1 hr | 1 hr | 5 | 61.54%
TAP-126005_EMBEDDED | 265 | 262 |  | 02.03.02.03.00.00.00.00 | TAP-126005 | TAP-126032 | [TAP-126005_EMBEDDED] ¦ [PnP][Zenith][Embedded] SRA HAL - Address Bug Fixes for Application Layer | User Story | In progress | Embedded | EMBEDDED | Child Task | User Stories | 18 | 8 | 1 hr | 1 hr | 10 | 44.44%
TAP-126005_EMBEDDED | 266 | 262 |  | 02.03.02.04.00.00.00.00 | TAP-126005 | TAP-116061 | [TAP-126005_EMBEDDED] ¦ [PnP][Zenith][Enabler] IDU Primary Update Unit Tests for Instrument, SIM, OneWireDeviceInterface Classes | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 23 | 8 | 1 hr | 1 hr | 15 | 100%
TAP-126005_EMBEDDED | 267 | 262 |  | 02.03.02.05.00.00.00.00 | TAP-126005 | TAP-125697 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Actual TC-3746 Updates | User Story | In progress | Embedded | EMBEDDED | Child Task | User Stories | 25 | 8 | 1 hr | 1 hr | 17 | 32%
TAP-126005_EMBEDDED | 268 | 262 |  | 02.03.02.06.00.00.00.00 | TAP-126005 | TAP-125704 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Actual TC-811 Updates | User Story | In progress | Embedded | EMBEDDED | Child Task | User Stories | 30 | 8 | 1 hr | 1 hr | 22 | 26.67%
TAP-126005_EMBEDDED | 269 | 262 |  | 02.03.02.07.00.00.00.00 | TAP-126005 | TAP-125716 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Actual TC-3555, 2678 Updates | User Story | In progress | Embedded | EMBEDDED | Child Task | User Stories | 35 | 8 | 1 hr | 1 hr | 27 | 22.86%
TAP-126005_EMBEDDED | 270 | 262 |  | 02.03.02.08.00.00.00.00 | TAP-126005 | TAP-125721 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Actual TC-3777 Updates | User Story | In progress | Embedded | EMBEDDED | Child Task | User Stories | 37 | 8 | 1 hr | 1 hr | 29 | 21.62%
TAP-126005_EMBEDDED | 271 | 262 |  | 02.03.02.09.00.00.00.00 | TAP-126005 | TAP-125727 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Actual TC-3816 Updates | User Story | In progress | Embedded | EMBEDDED | Child Task | User Stories | 40 | 8 | 1 hr | 1 hr | 32 | 20%
TAP-126005_EMBEDDED | 272 | 262 |  | 02.03.02.10.00.00.00.00 | TAP-126005 | TAP-125731 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] IDU Primary Actual TC-3875 Updates | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 42 | 8 | 1 hr | 1 hr | 34 | 100%
TAP-126005_EMBEDDED | 273 | 262 |  | 02.03.02.11.00.00.00.00 | TAP-126005 | TAP-97672 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] Test and fix EtherCAT Test Framework to unblock TC work | User Story | Done | Embedded | EMBEDDED | Child Task | User Stories | 47 | 8 | 1 hr | 1 hr | 39 | 100%
TAP-126005_EMBEDDED | 274 | 262 |  | 02.03.02.12.00.00.00.00 | TAP-126005 | TAP-126102 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] Test and fix EtherCAT Test Framework to unblock TC work | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 47 | 8 | 1 hr | 1 hr | 39 | 17.02%
TAP-126005_EMBEDDED | 275 | 262 |  | 02.03.02.13.00.00.00.00 | TAP-126005 | TAP-126105 | [TAP-126005_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] Dry run IDU Primary actual TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 48 | 8 | 1 hr | 1 hr | 40 | 16.67%
TAP-99224 | 276 |  | 319 | 03.01.01.00.00.00.00.00 |  | TAP-99224 | [TAP-99224] ¦ [PnP] [Architecture] [Enabler][Controls] EIN-SWI-176 Croc Controller Refactor | Feature | PROPOSED |  |  | Parent Task | User Stories | 48 | 8 | 1 hr | 1 hr | 40 | 16.67%
TAP-99224 | 277 | 276 |  | 03.01.01.01.00.00.00.00 | TAP-99224 | TAP-121522 | [TAP-99224] ¦ [PnP] [Architecture] [Enabler][Controls] EIN-SWI-176 Croc Controller Refactor | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 24 | 40 | 0 | 0%
TAP-103935 | 278 |  | 52 | 04.01.01.00.00.00.00.00 |  | TAP-103935 | [TAP-103935] ¦ [PnP][Arch][UFSW] MSC - Migrate Energy STM to Aux Fn Manager | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-103935_UFSW | 279 | 278 |  | 04.01.01.01.00.00.00.00 | TAP-103935 | TAP-97705 | [TAP-103935_UFSW] ¦ [Scrumbledores] MSC plug and play concept architecture and prototyping | User Story | Done | UFSW | UFSW | Child Task | User Stories | 6 | 6 | 0 | 0 | 0 | 100%
TAP-103935_UFSW | 280 | 278 |  | 04.01.01.01.01.00.00.00 | TAP-103935 | TAP-106972 | [TAP-103935_UFSW] ¦ [Scrumbledores][PnP] Preliminary prototype for Energy STM knowledge share | User Story | Done | UFSW | UFSW | Child Task | User Stories | 7 | 6 | 0 | 0 | 1 | 100%
TAP-103935_UFSW | 281 | 278 |  | 04.01.01.02.00.00.00.00 | TAP-103935 | TAP-108840 | [TAP-103935_UFSW] ¦ [Organelles][PnP][Spike] Investigate MSC Energy STM and begin design planning for PnP auxiliary function manager | User Story | Done | UFSW | UFSW | Child Task | User Stories | 10 | 6 | 0 | 0 | 4 | 100%
TAP-103935_UFSW | 282 | 278 |  | 04.01.01.03.00.00.00.00 | TAP-103935 | TAP-114605 | [TAP-103935_UFSW] ¦ [UFSW][PnP] Code implementation for Newton Aux Migration | User Story | Open | UFSW | UFSW | Child Task | User Stories | 18 | 6 | 0 | 0 | 12 | 33.33%
TAP-103935_UFSW | 283 | 278 |  | 04.01.01.04.00.00.00.00 | TAP-103935 | TAP-114622 | [TAP-103935_UFSW] ¦ [UFSW] Requirements set up/review - MSC - Migrate Energy STM to Aux Fn Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 23 | 6 | 0 | 0 | 17 | 26.09%
TAP-103935_UFSW | 284 | 278 |  | 04.01.01.05.00.00.00.00 | TAP-103935 | TAP-114660 | [TAP-103935_UFSW] ¦ [UFSW][PnP] Code implementation for Monopolar Aux Migration | User Story | Open | UFSW | UFSW | Child Task | User Stories | 28 | 6 | 0 | 0 | 22 | 21.43%
TAP-103935_UFSW | 285 | 278 |  | 04.01.01.06.00.00.00.00 | TAP-103935 | TAP-114679 | [TAP-103935_UFSW] ¦ [USFW] Prototype DoD - Set up containers for Newton UFSW implementation | User Story | Open | UFSW | UFSW | Child Task | User Stories | 33 | 6 | 0 | 0 | 27 | 18.18%
TAP-103935_UFSW | 286 | 278 |  | 04.01.01.07.00.00.00.00 | TAP-103935 | TAP-116310 | [TAP-103935_UFSW] ¦ [UFSW] Initial design MSC - Migrate Energy STM to Aux Fn Manager | User Story | Open | UFSW | UFSW | Child Task | User Stories | 38 | 6 | 0 | 0 | 32 | 15.79%
TAP-103935_UFSW | 287 | 278 |  | 04.01.01.08.00.00.00.00 | TAP-103935 | TAP-121527 | [TAP-103935_UFSW] ¦ [UFSW] Initial design MSC - Migrate Energy STM to Aux Fn Manager | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 38 | 6 | 37 | 50 | 32 | 15.79%
TAP-121902 | 288 | 1 | 63 | 04.02.01.00.00.00.00.00 |  | TAP-121902 | [TAP-121902] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Core Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 38 | 6 | 1 hr | 1 hr | 32 | 15.79%
TAP-121902 | 289 | 288 |  | 04.02.01.01.00.00.00.00 | TAP-121902 | TAP-121944 | [TAP-121902] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Core Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-121900 | 290 | 1 | 63 | 04.02.02.00.00.00.00.00 |  | TAP-121900 | [TAP-121900] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Croc Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121900 | 291 | 290 |  | 04.02.02.01.00.00.00.00 | TAP-121900 | TAP-121942 | [TAP-121900] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Croc Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-121898 | 292 | 1 | 63 | 04.02.03.00.00.00.00.00 |  | TAP-121898 | [TAP-121898] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Ligasure Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121898 | 293 | 292 |  | 04.02.03.01.00.00.00.00 | TAP-121898 | TAP-121941 | [TAP-121898] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Ligasure Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-121898_UFSW | 294 | 292 |  | 04.02.03.02.00.00.00.00 | TAP-121898 | TAP-125774 | [TAP-121898_UFSW] ¦ Finish PnP Test Strategy Docs | User Story | Done | UFSW | UFSW | Child Task | User Stories | 3 | 0 | 50 | 65 | 3 | 100%
TAP-121905 | 295 | 1 | 63 | 04.02.04.00.00.00.00.00 |  | TAP-121905 | [TAP-121905] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Single Use Instruments | Feature | PROPOSED |  |  | Parent Task | User Stories | 3 | 0 | 1 hr | 1 hr | 3 | 0%
TAP-121905 | 296 | 295 |  | 04.02.04.01.00.00.00.00 | TAP-121905 | TAP-121946 | [TAP-121905] ¦ [PnP][UFSW] Workflow Manager to Domain Integration: Single Use Instruments | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 0 | 0 | 50 | 65 | 0 | 0%
TAP-121922 | 297 | 386 | 245 | 04.03.01.00.00.00.00.00 |  | TAP-121922 | [TAP-121922] ¦ [PnP][Zenith][Embedded] Implement Instrumentation Latching within the SRA HAL/BSCM | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121922 | 298 | 297 |  | 04.03.01.01.00.00.00.00 | TAP-121922 | TAP-121961 | [TAP-121922] ¦ [PnP][Zenith][Embedded] Implement Instrumentation Latching within the SRA HAL/BSCM | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 85 | 115 | 0 | 0%
TAP-103932 | 299 |  |  | 04.04.01.00.00.00.00.00 |  | TAP-103932 | [TAP-103932] ¦ [PnP][Arch][UFSW] Migrate IX STM Instrument Attachment to PnP SWIs | Feature | Done |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 100%
TAP-103932_UFSW | 300 | 299 |  | 04.04.01.01.00.00.00.00 | TAP-103932 | TAP-105843 | [TAP-103932_UFSW] ¦ [UFSW][Newton][PnP] Initial design and requirements set up/review | User Story | Done | UFSW | UFSW | Child Task | User Stories | 10 | 10 | 1 hr | 1 hr | 0 | 100%
TAP-103932_UFSW | 301 | 299 |  | 04.04.01.02.00.00.00.00 | TAP-103932 | TAP-105844 | [TAP-103932_UFSW] ¦ SPIKE [UFSW][PnP] Generate domain side of requirements needed to complete use life migration | User Story | Done | UFSW | UFSW | Child Task | User Stories | 20 | 10 | 1 hr | 1 hr | 10 | 100%
TAP-103932_UFSW | 302 | 299 |  | 04.04.01.05.00.00.00.00 | TAP-103932 | TAP-106079 | [TAP-103932_UFSW] ¦ [Scrumbledores][UFSW] Code implementation and completion of DoD for SRA initial attachment functions | User Story | Done | UFSW | UFSW | Child Task | User Stories | 28 | 10 | 1 hr | 1 hr | 18 | 100%
TAP-103932_UFSW | 303 | 299 |  | 04.04.01.06.00.00.00.00 | TAP-103932 | TAP-106638 | [TAP-103932_UFSW] ¦ [Scrumbledores][Newton][MIL] Create TD for Initial Attachment migration | User Story | Done | UFSW | UFSW | Child Task | User Stories | 33 | 10 | 1 hr | 1 hr | 23 | 100%
TAP-103932_UFSW | 304 | 299 |  | 04.04.01.08.00.00.00.00 | TAP-103932 | TAP-108236 | [TAP-103932_UFSW] ¦ Newton PnP branch interface clean-up | User Story | Done | UFSW | UFSW | Child Task | User Stories | 36 | 10 | 1 hr | 1 hr | 26 | 100%
TAP-103932_UFSW | 305 | 299 |  | 04.04.01.09.00.00.00.00 | TAP-103932 | TAP-110839 | [TAP-103932_UFSW] ¦ [SPIKE] Investigate writing a MIL test at the sra_controller level | User Story | Done | UFSW | UFSW | Child Task | User Stories | 41 | 10 | 1 hr | 1 hr | 31 | 100%
TAP-103932_UFSW | 306 | 299 |  | 04.04.01.10.00.00.00.00 | TAP-103932 | TAP-112483 | [TAP-103932_UFSW] ¦ [PnP] [Scrumbledores] Code Implementation and completion of DoD for Use Life Migration to Domain | User Story | Done | UFSW | UFSW | Child Task | User Stories | 51 | 10 | 1 hr | 1 hr | 41 | 100%
TAP-103932_UFSW | 307 | 299 |  | 04.04.01.11.00.00.00.00 | TAP-103932 | TAP-121525 | [TAP-103932_UFSW] ¦ [PnP] [Scrumbledores] Code Implementation and completion of DoD for Use Life Migration to Domain | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 51 | 10 | 1 hr | 1 hr | 41 | 19.61%
TAP-103933 | 308 |  |  | 04.04.02.00.00.00.00.00 |  | TAP-103933 | [TAP-103933] ¦ [PnP][Arch][UFSW] Migrate IX STM Internal/External Calibration to PnP SWIs | Feature | Done |  |  | Parent Task | User Stories | 51 | 10 | 1 hr | 1 hr | 41 | 100%
TAP-103933_UFSW | 309 | 308 |  | 04.04.02.02.00.00.00.00 | TAP-103933 | TAP-106142 | [TAP-103933_UFSW] ¦ [Organelles][PnP][Spike] Draft Implementation plan for IX STM Internal/External Calibration migration | User Story | Done | UFSW | UFSW | Child Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-103933_UFSW | 310 | 308 |  | 04.04.02.03.00.00.00.00 | TAP-103933 | TAP-106143 | [TAP-103933_UFSW] ¦ [Organelles][PnP] Finalize new SSRs for IX STM Internal/External Calibration migration and complete documentation/FMEAs | User Story | Done | UFSW | UFSW | Child Task | User Stories | 11 | 5 | 1 hr | 1 hr | 6 | 100%
TAP-103933_UFSW | 311 | 308 |  | 04.04.02.04.00.00.00.00 | TAP-103933 | TAP-106144 | [TAP-103933_UFSW] ¦ [Organelles][PnP] Move IX STM Internal/External Calibration to PnP SWIs | User Story | Done | UFSW | UFSW | Child Task | User Stories | 18 | 5 | 1 hr | 1 hr | 13 | 100%
TAP-103933_UFSW | 312 | 308 |  | 04.04.02.05.00.00.00.00 | TAP-103933 | TAP-121532 | [TAP-103933_UFSW] ¦ [Organelles][PnP] Move IX STM Internal/External Calibration to PnP SWIs | Feature Estimation | Open | UFSW | UFSW | Child Task | User Stories | 18 | 5 | 1 hr | 1 hr | 13 | 27.78%
TAP-114308 | 313 | 424,422 | 319 | 04.04.03.00.00.00.00.00 |  | TAP-114308 | [TAP-114308] ¦ [PnP][Controls] Migration of IDU Controller SWIs | Feature | Done |  |  | Parent Task | User Stories | 18 | 5 | 1 hr | 1 hr | 13 | 100%
TAP-114308_CONTROLS | 314 | 313 |  | 04.04.03.03.00.00.00.00 | TAP-114308 | TAP-114494 | [TAP-114308_CONTROLS] ¦ [zenith] Data Corruption RCMs - Get Buy-In from Quality for Update | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 5 | 5 | 1 hr | 1 hr | 0 | 100%
TAP-114308_CONTROLS | 315 | 313 |  | 04.04.03.05.00.00.00.00 | TAP-114308 | TAP-114635 | [TAP-114308_CONTROLS] ¦ [PnP] Migrate Functionality into IDU Actuator Input Processing Container | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 12 | 5 | 1 hr | 1 hr | 7 | 100%
TAP-114308_CONTROLS | 316 | 313 |  | 04.04.03.07.00.00.00.00 | TAP-114308 | TAP-114402 | [TAP-114308_CONTROLS] ¦ [PnP][IDU] Impact Analysis of HALT State | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 13 | 5 | 1 hr | 1 hr | 8 | 100%
TAP-114308_CONTROLS | 317 | 313 |  | 04.04.03.09.00.00.00.00 | TAP-114308 | TAP-116617 | [TAP-114308_CONTROLS] ¦ [BH] [PnP] MIL peer review in verification of IDU Actuator Monitor Container | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 15 | 5 | 1 hr | 1 hr | 10 | 100%
TAP-114308_CONTROLS | 318 | 313 |  | 04.04.03.10.00.00.00.00 | TAP-114308 | TAP-121515 | [TAP-114308_CONTROLS] ¦ [BH] [PnP] MIL peer review in verification of IDU Actuator Monitor Container | Feature Estimation | Done | Controls | CONTROLS | Child Task | User Stories | 15 | 5 | 1 hr | 1 hr | 10 | 100%
TAP-114299 | 319 | 313,360,365,276 | 63 | 04.04.04.00.00.00.00.00 |  | TAP-114299 | [TAP-114299] ¦ [PnP][Controls] Setup IDU Controller Container | Feature | Done |  |  | Parent Task | User Stories | 15 | 5 | 1 hr | 1 hr | 10 | 100%
TAP-114299_CONTROLS | 320 | 319 |  | 04.04.04.01.00.00.00.00 | TAP-114299 | TAP-114400 | [TAP-114299_CONTROLS] ¦ [zenith] Identify SWIs to Migrate, wrangle their signals inside container, 1/2 | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 3 | 3 | 1 hr | 1 hr | 0 | 100%
TAP-114299_CONTROLS | 321 | 319 |  | 04.04.04.02.00.00.00.00 | TAP-114299 | TAP-114401 | [TAP-114299_CONTROLS] ¦ Identify SWIs to Migrate, wrangle their signals inside container, 2/2 | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 6 | 3 | 1 hr | 1 hr | 3 | 100%
TAP-114299_CONTROLS | 322 | 319 |  | 04.04.04.03.00.00.00.00 | TAP-114299 | TAP-114403 | [TAP-114299_CONTROLS] ¦ Set Up New Containers - 1/2 | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 8 | 3 | 1 hr | 1 hr | 5 | 100%
TAP-114299_CONTROLS | 323 | 319 |  | 04.04.04.04.00.00.00.00 | TAP-114299 | TAP-114404 | [TAP-114299_CONTROLS] ¦ [zenith] Set Up New Containers - 2/2 | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 10 | 3 | 1 hr | 1 hr | 7 | 100%
TAP-114299_CONTROLS | 324 | 319 |  | 04.04.04.05.00.00.00.00 | TAP-114299 | TAP-125714 | [TAP-114299_CONTROLS] ¦ [zenith] Set Up New Containers - 2/2 | Feature Estimation | Done | Controls | CONTROLS | Child Task | User Stories | 10 | 3 | 1 hr | 1 hr | 7 | 100%
TAP-121913 | 325 | 353,424,422 | 360,365 | 04.05.01.00.00.00.00.00 |  | TAP-121913 | [TAP-121913] ¦ [PnP][Controls] IDU Actuator Controller - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 10 | 3 | 1 hr | 1 hr | 7 | 30%
TAP-121913 | 326 | 325 |  | 04.05.01.01.00.00.00.00 | TAP-121913 | TAP-121954 | [TAP-121913] ¦ [PnP][Controls] IDU Actuator Controller - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 12 | 15 | 0 | 0%
TAP-121913_CONTROLS | 327 | 325 |  | 04.05.01.02.00.00.00.00 | TAP-121913 | TAP-114639 | [TAP-121913_CONTROLS] ¦ [PnP][zenith] Migrate Functionality into IDU Actuator Controller Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 12 | 15 | 0 | 0%
TAP-121913_CONTROLS | 328 | 325 |  | 04.05.01.03.00.00.00.00 | TAP-121913 | TAP-116612 | [TAP-121913_CONTROLS] ¦ [BH] [PnP] MIL peer review in verification of IDU Actuator Controller Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 12 | 15 | 0 | 0%
TAP-121913_CONTROLS | 329 | 325 |  | 04.05.01.04.00.00.00.00 | TAP-121913 | TAP-123982 | [TAP-121913_CONTROLS] ¦ [PnP][IDU] Move Actuator Controller Into Instrument Controller | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 1 | 0 | 12 | 15 | 1 | 0%
TAP-121913_CONTROLS | 330 | 325 |  | 04.05.01.05.00.00.00.00 | TAP-121913 | TAP-127578 | [TAP-121913_CONTROLS] ¦ [PnP][IDU] Add Pass Variable in UNIT_ActuatorControllerManager for All Motors | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 1 | 0 | 12 | 15 | 1 | 0%
TAP-121912 | 331 | 353,424,422 | 360,365 | 04.05.02.00.00.00.00.00 |  | TAP-121912 | [TAP-121912] ¦ [PnP][Controls] IDU Actuator Monitor - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 1 | 0 | 1 hr | 1 hr | 1 | 0%
TAP-121912 | 332 | 331 |  | 04.05.02.01.00.00.00.00 | TAP-121912 | TAP-121953 | [TAP-121912] ¦ [PnP][Controls] IDU Actuator Monitor - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 0%
TAP-121912_CONTROLS | 333 | 334,331 |  | 04.05.02.03.00.00.00.00 | TAP-121912 | TAP-114640 | [TAP-121912_CONTROLS] ¦ [PnP][zenith] Migrate Functionality into IDU Actuator Monitor Container | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 8 | 0 | 10 | 15 | 8 | 100%
TAP-121912_CONTROLS | 334 | 331 | 333 | 04.05.02.04.00.00.00.00 | TAP-121912 | TAP-124556 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] test fixes following pull request of initial migration | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 8 | 0 | 10 | 15 | 8 | 0%
TAP-121912_CONTROLS | 335 | 331 |  | 04.05.02.05.00.00.00.00 | TAP-121912 | TAP-125678 | [TAP-121912_CONTROLS] ¦ [PnP] Unit test for torque sensor range check | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 9 | 0 | 10 | 15 | 9 | 0%
TAP-121912_CONTROLS | 336 | 331 |  | 04.05.02.06.00.00.00.00 | TAP-121912 | TAP-125679 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] Unit tests for the IduTorqueSensorValidation units | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 15 | 0 | 10 | 15 | 15 | 0%
TAP-121912_CONTROLS | 337 | 331 |  | 04.05.02.07.00.00.00.00 | TAP-121912 | TAP-125683 | [TAP-121912_CONTROLS] ¦ [PnP] proto-MIL test for torque sensor range monitor EIN-SSR_IDUSW-299 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 16 | 0 | 10 | 15 | 16 | 0%
TAP-121912_CONTROLS | 338 | 331 |  | 04.05.02.08.00.00.00.00 | TAP-121912 | TAP-125685 | [TAP-121912_CONTROLS] ¦ [PnP] proto-MIL test for fan monitor EIN-SSR_IDUSW-324 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 17 | 0 | 10 | 15 | 17 | 0%
TAP-121912_CONTROLS | 339 | 331 |  | 04.05.02.09.00.00.00.00 | TAP-121912 | TAP-125684 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] proto-MIL test for temperature monitors EIN-SSR_IDUSW-314 and EIN-SSR_IDUSW-451 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 18 | 0 | 10 | 15 | 18 | 0%
TAP-121912_CONTROLS | 340 | 331 |  | 04.05.02.10.00.00.00.00 | TAP-121912 | TAP-125687 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] proto-MIL test for torque sensor and motor position estimation EIN-SSR_IDUSW-298 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 19 | 0 | 10 | 15 | 19 | 0%
TAP-121912_CONTROLS | 341 | 331 |  | 04.05.02.11.00.00.00.00 | TAP-121912 | TAP-125688 | [TAP-121912_CONTROLS] ¦ [PnP] proto-MIL test for power monitor EIN-SSR_IDUSW-353 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 20 | 0 | 10 | 15 | 20 | 0%
TAP-121912_CONTROLS | 342 | 331 |  | 04.05.02.12.00.00.00.00 | TAP-121912 | TAP-125689 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] proto-MIL test for torque sensor monitor EIN-SSR_IDUSW-547 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 21 | 0 | 10 | 15 | 21 | 0%
TAP-121912_CONTROLS | 343 | 331 |  | 04.05.02.13.00.00.00.00 | TAP-121912 | TAP-125690 | [TAP-121912_CONTROLS] ¦ [PnP] proto-MIL test for motor state monitor EIN-SSR_IDUSW-483 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 22 | 0 | 10 | 15 | 22 | 0%
TAP-121912_CONTROLS | 344 | 331 |  | 04.05.02.14.00.00.00.00 | TAP-121912 | TAP-125691 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] proto-MIL test for motor torque accuracy monitor EIN-SSR_IDUSW-482 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 23 | 0 | 10 | 15 | 23 | 0%
TAP-121912_CONTROLS | 345 | 331 |  | 04.05.02.15.00.00.00.00 | TAP-121912 | TAP-125692 | [TAP-121912_CONTROLS] ¦ [PnP] proto-MIL test for motor torque limits monitor EIN-SSR_IDUSW-306 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 24 | 0 | 10 | 15 | 24 | 0%
TAP-121912_CONTROLS | 346 | 331 |  | 04.05.02.16.00.00.00.00 | TAP-121912 | TAP-125693 | [TAP-121912_CONTROLS] ¦ [PnP] proto-MIL test for quality flags | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 26 | 0 | 10 | 15 | 26 | 0%
TAP-121912_CONTROLS | 347 | 331 |  | 04.05.02.17.00.00.00.00 | TAP-121912 | TAP-125717 | [TAP-121912_CONTROLS] ¦ [PnP] Informal PDR for IDU monitor | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 27 | 0 | 10 | 15 | 27 | 0%
TAP-121912_CONTROLS | 348 | 331 |  | 04.05.02.18.00.00.00.00 | TAP-121912 | TAP-125719 | [TAP-121912_CONTROLS] ¦ [PnP] Get requirements in acceptable draft state | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 29 | 0 | 10 | 15 | 29 | 0%
TAP-121912_CONTROLS | 349 | 331 |  | 04.05.02.19.00.00.00.00 | TAP-121912 | TAP-125720 | [TAP-121912_CONTROLS] ¦ [PnP] Analyze risk for IDU Monitor | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 32 | 0 | 10 | 15 | 32 | 0%
TAP-121912_CONTROLS | 350 | 331 |  | 04.05.02.20.00.00.00.00 | TAP-121912 | TAP-125734 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] Develop smoke tests for IDU Monitor | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 37 | 0 | 10 | 15 | 37 | 0%
TAP-121912_CONTROLS | 351 | 331 |  | 04.05.02.22.00.00.00.00 | TAP-121912 | TAP-126024 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] Static analysis for the IDU Monitor SWI | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 38 | 0 | 10 | 15 | 38 | 0%
TAP-121912_CONTROLS | 352 | 331 |  | 04.05.02.23.00.00.00.00 | TAP-121912 | TAP-126025 | [TAP-121912_CONTROLS] ¦ [PnP][Zenith] Design doc for IDU Monitor | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 39 | 0 | 10 | 15 | 39 | 0%
TAP-121925 | 353 | 422,424 | 372,408,325,331,375,378,397 | 04.05.03.00.00.00.00.00 |  | TAP-121925 | [TAP-121925] ¦ [PnP][Controls] IDU Controller SysIL Verification - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 39 | 0 | 1 hr | 1 hr | 39 | 0%
TAP-121925 | 354 | 353 |  | 04.05.03.01.00.00.00.00 | TAP-121925 | TAP-121963 | [TAP-121925] ¦ [PnP][Controls] IDU Controller SysIL Verification - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 21 | 30 | 0 | 0%
TAP-121925_CONTROLS | 355 | 353 |  | 04.05.03.02.00.00.00.00 | TAP-121925 | TAP-116070 | [TAP-121925_CONTROLS] ¦ [PnP][zenith] Verify Migration of Functionality into IDU Actuator Monitor Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 21 | 30 | 0 | 0%
TAP-121925_CONTROLS | 356 | 353 |  | 04.05.03.03.00.00.00.00 | TAP-121925 | TAP-116069 | [TAP-121925_CONTROLS] ¦ [PnP][zenith] Verify Migration of Functionality into IDU Actuator Controller Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 3 | 0 | 21 | 30 | 3 | 0%
TAP-121925_CONTROLS | 357 | 353 |  | 04.05.03.04.00.00.00.00 | TAP-121925 | TAP-116067 | [TAP-121925_CONTROLS] ¦ [PnP][zenith] Verify Migration of Functionality into IDU Actuator Output Processing Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 9 | 0 | 21 | 30 | 9 | 0%
TAP-121925_CONTROLS | 358 | 353 |  | 04.05.03.05.00.00.00.00 | TAP-121925 | TAP-116065 | [TAP-121925_CONTROLS] ¦ [PnP] Verify Migration of Functionality into Instrument Controller Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 15 | 0 | 21 | 30 | 15 | 0%
TAP-121925_CONTROLS | 359 | 353 |  | 04.05.03.06.00.00.00.00 | TAP-121925 | TAP-116064 | [TAP-121925_CONTROLS] ¦ [PnP] Verify Migration of Functionality into IDU Actuator Input Processing Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 21 | 0 | 21 | 30 | 21 | 0%
TAP-121923 | 360 | 372,408,325,331,375,378,424,422,397 | 319 | 04.05.04.00.00.00.00.00 |  | TAP-121923 | [TAP-121923] ¦ [PnP][Controls] IDU Controller Debug Logging - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 21 | 0 | 1 hr | 1 hr | 21 | 0%
TAP-121923 | 361 | 360 |  | 04.05.04.01.00.00.00.00 | TAP-121923 | TAP-121962 | [TAP-121923] ¦ [PnP][Controls] IDU Controller Debug Logging - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 0%
TAP-121923_CONTROLS | 362 | 360 |  | 04.05.04.02.00.00.00.00 | TAP-121923 | TAP-118838 | [TAP-121923_CONTROLS] ¦ [PnP][Zenith] Draft Informal Functional Requirements for Informal Verification | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 1 | 0 | 10 | 15 | 1 | 0%
TAP-121923_CONTROLS | 363 | 360 |  | 04.05.04.03.00.00.00.00 | TAP-121923 | TAP-125674 | [TAP-121923_CONTROLS] ¦ [PnP][Fusion] Design flexible IDU logging strategy | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 4 | 0 | 10 | 15 | 4 | 100%
TAP-121923_CONTROLS | 364 | 360 |  | 04.05.04.04.00.00.00.00 | TAP-121923 | TAP-125676 | [TAP-121923_CONTROLS] ¦ [PnP][Zenith] Address the LogHwData unit | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 5 | 0 | 10 | 15 | 5 | 0%
TAP-121920 | 365 | 372,408,325,331,375,378,424,422,397 | 319 | 04.05.05.00.00.00.00.00 |  | TAP-121920 | [TAP-121920] ¦ [PnP][Controls] IDU Controller Error Handler - Migration | Feature | Accepted |  |  | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121920 | 366 | 365 |  | 04.05.05.01.00.00.00.00 | TAP-121920 | TAP-121959 | [TAP-121920] ¦ [PnP][Controls] IDU Controller Error Handler - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 13 | 20 | 0 | 0%
TAP-121920_CONTROLS | 367 | 365 |  | 04.05.05.02.00.00.00.00 | TAP-121920 | TAP-125656 | [TAP-121920_CONTROLS] ¦ [PnP][Zenith] Add NOTCODE functionality for IDU Monitor | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 4 | 0 | 13 | 20 | 4 | 0%
TAP-121920_CONTROLS | 368 | 365 |  | 04.05.05.03.00.00.00.00 | TAP-121920 | TAP-125654 | [TAP-121920_CONTROLS] ¦ [PnP][Zenith] Add NOTCODE functionality for IDU Instrument Controller | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 8 | 0 | 13 | 20 | 8 | 0%
TAP-121920_CONTROLS | 369 | 365 |  | 04.05.05.04.00.00.00.00 | TAP-121920 | TAP-125665 | [TAP-121920_CONTROLS] ¦ [PnP] Add idu_local_fault functionality | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 10 | 0 | 13 | 20 | 10 | 0%
TAP-121920_CONTROLS | 370 | 365 |  | 04.05.05.05.00.00.00.00 | TAP-121920 | TAP-125667 | [TAP-121920_CONTROLS] ¦ [PnP] Add idu_fault functionality | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 11 | 0 | 13 | 20 | 11 | 0%
TAP-121920_CONTROLS | 371 | 365 |  | 04.05.05.06.00.00.00.00 | TAP-121920 | TAP-125671 | [TAP-121920_CONTROLS] ¦ [PnP] Add ringbuffer trigger functionality | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 13 | 0 | 13 | 20 | 13 | 0%
TAP-121919 | 372 | 353,424,422 | 360,365 | 04.05.06.00.00.00.00.00 |  | TAP-121919 | [TAP-121919] ¦ [PnP][Controls] IDU Controller "Workflow Manager" - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-121919 | 373 | 372 |  | 04.05.06.01.00.00.00.00 | TAP-121919 | TAP-121958 | [TAP-121919] ¦ [PnP][Controls] IDU Controller "Workflow Manager" - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 5 | 10 | 0 | 0%
TAP-121919_CONTROLS | 374 | 372 |  | 04.05.06.02.00.00.00.00 | TAP-121919 | TAP-123981 | [TAP-121919_CONTROLS] ¦ [PnP][IDU] Add SIM Usage Monitor | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 2 | 0 | 5 | 10 | 2 | 0%
TAP-121910 | 375 | 353,424,422 | 360,365 | 04.05.07.00.00.00.00.00 |  | TAP-121910 | [TAP-121910] ¦ [PnP][Controls] IDU Actuator Output Processing - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 2 | 0 | 1 hr | 1 hr | 2 | 0%
TAP-121910 | 376 | 375 |  | 04.05.07.01.00.00.00.00 | TAP-121910 | TAP-121951 | [TAP-121910] ¦ [PnP][Controls] IDU Actuator Output Processing - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 7 | 10 | 0 | 0%
TAP-121910_CONTROLS | 377 | 375 |  | 04.05.07.02.00.00.00.00 | TAP-121910 | TAP-114638 | [TAP-121910_CONTROLS] ¦ [PnP][zenith] Migrate Functionality into IDU Actuator Output Processing Container | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 7 | 10 | 0 | 0%
TAP-121908 | 378 | 353,424,422 | 360,365 | 04.05.08.00.00.00.00.00 |  | TAP-121908 | [TAP-121908] ¦ [PnP][Controls] IDU Actuator Input Processing - Migration | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121908 | 379 | 378 |  | 04.05.08.01.00.00.00.00 | TAP-121908 | TAP-121949 | [TAP-121908] ¦ [PnP][Controls] IDU Actuator Input Processing - Migration | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 0%
TAP-121908_CONTROLS | 380 | 378 |  | 04.05.08.02.00.00.00.00 | TAP-121908 | TAP-121292 | [TAP-121908_CONTROLS] ¦ [PnP] Convert IDU Actuator Input Processing Design Doc to Markdown | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 1 | 0 | 10 | 15 | 1 | 0%
TAP-121908_CONTROLS | 381 | 378 |  | 04.05.08.03.00.00.00.00 | TAP-121908 | TAP-123980 | [TAP-121908_CONTROLS] ¦ [PnP] [IDU] Remove UNIT_IduMotorThetaSignalModifier | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 2 | 0 | 10 | 15 | 2 | 0%
TAP-121908_CONTROLS | 382 | 378 |  | 04.05.08.04.00.00.00.00 | TAP-121908 | TAP-123985 | [TAP-121908_CONTROLS] ¦ [PnP][IDU] Migrate Estimation Units to Input Processing | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 3 | 0 | 10 | 15 | 3 | 0%
TAP-121908_CONTROLS | 383 | 378 |  | 04.05.08.05.00.00.00.00 | TAP-121908 | TAP-125647 | [TAP-121908_CONTROLS] ¦ [PnP] IDU Input Processing requirement gaps | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 5 | 0 | 10 | 15 | 5 | 0%
TAP-121906 | 384 | 433 | 386 | 04.05.09.00.00.00.00.00 |  | TAP-121906 | [TAP-121906] ¦ [PnP][Arch][Enabler][Embedded] Integrate BSCM with Subsystems | Feature | PROPOSED |  |  | Parent Task | User Stories | 5 | 0 | 1 hr | 1 hr | 5 | 0%
TAP-121906 | 385 | 384 |  | 04.05.09.01.00.00.00.00 | TAP-121906 | TAP-121947 | [TAP-121906] ¦ [PnP][Arch][Enabler][Embedded] Integrate BSCM with Subsystems | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 117 | 180 | 0 | 0%
TAP-97909 | 386 | 384,426 | 297 | 04.05.10.00.00.00.00.00 |  | TAP-97909 | [TAP-97909] ¦ [PnP][Zenith][Embedded] Implement Bedside Config Manager | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-97909_EMBEDDED | 387 | 386 |  | 04.05.10.01.00.00.00.00 | TAP-97909 | TAP-97616 | [TAP-97909_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Enabler] Cyclic EtherCAT SRA HAL Framework Update | User Story | Groomed | Embedded | EMBEDDED | Child Task | User Stories | 5 | 0 | 0 | 0 | 5 | 0%
TAP-97909_EMBEDDED | 388 | 386 |  | 04.05.10.02.00.00.00.00 | TAP-97909 | TAP-97667 | [TAP-97909_EMBEDDED] ¦ [Plug n Play][Architecture][zenith] SRA HAL Actual Data TC Updates | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 10 | 0 | 0 | 0 | 10 | 0%
TAP-97909_EMBEDDED | 389 | 386 |  | 04.05.10.03.00.00.00.00 | TAP-97909 | TAP-98081 | [TAP-97909_EMBEDDED] ¦ [Plug n Play][zenith][SRA HAL] SRA HAL Desired Test Case Updates | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 13 | 0 | 0 | 0 | 13 | 0%
TAP-97909_EMBEDDED | 390 | 386 |  | 04.05.10.04.00.00.00.00 | TAP-97909 | TAP-97707 | [TAP-97909_EMBEDDED] ¦ [Plug n Play][Architecture][zenith][Spike] Define TC and SSR Tracing Strategy | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 0 | 0 | 16 | 0%
TAP-97909_EMBEDDED | 391 | 386 |  | 04.05.10.05.00.00.00.00 | TAP-97909 | TAP-120181 | [TAP-97909_EMBEDDED] ¦ [PnP][Zenith]Add new IDU Primary TCs based on Requirements Improvement | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 0 | 0 | 16 | 0%
TAP-97909_EMBEDDED | 392 | 386 |  | 04.05.10.06.00.00.00.00 | TAP-97909 | TAP-120183 | [TAP-97909_EMBEDDED] ¦ [PnP][Zenith] IDU Primary Actual Data TCs for EtherCAT Transport and App Layer | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 0 | 0 | 16 | 0%
TAP-97909_EMBEDDED | 393 | 386 |  | 04.05.10.07.00.00.00.00 | TAP-97909 | TAP-120184 | [TAP-97909_EMBEDDED] ¦ [PnP][Zenith] IDU Primary Desired Data TCs for EtherCAT Transport and App Layer | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 0 | 0 | 16 | 0%
TAP-97909_EMBEDDED | 394 | 386 |  | 04.05.10.08.00.00.00.00 | TAP-97909 | TAP-120185 | [TAP-97909_EMBEDDED] ¦ [PnP][Zenith] IDU Primary General EtherCAT Transport and App Layer TCs | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 0 | 0 | 16 | 0%
TAP-97909_EMBEDDED | 395 | 386 |  | 04.05.10.09.00.00.00.00 | TAP-97909 | TAP-121521 | [TAP-97909_EMBEDDED] ¦ [PnP][Zenith] IDU Primary General EtherCAT Transport and App Layer TCs | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 43 | 65 | 16 | 0%
TAP-97909_EMBEDDED | 396 | 386 |  | 04.05.10.10.00.00.00.00 | TAP-97909 | TAP-130662 | [TAP-97909_EMBEDDED] ¦ [PnP][IDU][EMBSW] Create Interface Specification Between Bedside Configuration Manager and IDU Controller | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 16 | 0 | 43 | 65 | 16 | 0%
TAP-126766 | 397 | 353,424,422 | 360,365,408 | 04.05.11.00.00.00.00.00 |  | TAP-126766 | [TAP-126766] ¦ [PnP][Controls] Instrument Controller - Migration - Test Work | Feature | PROPOSED |  |  | Parent Task | User Stories | 16 | 0 | 1 hr | 1 hr | 16 | 0%
TAP-126766 | 398 | 397 |  | 04.05.11.01.00.00.00.00 | TAP-126766 | TAP-121956 | [TAP-126766] ¦ [PnP][Controls] Instrument Controller - Migration - Test Work | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 20 | 30 | 0 | 0%
TAP-126766_CONTROLS | 399 | 397 |  | 04.05.11.02.00.00.00.00 | TAP-126766 | TAP-114636 | [TAP-126766_CONTROLS] ¦ [PnP] Migrate Functionality into Instrument Controller Container | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 7 | 0 | 20 | 30 | 7 | 100%
TAP-126766_CONTROLS | 400 | 397 |  | 04.05.11.04.00.00.00.00 | TAP-126766 | TAP-125705 | [TAP-126766_CONTROLS] ¦ [PnP][Zenith] proto-MIL tests for SRA input jump check EIN-SSR_IDUSW-449 [training opportunity] | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 10 | 0 | 20 | 30 | 10 | 0%
TAP-126766_CONTROLS | 401 | 397 |  | 04.05.11.05.00.00.00.00 | TAP-126766 | TAP-125707 | [TAP-126766_CONTROLS] ¦ [PnP] proto-MIL test for SRA input joint limits EIN-SSR_IDUSW-475 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 11 | 0 | 20 | 30 | 11 | 0%
TAP-126766_CONTROLS | 402 | 397 |  | 04.05.11.06.00.00.00.00 | TAP-126766 | TAP-125709 | [TAP-126766_CONTROLS] ¦ [PnP][Zenith] proto-MIL test for request detachment of unsupported instruments EIN-SSR_IDUSW-619 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 12 | 0 | 20 | 30 | 12 | 0%
TAP-126766_CONTROLS | 403 | 397 |  | 04.05.11.07.00.00.00.00 | TAP-126766 | TAP-125710 | [TAP-126766_CONTROLS] ¦ [PnP] proto-MIL test for IDU state ready for calibration EIN-SSR_IDUSW-403 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 13 | 0 | 20 | 30 | 13 | 0%
TAP-126766_CONTROLS | 404 | 397 |  | 04.05.11.08.00.00.00.00 | TAP-126766 | TAP-125712 | [TAP-126766_CONTROLS] ¦ [PnP][Zenith] MIL test for IDU state position control entry EIN-SSR_IDUSW-408 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 14 | 0 | 20 | 30 | 14 | 0%
TAP-126766_CONTROLS | 405 | 397 |  | 04.05.11.09.00.00.00.00 | TAP-126766 | TAP-125713 | [TAP-126766_CONTROLS] ¦ [PnP][Zenith] proto-MIL test for IDU state HALT EIN-SSR_IDUSW-447 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 15 | 0 | 20 | 30 | 15 | 0%
TAP-126766_CONTROLS | 406 | 397 |  | 04.05.11.10.00.00.00.00 | TAP-126766 | TAP-125738 | [TAP-126766_CONTROLS] ¦ [PnP][Zenith] Develop smoke tests for Instrument Controller | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 18 | 0 | 20 | 30 | 18 | 0%
TAP-126766_CONTROLS | 407 | 397 |  | 04.05.11.12.00.00.00.00 | TAP-126766 | TAP-126031 | [TAP-126766_CONTROLS] ¦ [PnP][Zenith] Static analysis for the IDU Instrument Controller SWI | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 19 | 0 | 20 | 30 | 19 | 0%
TAP-121916 | 408 | 353,424,422,397 | 360,365 | 04.05.12.00.00.00.00.00 |  | TAP-121916 | [TAP-121916] ¦ [PnP][Controls] Instrument Controller - Migration - Dev Work | Feature | Accepted |  |  | Parent Task | User Stories | 19 | 0 | 1 hr | 1 hr | 19 | 0%
TAP-121916 | 409 | 408 |  | 04.05.12.01.00.00.00.00 | TAP-121916 | TAP-121956 | [TAP-121916] ¦ [PnP][Controls] Instrument Controller - Migration - Dev Work | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121916_CONTROLS | 410 | 408 |  | 04.05.12.02.00.00.00.00 | TAP-121916 | TAP-114636 | [TAP-121916_CONTROLS] ¦ [PnP] Migrate Functionality into Instrument Controller Container | User Story | Done | Controls | CONTROLS | Child Task | User Stories | 7 | 0 | 1 hr | 1 hr | 7 | 100%
TAP-121916_CONTROLS | 411 | 408 |  | 04.05.12.05.00.00.00.00 | TAP-121916 | TAP-124545 | [TAP-121916_CONTROLS] ¦ [PnP][IDU] Auto Motion Library Block Development | User Story | In progress | Controls | CONTROLS | Child Task | User Stories | 10 | 0 | 1 hr | 1 hr | 10 | 0%
TAP-121916_CONTROLS | 412 | 408 |  | 04.05.12.06.00.00.00.00 | TAP-121916 | TAP-125706 | [TAP-121916_CONTROLS] ¦ [PnP][BH] proto-MIL test for SRA input latency check EIN-SSR_IDUSW-450 | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 13 | 0 | 1 hr | 1 hr | 13 | 0%
TAP-121916_CONTROLS | 413 | 408 |  | 04.05.12.07.00.00.00.00 | TAP-121916 | TAP-125722 | [TAP-121916_CONTROLS] ¦ [PnP] Informal PDR for Instrument Controller | User Story | In progress | Controls | CONTROLS | Child Task | User Stories | 14 | 0 | 1 hr | 1 hr | 14 | 0%
TAP-121916_CONTROLS | 414 | 408 |  | 04.05.12.08.00.00.00.00 | TAP-121916 | TAP-125723 | [TAP-121916_CONTROLS] ¦ [PnP] IDU - Get requirements in acceptable state | User Story | In progress | Controls | CONTROLS | Child Task | User Stories | 16 | 0 | 1 hr | 1 hr | 16 | 0%
TAP-121916_CONTROLS | 415 | 408 |  | 04.05.12.09.00.00.00.00 | TAP-121916 | TAP-125725 | [TAP-121916_CONTROLS] ¦ [PnP] Analyze risk for Instrument Controller | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 18 | 0 | 1 hr | 1 hr | 18 | 0%
TAP-121916_CONTROLS | 416 | 408 |  | 04.05.12.11.00.00.00.00 | TAP-121916 | TAP-126033 | [TAP-121916_CONTROLS] ¦ [PnP] Design doc for IDU Instrument Controller | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 19 | 0 | 1 hr | 1 hr | 19 | 0%
TAP-121916_CONTROLS | 417 | 408 |  | 04.05.12.12.00.00.00.00 | TAP-121916 | TAP-126649 | [TAP-121916_CONTROLS] ¦ [PnP][CrocNRoll] Review/Sync on Logging Strategy | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 20 | 0 | 1 hr | 1 hr | 20 | 0%
TAP-121916_CONTROLS | 418 | 408 |  | 04.05.12.13.00.00.00.00 | TAP-121916 | TAP-130660 | [TAP-121916_CONTROLS] ¦ [PnP][IDU] Determine Future of Endoscope Controller | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 20 | 0 | 1 hr | 1 hr | 20 | 0%
TAP-121916_CONTROLS | 419 | 408 |  | 04.05.12.14.00.00.00.00 | TAP-121916 | TAP-130661 | [TAP-121916_CONTROLS] ¦ [PnP][IDU] Determine Future of Legacy IDU State Event Logging | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 20 | 0 | 1 hr | 1 hr | 20 | 0%
TAP-121916_CONTROLS | 420 | 408 |  | 04.05.12.15.00.00.00.00 | TAP-121916 | TAP-130663 | [TAP-121916_CONTROLS] ¦ [PnP][IDU] Implement Debug Logging for Legacy Instrument Controllers | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 20 | 0 | 1 hr | 1 hr | 20 | 0%
TAP-121916_CONTROLS | 421 | 408 |  | 04.05.12.16.00.00.00.00 | TAP-121916 | TAP-130789 | [TAP-121916_CONTROLS] ¦ [PnP][IDU] Convert Instrument Controller Library to SWI | User Story | Open | Controls | CONTROLS | Child Task | User Stories | 20 | 0 | 1 hr | 1 hr | 20 | 0%
TAP-121926 | 422 |  | 424,353,313,378,375,331,325,245,408,372,365,360,397 | 04.05.13.00.00.00.00.00 |  | TAP-121926 | [TAP-121926] ¦ [PnP][IDU][Controls] Merge to Develop Behind Build Flag | Feature | PROPOSED |  |  | Parent Task | User Stories | 20 | 0 | 1 hr | 1 hr | 20 | 0%
TAP-121926 | 423 | 422 |  | 04.05.13.01.00.00.00.00 | TAP-121926 | TAP-121964 | [TAP-121926] ¦ [PnP][IDU][Controls] Merge to Develop Behind Build Flag | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 15 | 25 | 0 | 0%
TAP-121917 | 424 | 422 | 313,378,375,331,325,245,408,372,365,360,353,397 | 04.05.14.00.00.00.00.00 |  | TAP-121917 | [TAP-121917] ¦ [PnP][IDU][Controls] Preliminary Integration of M-IRR and Newton | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121917 | 425 | 424 |  | 04.05.14.01.00.00.00.00 | TAP-121917 | TAP-121957 | [TAP-121917] ¦ [PnP][IDU][Controls] Preliminary Integration of M-IRR and Newton | Feature Estimation | Open | Controls | CONTROLS | Child Task | User Stories | 0 | 0 | 5 | 7 | 0 | 0%
TAP-94827 | 426 |  | 386 | 04.05.15.00.00.00.00.00 |  | TAP-94827 | [TAP-94827] ¦ [PnP][Architecture][Embedded] Update Tools to new Instrument Interfaces | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-94827 | 427 | 426 |  | 04.05.15.01.00.00.00.00 | TAP-94827 | TAP-121503 | [TAP-94827] ¦ [PnP][Architecture][Embedded] Update Tools to new Instrument Interfaces | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 10 | 15 | 0 | 0%
TAP-122018 | 428 |  | 245 | 04.05.16.00.00.00.00.00 |  | TAP-122018 | [TAP-122018] ¦ [PnP][Arch][Test]HIL Testing for Embedded IDU Testing | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-122018 | 429 | 428 |  | 04.05.16.01.00.00.00.00 | TAP-122018 | TAP-122041 | [TAP-122018] ¦ [PnP][Arch][Test]HIL Testing for Embedded IDU Testing | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 35 | 45 | 0 | 0%
TAP-84434 | 430 |  | 219 | 04.05.17.00.00.00.00.00 |  | TAP-84434 | [TAP-84434] ¦ [PnP][Arch][Enabler][Embedded] Create Infrastructure - Data Aggregator Interfaces | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-84434_EMBEDDED | 431 | 430 |  | 04.05.17.01.00.00.00.00 | TAP-84434 | TAP-85298 | [TAP-84434_EMBEDDED] ¦ [Newton][Enabler][Sunrisers] Config Data Manager and Instr. Data Interface Prototype | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 0 | 0 | 0 | 0%
TAP-84434_EMBEDDED | 432 | 430 |  | 04.05.17.02.00.00.00.00 | TAP-84434 | TAP-121492 | [TAP-84434_EMBEDDED] ¦ [Newton][Enabler][Sunrisers] Config Data Manager and Instr. Data Interface Prototype | Feature Estimation | Done | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 130 | 90 | 0 | 100%
TAP-121929 | 433 |  | 384 | 04.05.18.00.00.00.00.00 |  | TAP-121929 | [TAP-121929] ¦ [PnP][Zenith][Embedded] System Integration Testing for Controllers, IDU Primary, SRA HAL/BSCM | Feature | PROPOSED |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-121929 | 434 | 433 |  | 04.05.18.01.00.00.00.00 | TAP-121929 | TAP-121967 | [TAP-121929] ¦ [PnP][Zenith][Embedded] System Integration Testing for Controllers, IDU Primary, SRA HAL/BSCM | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 0 | 0 | 20 | 25 | 0 | 0%
TAP-97775 | 435 |  | 219 | 04.05.19.00.00.00.00.00 |  | TAP-97775 | [TAP-97775] ¦ [PnP][V5.0][Embedded] GECAT for Instruments Data Transportation: S-function interfaces - Foundation Support | Feature | Accepted |  |  | Parent Task | User Stories | 0 | 0 | 1 hr | 1 hr | 0 | 0%
TAP-97775_EMBEDDED | 436 | 435 |  | 04.05.19.01.00.00.00.00 | TAP-97775 | TAP-85764 | [TAP-97775_EMBEDDED] ¦ Support S-function development for Initial Attachment data usage | User Story | Open | Embedded | EMBEDDED | Child Task | User Stories | 5 | 0 | 0 | 0 | 5 | 0%
TAP-97775_EMBEDDED | 437 | 435 |  | 04.05.19.02.00.00.00.00 | TAP-97775 | TAP-128293 | [TAP-97775_EMBEDDED] ¦ Support S-function development for Initial Attachment data usage | Feature Estimation | Open | Embedded | EMBEDDED | Child Task | User Stories | 5 | 0 | 5 | 10 | 5 | 0%

## Log
DataTimeStamp | Event | Data | Selector | Unique ID Successors NOT FOUND | Unique ID Predecessors NOT FOUND
2024-09-13 12:02 | Start: | DANSAP Formatter, v1.6 | TAP-97775_EMBEDDED |  | TAP-121864
2024-09-13 12:02 | Input File: | PnP_Categorized_240904_1601 (discipline+refinement level updated).xls | TAP-97775_EMBEDDED |  | TAP-121864
2024-09-13 12:02 | Output File: | Project_Import_DS_7.xlsx | TAP-97775_EMBEDDED | TAP-121864
2024-09-13 12:02 | Info |  | TAP-97775_EMBEDDED | TAP-121864
2024-09-13 12:02 | Processing: | Jira Data: Rows: 497, Cols: 16 | TAP-97775_EMBEDDED | TAP-114818
2024-09-13 12:03 | Result: | Project Data: Rows: 437, Cols: 20 | TAP-97775_EMBEDDED | TAP-121864
2024-09-13 12:03 | Processing Complete: | 91.61714720726013 seconds | TAP-97775_EMBEDDED | TAP-121864
|  |  | TAP-97775_EMBEDDED | TAP-103479
|  |  | TAP-97775_EMBEDDED |  | TAP-121864
|  |  | TAP-97775_EMBEDDED |  | TAP-121864
|  |  | TAP-97775_EMBEDDED | TAP-94814
|  |  | TAP-97775_EMBEDDED | TAP-106649
|  |  | TAP-97775_EMBEDDED | TAP-123372

## Summary
Resource Names | Sum FDR
UFSW | 587
GUI | 887
EMBEDDED | 596
CONTROLS | 832
Total FDR: | 53392